## Background (what this is all about)

The purpose of this document is to provide an overview of what is needed from you to update our project's cost and schedule estimate.  The overall approach of this exercise is to, first, ensure that the scope, requirements, and assumptions for the remaining work are up to date. Applicable documents, namely the WBS dictionary, GRD, SRD's, and SDD's are to be reviewed and updated if necessary. Second, work plans and estimates will be updated and documented, clearly describing the basis of estimate (e.g., engineer’s estimate, vendor quotes, comparisons with similar work, etc.), assumptions, and allowance for problems. Estimates should cover what the work is expected to cost, with reasonable allowance for problems.  Once accepted by DOE these estimates will be placed under formal configuration control and will become the baseline against which performance will be measured.

Guidelines  (what YOU need to do)

Your estimates should reflect work scope to complete from February 1, 2007

GRD: Review and update (if necessary) your applicable GRD. Send either changes or confirmation that no changes are required to R. Strykowsky. The GRD can be found at:

General Requirements Document (GRD): Rev 4

SDD: Review and update your applicable SDD. Send either changes or confirmation that no changes are required to R. Strykowsky. The SDD can be found at:

http://ncsx.pppl.gov/NCSX_Engineering/Technical_Data/SDDs/index_SDDs.htm

SRD: Review and update (if applicable) your applicable SRD. Send either changes or confirmation that no changes are required to R. Strykowsky. The SRD (B & C SPECs) can be found at:

http://ncsx.pppl.gov/SystemsEngineering/Requirements/index_Specs.htm

WBS: Review and update (if necessary) your applicable WBS dictionary. Send either changes or confirmation that no changes are required to R. Strykowsky. The WBS can be found at:

http://ncsx.pppl.gov/SystemsEngineering/WBS/WBS_index.htm

ESTIMATE: Update your cost estimates using the attached spreadsheet "ESTIMATE WORKSHEET 20070108.xls". Call me if you have an alternate format you'd prefer to use.

(For reference to the original PDR backup documentation go to the backup links on the following site.)

http://ncsx.pppl.gov//Project_Control/PDR_PC/restricted/Cost_and_Schedule.HTML

For a tabulated version of the current resource loaded schedule ECP52 see attached "RESOURCE LOADED SCHEDULE ECP52.xls"

These are the documents that will used to develop the resource loaded schedule. A key part of your backup is to provide a rationale or basis to your estimates. You are asked to document the basis for your cost and schedule estimate (e.g., engineering judgment/scaling, vendor quotes if available, quantity takeoffs, unit pricing, etc.) as separate tabs in your spreadsheet. All laboratory labor estimates should be reported in manhours, type of labor (e.g., EAEM, EASB, EMTB, ORNL Engineers, ORNLDesigners, etc.).  Your estimate sheets will be used as input to the resource loaded schedule and as the basis for discussion you will have with the DOE reviewers.  Pricing will be performed through the Primavera resource loaded schedule database. For materials, procurements, and subcontracts at PPPL, only the direct estimates (in FY07 $) are required. For procurements placed by ORNL, we will need the fully loaded value to be input.

Schedule (when this material is due)

Project Reviews

Subsequent to receiving your estimates the project will set-up a series of reviews at which time you will be given the opportunity to explain your estimate package. The intent of this review is to ensure ourselves that all scope is accounted for and the cost and schedule estimate are achievable. Remember, the key to this exercise is to estimate the likely (center of the error bars) cost and schedule for your work and not an optimistic estimate.

Time for this exercise should be charged to you’re the charge numbers on the previous page.