## PF Design
|  | WBS:= | 13
|  | Job Number= | 1302
|  | Title= | PF Coil Design
|  | Job Manager= | Kalish
[6 empty] | FY07$K |  |  |  |  | HOURS
[6 empty] | 1308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 | 116.7 | 168.88 | 138.6 | 138.6 | 78.33 | 144.88 | 93.69 | 70.98 | 162.83 | 229.54 | 9789.08
Task ID |  | TASK DESCRIPTION | Comments | Pre-requisites | Start Date | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNLEM | ORNLDSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Rough Estimate Total (in FY07$)
Design
|  | Complete PF Coil SRD | [14 empty] | 24 | [10 empty] | 4338.96
|  | Update PF Analysis | Revised to reflect Manufaturing Upgrade | [13 empty] | 160 | [10 empty] | 28926.4
|  | Update PF Coil SDD | [14 empty] | 24 | [10 empty] | 4338.96
|  | Complete PF4 PDR Drawings | Revised to reflect Manufaturing Upgrade | [13 empty] | 80 | [10 empty] | 14463.2
|  | Complete PF5 PDR Drawings | Revised to reflect Manufaturing Upgrade | [13 empty] | 80 | [10 empty] | 14463.2
|  | Complete PF6 PDR Drawings | Revised to reflect Manufaturing Upgrade | [13 empty] | 80 | [10 empty] | 14463.2
|  | Prepare for PDR | [14 empty] | 88 | [10 empty] | 15909.52
|  | PDR | [14 empty] | 16 | [10 empty] | 2892.64
|  | Prepare PF Conductor and Coil Spec | [14 empty] | 24 | [10 empty] | 4338.96
|  | Detail Drawings PF4 | [14 empty] | 96 | [10 empty] | 17355.84
|  | Disposition PDR Chits | [14 empty] | 24 | [10 empty] | 4338.96
|  | Detail Drawings PF5 | [14 empty] | 96 | [10 empty] | 17355.84
|  | Detail Drawings PF6 | [14 empty] | 96 | [10 empty] | 17355.84
|  | PF Stress analysis with leads | [14 empty] | 144 | [10 empty] | 26033.76
|  | Review PF Coil and Conductor Spec | [14 empty] | 8 | [10 empty] | 1446.32
|  | Prepare for FDR | [14 empty] | 88 | [10 empty] | 15909.52
|  | PF FDR | [14 empty] | 16 | [10 empty] | 2892.64
|  | Resolve Chits | [14 empty] | 75 | [10 empty] | 13559.25
0
0
0
0
[5 empty] | TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220383.01
220383.01

## PF Fabrication
|  | WBS:= | 13
|  | Job Number= | 1352
|  | Title= | PF Coil Fabrication
|  | Job Manager= | Kalish
[6 empty] | FY07$K |  |  |  |  | HOURS
[6 empty] | 1308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 | 116.7 | 168.88 | 138.6 | 138.6 | 78.33 | 144.88 | 93.69 | 70.98 | 162.83 | 229.54 | 9789.08
Task ID |  | TASK DESCRIPTION | Comments | Pre-requisites | Start Date | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNLEM | ORNLDSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Rough Estimate Total (in FY07$)
0
| Procrurement & Fabrication | [26 empty] | 0
|  | PF Coil RFQ and Procurement | [14 empty] | 80 | [10 empty] | 14463.2
|  | Conductor Procurement PF4 | Outokumpu estimate |  |  | 28 | [10 empty] | 16 | [10 empty] | 39516.64
|  | Conductor Procurement PF5 | Outokumpu estimate |  |  | 35.61 | [10 empty] | 16 | [10 empty] | 49470.52
|  | Conductor Procurement PF6 | Outokumpu estimate |  |  | 25.44 | [10 empty] | 16 | [10 empty] | 36168.16
|  | Conductor Tooling Charge | Outokumpu estimate |  |  | 4 | [21 empty] | 5232
|  | PF 4 Materials | Internal PF4 Estimate |  |  | 41 | [21 empty] | 53628
|  | PF 5 Materials | Internal PF5 Estimate |  |  | 53 | [10 empty] | 24 | [10 empty] | 73662.96
|  | PF 6 Materials | Internal PF6 Estimate |  |  | 42 | [10 empty] | 24 | [10 empty] | 59274.96
|  | PF 4 Tooling | Everson Estimate |  |  | 72 | [21 empty] | 94176
|  | Fabrication of PF4 | Everson Estimate |  |  | 40.2 | [21 empty] | 52581.6
|  | PF 5 and PF 6 Tooling | Everson Estimate |  |  | 375 | [21 empty] | 490500
|  | Fabrication of PF 5 | Everson Estimate |  |  | 88.9 | [21 empty] | 116281.2
|  | Fabrication of PF 6 | Everson Estimate |  |  | 98 | [21 empty] | 128184
|  | Fabrication Oversight | 8months, 2days per week, +80hrs drafting (credit for 1 month TF overlap) | [13 empty] | 592 | [10 empty] | 107027.68
|  | Refurbish PF1a | [13 empty] | 80 | [11 empty] | 6266.4
|  | PF Inspection and Testing | One week per coil set for TB | [12 empty] | 120 | 60 | [10 empty] | 20247
0
|  | PF1a Assembly | two technicians for two weeks with oversight | [12 empty] | 160 | 40 | [10 empty] | 19764.4
0
[5 empty] | TOTAL | 903.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366444.72
1366444.72

## I&C
|  | WBS:= | 13
|  | Job Number= | 1355
|  | Title= | I&C Design and Installation
|  | Job Manager= | Kalish
[6 empty] | FY07$K |  |  |  |  | HOURS
[6 empty] | 1308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 | 116.7 | 168.88 | 138.6 | 138.6 | 78.33 | 144.88 | 93.69 | 70.98 | 162.83 | 229.54 | 9789.08
Task ID |  | TASK DESCRIPTION | Comments | Pre-requisites | Start Date | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNLEM | ORNLDSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Rough Estimate Total (in FY07$)
0
| I&C Design and Installation | [26 empty] | 0
|  | Procure Thermocouples TF | $40 per TE 6 per coil |  |  | 4320 | [10 empty] | 2 | [10 empty] | 5650921.58
|  | Procure Thermocouples PF4 | $40 per TE 6 per coil |  |  | 480 | [10 empty] | 2
|  | Procure Thermocouples PF5 | $40 per TE 6 per coil |  |  | 480 | [10 empty] | 2 | [10 empty] | 628201.58
|  | Procure Thermocouples PF6 | $40 per TE 6 per coil |  |  | 480 | [10 empty] | 2 | [10 empty] | 628201.58
|  | Procure Thermocouples PF1a | $40 per TE3 per coil |  |  | 240 | [10 empty] | 2 | [10 empty] | 314281.58
|  | Thermcocouple Wire | 500ft per TE |  |  | 4000 | [10 empty] | 2 | [10 empty] | 5232361.58
|  | Design and Review | Design | [13 empty] | 60 | [10 empty] | 10847.4
|  | Installation Procedures | Installation Procedures + Review and Approval | [13 empty] | 20 | [10 empty] | 3615.8
|  |  | Design Review | [13 empty] | 8 | [10 empty] | 1446.32
|  | Installation | Two hours per TE | [12 empty] | 396 | 40 | [10 empty] | 38250.28
0
0
0
0
0
0
0
0
0
0
[5 empty] | TOTAL | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13136329.28
12508127.7

## Trim Coil
|  | WBS:= | 13
|  | Job Number= | 1303
|  | Title= | Trim Coil
|  | Job Manager= | Kalish
[6 empty] | FY07$K |  |  |  |  | HOURS
[6 empty] | 1440 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 189.37 | 116.7 | 168.88 | 138.6 | 138.6 | 78.33 | 144.88 | 93.69 | 70.98 | 162.83 | 229.54 | 9929.66
Task ID |  | TASK DESCRIPTION | Comments | Pre-requisites | Start Date | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNLEM | ORNLDSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Rough Estimate Total (in FY07$)
Procrurement & Fabrication
|  | Complete PF Coil SRD | [14 empty] | 8 | [10 empty] | 1514.96
|  | Analysis | [14 empty] | 40 | [10 empty] | 7574.8
|  | PDR Dwgs | [14 empty] | 60 | [10 empty] | 11362.2
|  | Prepare for PDR | [14 empty] | 16 | [10 empty] | 3029.92
|  | PDR | [14 empty] | 8 | [10 empty] | 1514.96
|  | Prepare Procurement Coil Spec | [14 empty] | 24 | [10 empty] | 4544.88
|  | Detail Drawings | [14 empty] | 60 | [10 empty] | 11362.2
|  | Disposition PDR Chits | [14 empty] | 8 | [10 empty] | 1514.96
|  | Coil Procurement Support | [14 empty] | 24 | [10 empty] | 4544.88
|  | Conductor Procurement | Outokumpu Quote |  |  | 0.7 | [21 empty] | 1008
|  | Coil Tooling | Vendor Quote for Jupiter 2 Coil |  |  | 12.5 | [21 empty] | 18000
|  | Fabrication of Coil | Vendor Quote for More complex Coil |  |  | 20.5 | [21 empty] | 29520
|  | Fabrication Support | 3months, 1day per week, +20hrs drafting | [13 empty] | 116 | [10 empty] | 21966.92
[5 empty] | TOTAL | 33.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117458.68
117458.68