## Fab Project
WBS 192 Stellarator Core Integration and Global Analysis
Description:
This effort covers design integration activities for the Stellarator Core, including global Pro-E models and drawings for the Stellarator Core, Pro-Intralink database maintenance of all drawings and CAD models, analyses common to all of WBS 1, and design criteria documents.
Labor
Manhours per fiscal year by labor category
Level of Effort | [6 empty] | FY2007 | FY2008 | FY2009 | TOTAL
[7 empty] | 780 | 1560 | 1560 | 3900
M&S Costs
| Activity Title |  |  |  | Comment
Procured Hardware/Material
0
0
|  | 0 |  | FY07 to FY09
|  | software |  | 35997.6
|  | hardware |  | 20880
0
|  | subtotal, purchased parts |  | 56877.6
|  | Profit at 10% |  | 0 | profit already in numbers
|  | total, procured hdwe/matl. |  | 56877.6 | w/o G&A
| Purchased Design Services |  |  | 0 | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2007 -2009 | Comment
| Travel |  |  | 9000 | assumes one trip every 6 months
| Contingency |  |  |  | 10% | Overall on this WBS
[7 empty] | 131664 | 268164 | 279240 | 679068
735945.6
Design Integration: Designer 2080X.3X/yr Engineer 2080X.45/yr Total =3120

## M&S
WBS 192 Stellarator Core Integration and Global Analysis
Materials and Subcontracts (M&S)
Description:
This element covers the hardware and software required for WBS 1 activities at ORNL. These activities are not covered by overhead as they are at PPPL.
Purchased parts:
subtotal, purchased parts | 0
Purchased materials for in-house fabrication and sub-assembly
FY07 to FY09
software |  |  | 35997.6
hardware |  |  | 20880
subtotal purchased materials |  |  | 56877.6
Worksheet:
| no. | cost ea/yr | yrs | % to NCSX | total
Pro-E licenses | 7 | 2000 | 4 | 60% | 33600 | FY 2003 maint costs
ANSYS maintenance | 1 | 8743 | 4 | 60% | 20983.2 | FY 2003 maint costs
IPA maint. | 1 | 2005 | 4 | 60% | 4812 | FY 2003 maint costs
Rhino | 1 | 500 | 4 | 60% | 1200 | FY 2003 maint costs
Corel Draw | 1 | 600 | 4 | 60% | 1440 | FY 2003 maint costs
misc software | 1 | 1500 | 4 | 60% | 3600 | Based on historical costs
subtotal, software |  |  |  |  | 65635.2
Workstations | 8 | 2500 | 4 | 60% | 48000 | based on replacement every two years
Printer / Plotter maint. | 2 | 1200 | 4 | 60% | 5760 | based on historical maint. Costs
subtotal, hardware |  |  |  |  | 53760
Worksheet for FY2007 to 2009
| no. | cost ea/yr | yrs | % to NCSX | total
Pro-E licenses | 5 | 3330 | 2 | 60% | 19980 | FY 2007 maint costs
ANSYS maintenance | 1 | 8743 | 2 | 60% | 10491.6 | FY 2003 maint costs
IPA maint. | 1 | 2005 | 2 | 60% | 2406 | FY 2003 maint costs
Rhino | 1 | 500 | 2 | 60% | 600 | FY 2003 maint costs
Corel Draw | 1 | 600 | 2 | 60% | 720 | FY 2003 maint costs
misc software | 1 | 1500 | 2 | 60% | 1800 | Based on historical costs
subtotal, software |  |  |  |  | 35997.6
Workstations | 6 | 2500 | 2 | 60% | 18000 | based on replacement every two years
Printer / Plotter maint. | 2 | 1200 | 2 | 60% | 2880 | based on historical maint. Costs
subtotal, hardware |  |  |  |  | 20880