## Estimate
WBS: |  | 81 |  |  | Annualized FTE's , M&S ,Travel | [7 empty] | FY07 | [11 empty] | FY08 | [11 empty] | FY09 | [11 empty] | FY10
FY-07 ETC Update |  |  |  | Avg. last 24 months | FY07 | FY08 | FY09 | FY10 |  |  | hours |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
| 81 | R///RM3 | Neilson | 0.85 | 0.75 | 0.75 | 0.75 | 0.5 |  | R///RM3 | Neilson | hours | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 107.875 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167
| 81 | FC//AM | Strykowsky | 0.94 | 0.8 | 0.8 | 0.8 | 0.5 |  | FC//AM | Strykowsky | hours | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167
| 81 | B///CB | Hampton | 0.29 | 0.3 | 0.3 | 0.3 | 0.25 |  | B///CB | Hampton | hours | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 43.15 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583
| 81 | 41 | M&S | 6 | 12 | 10 | 10 | 6
| 81 | 35 | Travel | 9.7 | 10 | 10 | 10 | 8 |  |  | $k
| 81 | ORNL | Lyon,Akers,Martin,travel,m&s | 140 | 144.9 | 120 | 120 | 75 | budget based on actual plus 3.5%/yr | ORNL | Lyon,Akers,Martin,travel,m&s | $k | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25
| 81 | ORNL | Akers |  |  |  |  | 0
| 81 | ORNL 41 | M&S |  |  |  |  | 0
| 81 | ORNL 35 | Travel
| 89 Direct allocations (PPPL applied "overhead") |  |  | n/a | 218 | 224 | 232 | 240.12 | Estimated (as calculated by PPPL based on RM's and EA analysts plus hp techs)
CD-4

## Sept 04 Update
WBS: |  | 8 |  | FTE's , M&S ,Travel
Manager:
|  |  |  | FY03 (april-sept) | FY04 | FY05 | FY06 | FY07 | FY07
Revised Estimate | 82 | EA** EM | Reiersen | 0.425 | 0.85 | 0.85 | 0.85 | 0.63731 | 0.63731
Revised Estimate | 82 | EA** EM | Brown | 0.30012 | 0.6 | 0.5 | 0.4 | 0.2248 | 0.2248
Revised Estimate | 82 | EA** EM | Brooks | 0.15006 | 0.2 | 0.1 | 0.1 | 0 | 0
Revised Estimate | 82 | EM** EM | Dudek | 0.15064 | 0.25 | 0.15 | 0.05 | 0.037659 | 0.037659
Revised Estimate | 82 | EM** EM | Perry | 0 | 0.15 | 0.15 | 0.05 | 0.037659 | 0.037659
Revised Estimate | 82 | EE** AM | Such | 0.025 | 0.05 | 0.15 | 0.25 | 0.125 | 0.125
Revised Estimate | 82 | EAD* DM | Designer | 0.10023 | 0.5 | 0.5 | 0.5 | 0.37486 | 0.37486
Revised Estimate | 82 |  |  | 1.151 | 2.6 | 2.4 | 2.2 | 1.4373 | 1.4373
Revised Estimate | 82 | 35 | Travel | 4 | 10 | 10 | 5 | 5 | 5
Revised Estimate | 82 | 41 | M&S |  | 30
Revised Estimate |  |  |  | 291650.95 | 676424.2 | 629304.4 | 565960.2 | 375143.8 | 375190 |  | 2538483.55
FY03 (april-sept)
CDR Baseline | 82 | EA**EM | Reiersen | 0.425 | 0.85 | 0.85 | 0.85 | 0.4 | 0.4
CDR Baseline | 82 | EA**EM | Brown | 0.225 | 0.4 | 0.4 | 0.4 | 0.2 | 0.2
CDR Baseline | 82 | EAD*DM | Designer | 0.3 | 0.3 | 0.3 | 0.3 | 0.4 | 0.4
CDR Baseline | 82 |  |  | 0.95 | 1.55 | 1.55 | 1.55 | 1 | 1
CDR Baseline | 82 | 35 | Travel | 10 | 10 | 8 | 5 | 4 | 4
CDR Baseline | 82 | 41 | M&S (purchased services) | 30 | 30
CDR Baseline | 82 |  |  | 209158.1 | 369589.8 | 379773.2 | 396946.9 | 241002.8 | 241002.8 |  | 1596470.8
P&CO Support
|  |  |  | FY03 (april-sept) | FY04 | FY05 | FY06 | FY07 | FY07
Revised Estimate | 82 | FC** EM | Simmons | 0.47059 | 0.8 | 0.75 | 0.75 | 0.52941 | 0.52941
Revised Estimate | 82 | FC**AM | Strykowsky | 0.4 | 0.8 | 0.8 | 0.8 | 0.4 | 0.4
Revised Estimate |  |  |  | 0.87059 | 1.6 | 1.55 | 1.55 | 0.92941 | 0.92941
Revised Estimate |  |  |  | 232419.2 | 439821.824 | 424376.576 | 424376.576 | 259886.848 | 259886.848 |  | 1780881.024
|  | FC** EM | Simmons | 0.325 | 0.65 | 0.65 | 0.65 | 0.25 | 0.25
|  | FC**AM | Strykowsky | 0.1 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1
CDR Baseline | 82 | FC**AM/EM | Simmons/Strykowsky | 0.425 | 0.85 | 0.85 | 0.85 | 0.35 | 0.35
CDR Baseline |  |  |  | 112356.4 | 233701.312 | 233701.312 | 233701.312 | 95061.824 | 95061.824 |  | 908522.16
REBASELINE |  |  |  | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 |  |  | FY03 | FY04 | FY05 | FY06 | FY07 | Total
| 81 | R///RM3 | Neilson | 0.85 | 0.85 | 0.93043 | 0.85973 | 0.77093 | 0.55204 |  | 364.3408 | 309.6896 | 322.0772 | 366.6554 | 352.3458 | 328.5903 | 1679.3584
| 81 | R///RM3 | Schmidt | [7 empty] | 364.3408 | 0 | 0 | 0 | 0 | 0 | 0
| 81 | FC//AM | Strykowsky | 0.62 | 0.5 | 0.50601 | 0.50601 | 0.51116 | 0.32127 | 5.446 | 231.0069 | 143.2243 | 120.1236 | 126.4302 | 131.4874 | 138.1392 | 659.4047
| 81 | B///CB | Hampton | 0.41 | 0.3 | 0.3 | 0.15 | 0.038462 |  |  | 90.2096 | 36.9859 | 28.1454 | 29.2712 | 15.221 | 4.0589 | 113.6825
| 81 | 41 | M&S | 3 | 6 | 6 | 2 | 2 | 0 |  | 1.32 | 3.96 | 8.2368 | 8.5663 | 2.9696 | 3.0884 | 26.8211
| 81 | 35 | Travel | 8 | 8 | 8 | 4 | 4 | 0 |  | 1.685 | 13.48 | 14.0192 | 14.58 | 7.5816 | 7.8848 | 57.5456
| 81 | ORNL | Lyon | 0.25 | 0.2 | 0.10181 | 0.10181 | 0.12613 | 0.29412 |  | 330.78 | 82.695 | 68.8022 | 36.4247 | 37.8817 | 48.8085 | 274.6121
| 81 | ORNL | Benson | 0.1 | 0.1 | 0.080882 | 0.050339 | 0.012443 |  | 1.4241 | 246.1003 | 24.61 | 25.5944 | 21.5294 | 13.9354 | 3.5825 | 89.2518
| 81 | ORNL | Akers | 0.1 | 0.1 | 0.10068 | 0 | 0 | 0 |  | 146.92 | 14.692 | 15.2797 | 15.9987 | 0 | 0 | 45.9704
| 81 | ORNL 41 | M&S | 3 | 3 | 2 | 2 | 0 | 0 |  | 1 | 3 | 3.12 | 2.1632 | 2.2497 | 0 | 10.5329
| 81 | ORNL 35 | Travel | 4 | 4 | 3 | 2 | 0 | 0 |  | 1 | 4 | 4.16 | 3.2448 | 2.2497 | 0 | 13.6545 | 2970.8341
| 82 | EA** EM | Reiersen, Brown, Brooks | 1.795 | 2.2 | 1.8001 | 1.6002 | 0.79954 | 0.59965 |  | 263.3186 | 472.6568 | 602.4729 | 512.6826 | 473.9848 | 246.2936 | 2308.0907
| 82 | FC//EM | Simmons | 0.9 | 0.75 | 0.60733 | 0.50601 | 0.25301 | 0.20263 |  | 296.9179 | 267.2261 | 231.596 | 195.0408 | 169.0035 | 87.8818 | 950.7483
| 82 | EA** EM | Brown | [7 empty] | 263.3186 | 0 | 0 | 0 | 0 | 0 | 0
| 82 | EA** EM | Brooks | [6 empty] | 15.5152 | 263.3186 | 0 | 0 | 0 | 0 | 0 | 0
| 82 | EM** EM | Dudek | 0.28064 | 0.35 | 0.34994 | 0.34994 | 0.17381 | 0.26014 |  | 263.3186 | 73.897 | 95.848 | 99.6654 | 103.652 | 53.5421 | 426.6044
| 82 | EM** EM | Perry | 0 | 0 | [5 empty] | 263.3186 | 0 | 0 | 0 | 0 | 0 | 0
| 82 | EE** AM | Such | 0.025 | 0.05 | 0.15006 | 0.25029 | 0.12514 | 0.12978 |  | 44.5307 | 1.1133 | 2.3156 | 7.2275 | 12.5373 | 6.5194 | 29.7129
| 82 | EAD* DM | Designer | 0.45 | 0.5 | 0.5 | 0.5 | 0.24913 |  |  | 172.3929 | 77.5768 | 89.6443 | 93.2301 | 96.9593 | 50.2436 | 407.654
| 82 | 35 | Travel | 4 | 8 | 7 | 5 | 10 | 3 |  | 1.685 | 6.74 | 14.0192 | 12.7575 | 9.477 | 19.7121 | 62.7058
| 82 | 41 | M&S |  | 30 | [5 empty] | 1.32 | 0 | 41.184 | 0 | 0 | 0 | 41.184 | 4226.7001
| 84 | R///RM2 | HUDSON | 0.25 | [6 empty] | 251.6074 | 62.9018 | 0 | 0 | 0 | 0 | 62.9018
| 84 | R///RM2 | KUGEL | 0.15 | 0.03 |  |  |  |  | 1.77 | 251.6074 | 37.7411 | 7.8501 | 0 | 0 | 0 | 45.5913
| 84 | R///RM2 | ZARNSTORFF | 0.36 | 0.36 | [5 empty] | 251.6074 | 90.5786 | 94.2018 | 0 | 0 | 0 | 184.7804
| 84 | EA//EM | Ku | 0.62 | 0 | [5 empty] | 263.3186 | 163.2575 | 0 | 0 | 0 | 0 | 163.2575
| 84 | 35 | Travel | 5 | 1 | [5 empty] | 1.685 | 8.425 | 1.7524 | 0 | 0 | 0 | 10.1774
| 84 | 41 | M&S | 10 | 3 | [5 empty] | 1.32 | 13.2 | 4.1184 | 0 | 0 | 0 | 17.3184
| 84 | ORNLRM | Lazarus | 0.33 | 0.1 | 0 |  |  |  |  | 330.78 | 109.1574 | 34.4011 | 0 | 0 | 0 | 143.5585
| 84 | ORNL 41 | M&S | 1.3 | [6 empty] | 1 | 1.3 | 0 | 0 | 0 | 0 | 1.3
| 84 | ORNL 35 | Travel | 1.6 | [6 empty] | 1 | 1.6 | 0 | 0 | 0 | 0 | 1.6 | 630.4854
| 85 | EM** EM | Startup |  |  |  |  | 0.34762 | 0.34762 |  | 263.3186 |  |  |  |  | 107.0842 | 107.0842
| 85 | EM**SM | Startup |  |  |  |  | 0.41715 | 0.41715 |  | 171.0293 |  |  |  |  | 83.4633 | 83.4633
| 85 | EC**EM | Startup |  |  |  |  | 0.13905 | 0.13905 |  | 245.6443 |  |  |  |  | 39.9586 | 39.9586
| 85 | EE**EM | Startup |  |  |  |  | 0.13905 | 0.13905 |  | 246.9216 |  |  |  |  | 40.1664 | 40.1664
| 85 | EE**SM | Startup |  |  |  |  | 0.2781 | 0.2781 |  | 185.9075 |  |  |  |  | 60.4826 | 60.4826
| 85 | EM** EM | Procedures |  |  |  |  | 0.91541 | 0.91541 |  | 263.3186 |  |  |  |  | 281.9883 | 281.9883
| 85 | EM**SM | Procedures |  |  |  |  | 0.91541 | 0.91541 | 3.1518 | 171.0293 |  |  |  |  | 183.1556 | 183.1556 | 799.1991
[12 empty] | 2137 | 1946 | 1632 | 1421 | 1518 | 8655
8655
|  | FTE's (except as noted) |  | FY03 | FY04 | FY05 | FY06 | FY07 | FY08
81 Project Management & Control
|  | Project Management |  | 1.41 | 1.36 | 1.0322 | 0.96154 | 0.89706 | 0.84615 | [7 empty] | 2071
|  | Project Control |  | 0.72 | 0.6 | 0.58689 | 0.55635 | 0.52361 | 0.32127 | [7 empty] | 705
|  | Admin. |  | 0.54 | 0.45 | 0.40068 | 0.15 | 0.038462 | 0 | [7 empty] | 185
82 Engineering Mgt. & Integration
|  | Engineering Management |  | 2.01 | 1.95 | 1.75 | 1.65 | 1.06 | 1.06 | [7 empty] | 2482
|  | Design Integration |  | 0.96 | 1.1 | 1 | 0.9 | [9 empty] | 917
|  | Technical Assurance |  | 0.46 | 0.75 | 0.5 | 0.4 | [9 empty] | 587
| 83 E.S.&H. and QA |  |  | Included in G&A
| 84 Project Physics |  |  | 1.71 | 0.49 | 0.33 | [10 empty] | 690
| 85 Integrated System Test | [6 empty] | 3.15 | 3.15 | [7 empty] | 796
| 8 Travel & M&S ($k) |  |  | 40 | 63 | 30 | 13 | 3 | 3 | [7 empty] | 222
8655
| 81 | Project Management & Control |  | 2849 | 17%
| 82 | Engineering Mgt. & Integration |  | 3986 | 17%
| 83 | E.S.&H. and QA |  | G&A
| 84 | Project Physics |  | 472 | 1%
| 85 | Integrated System test |  | 770 | 20%
| 8 | Total |  | 8077 | 17%
|  | Contingency on work to go |  | 18%

## PDR Baseline
WBS: |  | 8 |  | FTE's , M&S ,Travel
Manager:
|  |  |  | FY03 (april-sept) | FY04 | FY05 | FY06 | FY07
Revised Estimate | 82 | EA** EM | Reiersen | 0.425 | 0.85 | 0.85 | 0.85 | 0.63731
Revised Estimate | 82 | EA** EM | Brown | 0.30012 | 0.6 | 0.5 | 0.4 | 0.2248
Revised Estimate | 82 | EA** EM | Brooks | 0.15006 | 0.2 | 0.1 | 0.1 | 0
Revised Estimate | 82 | EM** EM | Dudek | 0.15064 | 0.25 | 0.15 | 0.05 | 0.037659
Revised Estimate | 82 | EM** EM | Perry | 0 | 0.15 | 0.15 | 0.05 | 0.037659
Revised Estimate | 82 | EE** AM | Such | 0.025 | 0.05 | 0.15 | 0.25 | 0.125
Revised Estimate | 82 | EAD* DM | Designer | 0.10023 | 0.5 | 0.5 | 0.5 | 0.37486
Revised Estimate | 82 |  |  | 1.151 | 2.6 | 2.4 | 2.2 | 1.4373
Revised Estimate | 82 | 35 | Travel | 4 | 10 | 10 | 5 | 5
Revised Estimate | 82 | 41 | M&S |  | 30
Revised Estimate |  |  |  | 291650.95 | 676424.2 | 629304.4 | 565960.2 | 375143.8 |  | 2538483.55
FY03 (april-sept)
CDR Baseline | 82 | EA**EM | Reiersen | 0.425 | 0.85 | 0.85 | 0.85 | 0.4
CDR Baseline | 82 | EA**EM | Brown | 0.225 | 0.4 | 0.4 | 0.4 | 0.2
CDR Baseline | 82 | EAD*DM | Designer | 0.3 | 0.3 | 0.3 | 0.3 | 0.4
CDR Baseline | 82 |  |  | 0.95 | 1.55 | 1.55 | 1.55 | 1
CDR Baseline | 82 | 35 | Travel | 10 | 10 | 8 | 5 | 4
CDR Baseline | 82 | 41 | M&S (purchased services) | 30 | 30
CDR Baseline | 82 |  |  | 209158.1 | 369589.8 | 379773.2 | 396946.9 | 241002.8 |  | 1596470.8
P&CO Support
|  |  |  | FY03 (april-sept) | FY04 | FY05 | FY06 | FY07
Revised Estimate | 82 | FC** EM | Simmons | 0.47059 | 0.8 | 0.75 | 0.75 | 0.52941
Revised Estimate | 82 | FC**AM | Strykowsky | 0.4 | 0.8 | 0.8 | 0.8 | 0.4
Revised Estimate |  |  |  | 0.87059 | 1.6 | 1.55 | 1.55 | 0.92941
Revised Estimate |  |  |  | 232419.2 | 439821.824 | 424376.576 | 424376.576 | 259886.848 |  | 1780881.024
|  | FC** EM | Simmons | 0.325 | 0.65 | 0.65 | 0.65 | 0.25
|  | FC**AM | Strykowsky | 0.1 | 0.2 | 0.2 | 0.2 | 0.1
CDR Baseline | 82 | FC**AM/EM | Simmons/Strykowsky | 0.425 | 0.85 | 0.85 | 0.85 | 0.35
CDR Baseline |  |  |  | 112356.4 | 233701.312 | 233701.312 | 233701.312 | 95061.824 |  | 908522.16
REBASELINE |  |  |  | FY03 | FY04 | FY05 | FY06 | FY07 |  |  | FY03 | FY04 | FY05 | FY06 | FY07 | Total
| 81 | R///RM3 | Neilson | 0.85 | 0.85 | 0.85 | 0.85 | 0.55 |  | 364.3408 | 309.6896 | 322.0772 | 334.9603 | 348.3587 | 234.4249 | 1549.5109
| 81 | R///RM3 | Schmidt | 0.31 | 0.31 | 0.07 | 0 | 0 |  | 364.3408 | 112.9456 | 117.4635 | 27.585 | 0 | 0 | 257.9941
| 81 | FC//AM | Strykowsky | 0.62 | 0.5 | 0.5 | 0.5 | 0.375 | 8.295 | 231.0069 | 143.2243 | 120.1236 | 124.9285 | 129.9257 | 101.342 | 619.544
| 81 | B///CB | Hampton | 0.41 | 0.3 | 0.3 | 0.15 | 0 |  | 90.2096 | 36.9859 | 28.1454 | 29.2712 | 15.221 | 0 | 109.6236
| 81 | 41 | M&S | 3 | 6 | 6 | 2 | 0 |  | 1.32 | 3.96 | 8.2368 | 8.5663 | 2.9696 | 0 | 23.7327
| 81 | 35 | Travel | 8 | 8 | 8 | 4 | 0 |  | 1.685 | 13.48 | 14.0192 | 14.58 | 7.5816 | 0 | 49.6608
| 81 | ORNL | Lyon | 0.25 | 0.2 | 0.1 | 0.1 | 0.1 |  | 330.78 | 82.695 | 68.8022 | 35.7772 | 37.2083 | 38.6966 | 263.1792
| 81 | ORNL | Benson | 0.1 | 0.1 | 0.08 | 0.05 | 0 | 1.38 | 246.1003 | 24.61 | 25.5944 | 21.2946 | 13.8415 | 0 | 85.3405
| 81 | ORNL | Akers | 0.1 | 0.1 | 0.1 | 0 | 0 |  | 146.92 | 14.692 | 15.2797 | 15.8909 | 0 | 0 | 45.8625
| 81 | ORNL 41 | M&S | 3 | 3 | 2 | 0 | 0 |  | 1 | 3 | 3.12 | 2.1632 | 0 | 0 | 8.2832
| 81 | ORNL 35 | Travel | 4 | 4 | 3 | 2 | 0 |  | 1 | 4 | 4.16 | 3.2448 | 2.2497 | 0 | 13.6545 | 3026.386
| 82 | EA** EM | Reiersen | 0.825 | 0.85 | 0.8 | 0.8 | 0.6 |  | 263.3186 | 217.2378 | 232.7736 | 227.8443 | 236.9581 | 184.8273 | 1099.641
| 82 | FC//EM | Simmons | 0.9 | 0.75 | 0.6 | 0.5 | 0.2 |  | 296.9179 | 267.2261 | 231.596 | 192.6879 | 166.9961 | 69.4704 | 927.9765
| 82 | EA** EM | Brown | 0.51 | 0.6 | 0.5 | 0.4 | 0 |  | 263.3186 | 134.2925 | 164.3108 | 142.4027 | 118.479 | 0 | 559.485
| 82 | EA** EM | Brooks | 0.46 | 0.75 | 0.5 | 0.4 | 0 | 15.0881 | 263.3186 | 121.1265 | 205.3885 | 142.4027 | 118.479 | 0 | 587.3967
| 82 | EM** EM | Dudek | 0.28064 | 0.35 | 0.35 | 0.35 | 0.2625 |  | 263.3186 | 73.897 | 95.848 | 99.6819 | 103.6691 | 80.8619 | 453.9579
| 82 | EM** EM | Perry | 0 | 0 | 0 | 0 | 0 |  | 263.3186 | 0 | 0 | 0 | 0 | 0 | 0
| 82 | EE** AM | Such | 0.025 | 0.05 | 0.15 | 0.25 | 0.125 |  | 44.5307 | 1.1133 | 2.3156 | 7.2247 | 12.5227 | 6.5118 | 29.6881
| 82 | EAD* DM | Designer | 0.45 | 0.5 | 0.5 | 0.5 | 0 |  | 172.3929 | 77.5768 | 89.6443 | 93.2301 | 96.9593 | 0 | 357.4104
| 82 | 35 | Travel | 4 | 8 | 7 | 5 | 3 |  | 1.685 | 6.74 | 14.0192 | 12.7575 | 9.477 | 5.9136 | 48.9073
| 82 | 41 | M&S |  | 30 |  |  |  |  | 1.32 | 0 | 41.184 | 0 | 0 | 0 | 41.184 | 4105.647
| 84 | R///RM2 | HUDSON | 0.25 | [5 empty] | 251.6074 | 62.9018 | 0 | 0 | 0 | 0 | 62.9018
| 84 | R///RM2 | KUGEL | 0.15 | 0.03 | 0.03 |  |  | 2.1 | 251.6074 | 37.7411 | 7.8501 | 8.1642 | 0 | 0 | 53.7554
| 84 | R///RM2 | ZARNSTORFF | 0.36 | 0.36 | 0.3 | 0 | 0 |  | 251.6074 | 90.5786 | 94.2018 | 81.6416 | 0 | 0 | 266.422
| 84 | EA//EM | Ku | 0.62 | 0 |  |  |  |  | 263.3186 | 163.2575 | 0 | 0 | 0 | 0 | 163.2575
| 84 | 35 | Travel | 5 | 1 | 1 | 0 | 0 |  | 1.685 | 8.425 | 1.7524 | 1.8225 | 0 | 0 | 11.9999
| 84 | 41 | M&S | 10 | 3 | 3 | 0 | 0 |  | 1.32 | 13.2 | 4.1184 | 4.2831 | 0 | 0 | 21.6015
| 84 | ORNLRM | Lazarus | 0.33 | 0.1 | 0 |  |  |  | 330.78 | 109.1574 | 34.4011 | 0 | 0 | 0 | 143.5585
| 84 | ORNL 41 | M&S | 1.3 | [5 empty] | 1 | 1.3 | 0 | 0 | 0 | 0 | 1.3
| 84 | ORNL 35 | Travel | 1.6 | [5 empty] | 1 | 1.6 | 0 | 0 | 0 | 0 | 1.6 | 726.3967
| 85 | EM** EM | Startup |  |  |  |  | 0.34762 |  | 263.3186 |  |  |  |  | 107.0842 | 107.0842
| 85 | EM**SM | Startup |  |  |  |  | 0.41715 |  | 171.0293 |  |  |  |  | 83.4633 | 83.4633
| 85 | EC**EM | Startup |  |  |  |  | 0.13905 |  | 245.6443 |  |  |  |  | 39.9586 | 39.9586
| 85 | EE**EM | Startup |  |  |  |  | 0.13905 |  | 246.9216 |  |  |  |  | 40.1664 | 40.1664
| 85 | EE**SM | Startup |  |  |  |  | 0.2781 |  | 185.9075 |  |  |  |  | 60.4826 | 60.4826
| 85 | EM** EM | Procedures |  |  |  |  | 0.91541 |  | 263.3186 |  |  |  |  | 281.9883 | 281.9883
| 85 | EM**SM | Procedures |  |  |  |  | 0.91541 | 3.1518 | 171.0293 |  |  |  |  | 183.1556 | 183.1556 | 799.1991
[11 empty] | 2137 | 1946 | 1632 | 1421 | 1518 | 8655
8655
|  | FTE's (except as noted) |  | FY03 | FY04 | FY05 | FY06 | FY07
81 Project Management & Control
|  | Project Management |  | 1.41 | 1.36 | 1.02 | 0.95 | 0.65 | [7 empty] | 2071
|  | Project Control |  | 0.72 | 0.6 | 0.58 | 0.55 | 0.38 | [7 empty] | 705
|  | Admin. |  | 0.54 | 0.45 | 0.55 | 0.4 | 0.13 | [7 empty] | 185
82 Engineering Mgt. & Integration
|  | Engineering Management |  | 2.01 | 1.95 | 1.75 | 1.65 | 1.06 | [7 empty] | 2482
|  | Design Integration |  | 0.96 | 1.1 | 1 | 0.9 | [8 empty] | 917
|  | Technical Assurance |  | 0.46 | 0.75 | 0.5 | 0.4 | [8 empty] | 587
| 83 E.S.&H. and QA |  |  | Included in G&A
| 84 Project Physics |  |  | 1.71 | 0.49 | 0.33 | [9 empty] | 690
| 85 Integrated System Test | [6 empty] | 3.15 | [7 empty] | 796
| 8 Travel & M&S ($k) |  |  | 40 | 63 | 30 | 13 | 3 | [7 empty] | 222
8655
| 81 | Project Management & Control |  | 2849 | 17%
| 82 | Engineering Mgt. & Integration |  | 3986 | 17%
| 83 | E.S.&H. and QA |  | G&A
| 84 | Project Physics |  | 472 | 1%
| 85 | Integrated System test |  | 770 | 20%
| 8 | Total |  | 8077 | 17%
|  | Contingency on work to go |  | 18%