## Chits
Design Review/QA Audit [Cog Engr/RLM/Chair] | Rvw Date | # | Chit/Audit Finding [Originator] | Review Board Recommendation | Project Disposition | Responsibility | Status | Due Date
Magnetic Diagnostic PDR Labik/Johnson/Dudek | 2005-11-15 | 1 | Does ratcheting of Vacuum Vessel temperature affect design? [Dudek] | Concur | There is no impact to the design. The vessel shell is Inconel 625 and the cable sheath and conductor is Inconel 600 the difference in CTE from 70 to 600 F is about 5 % | G Labik
Magnetic Diagnostic PDR Labik/Johnson/Dudek | 2005-11-15 | 2 | At location where conductors are in danger of being bumped by modular coils consider providing 'armor' to protect. [Dudek] | Concur | This issue was reviewed with M Viola and armor is not required. The wire is sufficiently robust to with stand a light grazing impact and furthermore is shielded by the H/C lines | G Labik
Magnetic Diagnostic PDR Labik/Johnson/Dudek | 2005-11-15 | 3 | Investigate the possibility of sharp or pointed protuberances on the modular coils poking these coils and leads. May need armor. [Viola] | Concur (see chit #2) | See # 2 | G Labik
Magnetic Diagnostic PDR Labik/Johsnon/Dudek | 2005-11-15 | 4 | Consider bringing the leads of some fraction of the coils out along port 4 or NB port. [Viola] | Disagree (NB port access is needed for other utilities.) | None required | G Labik
Magnetic Diagnostic PDR Labik/Johsnon/Dudek | 2005-11-15 | 5 | Paul Goranson should confirm that thermocouples are to be installed after the vessel saddle loops and their loops have been installed. [Johnson] | Concur | P. Goranson did confirm this via E mail on 12/8/05 | G Labik
Magnetic Diagnostic PDR Labik/Johsnon/Dudek | 2005-11-15 | 6 | ONLY REALLY NEED 1 toroidally continuous measurement - can sum partial loops, and add to continuous loop to get V loop at other, 1) locations (more work ex-vessel) however [Menard] | Other (Consider Physics to meet next week to discuss. | This would require a complete array (in the toroidal direction) of saddle coils adjacent to the voltage loop and covering the poloidal range between the voltage loop and the other location where Vloop was to be measured. This requires many more saddle coils than the current plan, and would probably cost more than providing more toroidally continuous loops. | M Zarnstorff N Pomphrey
Magnetic Diagnostic PDR Labik/Johsnon/Dudek | 2005-11-15 | 7 | Investigate impact of noise on mode i.d. with "random" coil set. [Fredrickson] | Other (See chit #6) | The impact was investigated through evaluation of response matrix condition number. Noise impact is minimized by using random loop locations | M Zarnstorff N Pomphrey
Magnetic Diagnostic PDR Labik/Johsnon/Dudek | 2005-11-15 | 8 | Consider designing NSS loops optimized w.r.t. most likely coil position errors rather than helically symmetric equilibria - is above/below midplane better? [Menard] | Other (See chit #6) | Calculations show that the present designwill adequately resolve the NSS modes. Coil position errors will be addressed by other means. Toroidal arrays above and below midplane have been shown to be inferior to the randomized locations | M Zarnstorff N Pomphrey