## Overall Plan
Modular Coil Winding Form Final Design Review WBS 141
Feb 23, 2004
| Item | Task | Resp | Deliverable | Peer Review (or task completion) |  |  |  | FDR
[5 empty] | Cognizant Eng. | Date | Status | Status | Cognizant Eng. | Date | Status
REQUIREMENTS
| Modular coil design requirements | Specify functional requirements, characteristics, and constraints for modular coil systems. Requirements flow from GRD. | Williamson | NCSX-BSPEC-140-00 | Williamson |  | 2004-05-21 |  | Williamson | 2004-05-20
| Design Criteria | Update NCSX Structural design criteria to include all modular coil materials, including composite copper/epoxy conductor | Zatz | NCSX_DesCrit_IJZ_051302 -TBD | Zatz | 2004-04-15 |  |  | Zatz | 2004-05-20
| Material Properties | Produce reference material properties and allowables for modular coil materials, including composite copper/epoxy conductor | Zatz | TBD | Zatz | 2004-04-15 |  |  | Zatz | 2004-05-20
CONFIGURATION
| Basic geometry | Develop ProE models that define basic coil configuration, including electrical, thermal, and structural features: |  |  |  |  | 50%
|  | - Winding center and x-vector | Williamson | ibl files | [5 empty] | 2004-05-20
|  | - Winding pack dimensions | Williamson | models of concept | [5 empty] | 2004-05-20
|  | - Port openings | Williamson | models of concept | Cole | 2004-02-27 |  |  |  | 2004-05-20
|  | - Poloidal break | Williamson | models of concept | [5 empty] | 2004-05-20
|  | - Flanges | Williamson | models of concept | [5 empty] | 2004-05-20
|  | - Leads and crossover | Williamson | models of concept | [5 empty] | 2004-10-12
|  | - Clamp interfaces | Williamson | models of concept | [5 empty] | 2004-05-20
|  | - PF/TF Interface | Williamson | models of concept | [5 empty] | 2004-05-20
|  | - Vessel Structural Interface | Williamson | models of concept | [5 empty] | 2004-05-20
|  | - Wing-wing bladder details | Williamson | models of concept | [5 empty] | 2004-05-20
SPECIFICATIONS
| Specifications | Prepare Build-to specification for modular coil winding forms. | Williamson | NCSX-CSPEC-141-02 | Heitzenroeder | 2004-03-15 |  |  |  | 2004-05-20
|  | Prepare Build-to specification for modular coil assembly | Williamson | NCSX-CSPEC-142-01 | Chrzanowski | 2004-06-04
|  | Prepare Build-to spec / data sheet for clamps | Williamson | NCSX-CSPEC-142-02 | Williamson
|  | Prepare Build-to spec / data sheet for chill plates | Williamson | NCSX-CSPEC-142-03 | Williamson
|  | Prepare Build-to spec / data sheet for cooling tube assemblies | Williamson | NCSX-CSPEC-142-04 | Williamson
|  | Prepare Build-to spec / data sheet for lead blocks/hardware | Williamson | NCSX-CSPEC-142-05 | Williamson
|  | Prepare Build-to spec / data sheet for I&C sensors | Williamson | NCSX-CSPEC-143-01 | Williamson
|  | Prepare Build-to spec / data sheet for autoclave | Chrzanowski | NCSX-CSPEC-144-01 | Raftopoulos
Scale Models
| STL models | Create STL models of mod coils | Williamson | Post .zip file in Intralink | [5 empty] | 2004-05-20
|  | Procure models | Williamson | 1/12 scale models, two field periods | [5 empty] | 2004-05-20
Interface Control Documents
| Interface scope sheets | Check scope sheet listing and modify as required. Assign ICDs to inidividuals | Simmons |  |  | 2004-03-05 | Complete |  |  | 2004-05-20
| ICD: Support Structures | Define net loads (gravity / em / seismic etc.) from mod coil to interfacing structure | Williamson | ICD-140-150-0001 | Williamson | 2004-03-30 |  |  |  | 2004-05-20
|  | Define the physical interface between MC assembly and PF/TF structure. | Williamson | ICD-140-150-0002 | Williamson | 2004-03-30 |  |  |  | 2004-05-20
| ICD: Vacuum Vessel | Heat load from VV to Mod coils | Goranson | ICD-120-140-0000 | Goranson | 2004-03-17 |  |  |  | 2004-05-20
|  | Develop ICD that describes clearance envelope and any physical interface between VV port extensions and Mod coils | Goranson | ICD-121-140-0000 | Goranson | 2004-02-27 | scheduled |  |  | 2004-05-20
|  | VV / mod coil assembly orientation and clearances for field period assembly and final assembly | Goranson | ICD-121-142-0000 | Goranson | 2004-02-27 | scheduled |  |  | 2004-05-20
|  | Physical support attachment to mod coils | Goranson | ICD-124-140-0000 | Goranson | 2004-03-30 |  |  |  | 2004-05-20
| ICD: Coil Services | Define modular coil fault conditions | Williamson | ICD-142-163-0001 | Williamson | 2004-03-30 |  |  |  | 2004-05-20
|  | Define LN2 connections inside cryostat | Williamson | ICD-142-161-0001 | Williamson |  |  |  |  | 2004-05-20
|  | Define electrical leads and connections inside cryostat | Williamson | ICD-142-162-0001 | Williamson |  |  |  |  | 2004-05-20
|  | Define physical attachment of coil protection system interfaces between mod coils and leads | Williamson | ICD-142-163-0002 | Williamson |  |  |  |  | 2004-05-20
| ICD: Cryostat | Define mod coil parameters that affect cool-down, heat load to cryostat. | Williamson | ICD-142-170-0001 | Williamson |  |  |  |  | 2004-05-20
|  | Define build for filler insulation around ports and between coils | Gettlefinger? | ICD-142-170-0002 | Gettlefinger? |  |  |  |  | 2004-05-20
| ICD: Field period Assembly | Define asm related attachments, lifting points, clearance requirements for mod coil to mod coil assembly. | Williamson | ICD-142-185-0001 | Williamson |  |  |  |  | 2004-05-20
|  | Define asm related attachments, lifting points, clearance requirements for field period assembly. | Williamson | ICD-142-185-0002 | Williamson |  |  |  |  | 2004-05-20
| ICD: RF System | Perform study of RF launchers and feeds in revised vacuum vessel | Cole | ICD-120-240-0001 | Cole |  |  |  |  | 2004-05-20
|  | Define envelope to accommodate ICRH. | Cole | ICD-120-240-0002 | Cole |  |  |  |  | 2004-05-20
| ICD: Diagnostics | Define co-wound magnetic sensor loops for mod coils. Document on MC assembly drawings. | Stratton | ICD-140-310-0003 | Stratton |  | 70% | complete |  | 2004-05-20
| ICD: Power systems | Define modular coil grounding connection to NCSX grounding system outside cryostat | Raki | ICD-140-400-0001 | Raki |  |  |  |  | 2004-05-20
| ICD: Control system | Define mod coil local I&C connection | Williamson | ICD-143-500-0001 | Williamson |  |  |  |  | 2004-05-20
MODELS AND DRAWINGS
18 |  | Develop detailed ProE models and drawings of production winding forms. | Williamson | Post in Intralink | Lovett
19 |  | Develop detailed ProE models and drawings of winding packs, including leads. | Williamson | Post in Intralink | Lovett/Fogarty
20 |  | Develop detailed ProE models and drawings of clamps and cooling system. | Williamson | Post in Intralink | Lovett
21 |  | Develop assembly models and drawings, including bolts, insulation, assembly features. | Williamson | Post in Intralink | Miller?
ANALYSIS
| 0 | Electrical / thermal technical basis update and check | Reiersen | GRD appendices | Reiersen |  | 30%
| 1 | Thermal analysis of mod coil windings and local cooling
| 1a | 3D analysis using ANSYS | Fan | NCSX-CALC-142-004 | Fan
| 1b | 2-D Analysis using ANSYS | Freudenberg | NCSX-CALC-142-001 | Freudenberg
| 2 | Thermal-hydraulic analysis of mod coil cooling lines
| 2a | Global analysis, hand checks | Goranson | NCSX-CALC-142-002 | Goranson
| 2b | 3-D global analysis, FEA | Dahlgren Kalish / Parsells? | NCSX-CALC-142-003 | Dahlgren Kalish / Parsells?
| 3 | EM load calculations
| 3a | Using ANSYS | Fan | NCSX-CALC-142-005 | Fan
| 3b | Using MAGFOR | Williamson, Strickler | NCSX-CALC-142-006 | Williamson, Strickler
| 4 | Eddy current analyses
| 4a | Using SPARK | Brooks | NCSX-CALC-192-007 | Brooks
| 4b | Using Eddycuff | Strickler | NCSX-CALC-142-008 | Strickler
| 5 | Error field calculations
| 5a | Analysis input | Williamson | NCSX-CALC-142-009 | Williamson
| 5b | Vacisld calc | Brooks | NCSX-CALC-142-016 | Brooks
| 5c | Stellopt calc. | Strickler | NCSX-CALC-142-017 | Strickler
| 6 | Global structural analysis of shell structure
| 6a | Due to EM loads and all combined loads | Fan | NCSX-CALC-142-010 | Fan
| 6b | Due to EM loads and all combined loads | Myatt | NCSX-CALC-142-011 | Myatt
| 6c | Dynamic/seismic investigation | Titus | NCSX-CALC-142-012 | Titus
| 7 | Detailed analysis of shell structure, including wing bladders, shell to shell connections, shell to Conventional Coil interface structure
| 7a | Bladder analysis | Jun? | NCSX-CALC-142-017 | Jun?
| 7b | Bolted joints - shell to shell and shell to interfaces | Jun? | NCSX-CALC-142-018 | Jun?
90%
| 8 | Analysis of winding packs and clamps |  |  |  |  | 90%
| 8a | winding pack thermal and mechanical stresses | Freudenberg | NCSX-CALC-142-013 | Freudenberg |  | 30%
| 8b | clamp analysis | Freudenberg | NCSX-CALC-142-013 | Freudenberg
| 8c | local thermal stresses in cooling tube / winding pack interface | Freudenberg | NCSX-CALC-142-014 | Freudenberg |  | 30%
| 8d | Geometric non-linear model of composite conductor | Myatt | NCSX-CALC-142-015 | Myatt
| 9 | FMECA | Williamson | NCSX-FMECA-140-001 | Williamson
MANUFACTURING DEVELOPMENT
33 | Conductor Properties | Produce samples of vacuum-pressure impregnated conductor for use in mechanical and thermal tests. | Chrzanowski | see attached plan | Chrzanowski
|  | Perform mechanical and thermal tests to determine properties of single and bundled conductor |  | see attached plan
|  | Document test results | Zatz? | Design memo | Zatz?
| Winding Form R&D | Develop detailed models and drawings of Type C winding form casting. | Brown / Williamson | Post in Intralink | Brown / Williamson |  | 30%
|  | Develop "tool solids" machining details for Type C winding form | Williamson | Post in Intralink | Williamson
|  | Prepare Type C prototype evaluation plan | Heitzenroeder |  | Heitzenroeder
| PPPL Winding R&D | Conduct VPI trials on straight tee section. Develop VPI procedure, recommendation on needed design features. Document VPI procedure, current center analysis. | Chrzanowski | design memo | Chrzanowski |  | Complete
|  | Perform keystone trials on coil fixture using single and bundled conductor. Document recommendations. | Chrzanowski | design memo | Chrzanowski
Perform winding tests on "inchworm" twisted casting
| UT demo coil | Wind and VPI a racetrack demonstration coil with spliced crossover joint and leads. | UT wind PPPL pot | design memo
| Flat racetrack demo coil | Wind and VPI a multi-turn flat racetrack demonstration coil with spliced crossover joint and leads. | Chrzanowski | design memo | Chrzanowski
|  | Write test plan for ractrack coil | Nelson |  | Nelson
|  | Build test stand for racetrack coil | Gettlefinger |  | Gettlefinger
|  | Test Flat Racetrack coil | Gettlefinger | design memo | Gettlefinger
| Twisted racetrack coil | Design twisted racetrack winding form | Williamson | Pro-E models, drawings in Intralink | Williamson |  |  | complete
|  | Procure twisted racetrack winding form | Heitzenroeder | SOW | Heitzenroeder |  |  | to be delivered by end of March
|  | Design clamps, chill plates, leads, and cooling system for twisted racetrack coil | Williamson Fogarty, Freudenberg | Pro-E models, drawings in Intralink | Williamson
|  | Write test plan for twisted racetrack coil | Nelson | design memo | Nelson
|  | wind and VPI twisted racetrack | Chrzanowski |  | Chrzanowski
|  | Test twisted racetrack coil | Gettlefinger | design memo | Gettlefinger
| Prototype Type C coil winding | Design clamps, chill plates, leads, and cooling system for twisted racetrack coil | Williamson | Pro-E models, drawings in Intralink | Williamson
Prepare winding facility
Wind prototype C coil
| Prototype Type C coil testing | Develop test plan
MANUFACTURING PROCEDURES
|  | MIT/QA plan for Twisted racetrack | Chrzanowski |  | Chrzanowski
|  | MIT/QA plan for Prototype coil | Chrzanowski |  | Chrzanowski
|  | MIT/QA plan for production coils | Chrzanowski |  | Chrzanowski
ASSEMBLY PROCEDURES / INPUT
OTHER DOCUMENTS
|  | Prepare FMECA identifying potential failure modes and recovery provisions. | Williamson | NCSX-FMECA-140-001 | Williamson
|  | RAM evaluation | Williamson | TBD | Williamson
COST AND SCHEDULE
|  | Estimate cost to complete for winding forms as part of 6-month review | Williamson |  | Williamson
|  | Estimate cost to complete winding as part of 6-month review | Chrzanowski |  | Chrzanowski
PDR PREPARATION
48 |  | Prepare Final Design Report | Williamson | NCSX-SDD-140-001? Would be generic name? | Williamson
49 |  | Prepare presentations for FDR | Williamson |  | Williamson

## Analysis
| Task Title Subtask descriptions | Task Leader | Delivered document | Deliverables | Start and Finish Constraints | Start | Finish | Man-hours, total | Man-hours remaining | Brooks | Brown | Cole | Dahlgren | Fan | Freuden-berg | Goranson | Jun | Kalish | Myatt | ORNL eng | Parsells | Strickler | Titus | Williamson | Zatz
0 | Electrical / thermal technical basis update and check | Reiersen | GRD appendices | Technical specs listed on web page
1 | Thermal analysis of mod coil windings and local cooling
1a | 3D analysis using ANSYS | Fan | NCSX-CALC-142-004 | operating temp distribution, ratcheting, cooldown to LN2 from RT. | coil winding pack geometry and insulation scheme finalized |  |  | 160 | 40 |  |  |  |  | 40
1b | 2-D Analysis using ANSYS | Freudenberg | NCSX-CALC-142-001 | confirm 1a. | coil winding pack geometry and insulation scheme finalized |  |  | 40 | 20 | [5 empty] | 20
2 | Thermal-hydraulic analysis of mod coil cooling lines
2a | Global analysis, hand checks | Goranson | NCSX-CALC-142-002 | LN2 flow, pressure and pressure drop | cooling tube design finalized |  |  | 40 | 20 | [6 empty] | 20
2b | 3-D global analysis, FEA | Dahlgren Kalish / Parsells? | NCSX-CALC-142-003 | Operating temp distr., Pressure distr. among lines, Cooldown from RT to LN2 temp | cooling tube design finalized |  |  | 40 | 40 | [11 empty] | 40
3 | EM load calculations
3a | Using ANSYS | Fan | NCSX-CALC-142-005 | All combinations of EM loads on coils |  |  |  | 80 | 20 |  |  |  |  | 20
3b | Using MAGFOR | Williamson, Strickler | NCSX-CALC-142-006 | All combinations of EM loads on coils |  |  |  | 80 | 40 | [14 empty] | 40
4 | Eddy current analyses
4a | Using SPARK | Brooks | NCSX-CALC-192-007 | Provides time constant, error fields from shell |  |  |  | incl in WBS 19 | incl in WBS 19
4b | Using Eddycuff | Strickler | NCSX-CALC-142-008 | Confirm time constant, error fields from shell, island size |  |  |  | incl in WBS 19 | incl in WBS 19
5 | Error field calculations
5a | Analysis input | Williamson | NCSX-CALC-142-009 | - Need "coils file" for winding trajectory, including leads, for multiple turns for all coils - with and w/o predicted deformations - need postulated errors in winding geometry, location | need lead geometry, location |  |  | 80 | 80 | [14 empty] | 80
5b | Vacisld calc | Brooks | NCSX-CALC-142-016 | develop island sizes for various imperfections | Need info from 5a. |  |  | incl in WBS 19 | incl in WBS 19
5c | Stellopt calc. | Strickler | NCSX-CALC-142-017 | develop island sizes for various imperfections | Need info from 5a. |  |  | incl in WBS 19 | incl in WBS 19
6 | Global structural analysis of shell structure
6a | Due to EM loads and all combined loads | Fan | NCSX-CALC-142-010 | Stress and deflection Will windings be included to check 7a? | Need info from 3 |  |  | 3000 | 400 |  |  |  |  | 400
6b | Due to EM loads and all combined loads | Myatt | NCSX-CALC-142-011 | Stress and deflection Will windings be included to check 7a? | Need info from 3 |  |  | 320 | 320 | [9 empty] | 320
6c | Dynamic/seismic investigation | Titus | NCSX-CALC-142-012 | estimate dynamic effects for seismic loading |  |  |  | incl in VV task? | incl in VV task?
7 | Detailed analysis of shell structure, including wing bladders, shell to shell connections, shell to Conventional Coil interface structure
7a | Bladder analysis | Jun? | NCSX-CALC-142-017 | Stress and deflection | Need bladder design |  |  | 40 | 40 | [7 empty] | 40
7b | Bolted joints - shell to shell and shell to interfaces | Jun? | NCSX-CALC-142-018 | Stress and deflection | need interface loads from 5a,b,c |  |  | 40 | 40 | [7 empty] | 40
8 | Analysis of winding packs and clamps
8a | winding pack thermal and mechanical stresses | Freudenberg | NCSX-CALC-142-013 | distortion at end of cure, end of cooldown, beginning of pulse, end of pulse and maximum alternating strain for fatigue check | need final composite material properties, including cure shrinkage |  |  | 400 | 120 | [5 empty] | 120
8b | clamp analysis | Freudenberg | NCSX-CALC-142-013 | Temperature distribution along support for various end conditions | need clamp properties |  |  | 400 | 120 | [5 empty] | 120
8c | local thermal stresses in cooling tube / winding pack interface | Freudenberg | NCSX-CALC-142-014 | Temperature distribution along support for various end conditions | need winding pack / tube / insulation final properties |  |  | 40 | 20 | [5 empty] | 20
8d | Geometric non-linear model of composite conductor | Myatt | NCSX-CALC-142-015 | predict properties and non-linear stiffness behavior as well as internal thermal stresses during pulse |  |  |  | 40 | 8 | [9 empty] | 8
9 | FMECA | Williamson | NCSX-FMECA-140-001 |  |  |  |  | 40 | 40 | [9 empty] | 40
[8 empty] | 4840 | 1368 | 0 | 0 | 0 | 0 | 460 | 280 | 20 | 80 | 0 | 368 | 0 | 40 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1368

## Peer rev list
Pre-May 21 Peer Reviews
Peer reviews are being scheduled for two reasons. Having external reviewers at the FDRs does not give us control in measuring ourselves against our own standards. Peer reviews provide a formal mechanism (chits) for getting expert input and tracking resolution of that input. (ref W. Reiersen)
Peer review designation | Primary WBS | What | Cog engineer | When Initial (final) | Purpose
| 19 | VV port configuration. | Cole | 6-Feb-2004 (27 Feb 2004) | Part I of this peer review was exemplary. We need to hold Part II to close out the action items in a timely manner. At the conclusion of this peer review, the [1] port allocations will be completely defined, [2] port sizes, locations, and orientations will be finalized, and [3] clearances between the port extensions and other stellarator core hardware will be confirmed to be adequate.
| 12 | VV Development Spec. | Goranson | 2004-03-15 | A subsystem development spec has been drafted that defines the performance requirements for the vacuum vessel (WBS 12). A spec review should be conducted to assure that all relevant requirements have been captured; that we are confident that the design meets the requirements; and that evaluation criteria for verification of the requirements have been established.
| 12 | VVSA Product Spec. | Viola | 2004-03-25 | A product spec is needed that defines the requirements and the quality conformance inspections and tests that are needed in order to verify that the requirements have been met. A spec review should be conducted for the product spec prior to the May FDR (and also prior to preliminary release of the product spec to the suppliers for starting development of their proposals).
| 12 | VV Structural Design. | Dahlgren | 2004-04-23 | Detailed analysis plans have been drafted for the vacuum vessel. As the analyses are completed, they should be peer reviewed to assure that everything that needs to be done has been done, understand the implications of the results, and modify the design of the vacuum vessel and its interfaces as required.
| 12 | Weld joint R&D plan | Goranson | 2004-02-25 | Weld joint R&D plans should be peer reviewed as soon as the design of the articles is complete and the test plans have been documented. We have been caught once already by having the R&D completed before we carefully reviewed what we were doing.
|  | Weld joint R&D results | Viola | 7/12/2004 is latest
| 12 | Evaluation of the PVVS. | Viola |  | The two PVVS are supposed to be delivered to PPPL by the end of March. We will evaluate each prototype here at PPPL. The results of the evaluations should be peer reviewed to identify issues that might affect our designs, drawings, specifications, or MIT/QA plans.
| 12 | Review of VV Drawings. | Goranson | 1-Apr-04 (5/14/2004) | Prior to the FDR (and also prior to preliminary release of the drawings to the suppliers for starting development of their proposals), a peer review should be conducted for all VV drawings that will be part of the VVSA procurement.
| 13 | Conventional Coils and Coil Structures Development Spec. | Kalish |  | A subsystem development spec is being drafted that defines the performance requirements for the conventional coils (WBS 13) and coil structures (WBS 15). A spec review should be conducted in advance of the PDR to assure that all relevant requirements have been captured and that the design and analysis address all of the requirements.
| 18 | Field Period Assembly. | Brooks/Cole | 2004-03-31 | The purpose is to critically review the motions of the coils and vacuum vessel required for field period assembly, to verify that adequate clearances exist at all times, that the implied tooling requirements are reasonable and achievable, and that appropriate provisions for metrology and in-process sensors have been made.
| 7 | Machine Assembly. | Cole / Perry? | 2004-03-31 | The purpose is to critically review the motions of the field periods and spool pieces required for machine assembly, to verify that adequate clearances exist at all times, that the implied tooling requirements are reasonable and achievable, and that appropriate provisions for metrology and in-process sensors have been made. Machine assembly requirements for the design of the base support structure should also be finalized at this time.
| 19 | Seismic Design. | Titus | 2004-03-31 | Our plan is to do a seismic analysis of the whole stellarator core using a simplified “stick” model. The purpose of this analysis is to develop loads to be used in the seismic analysis of specific components. This information is required to complete subsequent analyses required for upcoming PDRs and FDRs.
| 14 | Modular Coil Development Spec. | Williamson | 2004-03-15 | A subsystem development spec has been drafted that defines the performance requirements for the modular coils (WBS 14). A spec review should be conducted soon to assure that all relevant requirements have been captured; that we are confident that the design meets the requirements; and that evaluation criteria for verification of the requirements have been established.
| 14 | MCWF Product Spec. | Heitzenroeder | 2004-03-15 | A product spec is needed that defines the requirements and the quality conformance inspections and tests that are needed in order to verify that the requirements have been met. A spec review should be conducted for the product spec prior to the May FDR (and also prior to preliminary release of the product spec to the suppliers for starting development of their proposals).
| 14 | Modular Coil Structural Design. | Williamson |  | Detailed analysis plans are being developed for the modular coils. As the analyses are completed, they should be peer reviewed to assure that everything that needs to be done has been done, understand the implications of the results, and modify the design of the modular coils and its interfaces as required.
| 14 | Evaluation of the Prototype MCWF. | Heitzenroeder |  | The two MCWFs are supposed to be delivered to PPPL this summer. We will evaluate each prototype here at PPPL. The results of the evaluations should be peer reviewed to identify issues that might affect our designs, drawings, specifications, or MIT/QA plans as well as supplier selection.
| 14 | Review of Modular Coil Drawings. | Williamson |  | Prior to the FDR (and also prior to preliminary release of the drawings to the suppliers for starting development of their proposals), a peer review should be conducted for all modular coil drawings that will be part of the MCWF procurement.
| 19 | Structural Design Criteria and Material Allowables - VV | Zatz? | 2004-03-10
| 19 | Structural Design Criteria and Material Allowables - VV | Zatz? | 2004-03-10
| 14 | Mod coil winding form hardware design | Williamson | 2004-04-14 | Machining details, Nuts, bolts, shims, bladders, assy balls, etc.
| 14 | Mod coil winding details design | Williamson | 2004-03-15 | We need to close the loop on the clamps, cooling tubes, chill plates, insulation scheme, slip planes, and leads
| 14 | Twisted Racetrack Design | Williamson | 2004-03-15
| 14 | Racetrack coil (Flat and twisted Test plan(s) | Nelson / Gettlefinger
| 14 | Twisted Racetrack MIT/QA plan | Chrzanowski
| 14 | Prototype Type C winding MIT/QA plan | Chrzanowski
| 14 | Production mod coil winding product spec | Chrzanowski
| 14 | Production modular coil MIT/QA plan | Chrzanowski
| 14 | Field period assembly mockups | Cole |  | We need to order these, and we need to know what and why we are ordering
| 19? | EM loads and fault conditions | Fan?
| 19 | Eddy currents and disruption loads | Brooks
|  | Type A,B mod coil castings for solidification analysis | Williamson | 2004-03-03