## Overall plan
Vacuum Vessel VVSA Final Design Review, WBS 121
Feb 23, 2004
| Item | Task | Resp. | Deliverable | Peer Review (or task completion) |  |  | FDR
[5 empty] | Cognizant Eng. | Date | Status | Cognizant Eng. | Date | Status
REQUIREMENTS
| Vacuum vessel system design requirements | Specify functional requirements, characteristics, and constraints for vacuum vessel (vv) systems. Requirements flow from GRD. | Goranson | NCSX-BSPEC-120-00 | Goranson | 2004-03-15 |  | Goranson | 2004-05-21
| Design Criteria | Update NCSX Structural design criteria to include all vessel materials and processes | Zatz | NCSX_DesCrit_IJZ_051302 -TBD | Zatz | 2004-03-15 |  | Zatz
| Material Properties | Produce reference material properties and allowables for vacuum vessel materials | Zatz | TBD | Zatz | 2004-03-15 |  | Zatz
CONFIGURATION
| Basic geometry | Develop ProE models that define basic vessel configuration, including heating, and structural features: | Goranson
|  | - Shell | Goranson | models of concept | Brooks / Brown / Nelson | 2004-03-03 | geometry defined |  | 2004-05-21
|  | - Ports and flanges | Goranson | models of concept | Cole | 2004-02-27 | scheduled |  | 2004-05-21
|  | - Insulation | Goranson | models of concept | Goranson | 2004-02-27
|  | - Cooling/heating lines | Goranson | models of concept | Goranson | 2004-02-27
|  | - Vessel support interfaces | Goranson | models of concept | Goranson | 2004-02-27
SPECIFICATIONS
| Specifications | Prepare Build-to specification for vvsa. | Goranson | NCSX-CSPEC-121-02 | Viola | 2004-03-25 |  |  | 2004-05-21
|  | Prepare Build-to specification for thermal insulation blankets. | Goranson | NCSX-CSPEC-122-01 | Goranson | 2005-01-15 | not reqd for VVSA review
|  | Prepare Build-to spec / data sheet for cooling tubes. | Goranson | NCSX-CSPEC-123-01 | Goranson | 2005-01-15 | not reqd for VVSA review
|  | Prepare Build-to spec / data sheet for port heaters | Goranson | NCSX-CSPEC-122-02 | Goranson | 2005-01-15 | not reqd for VVSA review
|  | Prepare Build-to spec / data sheet for VV supports | Goranson | NCSX-CSPEC-124-01 | Goranson | 2005-01-15 | not reqd for VVSA review
|  | Prepare Build-to spec / data sheet for VV I&C sensors | Goranson | NCSX-CSPEC-125-01 | Goranson | 2005-01-15 | not reqd for VVSA review
Scale Models
| STL models | Create STL models of vessel | Goranson | Post .zip file in Intralink | Cole | 2004-04-30
|  | Procure models through quickparts.com | Goranson | 1/12 scale models, 2 of each coil type | Cole | 2004-04-30
Interface Control Documents
| Interface scope sheets | Check scope sheet listing and modify as required. Assign ICDs to inidividuals | Simmons |  | Simmons / Nelson | 2004-03-05
| ICD: 12/13 Vacuum Vessel / Conv. Coils | Develop ICD that describes clearance envelope and any physical interface between VV and Conv. Coils | Goranson | ICD-120-130-0000 | Goranson | 2004-02-27 | scheduled |  | 2004-05-21
| ICD: 12/14 VV port ext. interface with mod coils | Heat load from VV to Mod coils | Goranson | ICD-120-140-0000 | Goranson | 2005-03-17 |  |  | 2004-05-21
|  | Develop ICD that describes clearance envelope and any physical interface between VV port extensions and Mod coils | Goranson | ICD-121-140-0000 | Goranson | 2004-02-27 | scheduled |  | 2004-05-21
|  | VV / mod coil assembly orientation and clearances for field period assembly and final assembly | Goranson | ICD-121-142-0000 | Goranson | 2004-02-27 | scheduled |  | 2004-05-21
|  | Physical support attachment to mod coils | Goranson | ICD-124-140-0000 | Goranson | 2004-03-30
| ICD: 12/17 vv/cryostat | Heat load from VV to cryo system | Goranson | ICD-120-160-0000 | Goranson | 2004-03-17 |  |  | 2004-05-21
|  | heating and cooling penetrations at cryostat boundary |  | ICD-123-160-0000 |  |  |  |  | 2004-05-21
|  | Define port extension interface with cryostat boundary. | Goranson | ICD-121-160-0000 | Goranson | 2004-03-17 |  | generic interface defined -need to identify interfaced ports for MIE proj. | 2004-05-21
| ICD: 12/18 vv/joint | VV field joint study - define requirements and results | Goranson | ICD-120-180-0001 | Goranson | 2004-04-30 |  |  | 2004-05-21
|  | define vessel tooling needs, lifting points, and clearances required for vessel field period assy. | Goranson | ICD-120-180-0002 | Goranson | 2005-03-17 |  |  | 2004-05-21
|  | define vessel field joint attachments, tooling needs, lifting points, and clearances required for final core assy. | Goranson | ICD-120-180-0003 | Goranson | 2005-03-17 |  |  | 2004-05-21
|  | define requirements for cooling tube and insulation attachment and installation | Goranson | ICD-120-184-0001 | Goranson | 2005-03-17 |  |  | 2004-05-21
|  | Define special tools/fixtures/clearance/measurement requirements for port attachment | Goranson | ICD-121-180-0001 | Goranson |  |  |  | 2004-05-21
| ICD: 12/21-23 vv/invessel components | Define attachment schemes and envelopes for in-vessel components. | Goranson | ICD-120-250-0001 | Goranson | 2004-03-03 |  |  | 2004-05-21
|  | Define attachment schemes and envelopes for pellet injector guide tubes | [6 empty] | 2004-05-21
| ICD: 12/24 vv/ICRH | Perform study of RF launchers and feeds in revised vacuum vessel | Cole | ICD-120-240-0001 | Cole |  |  |  | 2004-05-21
|  | Define envelope to accommodate ICRH. | Cole | ICD-120-240-0002 | Cole |  |  |  | 2004-05-21
| ICD: 12/25 vv/NBI | Define envelope to accommodate NBI. | Cole | ICD-123-310-0000 | Cole | 2004-02-27 | scheduled
| ICD: 12/3 vv/ports | Define port orientation, allocation, weight limits, etc.. | Cole | ICD-121-300-0001 | Cole | 2004-03-10 |  |  | 2004-05-21
|  | Define the interface between the magnetic diagnostics outside the VV and the cooling lines that trace the same region. | Goranson | ICD-123-310-0001 | Goranson |  | complete
| ICD: 12/4 vv/grounding | Define VV port heater requirements (#/power) | Goranson | ICD-123-140-0001 | Goranson
|  | Define VV grounding connection to NCSX ground system. | Goranson | ICD-120-140-0001 | Goranson |  |  |  | 2004-05-21
|  | Define heater power interfaces with WBS 4 | Goranson | ICD-120-140-0002 | Goranson |  |  |  | 2004-05-21
| ICD: 12/5 vv/I&C connect | Define heater control and connections to central I&C systems. | Goranson | ICD-123-500-0001 | Goranson
|  | Define local I&C connections to central I&C systems. | Goranson | ICD-125-500-0001 | Goranson
| ICD: 12/61,64 vv/cooling | Study to determine water or helium cooling / heating of VV | Goranson | ICD-123-600-0001 | Goranson
|  | Define VV cooling requirements (He temp/pressure/flow) | Goranson | ICD-123-640-0001 | Goranson
|  | Define physical attachments between VV and WBS 6 | Goranson | ICD-123-600-0001 | Goranson
MODELS AND DRAWINGS
|  | Develop detailed ProE models and drawings of production vv including ports | Goranson | See dwg list | Jones | 1-Apr-04 (5/14/2004) |  |  | 2004-05-21
|  | Develop interface ProE models and drawings of insulation. | Goranson | See dwg list | Fortier | 1-Apr-04 (5/14/2004) |  |  | 2004-05-21
|  | Develop interface ProE models and drawings of vv support interfaces. | Goranson | See dwg list | Fortier | 1-Apr-04 (5/14/2004) |  |  | 2004-05-21
|  | Develop assembly models of vv during field period assy and final assembly | Cole | See dwg list | Miller? | 1-Apr-04 (5/14/2004) |  |  | 2004-05-21
|  | Develop ProE models of vv coolant lines. | Goranson | See dwg list | Hargrove or Fortier | 1-Apr-04 (5/14/2004) |  |  | 2004-05-21
ANALYSIS
| 1 | Thermal-hydraulic analysis of vessel and cooling lines
| 1a | Analytical calculations | Goranson | NCSX-CALC-121-002 | Goranson | 2004-02-26 |  |  | 2004-05-21
| 1b | Analysis using software code | Kalish | NCSX-CALC-121-004 | Kalish |  |  |  | 2004-05-21
| 2 | Analysis of thermal insulation thickness, heat leak to coils
| 2a | Global analysis, hand checks | Goranson | NCSX-CALC-121-003 | Goranson | 2004-02-26 |  |  | 2004-05-21
| 2b | 3-D global analysis, FEA | Dahlgren | NCSX-CALC-121-005 | Dahlgren |  |  |  | 2004-05-21
| 2c | Local tube to shell / spacing analysis | Freudenberg (Goranson check in appendix) | NCSX-CALC-121-001 | Freudenberg (Goranson check in appendix) | 2004-02-11 | complete pending chit resolution |  | 2004-05-21
| 2d | Local VV to MC thermal analysis | Freudenberg | NCSX-CALC-121-006 | Freudenberg | 2004-03-03 |  |  | 2004-05-21
| 3 | Eddy current analyses
| 3a | During startup, error field | Brooks | NCSX-CALC-192-001 | Brooks | 2004-05-03 | needs doc. |  | 2004-05-21
| 3b | Disruption loads | Brooks | NCSX-CALC-192-002 | Brooks | complete | needs doc. |  | 2004-05-21
| 4 | Eddy current analysis check
| 4a | During startup, error field | Strickler | NCSX-CALC-192-003 | Strickler | 2004-06-14 |  |  | 2004-05-21
| 4b | Disruption loads | Strickler | NCSX-CALC-192-004 | Strickler | 2004-06-14 |  |  | 2004-05-21
| 5 | Structural analysis of vessel, including global analyses of assembly as well as detailed analysis of port to shell connections
| 5a | gravity loads, during / after assembly | Freudenberg | NCSX-CALC-121-007 | Freudenberg | 2004-04-15 |  |  | 2004-05-21
| 5b | Disruption loads, vacuum loads, assembly loads. Buckling | Dahlgren | NCSX-CALC-121-008 | Dahlgren | 2004-04-23 |  |  | 2004-05-21
| 5d | Dynamic/seismic/fatigue | Titus | NCSX-CALC-121-009 | Titus | 2004-04-15 |  |  | 2004-05-21
| 6 | Structural check | Titus | NCSX-CALC-121-010 | Titus | 2004-05-12 |  |  | 2004-05-21
| 7 | Analysis of vessel supports, thermal and mechanical
| 7a | Mechanical analysis of supports | Freudenberg? | NCSX-CALC-124-002 | Freudenberg? | 2004-03-30 |  |  | 2004-05-21
| 7b | Thermal analysis of supports | Freudenberg? | NCSX-CALC-124-003 | Freudenberg? | 2004-03-30 |  |  | 2004-05-21
| 7c | Geometric analysis of supports/VV motion | Nelson | NCSX-CALC-124-001 | Nelson | 2004-03-08 |  |  | 2004-05-21
| 8 | Fitup and final assembly considerations
| 8a | Spool piece handling | Goranson | NCSX-CALC-121-011 | Brown/Cole | 2004-03-30 |  |  | 2004-05-21
| 8b | Weld shrinkage | Goranson | NCSX-CALC-121-012 | Goranson | 2004-03-30 |  |  | 2004-05-21
| 8c | Temperature distribution | Goranson | NCSX-CALC-121-013 | Goranson | 2004-03-30 |  |  | 2004-05-21
| 9 | FMECA | Goranson | NCSX-FMECA-120-001 | Goranson | 2004-03-24 |  |  | 2004-05-21
MANUFACTURING DEVELOPMENT
|  | Prepare PVSA evaluation plan | Goranson | Evaluation plan | Viola | 2004-03-01
|  | Perform project evaluation of PVSA | Viola | memo to SPEB | Viola | 2004-04-05
|  | Prepare drawings and test procedure for vacuum vessel assembly joint welding R&D article | Goranson |  | Goranson | 2004-02-25
|  | Prepare VV assy joint test articles and perform tests | Viola |  | Viola | (7/12/2004 is latest)
OTHER DOCUMENTS
|  | Prepare FMECA identifying potential failure modes and recovery provisions | Goranson | NCSX-FMECA-120-001 |  | 2004-03-25 |  |  | 2004-05-21
|  | RAM evaluation | Goranson | TBD |  |  |  |  | 2004-05-21
COST AND SCHEDULE
|  | Estimate cost to complete as part of 6-month review | Goranson |  |  | 2004-06-01
FDR PREPARATION
|  | Prepare Final Design Report | Goranson | NCSX-SDD-120-001? Would be generic name? |  | 2004-05-05 |  |  | 2004-05-21
|  | Prepare presentations for FDR | Goranson |  |  | 2004-05-14 |  |  | 2004-05-21
Summary list of deliverables:
0 | GRD
1 | VV Design-to Specification
2 | Structural design criteria / materials database and allowables
3 | VV Design Basis Document
4 | VVSA build-to technical spec.
5 | Technical Data and Analysis
6 | Model and Drawing Description
7 | Interface Control Documents
8 | Manuf Development Results
9 | Updated Cost to complete
10 | Final MIT Plan
11 | Field Period and Machine Asm Plans
12 | Risk and Mitigation Plan
13 | PDR Chits Disposition Report

## Analysis plan
| Task Title Subtask descriptions | Task Leader | Deliverables | Start and Finish Constraints | Delivered document | Start | Finish | Man-hours, total | Man-hours remaining | Brooks | Brown | Cole | Dahlgren | Hirshman | Jun | Ku | ORNL eng | Strickler | Williamson | Zatz
1 | Thermal-hydraulic analysis of vessel and cooling lines
1a | Analytical calculations | Goranson | He flow, pressure and pressure drop | bakeout temperature and cooldown criteria decided | NCSX-CALC-121-002 |  |  | 80 | 20
1b | Analysis using software code | Kalish | confirm 1a. | bakeout temperature and cooldown criteria decided | NCSX-CALC-121-004 |  |  | 40 | 40
2 | Analysis of thermal insulation thickness, heat leak to coils
2a | Global analysis, hand checks | Goranson | insulation thickness, heat balance, port temp distr. and heater parameters | bakeout temperature and cooldown criteria decided | NCSX-CALC-121-003 |  |  | 80 | 32
2b | 3-D global analysis, FEA | Dahlgren | thermal time constant, 3-D temp distr during operation and baking, heat loss to cryostat | bakeout temperature and cooldown criteria decided | NCSX-CALC-121-005 |  |  | 200 | 80
2c | Local tube to shell / spacing analysis | Freudenberg (Goranson check in appendix) | VV local temp distr. Vs tube to tube and clamp to clamp spacing, local stresses due to temp gradient | tube attachment design | NCSX-CALC-121-001 |  |  | 40 | 8
2d | Local VV to MC thermal analysis | Freudenberg | local temp distr in MC clamps and shell vs insulation thickness |  | NCSX-CALC-121-006 |  |  | 40 | 20
3 | Eddy current analyses
3a | During startup, error field | Brooks | Provides time constant, error fields from vessel |  | NCSX-CALC-192-001 |  |  | incl in WBS 19
3b | Disruption loads | Brooks | Provides worst case disruption loads for VDE and radial disruption |  | NCSX-CALC-192-002 |  |  | incl in WBS 19
4 | Eddy current analysis check
4a | During startup, error field | Strickler | Confirm time constant, island size for typical case |  | NCSX-CALC-192-003 |  |  | incl in WBS 19
4b | Disruption loads | Strickler | Confirm disruption loads for VDE |  | NCSX-CALC-192-004 |  |  | incl in WBS 19
5 | Structural analysis of vessel, including global analyses of assembly as well as detailed analysis of port to shell connections
5a | gravity loads, during / after assembly | Freudenberg | Confirm low stress during assembly | work done for PDR, to be updated by Dahlgren in task 5b | NCSX-CALC-121-007 |  |  | 80 | 0
5b | Disruption loads, vacuum loads, assembly loads. Buckling | Dahlgren | Global Stress and deflection of vessel as well as local port to shell stresses | port size and distribution | NCSX-CALC-121-008 |  |  | 400 | 360
5d | Dynamic/seismic/fatigue | Titus | include dynamic effects for disruption / seismic loading |  | NCSX-CALC-121-009 |  |  | 160 | 160
6 | Structural check | Titus | Confirm Dahlgren analysis |  | NCSX-CALC-121-010 |  |  | 160 | 160
7 | Analysis of vessel supports, thermal and mechanical
7a | Mechanical analysis of supports | Freudenberg? | stress distribution in supports |  | NCSX-CALC-124-002
7b | Thermal analysis of supports | Freudenberg? | Temperature distribution along support for various end conditions |  | NCSX-CALC-124-003 |  |  | 40 | 40
7c | Geometric analysis of supports/VV motion | Nelson | vessel motion at RT, oper. Temp. and bakeout |  | NCSX-CALC-124-001 |  |  | 40 | 30
8 | Fitup and final assembly considerations
8a | Spool piece handling | Goranson | stresses in spool piece port attachment |  | NCSX-CALC-121-011
8b | Weld shrinkage | Goranson | Estimate weld shrinkage to compare with R&D, estimate initial position |  | NCSX-CALC-121-012 |  |  | 20 | 20
8c | Temperature distribution | Goranson | Temperature distribution around weld and heating of adjacent components |  | NCSX-CALC-121-013
9 | FMECA | Goranson | Failure modes for VV systems |  | NCSX-FMECA-120-001 |  |  | 40 | 40