## Sheet1
Chit# | Chit Content [Originator] | Review Board Comments and Recommendations | Review Board Comment/ Recommendation | Cognizant Engineer Disposition | RLM Review | Cognizant Engineer Closeout
1 | Consider making an intermediate port connection on all circular ports, with the joint just outboard of the modular coil. Consider making the extension tubes out of stainless. Consider an assembly strategy which would permit removal and replacement of extension tube at future date. [D. Johnson] | Concur | Action: M. Cole
2 | Present run of RF parts does not enter the vessel near enough to the ends at the antenna to allow a connection. RF parts need to be revisited. [R. Majeski] | Concur | Action: M. Cole
3 | Needs to reposition the PF 5 leads (or rotate coil) to eliminate lead interference with Port 16. [T. Brown] | Concur | Action: M. Cole and T. Brown
4 | Reposition port #13, its too close to the TF winding. [T. Brown] | Concur | Action: M. Cole and T. Brown Include RF issues in the analysis
5 | Consider unifying ports 9 and 13 to avoid interference during bake, to reduce costs. [Zarnstorff] | Concur | Action: M. Cole
6 | Near port 9, does the TF support structure have to be this large and come this close to the port? Can the edge of the support structure be pulled back? [Zarnstorff] | Concur | Action: T. Brown (Investigate clearance options)
7 | Consider stepping the diameter of port 3 to a larger diameter tube outside the modular coils. This would allow a larger angle of view of the oblate cross-section (a region that has limited access). [Zarnstorff] | Other | See Chit #1
8 | In the regions of very close proximity between vessel and coils, what instrumentation should be built into the structure to allow monitoring so that bake out does not endanger the coils. [Zarnstorff] | Disagree | Action: Reiersen to assign Not part of the requirements for this WBS. Should be considered during ISTP.
9 | On the NB Port: the internally bolted joints must be (somehow) designed so that each bolt does not become a virtual leak. [Zarnstorff] | Concur | Action: M. Cole
10 | Include (consider) the port tolerances in the minimum clearance study. [Heitzenroeder] | Concur | Action: M. Cole
11 | Port 16 vs. # small bolts issue (interference?) [Gettelfinger] | Concur | Action: M. Cole to solve
12 | Resolve bake out clearances at Port 4. Can diag stand a lesser port size? [Gettelfinger] | Concur | Action: M. Cole to resolve with diagnostic input
13 | Work out the assembly sequence of the NB transition duct internal seal. (Can a man make it up from the inside?) [Dudek] | Concur | Action: M. Cole
14 | Further consider port NB joint detail. Bolted joint with seal weld? [Gettelfinger] | Other | See Chit #13
15 | Consider beam geometry with port NB, all OK? [Gettelfinger] | Concur | Action: M. Cole
16 | Have all system interfaces been reviewed? Are services other than diagnostic e.q., (RF, NB) been consulted? [Viola] | Concur | Action: W. Reiersen to resolve (Are the port requiremnents for the invessel hardware, PFC's)
17 | This design represents # port additions of about 30% to the previous design. Besides the obvious installation of the ports there is additional insulating cooling tubes, assembly alignment etc. Is this cost budgeted? [Viola] | Concur | Action: B. Nelson to assess the cost and schedule impact
18 | Consider joining adjacent circular ports into one oval shape if there is any advantage. [Viola] |  | See Chit #5
19 | Be wary of conflate seal leaks due to thermal gradients across the copper. Sandia and PPPL have had failures. [Gettelfinger] | Concur | Action: M. Cole
20 | Check clearances between welds of adjacent tubes. You will get a significant amount of distortion. [Viola] | Concur | Action: M. Cole
21 | The additional ports virtually "use up" any spare locations where diamond wire cutting could occur. An alternative method of cutting the vessel is needed. [Viola] | Concur | Check ports cutting plans interferences.
22 | What is the project's position on Inconel vs. SS port extrusions? Pick one and document the decision. [Gettelfinger] | Concur | Action: P. Goranson to determine
23 | Re-orient rather than re-locate or re-sizing to address tight clearances. (This is ok with diagnostics.) [Heitzenroeder] | Concur | Action: M. Cole