## Sheet1
Chit# | Comment/Recommendation/Concern | Originator | Board Disposition | Review Board Comment/ Recommendation | Cognizant Engineer Disposition | RLM Review | Cognizant Engineer Closeout
1 | Verify that existing NEPA and WP cover the handling of cryogens and powering of test coils. | Reiersen | Concur
2 | Add engough instrumentation to verify our thermal and stress analysis-- looks tight now. | Reiersen | Concur
3 | Determine forces on clamp bolts and verfiy factor of safety with respect to pull out strength | Kalish | Concur
4 | Need to finalize design of clamps -- not clear that we have a desggin that works. | Reiersen | Concur | See chit #3
5 | Consider going back to the half-lapped insulation if that is likely to be the reference design. | Reiersen | Concur
6 | Try winding inside / outside turn rather than layer by layer | Nelson | Other | Jim C. to consider this .
7 | Suggest investigatin < half-lapped insulation for R&D program to verify "armadillo- effect". | Heitzenroeder | Other | Out of scope (see chit 5)
8 | Consider thermocouple buried in the base of the tee. This would measure any heat going into the casting. | Raftopoulos | Concur
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52