## Sheet1
Chit# | Comment/Recommendation/Concern | Originator | Board Disposition | Review Board Comment/ Recommendation | Cognizant Engineer Disposition | RLM Review | Cognizant Engineer Closeout
1 | Consider Cooling Coil to prevent over temperature and provide active control | Parsells | Concur
2 | Consider fusible link damper to prevent combustion products from escaping to test cell in case of fire in the tank. | Parsells | Concur
3 | During a rapid cooldown, tank will be vented to TFTR test cell. What design or administrative provisions are required for the safety of the test cell occupant (e.g. in the event of a fire in the pressure vessel)? | Reiersen | Concur | See Chit#2. S. Raftopoulos to investigate and respond.
4 | Lifting eyes on lid won't clear insulation as drawn. Do lid bolts? | Dudek | Concur | Raftopoulos to check other components for interference with insulation.
5 | Consider generationg a manufacturing, inspection, and test plan. | Malsbury | Concur | Will be considered.
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52