## Sheet1
Please click on NCR # to view the Nonconformance Report
NCR # | Originator | RAP # | Open Date | Status | Item | Nonconforming Condition | PPPL/Supplier
WBS 13 - Coils
SC07017 | Everson Tesla | NA | 4/9/2007 | CLOSED | Coil 1 | Parts conform ? Drawing but don't comply to plastic made that was machined to the low side | Supplier
SC07028 | Everson Tesla | NA | 6/27/2007 | CLOSED | Coil 3 | Wedge W08 with false cut was detailed in photographs and DR report | Supplier
SC07033 | Everson Tesla | NA | 7/17/2007 | CLOSED | Coil 1 | Lead position location of one lead 3/8" off center | Supplier
SC07034 | Everson Tesla | NA | 7/1707 | CLOSED | Coil 2 | O-Ring Material, Separation of wedge from coil #2 of the conclusion of the one stop VPI | Supplier
SC07036 | Everson Tesla | NA | 7/24/2007 | CLOSED | Coil 4 | Wedge W11 & W12 with ???? | Supplier
SC07038 | Everson Tesla | NA | 8/6/2007 | CLOSED | Coil 1 | Cold test temperature -193ºC, resistance -.00478 ohms, diagnostic loop wire on center within .015" | Supplier
SC07039 | Everson Tesla | NA | 8/7/2007 | CLOSED | Coil 1 | MPO .53028 page 7 .037" | Supplier
SC07043 | Everson Tesla | NA | 8/17/2007 | CLOSED | Coil 2 | See attached | Supplier
SC07046 | Everson Tesla | NA | 8/28/2007 | CLOSED | Coil 2 | MPO page #18 - the max. allowable | Supplier
SC07049 | Everson Tesla | NA | 9/12/2007 | CLOSED | Coil 5 | Minor Porosity in 3 lb. sst coatings wedge W09-W10 | Supplier
SC07052 | Everson Tesla | NA | 9/27/2007 | CLOSED | Coil 4 | Areas of dry glass/air, 12" wide -4ft. Left of lead, 16" wide - 3ft. Right of lead | Supplier
SC07053 | Everson Tesla | NA | 9/27/2007 | CLOSED | Coil 3 | Coil #3 outer area dry glass/air | Supplier
SC07058 | Everson Tesla | NA | 10/26/2007 | CLOSED | Coil 5 | MPO Page 32 resistance is 4.69 | Supplier
SC08005 | Everson Tesla | NA | 2/7/2008 | CLOSED | Coil 9 & 14 | Chromium content exceeds specification spec 1.77/18.2% actual is 18.5% | Supplier
SC08006 | Everson Tesla | NA | 2/5/2008 | CLOSED | Coil 10 | W20 & W30 wedges false holes in the inside face of both wedges | Supplier
SC08007 | Everson Tesla | NA | 2/18/2008 | CLOSED | Coil 9 | Coil #9 area of dry areas (see attached pictures) | Supplier
SC08010 | Everson Tesla | NA | 2/26/2008 | CLOSED | Coil 8 & 10 | Nickel content exceeds specification spec. 13/5/14.0% actual is 14.2% | Supplier
SC08013 | Everson Tesla | NA | 3/19/2008 | CLOSED | Coil 10 | Machine operator crashed tool holder into tope wedge of coil #10 prior to machining. | Supplier
SC08019 | Everson Tesla | NA | 4/16/2008 | CLOSED | Coil 12 & 13 | Tensile strength below 531 n/mm2 specification 537.8 n/mm2 minimum | Supplier
SC08020 | Everson Tesla | NA | 4/15/2008 | CLOSED | Coil 13 | Dimensional Tolerances | Supplier
SC08022 | Everson Tesla | NA | 1/2/2008 | CLOSED | Coil 8 & 12 | Tensile strength requirement 537.8 minimum N/mm2 | Supplier
SC08023 | Everson Tesla | NA | 1/2/2008 | CLOSED | Coil 8 & 12 | Elongation requirement of 32% minimum is 58-ok, 35-0k, 27 *> | Supplier
SC08027 | Everson Tesla | NA | 5/1/2008 | CLOSED | Coil 14 | Wedges W 22 & W26 with false cuts as detailed in photographs attached. | Supplier
SC08032 | Everson Tesla | NA | 5/21/2008 | CLOSED | Coil 13 | Dimensional Tolerances | Supplier
SC08035 | Everson Tesla | NA | 6/19/2008 | CLOSED | Coil 14 | Ring test measures 14 rings and should be 32 rings minimum resistance check on diagnostic wire shows there is a short in area, where lead wires are twisted. This is causing the low rings test reading on the coil. | Supplier
SC08036 | Everson Tesla | NA | 7/9/2008 | CLOSED | Coil 17 | Wedge W2 (C49) with false cut as detailed in photograph attached. | Supplier
SC08038 | Everson Tesla | NA | 7/17/2008 | CLOSED | Coil 15 | .100" deep false cut on bottom wedge ref. attached photos | Supplier
SC08043 | Everson Tesla | NA | 7/24/2008 | CLOSED | Coil 17 | .04" of extra material is missing from 10º surface. This extra material is needed to ensure complete cleanup at final machining after assembly. | Supplier
SC08045 | Everson Tesla | NA | 9/11/2008 | CLOSED | Coil 17 | Ring test measures 17 rings after WPI and should be 32 ring minimum. Resistance check on diagnostic wire shows there is short in area where lead wires are twisted. This is causing the low ring test reading on the coil | Supplier
Privacy and Security Notice
Please forward comments and questions to the Webmaster