## Sheet1
| WBS:= | 185
| Job Number= | 1802 and 1810
| Title= | Field period assembly | [5 empty] | 1.4225 |  |  |  |  | 175 |  | 169 |  |  |  |  | 84.5 | 150
| Job Manager= | Mike Viola |  |  |  |  | % DONE | 41MS $K |  |  |  |  | ORNLEM |  | EMEM |  |  | EMTB | CREW | NEW EMTB | EESM | [7 empty] | COMMENTS
[8 empty] | FY07$K |  |  |  |  | HOURS
Assumptions & basis
Assumes 5 day workweek 1 shift no overtime
|  | can do 2 shift for station 5 but requires add'l supervision | [5 empty] | 1308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 |  |  | 138.6 | 138.6 | 78.33 | 144.88 | 93.69 | 70.98 | 162.83 | 229.54 | 9322.71
parallel ops for sta 5 (2 fixtures available)
only 1 fixture for station 3 only one shift
Parallel ops for sta 2
Task ID |  | TASK DESCRIPTION | Original est. Work days | Work days | Start Date | Finish Date |  | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNLEM | ORNLDSN | EMEM | EMSM | EMSB | EMTB | CREW | NEW EMTB | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Rough Estimate Total (in FY07$)
Job: 1802 - FP Assy Oversight&Support-VIOLA
Oversight and Supervision
|  | Metrology Engineering Supervision FY07 raftopolous 50% | 362 | 181 | 2007-04-01 | 2007-09-28 | [8 empty] | 431.5 | [13 empty] | this is LOE adjust consistent with overall schedule
|  | Metrology Engineering Supervision FY08 raftopolous 50% | 362 | 362 | 2007-10-01 | 2008-09-28 | [8 empty] | 863 | [13 empty] | this is LOE adjust consistent with overall schedule
|  | Metrology Engineering Supervision FY09 raftopolous 50% (6 months???tbd |  | 181 | 2008-10-01 | 2009-04-01 | [8 empty] | 431.5 | [13 empty] | assume sta5 finishes March 2009
|  | PPPL EM LOE FY07 Viola 100% | 362 | 181 | 2007-04-01 | 2007-09-28 | [8 empty] | 863 | [13 empty] | this is LOE adjust consistent with overall schedule
|  | PPPL EM LOE FY08 Viola 100% | 273 | 362 | 2007-10-01 | 2008-09-28 | [8 empty] | 1726 | [13 empty] | this is LOE adjust consistent with overall schedule
|  | PPPL EM LOE FY09 Viola 100% (6 months???tbd) |  | 181 | 2008-10-01 | 2009-04-01 | [8 empty] | 863 | [13 empty] | assume sta5 finishes March 2009
|  | Title III field period assembly FY07 ORNL suppor cole,goranson,williamson 65% total | 362 | 181 | 2007-04-01 | 2007-09-28 | [6 empty] | 561.5 | [15 empty] | this is LOE adjust consistent with overall schedule awaiting estimate from Mike Cole
|  | Title III field period assembly FY08 ORNL suppor cole, goranson,williamson 33%total |  | 181 | 2007-10-01 | 2008-09-28 | [6 empty] | 562 | [15 empty] | this is LOE adjust consistent with overall schedule awaiting estimate from Mike Cole
|  | HP Coverage in the TFTR TC LOE FY07 @.75 fte | 365 | 181 | 2007-04-01 | 2007-09-28 | [8 empty] | 647.25 | [13 empty] | this is LOE thru stat3 only
|  | HP Coverage in the TFTR TC LOE FY08 @.75 fte | 189 | 362 | 2007-10-01 | 2008-09-28 | [8 empty] | 1294.5 | [13 empty] | this is LOE thru stat3 only
|  | HP Coverage in the TFTR TC LOE FY09 @.75 fte (6 months???tbd) |  | 181 | 2008-10-01 | 2009-04-01 | [8 empty] | 647.25 | [13 empty] | assume sta5 finishes March 2009
Station 2-Modular Coil Sub- Assembly
|  | Sequence plan | [12 empty] | brown | [13 empty] | budgeted in job 1803
|  | Metrology plan | [12 empty] | ellis | [13 empty] | budgeted in job 8205
|  | Procedures written & approved | 27 | 14 | 2007-04-30 | 2007-05-14 | [11 empty] | 7
|  | JHA completed | 6 | 6 | 2007-01-26 | 2007-02-01 | [11 empty] | 4
|  | Training needs identified & released | 6 | 6 | 2007-05-14 | 2007-05-20 | [11 empty] | 3
|  | ACC review completed | 6 | 2 | 2007-05-20 | 2007-05-22 | [11 empty] | 6
|  | Pre-job brief completed | 6 | 1 | 2007-05-22 | 2007-05-23 | [11 empty] | 1
|  | Station 2 operational |  |  |  | 2007-05-23
Station 3-Modular Coil to VVSA Assembly
|  | Sequence plan | [12 empty] | brown | [13 empty] | budgeted in job 1803
|  | Metrology plan | [12 empty] | ellis | [13 empty] | budgeted in job 8205
|  | Procedures approved | 27 | 10 | 2007-05-10 | 2007-05-20
|  | JHA completed | 6 | 6 | 2007-05-20 | 2007-05-26
|  | Training needs identified & released | 6 | 6 | 2007-06-22 | 2007-06-28
|  | ACC review completed | 6 | 6 | 2007-06-28 | 2007-07-04
|  | Pre-job brief completed | 6 | 6 | 2007-07-04 | 2007-07-10
|  | Station 3 operational |  | 1 | 2007-07-10 | 2007-07-11
|  | Fixtures installed | 6 | 6 | 2007-07-11 | 2007-07-17 | [11 empty] | 80
Station 5-Final Field Period Assembly
|  | Sequence plan | [12 empty] | brown | [13 empty] | budgeted in job 1803
|  | Metrology plan | [12 empty] | ellis | [13 empty] | budgeted in job 8205
|  | Procedures approved | 27 | 14 | 2007-10-01 | 2007-10-15
|  | JHA completed | 6 | 6 | 2007-10-15 | 2007-10-21
|  | Training needs identified & released | 6 | 6 | 2007-10-21 | 2007-10-27
|  | ACC review completed | 7 | 7 | 2007-10-27 | 2007-11-03
|  | Pre-job brief completed | 7 | 7 | 2007-11-03 | 2007-11-10
|  | Station 5 operational |  | 1 | 2007-11-10 | 2007-11-11
Job: 1802 - FP Assy Oversight&Support-VIOLA Total | [7 empty] | 0 | 0 | 0 | 0 | 0 | 1123.5 | 0 | 7767 | 0 | 0 | 101 | 0 | 0 | 0
Job: 1810 - Field Period Assembly-VIOLA
General F.P. Assy support
|  | LOE Crane support, fixture setupfor TFTR TC. FY07 1.2 fte | 362 | 181 | 2007-04-01 | 2007-09-28 | [11 empty] | 696.6605 |  | 1035.6 | [8 empty] | 2 men 3 day a week .LOE adjust consistent with schedule
|  | LOE Crane support, fixture setupfor TFTR TC. FY08 1.2 fte | 363 | 362 | 2007-10-01 | 2008-09-28 | [11 empty] | 838.34 |  | 2071.2 | [8 empty] | 2 men 3 day a week .LOE adjust consistent with schedule
|  | LOE Crane support, fixture setupfor TFTR TC. FY09 1.2 fte (6 months???tbd) |  |  | 2008-10-01 | 2009-04-01 | [22 empty] | assume sta5 finishes March 2009
|  | LOE Field Supervision for TFTR TC FY07 edwards |  | 181 | 2007-04-01 | 2007-09-28 | [14 empty] | 863 | [7 empty] | this is LOE adjust consistent with overall schedule
|  | LOE Field Supervision for TFTR TC FY08 edwards |  | 362 | 2007-10-01 | 2008-09-28 | [14 empty] | 1726 | [7 empty] | this is LOE adjust consistent with overall schedule
|  | LOE Field Supervision for TFTR TC FY09 edwards(6 months???tbd) |  | 181 | 2008-10-01 | 2009-04-01 | [14 empty] | 863 | [7 empty] | assume sta5 finishes March 2009
|  | LOE Metrology support FY07 1.5 fte engr plus ducco 100% | 362 | 181 | 2007-04-01 | 2007-09-28 | [8 empty] | 1294.5 |  |  | 1435.968 |  | 863 | [8 empty] | this is LOE adjust consistent with overall schedule
|  | LOE Metrology support FY08 1.5 fte engr plus ducco 100% | 362 | 362 | 2007-10-01 | 2008-09-28 | [8 empty] | 2589 |  |  | 1435.968 |  | 1726 | [8 empty] | this is LOE adjust consistent with overall schedule
|  | LOE Metrology support FY09 1.5 fte engr plus ducco 100% (6 months???tbd) |  | 181 | 2008-10-01 | 2009-04-01 | [8 empty] | 1294.5 |  |  |  |  | 863 | [8 empty] | assume sta5 finishes March 2009
|  | Misc M&S FY07 |  | 181 | 2007-04-01 | 2007-09-28 |  | 18 | [20 empty] | 3K/month
|  | Misc M&S FY08 |  | 362 | 2007-10-01 | 2008-09-28 |  | 36 | [20 empty] | 3K/month
|  | Misc M&S FY09 (6 months???tbd) |  | 181 | 2008-10-01 | 2009-04-01 |  | 18 | [20 empty] | assume sta5 finishes March 2009
Station 1-FP #1 VV Prep (hard surface components)
|  | Layout diagnostic&coolant paths on vessel | 75 | 35 | 2007-01-10 | 2007-02-14 | 100% | [10 empty] | 245
|  | Install heater tape on vertical ports | 75 | 7 | 2007-02-14 | 2007-02-21 | 100% | [10 empty] | 17.1
|  | Verify installation of heater tapes | 2 | 1 | 2007-02-21 | 2007-02-22 | 100%
|  | Attach studs for coolant lines | 75 | 3 | 2007-02-22 | 2007-02-25 | 100% | [10 empty] | 42
|  | Wind magnetic diagnostic sensors | 43 | 14 | 2007-02-25 | 2007-03-11 | 100% | [10 empty] | 256
|  | Install precision magnetic diagnostic sensors | 41 | 3 | 2007-03-11 | 2007-03-14 | 100% | [10 empty] | 240
|  | Verify installation magnetic diagnostic sensors |  | 4 | 2007-03-14 | 2007-03-18 | 100% | [10 empty] | 28
|  | Install local I&C (incl thermocouples) | 8 | 5 | 2007-03-18 | 2007-03-23 | 100% | [10 empty] | 65
|  | Verify installation of local I&C | 2 | 2 | 2007-03-23 | 2007-03-25 | 100% | [10 empty] | 28
|  | Install cooling/htg lines to vac vsl | 34 | 15 | 2007-03-25 | 2007-04-09 | 50% | [10 empty] | 192 | 2.5 | 300
|  | Weld cooling/htg risers | 34 | 10 | 2007-04-09 | 2007-04-19 | A | 2 | [9 empty] | 192 | 2.5 | 200 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Verify Instl of H/C lines,headers,manifolds | 6 | 5 | 2007-04-19 | 2007-04-24 | A | [10 empty] | 46 | 2.5 | 100 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Loop termination & verification | 6 | 18 | 2007-04-24 | 2007-05-12 | Floor | [10 empty] | 35 | 2.5 | 360 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | install Final Internal and External monuments and measure | 48 | 4 | 2007-05-12 | 2007-05-16 | [11 empty] | 288 | 2.5 | 80
|  | Final Scan | 7 | 4 | 2007-05-12 | 2007-05-16 | D | [10 empty] | 33.15 | 2.5 | 80 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Prepare and transfer completed VV to holding are | 4 | 2 | 2007-05-16 | 2007-05-18 | D | [10 empty] | 42 | 2.5 | 40 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
Station 1- FP #2 VV Prep (hrd surf cmpnts)
|  | Misc Hardware | [5 empty] | 2
|  | Layout diagnostic&coolant paths on vessel | 35 | 12 | 2007-02-18 | 2007-03-02 | 100% | [10 empty] | 245
|  | Install heater tape on vertical ports | 5 | 7 | 2007-03-02 | 2007-03-09 | 100% | [10 empty] | 53
|  | Verify installation of heater tapes | 0 | 1 | 2007-03-09 | 2007-03-10 | 100% | [10 empty] | 11
|  | Attach studs forcoolant lines | 15 | 3 | 2007-03-10 | 2007-03-13 | 100% | [10 empty] | 183
|  | Wind magnetic diagnostic sensors | 27 | 14 | 2007-03-13 | 2007-03-27 | 100% | [10 empty] | 280
|  | Install precision magnetic diagnostic sensors | 31 | 3 | 2007-03-27 | 2007-03-30 | 100% | [10 empty] | 163
|  | Verify installation magnetic diagnostic sensors |  | 4 | 2007-03-30 | 2007-04-03 | 100% | [10 empty] | 28
|  | Install local I&C (incl thermocouples) | 8 | 5 | 2007-04-03 | 2007-04-08 | A | [10 empty] | 80 | 2.5 | 100 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Verify installation of local I&C | 2 | 2 | 2007-04-08 | 2007-04-10 | A | [10 empty] | 23 | 2.5 | 40 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Install cooling/htg lines to vac vsl | 34 | 15 | 2007-04-10 | 2007-04-25 | C | [10 empty] | 384 | 2.5 | 300 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Weld cooling/htg risers | 34 | 10 | 2007-04-25 | 2007-05-05 | C | 2 | [9 empty] | 192 | 2.5 | 200 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Verify Instl of H/C lines,headers,manifolds | 7 | 5 | 2007-05-05 | 2007-05-10 | E | [10 empty] | 38 | 2.5 | 100 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Loop termination & verification | 12 | 18 | 2007-05-10 | 2007-05-28 | E | [10 empty] | 10 | 2.5 | 360 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | install Final Internal and External monuments and measure | 48 | 4 | 2007-05-28 | 2007-06-01 | [11 empty] | 288 | 2.5 | 80
|  | Final Scan | 4 | 4 | 2007-05-28 | 2007-06-01 | E | [10 empty] | 33.15 | 2.5 | 80 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Prepare and transfer completed VV to holding are | 2 | 2 | 2007-06-01 | 2007-06-03 | E | [10 empty] | 63 | 2.5 | 40 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
Station 1- FP #3 VV Prep (hrd surf cmpnts)
|  | Misc Hardware | [5 empty] | 2
|  | Layout diagnostic&coolant paths on vessel | 26 | 12 | 2007-04-09 | 2007-04-21 | 100% | [10 empty] | 221
|  | Install heater tape on vertical ports | 3 | 7 | 2007-04-21 | 2007-04-28 | B | [10 empty] | 29 | 2.5 | 140 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Verify installation of heater tapes | 0 | 1 | 2007-04-28 | 2007-04-29 | B | [10 empty] | 11 | 2.5 | 20 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Attach studs forcoolant lines | 15 | 3 | 2007-04-29 | 2007-05-02 | B | 2 | [9 empty] | 86 | 2.5 | 60 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Wind magnetic diagnostic sensors | 28 | 14 | 2007-05-02 | 2007-05-16 | C | [10 empty] | 420 | 2.5 | 280 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Install precision magnetic diagnostic sensors | 26 | 3 | 2007-05-16 | 2007-05-19 | C | [10 empty] | 266 | 2.5 | 60 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Verify installation magnetic diagnostic sensors |  | 4 | 2007-05-19 | 2007-05-23 | C | [10 empty] | 28 | 2.5 | 80 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Install local I&C (incl thermocouples) | 8 | 5 | 2007-05-23 | 2007-05-28 | F | [10 empty] | 50 | 2.5 | 100 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Verify installation of local I&C | 2 | 2 | 2007-05-28 | 2007-05-30 | F | [10 empty] | 22 | 2.5 | 40 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Install cooling/htg lines to vac vsl | 29 | 15 | 2007-05-30 | 2007-06-14 | F | [10 empty] | 352 | 2.5 | 300 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Weld cooling/htg risers | 34 | 10 | 2007-06-14 | 2007-06-24 | F | 2 | [9 empty] | 192 | 2.5 | 200 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Verify Instl of H/C lines,headers,manifolds | 4 | 5 | 2007-06-24 | 2007-06-29 | F | [10 empty] | 36 | 2.5 | 100 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Loop termination & verification | 2 | 18 | 2007-06-29 | 2007-07-17 | F | [10 empty] | 10 | 2.5 | 360 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | install Final Internal and External monuments and measure | 48 | 4 | 2007-07-17 | 2007-07-21 | [11 empty] | 288 | 2.5 | 80
|  | Final Scan | 2 | 4 | 2007-07-17 | 2007-07-21 | F | [10 empty] | 33.15 | 2.5 | 80 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
|  | Prepare and transfer completed VV to holding are | 2 | 2 | 2007-07-21 | 2007-07-23 | F | [10 empty] | 43 | 2.5 | 40 | [8 empty] | serial tasks alternating between FPA constant 2.5 men
| Station 1-Spool pieces (3) (spacers) | [18 empty] | 0
|  | Attach diagnostics, studs and coolant lines | 48 | 17 | 2008-01-10 | 2008-01-27 | [11 empty] | 288 | 2.5 | 340
|  | install Final Internal and External monuments and measure | 48 | 2 | 2008-01-27 | 2008-01-29 | [11 empty] | 288 | 2.5 | 40
Station 2 Trials & Setup
|  | Trial tensioning test on prototype | 46 | 2 | 2007-04-09 | 2007-04-11 |  | 3 | [10 empty] | 2.5 | 40
|  | Trial bushing and shim test on prototype | 67 | 12 | 2007-04-09 | 2007-04-21 |  | 2 | [10 empty] | 2.5 | 240
|  | Guidance f/post-VPI proced to include measuremen | 36 | 36 | 2007-03-29 | 2007-05-04 | [12 empty] | 0 | 0
|  | Perform trial x-y-z alignments on A1-A2. | 90 | 7 | 2007-04-03 | 2007-04-10 |  | 2 | [10 empty] | 2.5 | 140
|  | Alignment mechanisms, metro equipt &positioning | 6 | 6 | 2007-04-10 | 2007-04-16 |  | 40 | [10 empty] | 2.5 | 120
|  | Procure alignment mechanisms, fiducials, lifting | 56 | 20 | 2007-03-30 | 2007-04-19 |  | 25 | [10 empty] | 2.5 | 400
|  | Develop procedures for torquing bolts | 4 | 4 | 2007-04-02 | 2007-04-06 | [12 empty] | 2.5 | 80
|  | Determine fiducial types&locations | 11 | 11 | 2007-04-09 | 2007-04-20 |  | 2 | [10 empty] | 2.5 | 220
|  | Procure monuments&related metrology equipment | 42 | 15 | 2007-03-30 | 2007-04-14 |  | 15 | [10 empty] | 2.5 | 300
|  | Tools&tooling available for FPA operations |  |  |  | 2007-06-12 | [12 empty] | 2.5 | 0
|  | Hardware rework (1/2 FTE) | 2 | 120 | 2007-06-12 |  |  | 10 | [9 empty] | 48 | 1 | 960
|  | Install FIRST Holding 20 deg fixture | 4 | 4 | 2007-01-22 | 2007-01-26 |  | 2 | [9 empty] | 20 | 2.5 | 80
|  | Install SECOND Holding 20 deg fixture | 3 | 3 | 2007-04-07 | 2007-04-10 |  | 2 | [9 empty] | 10 | 2.5 | 60
|  | Install THIRD Holding 20 deg fixture |  | 6 | 2007-04-18 | 2007-04-24 |  | 2 | [9 empty] | 6 | 2.5 | 120
|  | Install LAST Holding 20 deg fixture |  | 3 | 2007-06-06 | 2007-06-09 |  | 2 | [9 empty] | 6 | 2.5 | 60
| Station 2-Modular Coil Subassembly-FP#1 | [18 empty] | 0
|  | Misc Hardware | [5 empty] | 5 | [11 empty] | 0
|  | Test out equipt & procedures | 7 | 7 | 2007-04-04 | 2007-04-11 | [11 empty] | 88 | 2.5 | 140
|  | Receive drawings and hardware (shims and bolts) | 7 | 7 | 2007-04-30 | 2007-05-07 | [11 empty] | 88 | 2.5 | 140
| * | Begin A1/B1/C1 |  | 1 | 2007-05-07 | 2007-05-08 | [11 empty] | 360 | 2.5 | 20
| * | Pre-fit & install alignment tooling A1-A2 | 2 | 4 | 2007-05-08 | 2007-05-12 | [11 empty] | 32 | 2.5 | 80
| * | Align A1-A2 | 2 | 2 | 2007-05-12 | 2007-05-14 | [11 empty] | 32 | 2.5 | 40
| * | Install Nose shear | 2 | 10 | 2007-05-14 | 2007-05-24 |  | 15 | [9 empty] | 32 | 5 | 400 | [8 empty] | nose shear can be done in parallel with studs/shims/bushings
| * | Install studs | 2 | 2 | 2007-05-24 | 2007-05-26 | [11 empty] | 32 | 5 | 80
| * | Install shims | 2 | 5 | 2007-05-26 | 2007-05-31 | [11 empty] | 32 | 5 | 200
| * | Measure and Drill Bushings | 2 | 2 | 2007-05-31 | 2007-06-02 | [11 empty] | 32 | 5 | 80
| * | Install Bushings | 2 | 5 | 2007-06-02 | 2007-06-07 | [11 empty] | 32 | 5 | 200
| * | Tension | 3 | 3 | 2007-06-07 | 2007-06-10 |  | 25 | [9 empty] | 16 | 5 | 120
| * | Verify alignment A1-A2 | 2 | 2 | 2007-06-10 | 2007-06-12 | [11 empty] | 32 | 2.5 | 40
| * | De Tension | 1 | 1 | 2007-06-12 | 2007-06-13 | [11 empty] | 16 | 2.5 | 20
| * | Adjust Nose shims | 2 | 4 | 2007-06-13 | 2007-06-17 | [11 empty] | 32 | 2.5 | 80
| * | Adjust shims | 2 | 3 | 2007-06-17 | 2007-06-20 | [11 empty] | 32 | 2.5 | 60
| * | Adjust Bushings | 2 | 3 | 2007-06-20 | 2007-06-23 | [11 empty] | 32 | 2.5 | 60
| * | Re Tension | 3 | 3 | 2007-06-23 | 2007-06-26 | [11 empty] | 16 | 2.5 | 60
52 | * | Verify alignment A1-A2 | 2 | 2 | 2007-06-26 | 2007-06-28 | [11 empty] | 32 | 2.5 | 40
37 |  | De -Tension | 3 | 1 | 2007-06-28 | 2007-06-29 | [11 empty] | 16 | 2.5 | 20
|  | Pre-fit C1-C5 | 4 | 7 | 2007-06-29 | 2007-07-06 | [11 empty] | 32 | 4 | 224
|  | Begin 3 pack A1/B1/C1 Install A1 |  | 3 | 2007-07-06 | 2007-07-09 | [11 empty] | 360 | 2.5 | 60
|  | Fit A1-B1 | 1 | 50 | 2007-07-09 | 2007-08-28 | [11 empty] | 16 | 4 | 1600
|  | Fit B1-C1 | 3 | 50 | 2007-08-28 | 2007-10-17 | [11 empty] | 16 | 4 | 1600
|  | Verify Align Mod-Coils A1/B1/C1 | 36 | 5 | 2007-10-17 | 2007-10-22 | [11 empty] | 360 | 2.5 | 100
|  | Pre-fit C2-C3 | 49 | 7 | 2007-10-22 | 2007-10-29 | [11 empty] | 720 | 4 | 224
|  | Fit A2-B2 | 42 | 50 | 2007-10-29 | 2007-12-18 | [11 empty] | 480 | 4 | 1600
|  | Fit B2-C2 |  | 50 | 2007-12-18 | 2008-02-06 | [12 empty] | 4 | 1600
|  | Verify Align Mod-Coils A2/B2/C2 | 1 | 5 | 2008-02-06 | 2008-02-11 | [11 empty] | 16 | 2.5 | 100
| Station 2-Modular Coil Subassembly-FP#2 | [18 empty] | 0
|  | Fit A3/A4 | 1 | 50 | 0 | 1900-02-18 | [11 empty] | 16 | 4 | 1600
|  | Assemble/Align Mod-Coils A3/B3/C3 | 35 | 100 | 2007-08-31 | 2007-12-09 | [11 empty] | 360 | 4 | 3200
|  | Pre-fit C6-C4 | 36 | 7 | 2007-10-31 | 2007-11-07 | [11 empty] | 360 | 4 | 224
|  | Assemble/Align Mod-Coils A4/B4/C4 | 43 | 100 | 2007-12-18 | 2008-03-27 | [11 empty] | 360 | 4 | 3200
| Station 2-Modular Coil Subassembly-FP#3 | [18 empty] | 0
|  | Fit A5/A6 | 1 | 50 | 0 | 1900-02-18 | [11 empty] | 16 | 4 | 1600
|  | Assemble/Align Mod-Coils A5/B5/C5 | 27 | 100 | 2007-07-25 | 2007-11-02 | [11 empty] | 360 | 4 | 3200
|  | Assemble/Align Mod-Coils A6/B6/C6 |  | 100 | 2007-11-02 | 2008-02-10 | [12 empty] | 4 | 3200
| Station 3-Assemble Mod Coils and VVSA-FP#1 | [16 empty] | 384
|  | Misc Hardware | [5 empty] | 5
|  | Procure and load test 3 legged actuator System | 2 | 4 | 2007-06-25 | 2007-06-29 |  | 43 | [9 empty] | 48 | 3 | 96
|  | Procure, Fabricate and load test 3 legged actuator Lift Fixture | 2 | 8 | 2007-06-25 | 2007-07-03 |  | 6 | [9 empty] | 48 | 2 | 128
|  | Begin Assembly of First Field Period Assy | 2 | 2 | 0 | 1900-01-01 | [11 empty] | 32 | 2.5 | 40
|  | Install station 3 platforms (8 required) | 2 | 4 | 1900-01-01 | 1900-01-05 |  | 10 | [9 empty] | 48 | 3.5 | 112
|  | Install and align station 3 screens | 2 | 5 | 1900-01-05 | 1900-01-10 |  | 2 | [9 empty] | 48 | 2.5 | 100
|  | Test out station 3 equipment and procedures | 2 | 4 | 1900-01-10 | 1900-01-14 |  | 10 | [9 empty] | 48 | 2.5 | 80
|  | Assemble/Disassemble abc1-abc2 (stage 3 fixture) | 5
|  | VV to MC turning fixt base; metr check | 3 | 3 | 1900-01-14 | 1900-01-17 | [11 empty] | 72 | 2.5 | 60
|  | Attach local protective strips to VV&locate sens | 5 | 2 | 1900-01-17 | 1900-01-19 | [11 empty] | 48 | 2.5 | 40
|  | Mount MC on crane; perform metr checks | 0 | 4 | 1900-01-19 | 1900-01-23 |  | 8 | [9 empty] | 24 | 2.5 | 80
|  | Rotate right MC to stand-off position&chk | 3 | 3 | 1900-01-23 | 1900-01-26 | [11 empty] | 48 | 2.5 | 60
|  | Transfer load to sprt sys and recheck position | 1 | 3 | 1900-01-26 | 1900-01-29 | [11 empty] | 48 | 2.5 | 60
|  | Move MC turning fixt; mount MC on crane | 20 | 5 | 1900-01-29 | 1900-02-03 | [11 empty] | 240 | 2.5 | 100
|  | Rotate left MC to stand-off position and check p | 13 | 5 | 1900-02-03 | 1900-02-08 | [11 empty] | 120 | 2.5 | 100
|  | Move left & right MC to final position & measure | 6 | 6 | 1900-02-08 | 1900-02-14 | [11 empty] | 72 | 2.5 | 120
|  | Bolt together at flange interface. | 6 | 40 | 1900-02-14 | 1900-03-26 | [11 empty] | 72 | 2.5 | 800
|  | Perform final metrology position check | 1 | 2 | 1900-03-26 | 1900-03-28 | [11 empty] | 48 | 2.5 | 40
|  | Remove temp interference strips&sensors | 1 | 1 | 1900-03-28 | 1900-03-29 | [11 empty] | 80 | 2.5 | 20
|  | Secure VV to MC's using temporary supports. | 23 | 5 | 1900-03-29 | 1900-04-03 | [11 empty] | 360 | 2.5 | 100
|  | Prepare Field Period for shipment | 5 | 5 | 1900-04-03 | 1900-04-08 | [11 empty] | 48 | 2.5 | 100
|  | Transfer completed assy to C-site test cell | 2 | 5 | 1900-04-08 | 1900-04-13 | [11 empty] | 32 | 5 | 200
| Station 3-Assemble Mod Coils and VVSA-FP#2 | [17 empty] | 2.5 | 0
|  | Assemble/Disassemble abc -abc4 (stage 3 fixture) | 4
|  | Mount VV to MC turning fixt base; metr check | 6 | 3 | 0 | 1900-01-02 | [11 empty] | 72 | 2.5 | 60
|  | Attach local protective strips to VV&locate sens | 1 | 2 | 1900-01-02 | 1900-01-04 | [11 empty] | 48 | 2.5 | 40
|  | Mount MC on crane; perform metr checks | 0 | 4 | 1900-01-04 | 1900-01-08 | [11 empty] | 24 | 2.5 | 80
|  | Rotate right MC to stand-off position&chk | 1 | 3 | 1900-01-08 | 1900-01-11 | [11 empty] | 48 | 2.5 | 60
|  | Transfer load to supt sys and recheck position | 1 | 3 | 1900-01-11 | 1900-01-14 | [11 empty] | 48 | 2.5 | 60
|  | Move MC turning fixt; mount MC on crane | 24 | 5 | 1900-01-14 | 1900-01-19 | [11 empty] | 240 | 2.5 | 100
|  | Rotate left MC to stand-off position and check p | 6 | 5 | 1900-01-19 | 1900-01-24 | [11 empty] | 120 | 2.5 | 100
|  | Move left & right MC to final position & measure | 2 | 6 | 1900-01-24 | 1900-01-30 | [11 empty] | 72 | 2.5 | 120
|  | Bolt together at flange interface. | 2 | 35 | 1900-01-30 | 1900-03-06 | [11 empty] | 72 | 2.5 | 700
|  | Perform final metrology position check | 3 | 3 | 1900-03-06 | 1900-03-09 | [11 empty] | 48 | 2.5 | 60
|  | Remove temp interference strips&sensors | 1 | 1 | 1900-03-09 | 1900-03-10 | [11 empty] | 80 | 2.5 | 20
|  | Secure VV to MC's using temporary supports. | 21 | 5 | 1900-03-10 | 1900-03-15 | [11 empty] | 360 | 2.5 | 100
|  | Prepare Field Period for shipment | 5 | 5 | 1900-03-15 | 1900-03-20 | [11 empty] | 48 | 2.5 | 100
|  | Transfer completed assy to C-site test cell | 2 | 5 | 1900-03-20 | 1900-03-25 | [11 empty] | 32 | 5 | 200
| Station 3-Assemble Mod Coils and VVSA-FP#3 | [17 empty] | 2.5 | 0
|  | Assemble/Disassemble abc -abc6 (Stage 3 fixture) | 3
|  | Mount VV to MC turning fixt base; metr check | 2 | 3 | 0 | 1900-01-02 | [11 empty] | 72 | 2.5 | 60
|  | Attach local protective strips to VV&locate sens | 3 | 2 | 1900-01-02 | 1900-01-04 | [11 empty] | 48 | 2.5 | 40
|  | Mount MC on crane; perform metr checks | 0 | 4 | 1900-01-04 | 1900-01-08 | [11 empty] | 24 | 2.5 | 80
|  | Rotate right MC to stand-off position&chk | 1 | 3 | 1900-01-08 | 1900-01-11 | [11 empty] | 48 | 2.5 | 60
|  | Transfer load to supt sysand recheck position | 3 | 3 | 1900-01-11 | 1900-01-14 | [11 empty] | 48 | 2.5 | 60
|  | Move MC turning fixt; mount MC on crane | 13 | 5 | 1900-01-14 | 1900-01-19 | [11 empty] | 240 | 2.5 | 100
|  | Rotate left MC to stand-off position and check p | 6 | 5 | 1900-01-19 | 1900-01-24 | [11 empty] | 120 | 2.5 | 100
|  | Move left & right MC to final position & measure | 2 | 6 | 1900-01-24 | 1900-01-30 | [11 empty] | 72 | 2.5 | 120
|  | Bolt together at flange interface. | 2 | 35 | 1900-01-30 | 1900-03-06 | [11 empty] | 72 | 2.5 | 700
|  | Perform final metrology position check | 3 | 3 | 1900-03-06 | 1900-03-09 | [11 empty] | 48 | 2.5 | 60
|  | Remove temp interference strips&sensors | 0 | 1 | 1900-03-09 | 1900-03-10 | [11 empty] | 80 | 2.5 | 20
|  | Transfer completed assy to C-site test cell | 2 | 5 | 1900-03-10 | 1900-03-15 | [11 empty] | 32 | 5 | 200
Job: 1815 - Field Period Assembly Station 5 (in NCSX TC)-VIOLA
Station 5- Final FP Assy -FP#1 (in NCSX TC)
NEW |  | metrology network |  | 10 | 2007-10-22 | 2007-11-05 |  | 7 | [11 empty] | 160
|  | 2 Port Extensions needed for first Plasma diagnostics |  | 12 | 2007-11-05 | 2007-11-17 | [12 empty] | 4 | 384 | [8 empty] | 10" ports provided by WBS 38
|  | MTM NCR Hardware repurchase | [5 empty] | 42
|  | Weld Wire & weld supples | [5 empty] | 15
|  | Testout Sta 5 equipt & procedures | 15 | 5 | 2007-11-05 | 2007-11-10 | [11 empty] | 80 | 4 | 160
|  | Check 3 sled interfaces adjust holes | 6 | 12 | 2007-11-10 | 2007-11-22 | [11 empty] | 80 | 4 | 384
|  | Fixtures installed - final metrology | 6 | 6 | 2007-11-22 | 2007-11-28 | [11 empty] | 80 | 4 | 192
|  | Install on support platform | 43 | 15 | 2007-11-10 | 2007-11-25 |  | 12 | [9 empty] | 960 | 5 | 600
|  | Mount MC/VV assembly to support frame a | 2 | 2 | 2007-11-25 | 2007-11-27 | [11 empty] | 96 | 2.5 | 40
|  | Position and weld all ports to VV | 3 | 30 | 2007-11-27 | 2007-12-27 | [11 empty] | 48 | 2.5 | 600
|  | Inspect Welds | 2 | 4 | 2007-12-27 | 2007-12-31 | [11 empty] | 96 | 2.5 | 80
|  | Assemble left TF Coil Assembly check position | 4 | 8 | 2007-12-31 | 2008-01-08 | [11 empty] | 72 | 4 | 256
|  | Change platforms | 1 | 1 | 2008-01-08 | 2008-01-09 | [11 empty] | 64 | 2.5 | 20
|  | Assemble right TF Coil Assembly chk position | 11 | 8 | 2008-01-09 | 2008-01-17 | [11 empty] | 192 | 4 | 256
|  | Attach TF coils to MC's | 0 | 4 | 2008-01-17 | 2008-01-21 | [11 empty] | 16 | 2.5 | 80
NEW |  | Align TF Coils |  | 8 | 2008-01-21 | 2008-01-29 | [12 empty] | 2.5 | 160
|  | Change platforms | -1 | 1 | 2008-01-29 | 2008-01-30 | [12 empty] | 2.5 | 20
|  | Position, tack-weld only two large horizontal diag ports (port 4's) | 13 | 8 | 2008-01-30 | 2008-02-07 | [11 empty] | 640 | 2.5 | 160
|  | Assemble external trim coils (in wbs75) | 13
|  | Close up VV, leak check | 1
|  | Adjust final support base interfaces | 1 | 8 | 2008-02-07 | 2008-02-15 | [11 empty] | 48 | 2.5 | 160
|  | Final metrology outside & inside | 39 | 10 | 2008-02-15 | 2008-02-25 | [11 empty] | 960 | 2.5 | 200
Station 5- Final FP Assy -FP#2 (in NCSX TC)
|  | Install on support platform | 4 | 15 | 2008-03-17 | 2008-04-01 | [11 empty] | 80 | 5 | 600
|  | Mount MC/VV assembly to support frame a | 2 | 2 | 2008-04-01 | 2008-04-03 | [11 empty] | 96 | 2.5 | 40
|  | Position and weld all ports to VV | 1 | 30 | 2008-04-03 | 2008-05-03 | [11 empty] | 48 | 2.5 | 600
|  | Inspect Welds | 2 | 4 | 2008-05-03 | 2008-05-07 | [11 empty] | 96 | 2.5 | 80
|  | Assemble left TF Coil Assembly check position | 4 | 8 | 2008-05-07 | 2008-05-15 | [11 empty] | 72 | 4 | 256
|  | Change platforms | 1 | 1 | 2008-05-15 | 2008-05-16 | [11 empty] | 64 | 2.5 | 20
|  | Assemble right TF Coil Assembly chk position | 11 | 8 | 2008-05-16 | 2008-05-24 | [11 empty] | 192 | 4 | 256
|  | Attach TF coils to MC's | 0 | 4 | 2008-05-24 | 2008-05-28 | [11 empty] | 16 | 2.5 | 80
NEW |  | Align TF Coils |  | 6 | 2008-05-28 | 2008-06-03 | [12 empty] | 2.5 | 120
|  | Change platforms | -1 | 1 | 2008-06-03 | 2008-06-04 | [12 empty] | 2.5 | 20
|  | Position, tack-weld only two large horizontal diag ports (port 4's) | 13 | 8 | 2008-06-04 | 2008-06-12 | [11 empty] | 640 | 2.5 | 160
|  | Assemble external trim coils (in wbs75) | 14
|  | Close up VV, leak check | 1
|  | Adjust final support base interfaces | 1 | 8 | 2008-06-12 | 2008-06-20 | [11 empty] | 48 | 2.5 | 160
|  | Final metrology outside & inside | 42 | 10 | 2008-06-20 | 2008-06-30 | [11 empty] | 960 | 2.5 | 200
Station 5- Final FP Assy -FP#3 (in NCSX TC)
|  | Install on support platform | 2 | 15 | 2008-06-02 | 2008-06-17 | [11 empty] | 80 | 5 | 600
|  | Mount MC/VV assembly to support frame a | 0 | 2 | 2008-06-17 | 2008-06-19 | [11 empty] | 96 | 2.5 | 40
|  | Position and weld all ports to VV*2 shift* | 0 | 30 | 2008-06-19 | 2008-07-19 | [11 empty] | 48 | 2.5 | 600
|  | Inspect Welds | 1 | 4 | 2008-07-19 | 2008-07-23 | [11 empty] | 96 | 2.5 | 80
|  | Assemble left TF Coil Assembly check position | 0 | 8 | 2008-07-23 | 2008-07-31 | [11 empty] | 72 | 4 | 256
|  | Change platforms | 0 | 1 | 2008-07-31 | 2008-08-01 | [11 empty] | 64 | 2.5 | 20
|  | Assemble right TF Coil Assembly chk position | 5 | 8 | 2008-08-01 | 2008-08-09 | [11 empty] | 192 | 4 | 256
|  | Attach TF coils to MC's | 0 | 4 | 2008-08-09 | 2008-08-13 | [11 empty] | 16 | 2.5 | 80
NEW |  | Align TF Coils |  | 6 | [14 empty] | 2.5 | 120
|  | Change platforms | -1 | 1 | 2008-08-13 | 2008-08-14 | [12 empty] | 2.5 | 20
|  | Position, tack-weld only two large horizontal diag ports (port 4's) | 6 | 8 | 2008-08-14 | 2008-08-22 | [11 empty] | 640 | 2.5 | 160
|  | Assemble external trim coils (in wbs75) | 4
Close up VV, leak check
|  | Adjust final support base interfaces |  | 8 | 2008-08-22 | 2008-08-30 | [12 empty] | 2.5 | 160
|  | Final metrology outside & inside |  | 10 | 2008-08-30 | 2008-09-09 | [12 empty] | 2.5 | 200
|  | Last field period assembled |  | 1 | 2008-09-09 | 2008-09-10 | [12 empty] | 2.5 | 20
Job:1810 - Field Period Assembly-VIOLA Total | [7 empty] | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 5178 | 0 | 0 | 24534.3865 |  | 54122.8 | 3452
|  | total 1802 & 1810 & 1815 | [5 empty] | 394000 | 0 | 0 | 0 | 0 | 1123.5 | 0 | 12945 | 0 | 0 | 24534.3865 |  | 52622.8 | 3452
[8 empty] | 1358 |  |  |  |  | 170 |  | 161 |  |  |  |  | 81 | 142
[7 empty] | etc= | 535052000 | 0 | 0 | 0 | 0 | 190995 | 0 | 2084145 | 0 | 0 | 0 | 0 | 4262446.8 | 490184 | [7 empty] | 542079770.8
[7 empty] | 1802 | 0 | 0 | 0 | 0 | 0 | 1123.5 | 0 | 7767 | 0 | 0 | 0 |  | 0 | 0
[8 empty] | 0 |  |  |  |  | 196612.5 |  | 1312623 |  |  |  |  | 0 | 0 | [7 empty] | 1509235.5
[7 empty] | 1810 | 318000 | 0 | 0 | 0 | 0 | 0 | 0 | 5178 | 0 | 0 | 16743.3865 |  | 43506.8 | 3452
[8 empty] | 452355 |  |  |  |  | 0 | 0 | 875082 |  |  |  |  | 3676324.6 | 517800 | [7 empty] | 5521561.6
[7 empty] | 1815 | 76000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048 |  | 9116 | 0
[8 empty] | 108110 |  |  |  |  | 0 |  | 0 |  |  |  |  | 770302 | 0 | [7 empty] | 878412
[8 empty] | 560465 |  |  |  |  | 196612.5 |  | 2187705 |  |  |  |  | 4446626.6 | 517800 | [7 empty] | 7909209.1
542079770.8
7909209.1
Formulas:
Finish Date = [Start Date]+[Work days]
Finish Date = [Finish Date, row above]
Start Date = [Finish Date, row above]