## Sheet1
| WBS:= | [6 empty] | % DONE | [5 empty] | ORNLEM |  | EMEM |  |  | EMTB | NEW EMTB | EAEM | NEW EAEM |  |  | EESM | NEW EESM
Job Number=
Title=
| Job Manager= |  | can do 2 shifht for station 5
|  |  | only 1 fixture for station 3 only one shifht | [5 empty] | FY07$K |  |  |  |  | HOURS
|  |  | assumes 2 man crews per shifht | [5 empty] | 1308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 |  | 180.79 |  | 116.7 | 168.88 | 138.6 |  | 138.6 | 78.33 | 144.88 | 93.69 | 70.98 | 162.83 | 229.54 | 9789.08
| Task ID |  | TASK DESCRIPTION | Original est. Work days | Work days | Start Date | Finish Date |  | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNLEM | ORNLDSN | EMEM | EMSM | EMSB | EMTB | em//tb | EAEM |  | EASB | EEEM | EESM |  | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Rough Estimate Total (in FY07$)
Job: 1802 - FP Assy Oversight&Support-VIOLA
1 |  | FY04 Work Plan
2 |  |  | Procedures approved | 25 | 25 | 2007-04-30 | 2007-05-25
3 |  |  | JHA completed | 6 | 6 | 2007-06-26 | 2007-07-02
4 |  |  | Training needs identified & released | 6 | 6 | 2007-05-29 | 2007-06-04
5 |  |  | ACC review completed | 7 | 7 | 2007-07-03 | 2007-07-10
6 |  |  | Pre-job brief completed | 7 | 7 | 2007-07-03 | 2007-07-10
7 |  |  | Station 4 operational |  |  |  | 2007-07-10
8 |  |  | Fixtures installed | 6 | 6 | 2007-06-19 | 2007-06-25 | [11 empty] | 80
9 |  | Oversight and Supervision
10 |  |  | PPPL EM LOE FY06 | #VALUE! | #VALUE! | 2005-12-01
11 |  |  | Metrology Engineering Supervision FY06 | #VALUE! | #VALUE! | 2006-05-01
12 |  |  | Metrology Engineering Supervision FY07 | 362 | 362 | 2006-10-01 | 2007-09-28 | [8 empty] | 863
13 |  |  | PPPL EM LOE FY07 | 362 | 362 | 2006-10-01 | 2007-09-28 | [8 empty] | 1467
14 |  |  | PPPL EM LOE FY08 | 273 | 273 | 2007-10-01 | 2008-06-30 | [8 empty] | 1467
15 |  |  | Title III field period assembly FY07 ORNL suppor | 362 | 362 | 2006-10-01 | 2007-09-28 | [6 empty] | 1123
16 |  |  | Title III field period assembly FY08 ORNL suppor |  | 192 | 2007-09-28 | 2008-04-07 | [6 empty] | 562
17 |  |  | HP Coverage in the TFTR TC LOE FY07 @.75 fte | 365 | 365 | 2006-10-01 | 2007-10-01 | [8 empty] | 1300
18 |  |  | HP Coverage in the TFTR TC LOE FY08 @.75 fte | 189 | 189 | 2007-10-01 | 2008-04-07 | [8 empty] | 841
19 |  |  | HP Coverage in the TFTR TC LOE FY06 | #VALUE! | #VALUE! | 2005-10-01 | [12 empty] | 80
20 |  | Station 2-Modular Coil Sub- Assembly
21 |  |  | Procedures written & approved | 27 | 14 | 2007-04-30 | 2007-05-14 | [11 empty] | 7 | 40
22 |  |  | JHA completed | 6 | 6 | 2007-01-26 | 2007-02-01 | [11 empty] | 4 | 24
23 |  |  | Sequence plan
24 |  |  | Metrology plan
25 |  |  | Training needs identified & released | 6 | 6 | 2007-05-14 | 2007-05-20 | [11 empty] | 3 | 24
26 |  |  | ACC review completed | 6 | 2 | 2007-05-20 | 2007-05-22 | [11 empty] | 6 | 32
27 |  |  | Pre-job brief completed | 6 | 1 | 2007-05-22 | 2007-05-23 | [11 empty] | 1 | 16
28 |  |  | Station 2 operational |  |  |  | 2007-05-23
29 |  | Station 3-Modular Coil to VVSA Assembly
30 |  |  | Procedures approved | 27 | 10 | 2007-05-10 | 2007-05-20 | [12 empty] | 32
31 |  |  | JHA completed | 6 | 6 | 2007-05-20 | 2007-05-26 | [12 empty] | 24
32 |  |  | Sequence plan
33 |  |  | Metrology plan
34 |  |  | Training needs identified & released | 6 | 6 | 2007-06-22 | 2007-06-28 | [12 empty] | 24
35 |  |  | ACC review completed | 6 | 6 | 2007-06-28 | 2007-07-04 | [12 empty] | 96
36 |  |  | Pre-job brief completed | 6 | 6 | 2007-07-04 | 2007-07-10 | [12 empty] | 96
37 |  |  | Station 3 operational |  | 1 | 2007-07-10 | 2007-07-11
38 |  |  | Fixtures installed | 6 | 6 | 2007-07-11 | 2007-07-17 | [11 empty] | 80 | 96
39 |  | Station 5-Final Field Period Assembly
40 |  |  | Procedures approved | 27 | 14 | 2007-10-01 | 2007-10-15 | [12 empty] | 24
41 |  |  | JHA completed | 6 | 6 | 2007-10-15 | 2007-10-21 | [12 empty] | 10.2857
42 |  |  | Sequence plan
43 |  |  | Metrology plan
44 |  |  | Training needs identified & released | 6 | 6 | 2007-10-21 | 2007-10-27 | [12 empty] | 10.2857
45 |  |  | ACC review completed | 7 | 7 | 2007-10-27 | 2007-11-03 | [12 empty] | 12
46 |  |  | Pre-job brief completed | 7 | 7 | 2007-11-03 | 2007-11-10 | [12 empty] | 12
47 |  |  | Station 5 operational |  | 1 | 2007-11-10 | 2007-11-11
48 |  |  | Fixtures installed | 6 | 6 | 2007-11-11 | 2007-11-17 | [11 empty] | 80 | 10.2857
49 | Job: 1802 - FP Assy Oversight&Support-VIOLA Total
50 | Job: 1810 - Field Period Assembly-VIOLA
51 |  | General F.P. Assy support | [17 empty] | 0
52 |  |  | LOE Crane support, fixture setupfor TFTR TC. | 362 | 362 | 2006-10-01 | 2007-09-28 | [11 empty] | 696.6605 | 2400 | [13 empty] | 2 men 3 day a week
53 |  |  | LOE Crane support, fixture setupfor TFTR TC. | 363 | 363 | 2007-09-28 | 2008-09-25 | [11 empty] | 838.34 | 2400 | [13 empty] | 2 men 3 day a week
54 |  |  | LOE Field Supervision for TFTR TC FY07 |  | 362 | 2006-10-01 | 2007-09-28 | [17 empty] | 2068.5714
55 |  |  | LOE Field Supervision for TFTR TC FY08 |  | 363 | 2007-10-01 | 2008-09-28 | [17 empty] | 2074.2857
56 |  |  | LOE Metrology support FY07 | 362 | 362 | 2007-09-28 | 2008-09-24 | [8 empty] | 3516.5714 |  |  | 1435.968 | 2068.5714
57 |  |  | LOE Metrology support FY08 | 362 | 362 | 2008-09-25 | 2009-09-22 | [8 empty] | 2068.5714 |  |  | 1435.968 | 2068.5714
58 | Station 1-FP #1 VV Prep (hard surface components)
59 | Station 1-FP #1 VV Prep (hard surface components) |  | Layout diagnostic&coolant paths on vessel | 75 | 35 | 2007-01-10 | 2007-02-14 | 100% | [10 empty] | 245 | 480 | [5 empty] | NONE
60 | Station 1-FP #1 VV Prep (hard surface components) |  | Install heater tape on vertical ports | 75 | 7 | 2007-02-14 | 2007-02-21 | 100% | [10 empty] | 17.1 | 96
61 | Station 1-FP #1 VV Prep (hard surface components) |  | Verify installation of heater tapes | 2 | 1 | 2007-02-21 | 2007-02-22 | 100% | [11 empty] | 16
62 | Station 1-FP #1 VV Prep (hard surface components) |  | Attach studs for coolant lines | 75 | 3 | 2007-02-22 | 2007-02-25 | 100% | [10 empty] | 42 | 48
63 | Station 1-FP #1 VV Prep (hard surface components) |  | Wind magnetic diagnostic sensors | 43 | 14 | 2007-02-25 | 2007-03-11 | 100% | [10 empty] | 256 | 192
64 | Station 1-FP #1 VV Prep (hard surface components) |  | Install precision magnetic diagnostic sensors | 41 | 3 | 2007-03-11 | 2007-03-14 | 100% | [10 empty] | 240 | 48
65 | Station 1-FP #1 VV Prep (hard surface components) |  | Verify installation magnetic diagnostic sensors |  | 4 | 2007-03-14 | 2007-03-18 | 100% | [10 empty] | 28 | 64
66 | Station 1-FP #1 VV Prep (hard surface components) |  | Install local I&C (incl thermocouples) | 8 | 5 | 2007-03-18 | 2007-03-23 | 100% | [10 empty] | 65 | 80
67 | Station 1-FP #1 VV Prep (hard surface components) |  | Verify installation of local I&C | 2 | 2 | 2007-03-23 | 2007-03-25 | 100% | [10 empty] | 28 | 32
68 | Station 1-FP #1 VV Prep (hard surface components) |  | Install cooling/htg lines to vac vsl | 34 | 15 | 2007-03-25 | 2007-04-09 | 50% | [10 empty] | 192 | 208
69 | Station 1-FP #1 VV Prep (hard surface components) |  | Weld cooling/htg risers | 34 | 10 | 2007-04-09 | 2007-04-19 | A | [10 empty] | 192 | 144
70 | Station 1-FP #1 VV Prep (hard surface components) |  | Verify Instl of H/C lines,headers,manifolds | 6 | 5 | 2007-04-19 | 2007-04-24 | A | [10 empty] | 46 | 80
71 | Station 1-FP #1 VV Prep (hard surface components) |  | Loop termination & verification | 6 | 18 | 2007-04-24 | 2007-05-12 | Floor | [10 empty] | 35 | 256
72 | Station 1-FP #1 VV Prep (hard surface components) |  | Final Scan | 7 | 4 | 2007-05-12 | 2007-05-16 | D | [10 empty] | 33.15 | 64
73 | Station 1-FP #1 VV Prep (hard surface components) |  | Prepare and transfer completed VV to holding are | 4 | 2 | 2007-05-16 | 2007-05-18 | D | [10 empty] | 42 | 32
74 | Station 1- FP #2 VV Prep (hrd surf cmpnts)
75 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Layout diagnostic&coolant paths on vessel | 35 | 12 | 2007-02-18 | 2007-03-02 | 100% | [10 empty] | 245 | 176 | [5 empty] | NONE
76 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Install heater tape on vertical ports | 5 | 7 | 2007-03-02 | 2007-03-09 | 100% | [10 empty] | 53 | 96
77 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Verify installation of heater tapes | 0 | 1 | 2007-03-09 | 2007-03-10 | 100% | [10 empty] | 11 | 16
78 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Attach studs forcoolant lines | 15 | 3 | 2007-03-10 | 2007-03-13 | 100% | [10 empty] | 183 | 48
79 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Wind magnetic diagnostic sensors | 27 | 14 | 2007-03-13 | 2007-03-27 | 100% | [10 empty] | 280 | 192
80 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Install precision magnetic diagnostic sensors | 31 | 3 | 2007-03-27 | 2007-03-30 | 100% | [10 empty] | 163 | 48
81 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Verify installation magnetic diagnostic sensors |  | 4 | 2007-03-30 | 2007-04-03 | 100% | [10 empty] | 28 | 64
82 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Install local I&C (incl thermocouples) | 8 | 5 | 2007-04-03 | 2007-04-08 | A | [10 empty] | 80 | 80
83 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Verify installation of local I&C | 2 | 2 | 2007-04-08 | 2007-04-10 | A | [10 empty] | 23 | 32
84 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Install cooling/htg lines to vac vsl | 34 | 15 | 2007-04-10 | 2007-04-25 | C | [10 empty] | 384 | 208
85 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Weld cooling/htg risers | 34 | 10 | 2007-04-25 | 2007-05-05 | C | [10 empty] | 192 | 144
86 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Verify Instl of H/C lines,headers,manifolds | 7 | 5 | 2007-05-05 | 2007-05-10 | E | [10 empty] | 38 | 80
87 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Loop termination & verification | 12 | 18 | 2007-05-10 | 2007-05-28 | E | [10 empty] | 10 | 256
88 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Final Scan | 4 | 4 | 2007-05-28 | 2007-06-01 | E | [10 empty] | 33.15 | 64
89 | Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Prepare and transfer completed VV to holding are | 2 | 2 | 2007-06-01 | 2007-06-03 | E | [10 empty] | 63 | 32
90 | Station 1- FP #3 VV Prep (hrd surf cmpnts)
91 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Layout diagnostic&coolant paths on vessel | 26 | 12 | 2007-04-09 | 2007-04-21 | 100% | [10 empty] | 221 | 176
92 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Install heater tape on vertical ports | 3 | 7 | 2007-04-21 | 2007-04-28 | B | [10 empty] | 29 | 96
93 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Verify installation of heater tapes | 0 | 1 | 2007-04-28 | 2007-04-29 | B | [10 empty] | 11 | 16
94 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Attach studs forcoolant lines | 15 | 3 | 2007-04-29 | 2007-05-02 | B | [10 empty] | 86 | 48
95 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Wind magnetic diagnostic sensors | 28 | 14 | 2007-05-02 | 2007-05-16 | C | [10 empty] | 420 | 192
96 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Install precision magnetic diagnostic sensors | 26 | 3 | 2007-05-16 | 2007-05-19 | C | [10 empty] | 266 | 48
97 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Verify installation magnetic diagnostic sensors |  | 4 | 2007-05-19 | 2007-05-23 | C | [10 empty] | 28 | 64
98 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Install local I&C (incl thermocouples) | 8 | 5 | 2007-05-23 | 2007-05-28 | F | [10 empty] | 50 | 80
99 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Verify installation of local I&C | 2 | 2 | 2007-05-28 | 2007-05-30 | F | [10 empty] | 22 | 32
100 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Install cooling/htg lines to vac vsl | 29 | 15 | 2007-05-30 | 2007-06-14 | F | [10 empty] | 352 | 208
101 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Weld cooling/htg risers | 34 | 10 | 2007-06-14 | 2007-06-24 | F | [10 empty] | 192 | 144
102 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Verify Instl of H/C lines,headers,manifolds | 4 | 5 | 2007-06-24 | 2007-06-29 | F | [10 empty] | 36 | 80
103 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Loop termination & verification | 2 | 18 | 2007-06-29 | 2007-07-17 | F | [10 empty] | 10 | 256
104 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Final Scan | 2 | 4 | 2007-07-17 | 2007-07-21 | F | [10 empty] | 33.15 | 64
105 | Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Prepare and transfer completed VV to holding are | 2 | 2 | 2007-07-21 | 2007-07-23 | F | [10 empty] | 43 | 32
106 |  | Station 1-Spool pieces (3) (spacers) | [17 empty] | 0
107 |  |  | Attachdiagnostics, studs and coolant lines | 48 | 48 | 2008-01-10 | 2008-02-27 | [11 empty] | 288 | 672
108 |  | Station 2 Trials & Setup | [17 empty] | 0
109 |  |  | Trial tensioning test on prototype | 46 | 2 | 2007-04-09 | 2007-04-11 | [12 empty] | 32
110 |  |  | Trial bushing and shim test on prototype | 67 | 12 | 2007-04-09 | 2007-04-21 | [12 empty] | 176
111 |  |  | Guidance f/post-VPI proced to include measuremen | 36 | 36 | 2007-03-29 | 2007-05-04 | [12 empty] | 496
112 |  |  | Perform trial x-y-z alignments on A1-A2. | 90 | 7 | 2007-04-03 | 2007-04-10 | [12 empty] | 96
113 |  |  | Alignment mechanisms, metro equipt &positioning | 6 | 6 | 2007-04-10 | 2007-04-16 | [12 empty] | 96
114 |  |  | Procure alignment mechanisms, fiducials, lifting | 56 | 20 | 2007-03-30 | 2007-04-19 | [12 empty] | 288
115 |  |  | Develop procedures for torquing bolts | 4 | 4 | 2007-04-02 | 2007-04-06 | [12 empty] | 64
116 |  |  | Determine fiducial types&locations | 11 | 11 | 2007-04-09 | 2007-04-20 | [12 empty] | 160
117 |  |  | Procure monuments&related metrology equipment | 42 | 15 | 2007-03-30 | 2007-04-14 | [12 empty] | 208
118 |  |  | Tools&tooling available for FPA operations |  |  |  | 2007-06-12 | [12 empty] | 0
119 |  |  | Install FIRST Holding fixture | 4 | 4 | 2007-01-22 | 2007-01-26 | [11 empty] | 20 | 64
120 |  |  | Install SECOND Holding fixture | 3 | 3 | 2007-04-07 | 2007-04-10 | [11 empty] | 10 | 48
121 |  |  | Install THIRD Holding fixture |  | 6 | 2007-04-18 | 2007-04-24 | [11 empty] | 6 | 96
122 |  |  | Install LAST Holding fixture |  | 3 | 2007-06-06 | 2007-06-09 | [11 empty] | 6 | 48
123 |  | Station 2-Modular Coil Subassembly-FP#1 | [17 empty] | 0
124 |  |  | Test out equipt & procedures | 7 | 7 | 2007-04-04 | 2007-04-11 | [11 empty] | 88 | 96
124 |  |  | Receive drawings and hardware (shims and bolts) | 7 | 7 | 2007-04-30 | 2007-05-07 | [11 empty] | 88 | 96
143 |  |  | Begin A1/B1/C1 |  | 1 | 2007-05-07 | 2007-05-08 | [11 empty] | 360 | 16
125 |  |  | Pre-fit & install alignment tooling A1-A2 | 2 | 4 | 2007-05-08 | 2007-05-12 | [11 empty] | 32 | 64
126 |  |  | Align A1-A2 | 2 | 2 | 2007-05-12 | 2007-05-14 | [11 empty] | 32 | 32
127 |  |  | Install Nose shear | 2 | 10 | 2007-05-14 | 2007-05-24 | [11 empty] | 32 | 144
128 |  |  | Install studs | 2 | 2 | 2007-05-24 | 2007-05-26 | [11 empty] | 32 | 32
129 |  |  | Install shims | 2 | 5 | 2007-05-26 | 2007-05-31 | [11 empty] | 32 | 80
130 |  |  | Install Bushings | 2 | 5 | 2007-05-31 | 2007-06-05 | [11 empty] | 32 | 80
131 |  |  | Tension | 3 | 3 | 2007-06-05 | 2007-06-08 | [11 empty] | 16 | 48
132 |  |  | Verify alignment A1-A2 | 2 | 2 | 2007-06-08 | 2007-06-10 | [11 empty] | 32 | 32
133 |  |  | De Tension | 1 | 1 | 2007-06-10 | 2007-06-11 | [11 empty] | 16 | 16
134 |  |  | Adjust Nose shear | 2 | 4 | 2007-06-11 | 2007-06-15 | [11 empty] | 32 | 64
135 |  |  | Adjust shims | 2 | 3 | 2007-06-15 | 2007-06-18 | [11 empty] | 32 | 48
136 |  |  | Adjust Bushings | 2 | 3 | 2007-06-18 | 2007-06-21 | [11 empty] | 32 | 48
137 |  |  | Re Tension | 3 | 3 | 2007-06-21 | 2007-06-24 | [11 empty] | 16 | 48
138 |  |  | Verify alignment A1-A2 | 2 | 2 | 2007-06-24 | 2007-06-26 | [11 empty] | 32 | 32
139 |  |  | De Tension | 3 | 1 | 2007-06-26 | 2007-06-27 | [11 empty] | 16 | 16
140 |  |  | Pre-fit C1-C5 | 4 | 50 | 2007-06-27 | 2007-08-16 | [11 empty] | 32 | 688
143 |  |  | Begin 3 pack A1/B1/C1 Install A1 |  | 3 | 2007-08-16 | 2007-08-19 | [11 empty] | 360 | 48
141 |  |  | Fit A1-B1 | 1 | 50 | 2007-08-19 | 2007-10-08 | [11 empty] | 16 | 688
142 |  |  | Fit B1-C1 | 3 | 50 | 2007-10-08 | 2007-11-27 | [11 empty] | 16 | 688
143 |  |  | Verify Align Mod-Coils A1/B1/C1 | 36 | 5 | 2007-11-27 | 2007-12-02 | [11 empty] | 360 | 80
144 |  |  | Pre-fit C2-C3 | 49 | 50 | 2007-12-02 | 2008-01-21 | [11 empty] | 720 | 688
145 |  |  | Fit A2-B2 | 42 | 50 | 2008-01-21 | 2008-03-11 | [11 empty] | 480 | 688
146 |  |  | Fit B2-C2 |  | 50 | 2008-03-11 | 2008-04-30 | [12 empty] | 688
147 |  |  | Verify Align Mod-Coils A2/B2/C2 | 1 | 5 | 2008-04-30 | 2008-05-05 | [11 empty] | 16 | 80
148 |  | Station 2-Modular Coil Subassembly-FP#2
149 |  |  | Assemble/Align Mod-Coils A3/B3/C3 | 35 | 55 | 2007-08-31 | 2007-10-25 | [11 empty] | 360 | 768
150 |  |  | Pre-fit C6-C4 | 36 | 50 | 2007-10-31 | 2007-12-20 | [11 empty] | 360 | 688
151 |  |  | Assemble/Align Mod-Coils A4/B4/C4 | 43 | 55 | 2007-12-18 | 2008-02-11 | [11 empty] | 360 | 768
152 |  | Station 2-Modular Coil Subassembly-FP#3
153 |  |  | Assemble/Align Mod-Coils A5/B5/C5 | 27 | 55 | 2007-07-25 | 2007-09-18 | [11 empty] | 360 | 768
154 |  |  | Assemble/Align Mod-Coils A6/B6/C6 |  | 55 | 2007-09-18 | 2007-11-12 | [12 empty] | 768
155 |  | Station 3-Assemble Mod Coils and VVSA-FP#1 | [16 empty] | 384
157 |  |  | Begin Assembly of First Field Period Assy | 2 | 2 | 2007-08-24 | 2007-08-26 | [11 empty] | 32 | 32
158 |  |  | Test out station 3 equipment and procedures | 2 | 2 | 2007-08-26 | 2007-08-28 | [11 empty] | 48 | 32
156 |  |  | Assemble/Disassemble abc1-abc2 (stage 3 fixture) | 5 | 15 | 2007-08-09 | 2007-08-24 | [11 empty] | 48 | 208
159 |  |  | VV to MC turning fixt base; metr check | 3 | 3 | 2007-08-28 | 2007-08-31 | [11 empty] | 72 | 48
160 |  |  | Attach local protective strips to VV&locate sens | 5 | 2 | 2007-08-31 | 2007-09-02 | [11 empty] | 48 | 32
161 |  |  | Mount MC on crane; perform metr checks | 0 | 4 | 2007-09-02 | 2007-09-06 | [11 empty] | 24 | 64
162 |  |  | Rotate right MC to stand-off position&chk | 3 | 3 | 2007-09-06 | 2007-09-09 | [11 empty] | 48 | 120
163 |  |  | Transfer load to sprt sys and recheck position | 1 | 3 | 2007-09-09 | 2007-09-12 | [11 empty] | 48 | 48
164 |  |  | Move MC turning fixt; mount MC on crane | 20 | 5 | 2007-09-12 | 2007-09-17 | [11 empty] | 240 | 80
165 |  |  | Rotate left MC to stand-off position and check p | 13 | 5 | 2007-09-17 | 2007-09-22 | [11 empty] | 120 | 200
166 |  |  | Move left & right MC to final position & measure | 6 | 6 | 2007-09-22 | 2007-09-28 | [11 empty] | 72 | 96
167 |  |  | Pot 3 packs together | 6 | 10 | 2007-09-28 | 2007-10-08 | [11 empty] | 48 | 144
168 |  |  | Bolt together at flange interface. | 6 | 35 | 2007-10-08 | 2007-11-12 | [11 empty] | 72 | 480
169 |  |  | Perform final metrology position check | 1 | 2 | 2007-11-12 | 2007-11-14 | [11 empty] | 48 | 32
170 |  |  | Remove temp interference strips&sensors | 1 | 1 | 2007-11-14 | 2007-11-15 | [11 empty] | 80 | 16
172 |  |  | Secure VV to MC's using temporary supports. | 23 | 5 | 2007-10-08 | 2007-10-13 | [11 empty] | 360 | 80
173 |  |  | Prepare Field Period for shipment | 5 | 5 | 2007-10-13 | 2007-10-18 | [11 empty] | 48 | 80
174 |  |  | Transfer completed assy to C-site test cell | 2 | 2 | 2007-10-18 | 2007-10-20 | [11 empty] | 32 | 32
171 |  | Station 3-Assemble Mod Coils and VVSA-FP#2
175 |  |  | Assemble/Disassemble abc -abc4 (stage 3 fixture) | 4 | 15 | 2007-10-20 | 2007-11-04 | [11 empty] | 48 | 208
176 |  |  | Mount VV to MC turning fixt base; metr check | 6 | 3 | 2007-11-04 | 2007-11-07 | [11 empty] | 72 | 48
177 |  |  | Attach local protective strips to VV&locate sens | 1 | 2 | 2007-11-07 | 2007-11-09 | [11 empty] | 48 | 32
178 |  |  | Mount MC on crane; perform metr checks | 0 | 4 | 2007-11-09 | 2007-11-13 | [11 empty] | 24 | 64
179 |  |  | Rotate right MC to stand-off position&chk | 1 | 3 | 2007-11-13 | 2007-11-16 | [11 empty] | 48 | 120
180 |  |  | Transfer load to supt sys and recheck position | 1 | 3 | 2007-11-16 | 2007-11-19 | [11 empty] | 48 | 48
181 |  |  | Move MC turning fixt; mount MC on crane | 24 | 5 | 2007-11-19 | 2007-11-24 | [11 empty] | 240 | 80
182 |  |  | Rotate left MC to stand-off position and check p | 6 | 5 | 2007-11-24 | 2007-11-29 | [11 empty] | 120 | 200
183 |  |  | Move left & right MC to final position & measure | 2 | 6 | 2007-11-29 | 2007-12-05 | [11 empty] | 72 | 96
184 |  |  | Pot 3 packs together | 3 | 8 | 2007-12-05 | 2007-12-13 | [11 empty] | 48 | 112
185 |  |  | Bolt together at flange interface. | 2 | 30 | 2007-12-13 | 2008-01-12 | [11 empty] | 72 | 416
186 |  |  | Perform final metrology position check | 3 | 3 | 2008-01-12 | 2008-01-15 | [11 empty] | 48 | 48
187 |  |  | Remove temp interference strips&sensors | 1 | 1 | 2008-01-15 | 2008-01-16 | [11 empty] | 80 | 16
189 |  |  | Secure VV to MC's using temporary supports. | 21 | 5 | 2008-01-31 | 2008-02-05 | [11 empty] | 360 | 80
190 |  |  | Prepare Field Period for shipment | 5 | 5 | 2008-02-05 | 2008-02-10 | [11 empty] | 48 | 80
191 |  |  | Transfer completed assy to C-site test cell | 2 | 2 | 2008-02-10 | 2008-02-12 | [11 empty] | 32 | 32
188 |  | Station 3-Assemble Mod Coils and VVSA-FP#3
192 |  |  | Assemble/Disassemble abc -abc6 (Stage 3 fixture) | 3 | 15 | 2008-02-12 | 2008-02-27 | [11 empty] | 48 | 208
193 |  |  | Mount VV to MC turning fixt base; metr check | 2 | 3 | 2008-02-27 | 2008-03-01 | [11 empty] | 72 | 48
194 |  |  | Attach local protective strips to VV&locate sens | 3 | 2 | 2008-03-01 | 2008-03-03 | [11 empty] | 48 | 32
195 |  |  | Mount MC on crane; perform metr checks | 0 | 4 | 2008-03-03 | 2008-03-07 | [11 empty] | 24 | 64
196 |  |  | Rotate right MC to stand-off position&chk | 1 | 3 | 2008-03-07 | 2008-03-10 | [11 empty] | 48 | 120
197 |  |  | Transfer load to supt sysand recheck position | 3 | 3 | 2008-03-10 | 2008-03-13 | [11 empty] | 48 | 48
198 |  |  | Move MC turning fixt; mount MC on crane | 13 | 5 | 2008-03-13 | 2008-03-18 | [11 empty] | 240 | 80
199 |  |  | Rotate left MC to stand-off position and check p | 6 | 5 | 2008-03-18 | 2008-03-23 | [11 empty] | 120 | 200
200 |  |  | Move left & right MC to final position & measure | 2 | 6 | 2008-03-23 | 2008-03-29 | [11 empty] | 72 | 96
201 |  |  | Pot 3 packs together | 3 | 8 | 2008-03-29 | 2008-04-06 | [11 empty] | 48 | 112
202 |  |  | Bolt together at flange interface. | 2 | 25 | 2008-04-06 | 2008-05-01 | [11 empty] | 72 | 352
203 |  |  | Perform final metrology position check | 3 | 3 | 2008-05-01 | 2008-05-04 | [11 empty] | 48 | 48
204 |  |  | Remove temp interference strips&sensors | 0 | 1 | 2008-05-04 | 2008-05-05 | [11 empty] | 80 | 16
205 |  | Station 4 - TF HP Pre-Assy |  | I think station 4 goes away because we are installing them after the ports are welded on one at a time.
209 |  |  | Test out station 4 equipment and procedures
206 |  |  | Secure VV to MC's using temporary supports.
207 |  |  | Prepare Field Period for shipment
208 |  |  | Transfer completed assy to C-site test cell
210 |  |  | Assemble 3 TF coils&structure -Left-Period #1
211 |  |  | Assemble 3 TF coils&structure -Right -Period #1
212 |  |  | Assemble/disassemble TF 6 pac (FP#1)
213 |  |  | Assemble 3 TF coils&structure -Left-Period #2
214 |  |  | Assemble 3 TF coils&structure -Right -Period #2
215 |  |  | Assemble/disassemble TF 6 pac (FP#2)
216 |  |  | Assemble 3 TF coils&structure -Left -Period #3
217 |  |  | Assemble 3 TF coils&structure -Right -Period #3
218 |  |  | Assemble/disassemble TF 6 pac (FP#3)
219 |  | Station 5- Final FP Assy -FP#1 (in NCSX TC) | [17 empty] | 0
221 |  |  | Testout Sta5 equipt & procedures | 15 | 5 | 2007-11-05 | 2007-11-10 | [11 empty] | 80 | 80
220 |  |  | Install on support platform | 43 | 15 | 2007-11-10 | 2007-11-25 | [11 empty] | 960 | 208
222 |  |  | Mount MC/VV assembly to support frame a | 2 | 2 | 2007-11-25 | 2007-11-27 | [11 empty] | 96 | 32
223 |  |  | Position and weld all ports to VV | 3 | 25 | 2007-11-27 | 2007-12-22 | [11 empty] | 48 | 352
224 |  |  | Inspect Welds | 2 | 4 | 2007-12-22 | 2007-12-26 | [11 empty] | 96 | 64
225 |  |  | Assemble left TF Coil Assembly check position | 4 | 8 | 2007-12-26 | 2008-01-03 | [11 empty] | 72 | 112
226 |  |  | Change platforms | 1 | 1 | 2008-01-03 | 2008-01-04 | [11 empty] | 64 | 16
227 |  |  | Assemble right TF Coil Assembly chk position | 11 | 8 | 2008-01-04 | 2008-01-12 | [11 empty] | 192 | 112
228 |  |  | Attach TF coils to MC's | 0 | 4 | 2008-01-12 | 2008-01-16 | [11 empty] | 16 | 64
229 |  |  | Change platforms | -1 | 1 | 2008-01-16 | 2008-01-17 | [12 empty] | 16
230 |  |  | Position, weld two large horizontal diag ports | 13 | 12 | 2008-01-17 | 2008-01-29 | [11 empty] | 640 | 176
231 |  |  | Inspect Welds | 13 | 5 | 2008-01-29 | 2008-02-03 | [11 empty] | 48 | 80
232 |  |  | Assemble external trim coils (in wbs75) | 13 | 15 | 2008-02-03 | 2008-02-18 | [12 empty] | 208
233 |  |  | Close up VV, leak check | 1 | 21 | 2008-02-18 | 2008-03-10 | [11 empty] | 48 | 288
234 |  |  | Adjust final support base interfaces | 1 | 8 | 2008-03-10 | 2008-03-18 | [11 empty] | 48 | 112
235 |  |  | Final metrology outside & inside | 39 | 10 | 2008-03-18 | 2008-03-28 | [11 empty] | 960 | 144
236 |  | Station 5- Final FP Assy -FP#2 (in NCSX TC)
237 |  |  | Install on support platform | 4 | 15 | 2008-03-17 | 2008-04-01 | [11 empty] | 80 | 208
238 |  |  | Mount MC/VV assembly to support frame a | 2 | 2 | 2008-04-01 | 2008-04-03 | [11 empty] | 96 | 32
239 |  |  | Position and weld all ports to VV | 1 | 25 | 2008-04-03 | 2008-04-28 | [11 empty] | 48 | 352
240 |  |  | Inspect Welds | 2 | 4 | 2008-04-28 | 2008-05-02 | [11 empty] | 96 | 64
241 |  |  | Assemble left TF Coil Assembly check position | 4 | 8 | 2008-05-02 | 2008-05-10 | [11 empty] | 72 | 112
242 |  |  | Change platforms | 1 | 1 | 2008-05-10 | 2008-05-11 | [11 empty] | 64 | 16
243 |  |  | Assemble right TF Coil Assembly chk position | 11 | 8 | 2008-05-11 | 2008-05-19 | [11 empty] | 192 | 112
244 |  |  | Attach TF coils to MC's | 0 | 4 | 2008-05-19 | 2008-05-23 | [11 empty] | 16 | 64
245 |  |  | Change platforms | -1 | 1 | 2008-05-23 | 2008-05-24 | [12 empty] | 16
246 |  |  | Position, weld two large horizontal diag ports | 13 | 12 | 2008-05-24 | 2008-06-05 | [11 empty] | 640 | 176
247 |  |  | Inspect Welds | 13 | 5 | 2008-06-05 | 2008-06-10 | [11 empty] | 48 | 80
248 |  |  | Assemble external trim coils (in wbs75) | 14 | 15 | 2008-06-10 | 2008-06-25 | [12 empty] | 208
249 |  |  | Close up VV, leak check | 1 | 21 | 2008-06-25 | 2008-07-16 | [11 empty] | 48 | 288
250 |  |  | Adjust final support base interfaces | 1 | 8 | 2008-07-16 | 2008-07-24 | [11 empty] | 48 | 112
251 |  |  | Final metrology outside & inside | 42 | 10 | 2008-07-24 | 2008-08-03 | [11 empty] | 960 | 144
252 |  | Station 5- Final FP Assy -FP#3 (in NCSX TC) | [17 empty] | 0
253 |  |  | Install on support platform | 2 | 15 | 2008-06-02 | 2008-06-17 | [11 empty] | 80 | 208
254 |  |  | Mount MC/VV assembly to support frame a | 0 | 2 | 2008-06-17 | 2008-06-19 | [11 empty] | 96 | 32
255 |  |  | Position and weld all ports to VV*2 shift* | 0 | 25 | 2008-06-19 | 2008-07-14 | [11 empty] | 48 | 352
256 |  |  | Inspect Welds | 1 | 4 | 2008-07-14 | 2008-07-18 | [11 empty] | 96 | 64
257 |  |  | Assemble left TF Coil Assembly check position | 0 | 8 | 2008-07-18 | 2008-07-26 | [11 empty] | 72 | 112
258 |  |  | Change platforms | 0 | 1 | 2008-07-26 | 2008-07-27 | [11 empty] | 64 | 16
259 |  |  | Assemble right TF Coil Assembly chk position | 5 | 8 | 2008-07-27 | 2008-08-04 | [11 empty] | 192 | 112
260 |  |  | Attach TF coils to MC's | 0 | 4 | 2008-08-04 | 2008-08-08 | [11 empty] | 16 | 64
261 |  |  | Change platforms | -1 | 1 | 2008-08-08 | 2008-08-09 | [12 empty] | 16
262 |  |  | Position, weld two large horizontal diag ports | 6 | 12 | 2008-08-09 | 2008-08-21 | [11 empty] | 640 | 176
263 |  |  | Inspect Welds | 6 | 5 | 2008-08-21 | 2008-08-26 | [11 empty] | 48 | 80
264 |  |  | Assemble external trim coils (in wbs75) | 4 | 15 | 2008-08-26 | 2008-09-10 | [12 empty] | 208
265 |  |  | Close up VV, leak check |  | 21 | 2008-09-10 | 2008-10-01 | [12 empty] | 288
266 |  |  | Adjust final support base interfaces |  | 8 | 2008-10-01 | 2008-10-09 | [18 empty] | 0
267 |  |  | Final metrology outside & inside |  | 10 | 2008-10-09 | 2008-10-19
268 |  |  | Last field period assembled |  | 1 | 2008-10-19 | 2008-10-20
269 | Job:1810 - Field Period Assembly-VIOLA Total | [12 empty] | 1685 | 0 | 11523.1429 | 0 | 0 | 25551.4865 | 36768 | 0 | 0 | 0 | 0 | 4142.8571 | 0
[16 empty] | 160.5 |  |  |  | 80.19 |  |  |  |  | 142
|  |  | 5386176.0629 | [12 empty] | 1849464.4286 |  |  |  | 2948425.92 |  |  |  |  | 588285.7143
3154000
Formulas:
Finish Date = [Start Date]+[Work days]
Finish Date = [Finish Date, row above]
Start Date = [Finish Date, row above]