## Table I - Dsn Labor
WBS Number: 185
WBS Title: Assembly of Field Periods
Job Number: 1815
Job Title: FPA Activities for Stations 5 in the TFTR Test Cell
Job Manager: Mike Viola
Fabrication and Assembly
Assumptions:
Assumes 5 day workweek 1 shift no overtime
Can do 2 shift for Station 5, but would require additional supervision
Parallel ops for sta 5 (2 fixtures available)
Only 1 fixture for station 3 only one shift
Parallel ops for sta 2
| TASK DESCRIPTION | Work days | 41MS | 48MS | 35TRVL | 31OT | ORNL EM/DSN | SHTB | EMEM | EMSM | EMSB | EMTB | CREW | NEW EMTB | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3
This is a fabrication job - all design support included in Table III.
HP Techs EMEM???
Is this in Job 1805?
What is this?

## Table II - M&S
WBS Number: 185
WBS Title: Assembly of Field Periods
Job Number: 1815
Job Title: FPA Activities for Stations 5 in the TFTR Test Cell
Job Manager: Mike Viola
Materials and Supplies

## Table III - Fab & Assy
WBS Number: 185
WBS Title: Assembly of Field Periods
Job Number: 1815
Job Title: FPA Activities for Stations 5 in the TFTR Test Cell
Job Manager: Mike Viola
Fabrication and Assembly
Assumptions:
Assumes 5 day workweek 1 shift no overtime
Can do 2 shift for Station 5, but would require additional supervision
Parallel ops for sta 5 (2 fixtures available)
Only 1 fixture for station 3 only one shift
Parallel ops for sta 2
| TASK DESCRIPTION | Work days | 41MS | 48MS | 37STK | ORNL EM/DSN | SHTB | EMEM | EMSM | EMSB | EMTB | CREW | Basis of Estimate
Based on quotes from PPPL Tech Shop based on similar tasks, tempered (adjusted) for complexity of having to do all welds from inside of the vessel.
Job: 1815 - Field Period Assembly Station 5 (in NCSX TC)-VIOLA
Station 5- Final FP Assy -FP#1 (in NCSX TC)
| metrology network | 10 | 7 | [7 empty] | 160
| Bolt on 2 Port Extensions needed for first Plasma diagnostics | 1 | [8 empty] | 16 | 2 | 10" ports provided by WBS 38
| MTM NCR Hardware repurchase (bolt kits & cover plates) |  | 42
| Weld Wire & weld supples |  | 15
| Testout Sta 5 equipt & procedures | 5 | [8 empty] | 160 | 4
| Check 3 sled interfaces adjust holes | 12 | [8 empty] | 384 | 4
| Fixtures installed - final metrology | 6 | [8 empty] | 192 | 4
| Install on support platform | 15 | 12 | [7 empty] | 600 | 5
| Mount MC/VV assembly to support frame a | 2 | [8 empty] | 40 | 2.5
| Position and weld all ports to VV | 30 | [8 empty] | 600 | 2.5
| Inspect Welds | 4 | [8 empty] | 80 | 2.5
| Assemble left TF Coil Assembly check position | 8 | [8 empty] | 256 | 4
| Change platforms | 1 | [8 empty] | 20 | 2.5
| Assemble right TF Coil Assembly chk position | 8 | [8 empty] | 256 | 4
| Attach TF coils to MC's | 4 | [8 empty] | 80 | 2.5
| Align TF Coils | 8 | [8 empty] | 160 | 2.5
| Change platforms | 1 | [8 empty] | 20 | 2.5
| Position, tack-weld only two large horizontal diag ports (port 4's) | 8 | [8 empty] | 160 | 2.5
Assemble external trim coils (in wbs75)
Close up VV, leak check
| Adjust final support base interfaces | 8 | [8 empty] | 160 | 2.5
| Final metrology outside & inside | 10 | [8 empty] | 200 | 2.5
| Lift onto Station 6 assembly structure | 1 | [8 empty] | 20 | 2.5
Station 5- Final FP Assy -FP#2 (in NCSX TC)
| Install on support platform | 15 | [8 empty] | 600 | 5
| Mount MC/VV assembly to support frame a | 2 | [8 empty] | 40 | 2.5
| Position and weld all ports to VV | 30 | [8 empty] | 600 | 2.5
| Inspect Welds | 4 | [8 empty] | 80 | 2.5
| Assemble left TF Coil Assembly check position | 8 | [8 empty] | 256 | 4
| Change platforms | 1 | [8 empty] | 20 | 2.5
| Assemble right TF Coil Assembly chk position | 8 | [8 empty] | 256 | 4
| Attach TF coils to MC's | 4 | [8 empty] | 80 | 2.5
| Align TF Coils | 6 | [8 empty] | 120 | 2.5
| Change platforms | 1 | [8 empty] | 20 | 2.5
| Position, tack-weld only two large horizontal diag ports (port 4's) | 8 | [8 empty] | 160 | 2.5
Assemble external trim coils (in wbs75)
Close up VV, leak check
| Adjust final support base interfaces | 8 | [8 empty] | 160 | 2.5
| Final metrology outside & inside | 10 | [8 empty] | 200 | 2.5
| Lift onto Station 6 assembly structure | 1 | [8 empty] | 20 | 2.5
Station 5- Final FP Assy -FP#3 (in NCSX TC)
| Install on support platform | 15 | [8 empty] | 600 | 5
| Mount MC/VV assembly to support frame a | 2 | [8 empty] | 40 | 2.5
| Position and weld all ports to VV*2 shift* | 30 | [8 empty] | 600 | 2.5
| Inspect Welds | 4 | [8 empty] | 80 | 2.5
| Assemble left TF Coil Assembly check position | 8 | [8 empty] | 256 | 4
| Change platforms | 1 | [8 empty] | 20 | 2.5
| Assemble right TF Coil Assembly chk position | 8 | [8 empty] | 256 | 4
| Attach TF coils to MC's | 4 | [8 empty] | 80 | 2.5
| Align TF Coils | 6 | [8 empty] | 120 | 2.5
| Change platforms | 1 | [8 empty] | 20 | 2.5
| Position, tack-weld only two large horizontal diag ports (port 4's) | 8 | [8 empty] | 160 | 2.5
Assemble external trim coils (in wbs75)
Close up VV, leak check
| Adjust final support base interfaces | 8 | [8 empty] | 160 | 2.5
| Final metrology outside & inside | 10 | [8 empty] | 200 | 2.5
| Last field period assembled | 1 | [8 empty] | 20 | 2.5
| Lift onto Station 6 assembly structure | 1 | [8 empty] | 20 | 2.5
Job:1810 - Field Period Assembly-VIOLA Total | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Job: 1815 - Field Period Assembly Station 5 (in NCSX TC)-VIOLA |  |  | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8808
HP Techs EMEM???
Is this in Job 1805?
What is this?
Is this in Job 1805?

## Table IV - Conting & Risk
WBS Number: 185
WBS Title: Assembly of Field Periods
Job Number: 1802
Job Title: FPA Oversight and Support
Job Manager: Mike Viola
Uncertainty of the Estimate
|  | High | Medium | Low | Comments/Other Cionsiderations
| Design Maturity | X |  |  | Standard welding techniques adjust for welding in tight confines inside vessel
| Design Complexity |  | X |  | Welding vessel while using metrology for measuring distortion
Residual Risks
Risk |  |  | Liklihood of Occurring |  |  |  | Mitigation Stgrategies | Consequence if Occurs
|  |  | Very Likely | Likely | Not Likely | Very Unlikely |  | Cost | Schedule
#1 | Welds fail inspection |  |  |  | X |  |  | 2 m-d/weld | 2 days/rejected weld
#2 | Excessive distortion |  |  | X |  |  | Apply torch heat to adjust distortion or grind and re-weld as necessary | 1/2 m-d for torch heat adjustments and ~2m-d if need to grind out and re-weld | 1/2 to 2 m-d per instance