## Sheet1
WBS:= | [11 empty] | ORNLEM |  | EMEM |  |  | EMTB | NEW EMTB | EAEM | NEW EAEM |  |  | EESM | NEW EESM
Job Number=
Title=
Job Manager=
[7 empty] | FY07$K |  |  |  |  | HOURS
[7 empty] | 1308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 |  | 180.79 |  | 116.7 | 168.88 | 138.6 |  | 138.6 | 78.33 | 144.88 | 93.69 | 70.98 | 162.83 | 229.54 | 9789.08
Task ID |  | TASK DESCRIPTION | Original est. Work days | Work days | Start Date | Finish Date | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNLEM | ORNLDSN | EMEM | EMSM | EMSB | EMTB |  | EAEM |  | EASB | EEEM | EESM |  | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Rough Estimate Total (in FY07$)
Job: 1802 - FP Assy Oversight&Support-VIOLA
FY04 Work Plan
|  | Procedures approved | 25 | 25 | 2007-04-30 | 2007-05-25
|  | JHA completed | 6 | 6 | 2007-06-26 | 2007-07-02
|  | Training needs identified & released | 6 | 6 | 2007-05-29 | 2007-06-04
|  | ACC review completed | 7 | 7 | 2007-07-03 | 2007-07-10
|  | Pre-job brief completed | 7 | 7 | 2007-07-03 | 2007-07-10
|  | Station 4 operational |  |  |  | 2007-07-10
|  | Fixtures installed | 6 | 6 | 2007-06-19 | 2007-06-25 | [10 empty] | 80
Oversight and Supervision
|  | PPPL EM LOE FY06 | #VALUE! | #VALUE! | 2005-12-01
|  | Metrology Engineering Supervision FY06 | #VALUE! | #VALUE! | 2006-05-01
|  | Metrology Engineering Supervision FY07 | 362 | 362 | 2006-10-01 | 2007-09-28 | [7 empty] | 140
|  | PPPL EM LOE FY07 | 362 | 362 | 2006-10-01 | 2007-09-28 | [7 empty] | 362
|  | PPPL EM LOE FY08 | 273 | 273 | 2007-10-01 | 2008-06-30 | [7 empty] | 362
|  | Title III field period assembly FY07 ORNL suppor | 362 | 362 | 2006-10-01 | 2007-09-28 | [5 empty] | 365
|  | Title III field period assembly FY08 ORNL suppor |  | 192 | 2007-09-28 | 2008-04-07 | [5 empty] | 180
|  | HP Coverage in the TFTR TC LOE FY07 | 365 | 365 | 2006-10-01 | 2007-10-01 | [7 empty] | 365
|  | HP Coverage in the TFTR TC LOE FY08 | 189 | 189 | 2007-10-01 | 2008-04-07 | [7 empty] | 180
|  | HP Coverage in the TFTR TC LOE FY06 | #VALUE! | #VALUE! | 2005-10-01 | [11 empty] | 80
Station 2-Modular Coil Sub- Assembly
|  | JHA completed | 6 | 6 | 2007-01-26 | 2007-02-01 | [10 empty] | 4
Sequence plan
Metrology plan
|  | Procedures written & approved | 27 | 14 | 2007-04-30 | 2007-05-14 | [10 empty] | 7
|  | Training needs identified & released | 6 | 6 | 2007-05-14 | 2007-05-20 | [10 empty] | 3
|  | ACC review completed | 6 | 6 | 2007-05-20 | 2007-05-26 | [10 empty] | 6
|  | Pre-job brief completed | 6 | 6 | 2007-05-26 | 2007-06-01 | [10 empty] | 1
|  | Station 2 operational |  |  |  | 2007-06-01
Station 3-Modular Coil to VVSA Assembly
|  | Procedures approved | 27 | 10 | 2007-05-10 | 2007-05-20
|  | JHA completed | 6 | 6 | 2007-05-20 | 2007-05-26
Sequence plan
Metrology plan
|  | Training needs identified & released | 6 | 6 | 2007-05-08 | 2007-05-14
|  | ACC review completed | 6 | 6 | 2007-05-14 | 2007-05-20
|  | Pre-job brief completed | 6 | 6 | 2007-05-20 | 2007-05-26
|  | Station 3 operational |  |  | 2007-05-26 | 2007-07-11
|  | Fixtures installed | 6 | 6 | 2007-07-11 | 2007-07-17 | [10 empty] | 80
Station 5-Final Field Period Assembly
|  | Procedures approved | 27 | 14 | 2007-10-01 | 2007-10-15
|  | JHA completed | 6 | 6 | 2007-10-15 | 2007-10-21
Sequence plan
Metrology plan
|  | Training needs identified & released | 6 | 6 | 2007-08-21 | 2007-08-27
|  | ACC review completed | 7 | 7 | 2007-08-27 | 2007-09-03
|  | Pre-job brief completed | 7 | 7 | 2007-09-03 | 2007-09-10
|  | Station 5 operational |  |  | 2007-09-10 | 2007-09-04
|  | Fixtures installed | 6 | 6 | 2007-09-04 | 2007-09-10 | [10 empty] | 80
Job: 1802 - FP Assy Oversight&Support-VIOLA Total |  |  | 0 | 0 | [12 empty] | 320
Job: 1810 - Field Period Assembly-VIOLA |  |  |  | 124 | [7 empty] | 0 |  | 0 |  |  | 501 |  | 0 |  |  |  | 0
General F.P. Assy support
|  | LOE Crane support, fixture setupfor TFTR TC. | 362 | 362 | 2006-10-01 | 2007-09-28 | [10 empty] | 696.6605 | 620.5714
|  | LOE Crane support, fixture setupfor TFTR TC. | 363 | 363 | 2007-09-28 | 2008-09-25 | [10 empty] | 838.34 | 622.2857
|  | LOE Field Supervision for TFTR TC FY07 |  | 362 | 2006-10-01 | 2007-09-28 | [11 empty] | 2068.5714
|  | LOE Field Supervision for TFTR TC FY08 |  | 363 | 2007-10-01 | 2008-09-28 | [11 empty] | 2074.2857
|  | LOE Metrology support FY07 | 362 | 362 | 2007-09-28 | 2008-09-24 | [7 empty] | 3516.5714 |  |  | 1435.968 | 2068.5714
|  | LOE Metrology support FY08 | 362 | 362 | 2008-09-25 | 2009-09-22 | [7 empty] | 2068.5714 |  |  | 1435.968 | 2068.5714
Station 1-FP #1 VV Prep (hard surface components) | [17 empty] | 0
Station 1-FP #1 VV Prep (hard surface components) |  | Layout diagnostic&coolant paths on vessel | 75 | 35 | 2007-01-10 | 2007-02-14 | [10 empty] | 245 | 480 |  |  |  |  | 67 | NONE
Station 1-FP #1 VV Prep (hard surface components) |  | Install heater tape on vertical ports | 75 | 7 | 2007-02-14 | 2007-02-21 | [10 empty] | 17.1 | 96 |  |  |  |  | 47.736
Station 1-FP #1 VV Prep (hard surface components) |  | Verify installation of heater tapes | 2 | 1 | 2007-02-21 | 2007-02-22 | [11 empty] | 16 |  |  |  |  | 18
Station 1-FP #1 VV Prep (hard surface components) |  | Attach studs for coolant lines | 75 | 3 | 2007-02-22 | 2007-02-25 | [10 empty] | 42 | 48 |  |  |  |  | 42
Station 1-FP #1 VV Prep (hard surface components) |  | Wind magnetic diagnostic sensors | 43 | 14 | 2007-02-25 | 2007-03-11 | [10 empty] | 256 | 192 |  |  |  |  | 256
Station 1-FP #1 VV Prep (hard surface components) |  | Install precision magnetic diagnostic sensors | 41 | 3 | 2007-03-11 | 2007-03-14 | [10 empty] | 240 | 48 |  |  |  |  | 240
Station 1-FP #1 VV Prep (hard surface components) |  | Verify installation magnetic diagnostic sensors |  | 4 | 2007-03-14 | 2007-03-18 | [10 empty] | 28 | 64 |  |  |  |  | 28
Station 1-FP #1 VV Prep (hard surface components) |  | Install local I&C (incl thermocouples) | 8 | 5 | 2007-03-18 | 2007-03-23 | [10 empty] | 65 | 80 |  |  |  |  | 65
Station 1-FP #1 VV Prep (hard surface components) |  | Verify installation of local I&C | 2 | 2 | 2007-03-23 | 2007-03-25 | [10 empty] | 28 | 32 |  |  |  |  | 28
Station 1-FP #1 VV Prep (hard surface components) |  | Install cooling/htg lines to vac vsl | 34 | 15 | 2007-03-25 | 2007-04-09 | [10 empty] | 192 | 208 |  |  |  |  | 192
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Install local I&C (incl thermocouples) | 8 | 5 | 2007-04-02 | 2007-04-07 | [10 empty] | 80 | 80 |  |  |  |  | 27
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Verify installation of local I&C | 2 | 2 | 2007-04-07 | 2007-04-09 | [10 empty] | 23 | 32 |  |  |  |  | 23
Station 1-FP #1 VV Prep (hard surface components) |  | Weld cooling/htg risers | 34 | 10 | 2007-04-09 | 2007-04-19 | [10 empty] | 192 | 144 |  |  |  |  | 192
Station 1-FP #1 VV Prep (hard surface components) |  | Verify Instl of H/C lines,headers,manifolds | 6 | 5 | 2007-04-09 | 2007-04-14 | [10 empty] | 46 | 80 |  |  |  |  | 46
Station 1-FP #1 VV Prep (hard surface components) |  | Loop termination & verification | 6 | 18 | 2007-04-14 | 2007-05-02 | [10 empty] | 35 | 256
Station 1-FP #1 VV Prep (hard surface components) |  | Final Scan | 7 | 4 | 2007-05-02 | 2007-05-06 | [10 empty] | 33.15 | 64 |  |  |  |  | 33.15
Station 1-FP #1 VV Prep (hard surface components) |  | Prepare and transfer completed VV to holding are | 4 | 2 | 2007-05-06 | 2007-05-08 | [10 empty] | 42 | 32 |  |  |  |  | 42
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Layout diagnostic&coolant paths on vessel | 35 | 12 | 2007-02-10 | 2007-02-22 | [10 empty] | 245 | 176 |  |  |  |  | 67 | NONE
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Install heater tape on vertical ports | 5 | 7 | 2007-02-22 | 2007-03-01 | [10 empty] | 53 | 96 |  |  |  |  | 8
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Verify installation of heater tapes | 0 | 1 | 2007-03-01 | 2007-03-02 | [10 empty] | 11 | 16 |  |  |  |  | 4
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Attach studs forcoolant lines | 15 | 3 | 2007-03-02 | 2007-03-05 | [10 empty] | 183 | 48
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Wind magnetic diagnostic sensors | 27 | 14 | 2007-03-05 | 2007-03-19 | [10 empty] | 280 | 192
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Install precision magnetic diagnostic sensors | 31 | 3 | 2007-03-19 | 2007-03-22 | [10 empty] | 163 | 48 |  |  |  |  | 163
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Verify installation magnetic diagnostic sensors |  | 4 | 2007-03-29 | 2007-04-02 | [10 empty] | 28 | 64 |  |  |  |  | 28
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Install cooling/htg lines to vac vsl | 34 | 15 | 2007-04-09 | 2007-04-24 | [10 empty] | 384 | 208
Station 1-FP #1 VV Prep (hard surface components) |  | Weld cooling/htg risers | 34 | 10 | 2007-04-24 | 2007-05-04 | [10 empty] | 192 | 144 |  |  |  |  | 192
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Verify Instl of H/C lines,headers,manifolds | 7 | 5 | 2007-04-24 | 2007-04-29 | [10 empty] | 38 | 80 |  |  |  |  | 38
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Loop termination & verification | 12 | 18 | 2007-04-29 | 2007-05-17 | [10 empty] | 10 | 256
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Final Scan | 4 | 4 | 2007-05-17 | 2007-05-21 | [10 empty] | 33.15 | 64 |  |  |  |  | 33.15
Station 1- FP #2 VV Prep (hrd surf cmpnts) |  | Prepare and transfer completed VV to holding are | 2 | 2 | 2007-05-21 | 2007-05-23 | [10 empty] | 63 | 32 |  |  |  |  | 6
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Layout diagnostic&coolant paths on vessel | 26 | 12 | 2007-07-11 | 2007-07-23 | [10 empty] | 221 | 176 |  |  |  |  | 74
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Install heater tape on vertical ports | 3 | 7 | 2007-07-23 | 2007-07-30 | [10 empty] | 29 | 96 |  |  |  |  | 29
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Verify installation of heater tapes | 0 | 1 | 2007-07-30 | 2007-07-31 | [10 empty] | 11 | 16 |  |  |  |  | 4
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Attach studs forcoolant lines | 15 | 3 | 2007-07-31 | 2007-08-03 | [10 empty] | 86 | 48 |  |  |  |  | 86
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Wind magnetic diagnostic sensors | 28 | 14 | 2007-08-03 | 2007-08-17 | [10 empty] | 420 | 192
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Install precision magnetic diagnostic sensors | 26 | 3 | 2007-08-17 | 2007-08-20 | [10 empty] | 266 | 48
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Verify installation magnetic diagnostic sensors |  | 4 | 2007-08-20 | 2007-08-24 | [10 empty] | 28 | 64 |  |  |  |  | 28
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Install local I&C (incl thermocouples) | 8 | 5 | 2007-08-24 | 2007-08-29 | [10 empty] | 50 | 80 |  |  |  |  | 50
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Verify installation of local I&C | 2 | 2 | 2007-08-29 | 2007-08-31 | [10 empty] | 22 | 32 |  |  |  |  | 22
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Install cooling/htg lines to vac vsl | 29 | 15 | 2007-08-31 | 2007-09-15 | [10 empty] | 352 | 208
Station 1-FP #1 VV Prep (hard surface components) |  | Weld cooling/htg risers | 34 | 10 | 2007-09-15 | 2007-09-25 | [10 empty] | 192 | 144 |  |  |  |  | 192
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Verify Instl of H/C lines,headers,manifolds | 4 | 5 | 2007-09-15 | 2007-09-20 | [10 empty] | 36 | 80 |  |  |  |  | 36
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Loop termination & verification | 2 | 18 | 2007-09-20 | 2007-10-08 | [10 empty] | 10 | 256
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Final Scan | 2 | 4 | 2007-10-08 | 2007-10-12 | [10 empty] | 33.15 | 64 |  |  |  |  | 33.15
Station 1- FP #3 VV Prep (hrd surf cmpnts) |  | Prepare and transfer completed VV to holding are | 2 | 2 | 2007-10-12 | 2007-10-14 | [10 empty] | 43 | 32 |  |  |  |  | 22
| Station 1-Spool pieces (3) (spacers) | [16 empty] | 0
|  | Attachdiagnostics, studs and coolant lines | 48 | 48 | 2008-01-10 | 2008-02-27 | [10 empty] | 288 | 672 |  |  |  |  | 96
| Station 2 Trials & Setup | [16 empty] | 0
|  | Trial tensioning test on prototype | 46 | 2 | 2007-03-01 | 2007-03-03 | [11 empty] | 32
|  | Trial bushing and shim test on prototype | 67 | 12 | 2007-02-01 | 2007-02-13 | [11 empty] | 176
|  | Guidance f/post-VPI proced to include measuremen | 36 | 36 | 2007-03-01 | 2007-04-06 | [11 empty] | 496
|  | Perform trial x-y-z alignments on A1-A2. | 90 | 7 | 2007-04-03 | 2007-04-10 | [11 empty] | 96
|  | Alignment mechanisms, metro equipt &positioning | 6 | 6 | 2007-04-10 | 2007-04-16 | [11 empty] | 96
|  | Procure alignment mechanisms, fiducials, lifting | 56 | 56 | 2007-04-17 | 2007-06-12 | [11 empty] | 768
|  | Develop procedures for torquing bolts | 4 | 4 | 2007-04-02 | 2007-04-06 | [11 empty] | 64
|  | Determine fiducial types&locations | 11 | 11 | 2007-04-09 | 2007-04-20 | [11 empty] | 160
|  | Procure monuments&related metrology equipment | 42 | 15 | 2007-04-23 | 2007-05-08 | [11 empty] | 208
|  | Tools&tooling available for FPA operations |  |  |  | 2007-06-12 | [11 empty] | 0
|  | Install FIRST Holding fixture | 4 | 4 | 2007-01-22 | 2007-01-26 | [10 empty] | 20 | 64
|  | Install SECOND Holding fixture | 3 | 3 | 2007-04-07 | 2007-04-10 | [10 empty] | 10 | 48
|  | Install THIRD Holding fixture |  |  | 2007-04-18 | 2007-04-18 | [10 empty] | 6 | 0
|  | Install LAST Holding fixture |  |  | 2007-06-06 | 2007-06-06 | [10 empty] | 6 | 0
| Station 2-Modular Coil Subassembly-FP#1 | [16 empty] | 0
|  | Pre-fit C2-C3 (no re-work) | 4 | 4 | 2006-12-01 | 2006-12-05 | [10 empty] | 32 | 64
|  | Pre-fit C1-C5 | 2 | 2 | 2006-12-06 | 2006-12-08 | [10 empty] | 32 | 32
|  | Pre-fit A1-A2 | 2 | 2 | 2007-02-12 | 2007-02-14 | [10 empty] | 32 | 32
|  | Pre-fit C6-C4 | 1 | 1 | 2007-05-01 | 2007-05-02 | [10 empty] | 16 | 16
|  | Test out equipt & procedures | 7 | 7 | 2007-03-13 | 2007-03-20 | [10 empty] | 88 | 96
|  | Fit C1-B1 | 1 | 1 | 2007-03-21 | 2007-03-22 | [10 empty] | 16 | 16
|  | Fit B1-A1 | 3 | 3 | 2007-03-23 | 2007-03-26 | [10 empty] | 16 | 48
|  | Fit A2-B2 | 1 | 1 | 2007-04-04 | 2007-04-05 | [10 empty] | 16 | 16
|  | Fit B2-C2 | 3 | 3 | 2007-04-06 | 2007-04-09 | [10 empty] | 16 | 48
|  | Assemble/Align Mod-Coils A1/B1/C1 | 49 | 49 | 2007-04-23 | 2007-06-11 | [10 empty] | 720 | 672
|  | Assemble/Align Mod-Coils A2/B2/C2 | 42 | 42 | 2007-06-12 | 2007-07-24 | [10 empty] | 480 | 576
| Station 2-Modular Coil Subassembly-FP#2 | [16 empty] | 0
|  | Assemble/Align Mod-Coils A3/B3/C3 | 36 | 36 | 2007-07-25 | 2007-08-30 | [10 empty] | 360 | 496
|  | Assemble/Align Mod-Coils A4/B4/C4 | 35 | 35 | 2007-08-31 | 2007-10-05 | [10 empty] | 360 | 480
| Station 2-Modular Coil Subassembly-FP#3 | [16 empty] | 0
|  | Assemble/Align Mod-Coils A5/B5/C5 | 36 | 36 | 2007-10-31 | 2007-12-06 | [10 empty] | 360 | 496
|  | Assemble/Align Mod-Coils A6/B6/C6 | 43 | 43 | 2007-12-18 | 2008-01-30 | [10 empty] | 360 | 592
| Station 3-Assemble Mod Coils and VVSA-FP#1 | [16 empty] | 0
|  | Assemble/Disassemble abc1-abc2 (stage 3 fixture) | 27 | 27 | 2007-07-25 | 2007-08-21 | [10 empty] | 360 | 384
|  | Begin Assembly of First Field Period Assy |  |  |  | #VALUE! | [11 empty] | 0
|  | Test out station 3 equipment and procedures | 27 | 27 | 2007-07-12 | 2007-08-08 | [10 empty] | 384 | 384
|  | VV to MC turning fixt base; metr check | 5 | 5 | 2007-08-09 | 2007-08-14 | [10 empty] | 48 | 80
|  | Attach local protective strips to VV&locate sens | 2 | 2 | 2007-08-15 | 2007-08-17 | [10 empty] | 32 | 32
|  | Mount MC on crane; perform metr checks | 2 | 2 | 2007-08-22 | 2007-08-24 | [10 empty] | 48 | 32
|  | Rotate right MC to stand-off position&chk | 3 | 3 | 2007-08-27 | 2007-08-30 | [10 empty] | 72 | 48
|  | Transfer load to sprt sys and recheck position | 5 | 5 | 2007-08-31 | 2007-09-05 | [10 empty] | 48 | 80
|  | Move MC turning fixt; mount MC on crane | 0 | 0 | 2007-09-06 | 2007-09-06 | [10 empty] | 24 | 0
|  | Rotate left MC to stand-off position and check p | 3 | 3 | 2007-09-07 | 2007-09-10 | [10 empty] | 48 | 48
|  | Move left & right MC to final position & measure | 1 | 1 | 2007-09-11 | 2007-09-12 | [10 empty] | 48 | 16
|  | Pot 3 packs together | 20 | 20 | 2007-09-27 | 2007-10-17 | [10 empty] | 240 | 288
|  | Bolt together at flange interface. | 13 | 13 | 2007-09-13 | 2007-09-26 | [10 empty] | 120 | 192
|  | Perform final metrology position check | 6 | 6 | 2007-10-18 | 2007-10-24 | [10 empty] | 72 | 96
|  | Remove temp interference strips&sensors | 6 | 6 | 2007-10-25 | 2007-10-31 | [10 empty] | 48 | 96
|  | Secure VV to MC's using temporary supports. | 6 | 6 | 2007-11-01 | 2007-11-07 | [10 empty] | 72 | 96
|  | Prepare Field Period for shipment | 1 | 1 | 2007-11-08 | 2007-11-09 | [10 empty] | 48 | 16
|  | Transfer completed assy to C-site test cell | 1 | 1 | 2007-11-12 | 2007-11-13 | [10 empty] | 80 | 16
| Station 3-Assemble Mod Coils and VVSA-FP#2 | [16 empty] | 0
|  | Assemble/Disassemble abc -abc4 (stage 3 fixture) | 23 | 23 | 2007-10-08 | 2007-10-31 | [10 empty] | 360 | 320
|  | Mount VV to MC turning fixt base; metr check | 5 | 5 | 2007-11-14 | 2007-11-19 | [10 empty] | 48 | 80
|  | Attach local protective strips to VV&locate sens | 2 | 2 | 2007-11-20 | 2007-11-22 | [10 empty] | 32 | 32
|  | Mount MC on crane; perform metr checks | 4 | 4 | 2007-11-23 | 2007-11-27 | [10 empty] | 48 | 64
|  | Rotate right MC to stand-off position&chk | 6 | 6 | 2007-11-28 | 2007-12-04 | [10 empty] | 72 | 96
|  | Transfer load to supt sys and recheck position | 1 | 1 | 2007-12-05 | 2007-12-06 | [10 empty] | 48 | 16
|  | Move MC turning fixt; mount MC on crane | 0 | 0 | 2007-12-07 | 2007-12-07 | [10 empty] | 24 | 0
|  | Rotate left MC to stand-off position and check p | 1 | 1 | 2007-12-10 | 2007-12-11 | [10 empty] | 48 | 16
|  | Move left & right MC to final position & measure | 1 | 1 | 2007-12-12 | 2007-12-13 | [10 empty] | 48 | 16
|  | Pot 3 packs together | 24 | 24 | 2007-12-21 | 2008-01-14 | [10 empty] | 240 | 336
|  | Bolt together at flange interface. | 6 | 6 | 2007-12-14 | 2007-12-20 | [10 empty] | 120 | 96
|  | Perform final metrology position check | 2 | 2 | 2008-01-15 | 2008-01-17 | [10 empty] | 72 | 32
|  | Remove temp interference strips&sensors | 3 | 3 | 2008-01-18 | 2008-01-21 | [10 empty] | 48 | 48
|  | Secure VV to MC's using temporary supports. | 2 | 2 | 2008-01-22 | 2008-01-24 | [10 empty] | 72 | 32
|  | Prepare Field Period for shipment | 3 | 3 | 2008-01-25 | 2008-01-28 | [10 empty] | 48 | 48
|  | Transfer completed assy to C-site test cell | 1 | 1 | 2008-01-29 | 2008-01-30 | [10 empty] | 80 | 16
| Station 3-Assemble Mod Coils and VVSA-FP#3 | [16 empty] | 0
|  | Assemble/Disassemble abc -abc6 (Stage 3 fixture) | 21 | 21 | 2008-01-31 | 2008-02-21 | [10 empty] | 360 | 288
|  | Mount VV to MC turning fixt base; metr check | 5 | 5 | 2008-01-31 | 2008-02-05 | [10 empty] | 48 | 80
|  | Attach local protective strips to VV&locate sens | 2 | 2 | 2008-02-06 | 2008-02-08 | [10 empty] | 32 | 32
|  | Mount MC on crane; perform metr checks | 3 | 3 | 2008-02-22 | 2008-02-25 | [10 empty] | 48 | 48
|  | Rotate right MC to stand-off position&chk | 2 | 2 | 2008-02-26 | 2008-02-28 | [10 empty] | 72 | 32
|  | Transfer load to supt sysand recheck position | 3 | 3 | 2008-02-29 | 2008-03-03 | [10 empty] | 48 | 48
|  | Move MC turning fixt; mount MC on crane | 0 | 0 | 2008-03-04 | 2008-03-04 | [10 empty] | 24 | 0
|  | Rotate left MC to stand-off position and check p | 1 | 1 | 2008-03-05 | 2008-03-06 | [10 empty] | 48 | 16
|  | Move left & right MC to final position & measure | 3 | 3 | 2008-03-07 | 2008-03-10 | [10 empty] | 48 | 48
|  | Pot 3 packs together | 13 | 13 | 2008-03-18 | 2008-03-31 | [10 empty] | 240 | 192
|  | Bolt together at flange interface. | 6 | 6 | 2008-03-11 | 2008-03-17 | [10 empty] | 120 | 96
|  | Perform final metrology position check | 2 | 2 | 2008-04-01 | 2008-04-03 | [10 empty] | 72 | 32
|  | Remove temp interference strips&sensors | 3 | 3 | 2008-04-04 | 2008-04-07 | [10 empty] | 48 | 48
|  | Secure VV to MC's using temporary supports. | 2 | 2 | 2008-04-08 | 2008-04-10 | [10 empty] | 72 | 32
|  | Prepare Field Period for shipment | 3 | 3 | 2008-04-11 | 2008-04-14 | [10 empty] | 48 | 48
|  | Transfer completed assy to C-site test cell | 0 | 0 | 2008-04-15 | 2008-04-15 | [10 empty] | 80 | 0
| Station 4 - TF HP Pre-Assy | [16 empty] | 0
|  | Test out station 4 equipment and procedures | 42 | 42 | 2007-08-20 | 2007-10-01 | [10 empty] | 480 | 576
|  | Assemble 3 TF coils&structure -Left-Period #1 | 22 | 22 | 2007-11-14 | 2007-12-06 | [10 empty] | 360 | 304
|  | Assemble 3 TF coils&structure -Right -Period #1 | 13 | 13 | 2007-12-07 | 2007-12-20 | [10 empty] | 240 | 192
|  | Assemble/disassemble TF 6 pac (FP#1) | 24 | 24 | 2007-12-21 | 2008-01-14 | [10 empty] | 240 | 336
|  | Assemble 3 TF coils&structure -Left-Period #2 | 13 | 13 | 2008-01-15 | 2008-01-28 | [10 empty] | 240 | 192
|  | Assemble 3 TF coils&structure -Right -Period #2 | 13 | 13 | 2008-01-29 | 2008-02-11 | [10 empty] | 240 | 192
|  | Assemble/disassemble TF 6 pac (FP#2) | 6 | 6 | 2008-02-12 | 2008-02-18 | [10 empty] | 120 | 96
|  | Assemble 3 TF coils&structure -Left -Period #3 | 13 | 13 | 2008-02-19 | 2008-03-03 | [10 empty] | 240 | 192
|  | Assemble 3 TF coils&structure -Right -Period #3 | 11 | 11 | 2008-05-12 | 2008-05-23 | [10 empty] | 240 | 160
|  | Assemble/disassemble TF 6 pac (FP#3) | 6 | 6 | 2008-05-27 | 2008-06-02 | [10 empty] | 120 | 96
| Station 5- Final FP Assy -FP#1 (in NCSX TC) | [16 empty] | 0
|  | Install on support platform | 1 | 1 | 2008-03-27 | 2008-03-28 | [10 empty] | 48 | 16
|  | Testout Sta5 equipt & procedures | 20 | 20 | 2007-09-05 | 2007-09-25 | [10 empty] | 360 | 288
|  | Mount MC/VV assembly to support frame a | 1 | 1 | 2007-09-26 | 2007-09-27 | [10 empty] | 48 | 16
|  | Position and weld all ports to VV | 43 | 43 | 2007-11-05 | 2007-12-18 | [10 empty] | 960 | 592
|  | Inspect Welds | 15 | 15 | 2007-12-19 | 2008-01-03 | [10 empty] | 80 | 208
|  | Assemble left TF Coil Assembly check position | 2 | 2 | 2008-01-15 | 2008-01-17 | [10 empty] | 96 | 32
|  | Change platforms | 3 | 3 | 2008-01-18 | 2008-01-21 | [10 empty] | 48 | 48
|  | Assemble right TF Coil Assembly chk position | 2 | 2 | 2008-01-22 | 2008-01-24 | [10 empty] | 96 | 32
|  | Attach TF coils to MC's | 4 | 4 | 2008-01-25 | 2008-01-29 | [10 empty] | 72 | 64
|  | Change platforms | 1 | 1 | 2008-01-30 | 2008-01-31 | [10 empty] | 64 | 16
|  | Position, weld two large horizontal diag ports | 11 | 11 | 2008-02-01 | 2008-02-12 | [10 empty] | 192 | 160
|  | Inspect Welds | 0 | 0 | 2008-02-13 | 2008-02-13 | [10 empty] | 16 | 0
|  | Assemble external trim coils (in wbs75) | -1 | -1 | 2008-01-25 | 2008-01-24 | [11 empty] | 0
|  | Close up VV, leak check | 13 | 13 | 2008-02-14 | 2008-02-27 | [10 empty] | 640 | 192
|  | Adjust final support base interfaces | 13 | 13 | 2008-02-28 | 2008-03-12 | [10 empty] | 48 | 192
|  | Final metrology outside & inside | 13 | 13 | 2008-03-13 | 2008-03-26 | [11 empty] | 192
| Station 5- Final FP Assy -FP#2 (in NCSX TC) | [16 empty] | 0
|  | Install on support platform | 1 | 1 | 2008-06-05 | 2008-06-06 | [10 empty] | 48 | 16
|  | Mount MC/VV assembly to support frame a | 1 | 1 | 2008-01-31 | 2008-02-01 | [10 empty] | 48 | 16
|  | Position and weld all ports to VV | 39 | 39 | 2008-02-04 | 2008-03-14 | [10 empty] | 960 | 544
|  | Inspect Welds | 4 | 4 | 2008-03-17 | 2008-03-21 | [10 empty] | 80 | 64
|  | Assemble left TF Coil Assembly check position | 2 | 2 | 2008-03-24 | 2008-03-26 | [10 empty] | 96 | 32
|  | Change platforms | 1 | 1 | 2008-03-27 | 2008-03-28 | [10 empty] | 48 | 16
|  | Assemble right TF Coil Assembly chk position | 2 | 2 | 2008-03-31 | 2008-04-02 | [10 empty] | 96 | 32
|  | Attach TF coils to MC's | 4 | 4 | 2008-04-03 | 2008-04-07 | [10 empty] | 72 | 64
|  | Change platforms | 1 | 1 | 2008-04-08 | 2008-04-09 | [10 empty] | 64 | 16
|  | Position, weld two large horizontal diag ports | 11 | 11 | 2008-04-10 | 2008-04-21 | [10 empty] | 192 | 160
|  | Inspect Welds | 0 | 0 | 2008-04-22 | 2008-04-22 | [10 empty] | 16 | 0
|  | Assemble external trim coils (in wbs75) | -1 | -1 | 2008-04-03 | 2008-04-02 | [11 empty] | 0
|  | Close up VV, leak check | 13 | 13 | 2008-04-23 | 2008-05-06 | [10 empty] | 640 | 192
|  | Adjust final support base interfaces | 13 | 13 | 2008-05-07 | 2008-05-20 | [10 empty] | 48 | 192
|  | Final metrology outside & inside | 14 | 14 | 2008-05-21 | 2008-06-04 | [11 empty] | 192
| Station 5- Final FP Assy -FP#3 (in NCSX TC) | [16 empty] | 0
|  | Install on support platform | 1 | 1 | 2008-07-14 | 2008-07-15 | [10 empty] | 48 | 16
|  | Mount MC/VV assembly to support frame a | 1 | 1 | 2008-04-16 | 2008-04-17 | [10 empty] | 48 | 16
|  | Position and weld all ports to VV*2 shift* | 42 | 42 | 2008-04-18 | 2008-05-30 | [10 empty] | 960 | 576
|  | Inspect Welds | 2 | 2 | 2008-06-02 | 2008-06-04 | [10 empty] | 80 | 32
|  | Assemble left TF Coil Assembly check position | 0 | 0 | 2008-06-05 | 2008-06-05 | [10 empty] | 96 | 0
|  | Change platforms | 0 | 0 | 2008-06-06 | 2008-06-06 | [10 empty] | 48 | 0
|  | Assemble right TF Coil Assembly chk position | 1 | 1 | 2008-06-09 | 2008-06-10 | [10 empty] | 96 | 16
|  | Attach TF coils to MC's | 0 | 0 | 2008-06-11 | 2008-06-11 | [10 empty] | 72 | 0
|  | Change platforms | 0 | 0 | 2008-06-12 | 2008-06-12 | [10 empty] | 64 | 0
|  | Position, weld two large horizontal diag ports | 5 | 5 | 2008-06-13 | 2008-06-18 | [10 empty] | 192 | 80
|  | Inspect Welds | 0 | 0 | 2008-06-19 | 2008-06-19 | [10 empty] | 16 | 0
|  | Assemble external trim coils (in wbs75) | -1 | -1 | 2008-06-11 | 2008-06-10 | [11 empty] | 0
|  | Close up VV, leak check | 6 | 6 | 2008-06-20 | 2008-06-26 | [10 empty] | 640 | 96
|  | Adjust final support base interfaces | 6 | 6 | 2008-06-27 | 2008-07-03 | [10 empty] | 48 | 96
|  | Final metrology outside & inside | 4 | 4 | 2008-07-07 | 2008-07-11 | [11 empty] | 64
|  | Last field period assembled |  |  |  | 2008-07-11 | [11 empty] | 0
Job:1810 - Field Period Assembly-VIOLA Total | [13 empty] | 5585.1429 |  |  | 27399.4865 | 32098.8571 |  | 0 |  |  | 2558.186 | 0
Formulas:
Start Date = [Finish Date, row above]
Finish Date = [Start Date]+[Work days]
Finish Date = [Finish Date, row above]