## Sheet1
WBS Number: 185
WBS Title: Assembly of Field Perids
Job Numbes: 1802, 1810, and 1815
Job Title: FPA Oversight & support (1802)
Job Title: FPA Operations - Stations 1, 2, & 3 (1810)
Job Title: FPA Operations - Station 5 (1815)
Job Manager: Mike Viola
Fabrication and Assembly
Assumptions:
Assumes 5 day workweek 1 shift no overtime
Parallel ops for sta 5 (2 fixtures available)
Parallel ops for sta 5 (2 fixtures available)
Only 1 fixture for station 3 only one shift
Parallel ops for sta 2
| Reflects rls plan rev 6 |  | K$ |  |  |  | Hours
| TASK DESCRIPTION | Work days | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM/DSN | SHTB | EMEM | EMSM | EMSB | EMTB | CREW | Basis of Estimate
Estimate based on recent NCSX FPA activities and the amount of oversight and supervision that is required, adjusted by recognition of complexity of work remaining.
Job 1802
Oversight & Supervision
| Metrology Engineering Supervision FY07 raftopolous 50% | 181 | [7 empty] | 431.5 |  |  |  |  | this is LOE adjust consistent with overall schedule
| Metrology Engineering Supervision FY08 raftopolous 50% | 362 | [7 empty] | 863 |  |  |  |  | this is LOE adjust consistent with overall schedule
| Metrology Engineering Supervision FY09 raftopolous 50% (6 months???tbd | 181 | [7 empty] | 431.5 |  |  |  |  | assume sta5 finishes March 2009
| PPPL EM LOE FY07 Viola 100% | 181 | [7 empty] | 863 |  |  |  |  | this is LOE adjust consistent with overall schedule
| PPPL EM LOE FY08 Viola 100% | 362 | [7 empty] | 1726 |  |  |  |  | this is LOE adjust consistent with overall schedule
| PPPL EM LOE FY09 Viola 100% (6 months???tbd) | 181 | [7 empty] | 863 |  |  |  |  | assume sta5 finishes March 2009
| Title III field period assembly FY07 ORNL suppor cole,goranson,williamson 65% total | 181 | [5 empty] | 561.5 | [6 empty] | this is LOE adjust consistent with overall schedule awaiting estimate from Mike Cole
| Title III field period assembly FY08 ORNL suppor cole, goranson,williamson 33%total | 181 | [5 empty] | 562 | [6 empty] | this is LOE adjust consistent with overall schedule awaiting estimate from Mike Cole
| Title III field period assembly FY07 & FY08 Support @ 40hr/month + travel (assume 10 months) - PJ Fogarty |  |  |  |  | 25 |  | 400
| HP Coverage in the TFTR TC LOE FY07@.75 fte | 181 | [6 empty] | 647.25 | [5 empty] | this is LOE thru stat3 only
| HP Coverage in the TFTR TC LOE FY08 @.75 fte | 362 | [6 empty] | 1294.5 | [5 empty] | this is LOE thru stat3 only
| HP Coverage in the TFTR TC LOE FY09 @.75 fte (6 months???tbd) | 181 | [6 empty] | 647.25 | [5 empty] | assume sta5 finishes March 2009
Station 2-Modular Coil Sub- Assembly
Sequence Plan (Brown) - Covered in Job 1803
Metrology Plan (Elllis) - Covered in Job 8202
| Procedures written & approved | 14
| JHA completed | 6
| Training needs identified & released | 6
| ACC review completed | 2
| Pre-job brief completed | 1
Station 2 operational
Station 3-Modular Coil to VVSA Assembly
Sequence Plan (Brown) - Covered in Job 1803
Metrology Plan (Elllis) - Covered in Job 8202
| Procedures approved | 10
| JHA completed | 6
| Training needs identified & released | 6
| ACC review completed | 6
| Pre-job brief completed | 6
| Station 3 operational | 1
| Fixtures installed | 6
Station 5-Final Field Period Assembly
Sequence Plan (Brown) - Covered in Job 1803
Metrology Plan (Elllis) - Covered in Job 8202
| Procedures approved | 14
| JHA completed | 6
| Training needs identified & released | 6
| ACC review completed | 7
| Pre-job brief completed | 7
| Station 5 operational | 1
Job: 1802 - FP Assy Oversight&Support-VIOLA Total |  |  | 0 | 0 | 0 | 25 | 0 | 1523.5 | 2589 | 5178 | 0 | 0 | 0
| TASK DESCRIPTION | Work days | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM/DSN | SHTB | EMEM | EMSM | EMSB | EMTB | CREW | Basis of Estimate
Job: 1810 - Field Period Assembly-VIOLA
Station 1: Based on actual VV #1 costs - almost completed.
Station 2: Based on actual VV #1 costs - almost completed.
Based on experience to accomplish similar tasks (e.g., metrology scans/lock-ins, coil trial fitups, gross checks)
Nose/Bushing related items based on conceptual designs and rough estimates
Assumed nose concept based on application of epoxy & set-up times
Station 3: Setup and Metrology estimates based on conceptual designs tempered with experieince in alignment of multiple components (half field periods and screens proof-of principle tests)
General F.P. Assy support
| LOE Crane support, fixture setupfor TFTR TC. FY07 1.2 fte | 181 | [10 empty] | 1035.6 |  | 2 men 3 day a week .LOE adjust consistent with schedule
| LOE Crane support, fixture setupfor TFTR TC. FY08 1.2 fte | 362 | [10 empty] | 2071.2 |  | 2 men 3 day a week .LOE adjust consistent with schedule
| LOE Crane support, fixture setupfor TFTR TC. FY09 1.2 fte (6 months???tbd) | [13 empty] | assume sta5 finishes March 2009
| LOE Field Supervision for TFTR TC FY07 edwards | 181 | [8 empty] | 863 |  |  |  | this is LOE adjust consistent with overall schedule
| LOE Field Supervision for TFTR TC FY08 edwards | 362 | [8 empty] | 1726 |  |  |  | this is LOE adjust consistent with overall schedule
| LOE Field Supervision for TFTR TC FY09 edwards(6 months???tbd) | 181 | [8 empty] | 863 |  |  |  | assume sta5 finishes March 2009
| LOE Metrology support FY07 1.5 fte engr plus ducco 100% | 181 | [5 empty] | 1294.5 |  |  |  |  | 863 |  | this is LOE adjust consistent with overall schedule
| LOE Metrology support FY08 1.5 fte engr plus ducco 100% | 362 | [5 empty] | 2589 |  |  |  |  | 1726 |  | this is LOE adjust consistent with overall schedule
| LOE Metrology support FY09 1.5 fte engr plus ducco 100% (6 months???tbd) | 181 | [5 empty] | 1294.5 |  |  |  |  | 863 |  | assume sta5 finishes March 2009
| Misc M&S FY07 | 181 | 18 | [11 empty] | 3K/month
| Misc M&S FY08 | 362 | 36 | [11 empty] | 3K/month
| Misc M&S FY09 (6 months???tbd) | 181 | 18 | [11 empty] | assume sta5 finishes March 2009
Station 1-FP #1 VV Prep (hard surface components)
| Layout diagnostic&coolant paths on vessel - Completed | 35
| Install heater tape on vertical ports - Completed | 7
| Verify installation of heater tapes - Completed | 1
| Attach studs for coolant lines - Completed | 3
| Wind magnetic diagnostic sensors - Completed | 14
| Install precision magnetic diagnostic sensors - Completed | 3
| Verify installation magnetic diagnostic sensors - Completed | 4
| Install local I&C (incl thermocouples) - Completed | 5
| Verify installation of local I&C | 2
| Install cooling/htg lines to vac vsl | 15 | [10 empty] | 300 | 2.5
| Weld cooling/htg risers | 10 | 2 | [9 empty] | 200 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Verify Instl of H/C lines,headers,manifolds | 5 | [10 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Perform final acceptance testing (H/C flow test) | 5 | 4 | [9 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Trim seal plates | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Loop termination & verification | 18 | [10 empty] | 360 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| install Final Internal and External monuments and measure | 4 | [10 empty] | 80 | 2.5
| Final Scan | 4 | [10 empty] | 80 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Install heater tape on removeable ports | 6 | [10 empty] | 120 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Prepare and transfer completed VV to holding are | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
Station 1- FP #2 VV Prep (hrd surf cmpnts)
| Misc Hardware - Completed |  | 2
| Layout diagnostic&coolant paths on vessel - Completed | 12
| Install heater tape on vertical ports - Completed | 7
| Verify installation of heater tapes - Completed | 1
| Attach studs forcoolant lines - Completed | 3
| Wind magnetic diagnostic sensors - Completed | 14
| Install precision magnetic diagnostic sensors - Completed | 3
| Verify installation magnetic diagnostic sensors - Completed | 4
| Install local I&C (incl thermocouples) - Completed | 5 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Verify installation of local I&C - Completed | 2 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Install cooling/htg lines to vac vsl | 15 | [10 empty] | 300 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Weld cooling/htg risers | 10 | 2 | [9 empty] | 200 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Verify Instl of H/C lines,headers,manifolds | 5 | [10 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Perform final acceptance testing (H/C flow test) | 5 | 4 | [9 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Trim seal plates | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Loop termination & verification | 18 | [10 empty] | 360 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| install Final Internal and External monuments and measure | 4 | [10 empty] | 80 | 2.5
| Final Scan | 4 | [10 empty] | 80 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Install heater tape on removeable ports | 6 | [10 empty] | 120 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Prepare and transfer completed VV to holding are | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
Station 1- FP #3 VV Prep (hrd surf cmpnts)
| Misc Hardware |  | 2
| Layout diagnostic&coolant paths on vessel - Completed | 12
| Install heater tape on vertical ports - Completed | 7 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Verify installation of heater tapes - Completed | 1 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Attach studs for coolant lines - Completed | 3 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Wind magnetic diagnostic sensors - Completed | 14 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Install precision magnetic diagnostic sensors - Completed | 3 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Verify installation magnetic diagnostic sensors - Completed | 4 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Install local I&C (incl thermocouples) | 5 | [10 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Verify installation of local I&C | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Install cooling/htg lines to vac vsl | 15 | [10 empty] | 300 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Weld cooling/htg risers | 10 | 2 | [9 empty] | 200 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Verify Instl of H/C lines,headers,manifolds | 5 | [10 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Perform final acceptance testing (H/C flow test) | 5 | 4 | [9 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Trim seal plates | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Loop termination & verification | 18 | [10 empty] | 360 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Install Final Internal and External monuments and measure | 4 | [10 empty] | 80 | 2.5
| Final Scan | 4 | [10 empty] | 80 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Install heater tape on removeable ports | 6 | [10 empty] | 120 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Prepare and transfer completed VV to holding are | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
Station 1-Spool pieces (3) (spacers)
| Attach diagnostics, studs and coolant lines | 17 | [10 empty] | 340 | 2.5
| install Final Internal and External monuments and measure | 2 | [10 empty] | 40 | 2.5
Station 2 Trials & Setup
| Trial tensioning test on prototype | 2 | 3 | [9 empty] | 40 | 2.5
| Trial bushing and shim test on prototype | 12 | 2 | [9 empty] | 240 | 2.5
| Guidance f/post-VPI proced to include measuremen | 36 | [10 empty] | 0 | 0
| Perform trial x-y-z alignments on A1-A2. | 7 | 2 | [9 empty] | 140 | 2.5
| Perform developmental trials on A1-A2. | 30 | 2 | [9 empty] | 600 | 2.5
| Alignment mechanisms, metro equipt &positioning | 6 | 40 | [9 empty] | 120 | 2.5
| Procure alignment mechanisms, fiducials, lifting | 20 | 25 | [9 empty] | 400 | 2.5
| Develop procedures for torquing bolts | 4 | [10 empty] | 80 | 2.5
| Determine fiducial types&locations | 11 | 2 | [9 empty] | 220 | 2.5
| Procure monuments&related metrology equipment | 15 | 15 | [9 empty] | 300 | 2.5
| Tools&tooling available for FPA operations | [11 empty] | 0 | 2.5
| Hardware rework (1/2 FTE) | 120 | 10 | [9 empty] | 960 | 1
| Install FIRST Holding 20 deg fixture | 4 | 2 | [9 empty] | 80 | 2.5
| Install SECOND Holding 20 deg fixture | 3 | 2 | [9 empty] | 60 | 2.5
| Install THIRD Holding 20 deg fixture | 6 | 2 | [9 empty] | 120 | 2.5
| Install LAST Holding 20 deg fixture | 3 | 2 | [9 empty] | 60 | 2.5
Station 2-Modular Coil Subassembly-FP#1
| Misc Hardware |  | 5
| Test out equipt & procedures | 7 | [10 empty] | 140 | 2.5
| Receive drawings and hardware (shims and bolts) | 7 | [10 empty] | 140 | 2.5
| Remeasure Type A "A" flange | 2.5 | [10 empty] | 50 | 2.5
| Begin A1/B1/C1 | 1 | [10 empty] | 20 | 2.5
| Pre-fit & install alignment tooling A1-A2 | 4 | [10 empty] | 80 | 2.5
| Align A1-A2 | 2 | [10 empty] | 40 | 2.5
| Install studs | 0.5 | [10 empty] | 10 | 2.5
| Install shims | 1 | [10 empty] | 20 | 2.5
| Measure and Drill Bushings | 0.5 | [10 empty] | 10 | 2.5
| Install Bushings | 2 | [10 empty] | 40 | 2.5
| Tension | 1 | 25 | [9 empty] | 40 | 5
| Weld nose | 20 | 15 | [9 empty] | 40 | 2.5
| Verify alignment A1-A2 | 2 | [10 empty] | 40 | 2.5
| De Tension | 1 | [10 empty] | 40 | 5
| Adjust Nose shims | 0 | [10 empty] | 0
| Adjust shims | 1 | [10 empty] | 20 | 2.5
| Adjust Bushings | 1 | [10 empty] | 10 | 2.5
| Re Tension | 1 | [10 empty] | 40 | 5
| Verify alignment A1-A2 | 2 | [10 empty] | 40 | 2.5
| De -Tension | 1 | [10 empty] | 20 | 2.5
| Pre-fit C1-C5 | 7 | [10 empty] | 224 | 4
| Begin 3 pack A1/B1/C1 Install A1 | 3 | [10 empty] | 60 | 2.5
| Fit A1-B1 | 22 | [10 empty] | 490 | 2.8
| Fit B1-C1 | 35 | [10 empty] | 490 | 2.8
| Verify Align Mod-Coils A1/B1/C1 | 5 | [10 empty] | 100 | 2.5
| Pre-fit C2-C3 | 7 | [10 empty] | 224 | 4
| Re-measure Type A"A" flange | 2.5 | [10 empty] | 50 | 2.5
| Fit A2-B2 | 22 | [10 empty] | 490 | 2.8
| Fit B2-C2 | 22 | [10 empty] | 490 | 2.8
| Verify Align Mod-Coils A2/B2/C2 | 5 | [10 empty] | 100 | 2.5
Station 2-Modular Coil Subassembly-FP#2
| Re-measure Type A"A" flange | 2.5 | [10 empty] | 50 | 2.5
| Fit A3/A4 | 22 | [10 empty] | 490 | 2.8
| Assemble/Align Mod-Coils A3/B3/C3 | 49 | [10 empty] | 1080 | 2.8
| Pre-fit C6-C4 | 7 | [10 empty] | 224 | 4
| Re-measure Type A"A" flange | 2.5 | [10 empty] | 50 | 2.5
| Assemble/Align Mod-Coils A4/B4/C4 | 49 | [10 empty] | 1080 | 2.8
Station 2-Modular Coil Subassembly-FP#3
| Re-measure Type A"A" flange | 2.5 | [10 empty] | 50 | 2.5
| Fit A5/A6 | 22 | [10 empty] | 490 | 2.8
| Assemble/Align Mod-Coils A5/B5/C5 | 49 | [10 empty] | 1080 | 2.8
| Re-measure Type A"A" flange | 2.5 | [10 empty] | 50 | 2.5
| Assemble/Align Mod-Coils A6/B6/C6 | 49 | [10 empty] | 1080 | 2.8
Station 3-Assemble Mod Coils and VVSA-FP#1
| Misc Hardware |  | 5
| Procure and load test 3 legged actuator System | 4 | 43 | [9 empty] | 96 | 3
| Procure, Fabricate and load test 3 legged actuator Lift Fixture | 8 | 6 | [9 empty] | 128 | 2
| Begin Assembly of First Field Period Assy | 2 | [10 empty] | 40 | 2.5
| Fab new legs | 4 | [10 empty] | 64 | 2
| Install station 3 platforms (8 required) | 4 | 10 | [9 empty] | 112 | 3.5
| Pre-installation set-up (Steps 1.x) | 7 | [10 empty] | 180 | 3.21
| Pre-assemblies left MCHP (Steps 2.x) | 7 | [10 empty] | 140 | 2.5
| Pre-assembliess right MHCP (Steps 3.x) | 7 | [10 empty] | 130 | 2.5
| Install and align station 3 screens (Steps 4.x) | 5 | 2 | [9 empty] | 100 | 2.5
| Test out station 3 equipment and procedures | 4 | 10 | [9 empty] | 80 | 2.5
Assemble/Disassemble abc1-abc2 (stage 3 fixture)
| VV to MC turning fixt base; metr check | 3 | [10 empty] | 60 | 2.5
| Attach local protective strips to VV&locate sens | 2 | [10 empty] | 40 | 2.5
| Mount MC on crane; perform metr checks | 4 | 8 | [9 empty] | 80 | 2.5
| Rotate right MC to stand-off position&chk | 3 | [10 empty] | 60 | 2.5
| Transfer load to sprt sys and recheck position | 3 | [10 empty] | 60 | 2.5
| Move MC turning fixt; mount MC on crane | 3 | [10 empty] | 60 | 2.5
| Rotate left MC to stand-off position and check p | 3 | [10 empty] | 60 | 2.5
| Move left & right MC to final position & measure | 2 | [10 empty] | 40 | 2.5
| Bolt together at flange interface. | 40 | [10 empty] | 800 | 2.5
| Perform final metrology position check | 2 | [10 empty] | 40 | 2.5
| Remove temp interference strips&sensors | 1 | [10 empty] | 20 | 2.5
| Secure VV to MC's using temporary supports. | 5 | [10 empty] | 100 | 2.5
| Prepare Field Period for shipment | 5 | [10 empty] | 100 | 2.5
| Transfer completed assy to C-site test cell | 5 | [10 empty] | 200 | 5
Station 3-Assemble Mod Coils and VVSA-FP#2
| Assemble/Disassemble abc -abc4 (stage 3 fixture) | 4
| Pre-assemblies left MCHP (Steps 2.x) | 7 | [10 empty] | 140 | 2.5
| Pre-assembliess right MHCP (Steps 3.x) | 7 | [10 empty] | 130 | 2.5
| Install and align station 3 screens (Steps 4.x) | 5 | 2 | [9 empty] | 100 | 2.5
| Mount VV to MC turning fixt base; metr check (Steps 5x) | 3 | [10 empty] | 60 | 2.5
| Attach local protective strips to VV & locate sens (Stes 6.01) | 1 | [10 empty] | 20 | 2.5
| Mount MC on crane; perform metr checks | 4 | [10 empty] | 80 | 2.5
| Rotate right MC to stand-off position&chk | 3 | [10 empty] | 60 | 2.5
| Transfer load to supt sys and recheck position | 3 | [10 empty] | 60 | 2.5
| Move MC turning fixt; mount MC on crane | 3 | [10 empty] | 60 | 2.5
| Rotate left MC to stand-off position and check p | 3 | [10 empty] | 60 | 2.5
| Move left & right MC to final position & measure | 2 | [10 empty] | 40 | 2.5
| Bolt together at flange interface. | 35 | [10 empty] | 700 | 2.5
| Perform final metrology position check | 3 | [10 empty] | 60 | 2.5
| Remove temp interference strips&sensors | 1 | [10 empty] | 20 | 2.5
| Secure VV to MC's using temporary supports. | 2 | [10 empty] | 40 | 2.5
| Prepare Field Period for shipment | 2 | [10 empty] | 64 | 4
| Transfer completed assy to C-site test cell | 1 | [10 empty] | 48 | 6
Station 3-Assemble Mod Coils and VVSA-FP#3
| Assemble/Disassemble abc -abc6 (Stage 3 fixture) | 3
| Pre-assemblies left MCHP (Steps 2.x) | 7 | [10 empty] | 140 | 2.5
| Pre-assembliess right MHCP (Steps 3.x) | 7 | [10 empty] | 130 | 2.5
| Install and align station 3 screens (Steps 4.x) | 5 | 2 | [9 empty] | 100 | 2.5
| Mount VV to MC turning fixt base; metr check (Steps 5x) | 3 | [10 empty] | 60 | 2.5
| Attach local protective strips to VV & locate sens (Stes 6.01) | 1 | [10 empty] | 20 | 2.5
| Mount MC on crane; perform metr checks | 4 | [10 empty] | 80 | 2.5
| Rotate right MC to stand-off position&chk | 3 | [10 empty] | 60 | 2.5
| Transfer load to supt sysand recheck position | 3 | [10 empty] | 60 | 2.5
| Move MC turning fixt; mount MC on crane | 3 | [10 empty] | 60 | 2.5
| Rotate left MC to stand-off position and check p | 3 | [10 empty] | 60 | 2.5
| Move left & right MC to final position & measure | 2 | [10 empty] | 40 | 2.5
| Bolt together at flange interface. | 35 | [10 empty] | 700 | 2.5
| Perform final metrology position check | 3 | [10 empty] | 60 | 2.5
| Remove temp interference strips&sensors | 1 | [10 empty] | 20 | 2.5
| Secure VV to MC's using temporary supports. | 2 | [10 empty] | 40 | 2.5
| Prepare Field Period for shipment | 2 | [10 empty] | 64 | 4
| Transfer completed assy to C-site test cell | 1 | [10 empty] | 48 | 6
Job: 1810 - Field Period Assembly-VIOLA |  |  | 336 | 0 | 0 | 0 | 0 | 5178 | 0 | 0 | 3452 | 0 | 30314.8
| TASK DESCRIPTION | Work days | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM/DSN | SHTB | EMEM | EMSM | EMSB | EMTB | CREW | Basis of Estimate
Based on quotes from PPPL Tech Shop based on similar tasks, tempered (adjusted) for complexity of having to do all welds from inside of the vessel.
Job: 1815 - Field Period Assembly Station 5 (in NCSX TC)-VIOLA
Station 5- Final FP Assy -FP#1 (in NCSX TC)
| metrology network | 10 | 7 | [9 empty] | 160
| Bolt on 2 Port Extensions needed for first Plasma diagnostics | 1 | [10 empty] | 16 | 2 | 10" ports provided by WBS 38
| MTM NCR Hardware repurchase (bolt kits & cover plates) |  | 42
| Weld Wire & weld supples |  | 15
| Testout Sta 5 equipt & procedures | 5 | [10 empty] | 160 | 4
| Check 3 sled interfaces adjust holes | 12 | [10 empty] | 384 | 4
| Fixtures installed - final metrology | 6 | [10 empty] | 192 | 4
| Install on support platform | 15 | 12 | [9 empty] | 600 | 5
| Mount MC/VV assembly to support frame a | 2 | [10 empty] | 40 | 2.5
| Position and weld all ports to VV | 30 | [10 empty] | 600 | 2.5
| Inspect Welds | 4 | [10 empty] | 80 | 2.5
| Assemble left TF Coil Assembly check position | 8 | [10 empty] | 256 | 4
| Change platforms | 1 | [10 empty] | 20 | 2.5
| Assemble right TF Coil Assembly chk position | 8 | [10 empty] | 256 | 4
| Attach TF coils to MC's | 4 | [10 empty] | 80 | 2.5
| Align TF Coils | 8 | [10 empty] | 160 | 2.5
| Change platforms | 1 | [10 empty] | 20 | 2.5
| Position, tack-weld only two large horizontal diag ports (port 4's) | 8 | [10 empty] | 160 | 2.5
Assemble external trim coils (in wbs75)
Close up VV, leak check
| Adjust final support base interfaces | 8 | [10 empty] | 160 | 2.5
| Final metrology outside & inside | 10 | [10 empty] | 200 | 2.5
| Lift onto Station 6 assembly structure | 1 | [10 empty] | 20 | 2.5
Station 5- Final FP Assy -FP#2 (in NCSX TC)
| Install on support platform | 15 | [10 empty] | 600 | 5
| Mount MC/VV assembly to support frame a | 2 | [10 empty] | 40 | 2.5
| Position and weld all ports to VV | 30 | [10 empty] | 600 | 2.5
| Inspect Welds | 4 | [10 empty] | 80 | 2.5
| Assemble left TF Coil Assembly check position | 8 | [10 empty] | 256 | 4
| Change platforms | 1 | [10 empty] | 20 | 2.5
| Assemble right TF Coil Assembly chk position | 8 | [10 empty] | 256 | 4
| Attach TF coils to MC's | 4 | [10 empty] | 80 | 2.5
| Align TF Coils | 6 | [10 empty] | 120 | 2.5
| Change platforms | 1 | [10 empty] | 20 | 2.5
| Position, tack-weld only two large horizontal diag ports (port 4's) | 8 | [10 empty] | 160 | 2.5
Assemble external trim coils (in wbs75)
Close up VV, leak check
| Adjust final support base interfaces | 8 | [10 empty] | 160 | 2.5
| Final metrology outside & inside | 10 | [10 empty] | 200 | 2.5
| Lift onto Station 6 assembly structure | 1 | [10 empty] | 20 | 2.5
Station 5- Final FP Assy -FP#3 (in NCSX TC)
| Install on support platform | 15 | [10 empty] | 600 | 5
| Mount MC/VV assembly to support frame a | 2 | [10 empty] | 40 | 2.5
| Position and weld all ports to VV*2 shift* | 30 | [10 empty] | 600 | 2.5
| Inspect Welds | 4 | [10 empty] | 80 | 2.5
| Assemble left TF Coil Assembly check position | 8 | [10 empty] | 256 | 4
| Change platforms | 1 | [10 empty] | 20 | 2.5
| Assemble right TF Coil Assembly chk position | 8 | [10 empty] | 256 | 4
| Attach TF coils to MC's | 4 | [10 empty] | 80 | 2.5
| Align TF Coils | 6 | [10 empty] | 120 | 2.5
| Change platforms | 1 | [10 empty] | 20 | 2.5
| Position, tack-weld only two large horizontal diag ports (port 4's) | 8 | [10 empty] | 160 | 2.5
Assemble external trim coils (in wbs75)
Close up VV, leak check
| Adjust final support base interfaces | 8 | [10 empty] | 160 | 2.5
| Final metrology outside & inside | 10 | [10 empty] | 200 | 2.5
| Last field period assembled | 1 | [10 empty] | 20 | 2.5
| Lift onto Station 6 assembly structure | 1 | [10 empty] | 20 | 2.5
Job:1810 - Field Period Assembly-VIOLA Total | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Job: 1815 - Field Period Assembly Station 5 (in NCSX TC)-VIOLA |  |  | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8808
HP Techs EMEM???
Is this in Job 1805?
What is this?
Is this in Job 1805?