## Sheet1
NCSX ECP-52 BCWR (12/1/06) | [14 empty] | Duration | Crew Size
[9 empty] | $k | Hours | Hours | Hours | Hours | Hours | Days | Persons | Assumptions
Sum of BCWR | [7 empty] | RES
WBS2 | Job Title | ACT | TITLE | OD | Shifts | ES | EF |  | 41 | EA EM | EE SM | EM EM | EM SM | EM TB
72 | Job: 7201 - Control Room Walls&Floors-PERRY | 710.001 | Install Wall east side control room | 24 |  | 2007-06-01 | 2007-08-01 | 0 | [8 empty] | GPP
|  | 711B.050 | Complete Control Room Flooring **post CD-4** | 18 |  | 2007-08-01 | 2007-10-01 | 0 | [8 empty] | GPP
73 | Job: 7301 - Platform Design & Fab-PERRY | 711A.040 | Platform nut plates | 166 |  | 2007-06-01 | 2007-08-01 |  | 0.1 |  |  |  |  | 36
|  | 712.020 | Platform Parts | 22 |  | 2007-06-01 | 2007-10-01 |  | 3 |  |  | 32 | 0 | 300
|  |  | Survey and layout locations for platform posts |  |  | 2007-09-01 | 2007-10-31 |  |  |  |  | 40 | 40 | 160 | 10 | 2
|  | 712.030 | Misc Platform Hardware/Material | 83 |  | 2007-10-01 | 2008-05-31 |  | 16
|  |  | Machine Platform Trial Assembly and Fit-up |  |  | 2007-10-01 | 2008-01-01 |  |  |  |  | 48 | 240 | 960 | 20 | 6
74 | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 714.020 | LOE FY06 prior to assy starting | 185 |  | 2007-04-02 | 2007-12-21 |  |  |  | 90 | 120
|  | 714.030 | LOE FY07 thru first plasma | 313 |  | 2008-01-02 | 2009-03-31 |  |  |  |  | 2640 | 2640 |  |  |  | 15 month duration
|  | 613.030 | Test Cell copper ground plane cuts | 130 |  | 2005-07-01 | 2007-06-29 |  | 0.2 |  |  |  |  | 24 |  |  | deleted - copper plate removed
|  | 7502-001 | Test Cell 110v outlets | 256 |  | 2005-04-01 | 2007-09-28 | [5 empty] | 48 |  |  |  | GPP
|  | 7502-002 | Test Cell 208v outlets | 256 |  | 2005-04-01 | 2007-09-28 | [5 empty] | 24 |  |  |  | GPP
75 | 7501 - Construction Support Crew | 7501-05 | Construction Support Crew during machine assy | 173 |  | 2008-05-21 | 2009-02-03 | [5 empty] | 1359.6 | 3399
|  | 7501-06 | Construction Support Crew e-beam mapping&ISTP | 35 |  | 2009-02-04 | 2009-03-24 | [6 empty] | 1120
|  |  | Fabricate assembly structure | [8 empty] | 96 | 240 | 960 | 20 | 6 | Design by others
| 7503 - Machine Assembly | 7503-020 | Install & Level Support Base Plates | 8 | 2 | 2008-05-21 | 2008-06-02 |  |  | 60 |  |  | 120 | 480
|  |  | Install assembly structure | [8 empty] | 72 | 180 | 720 | 15 | 6
|  | 7503-070 | Install 3 Spool Pieces on fixt & test movement | 10 |  | 2008-06-24 | 2008-07-08 |  |  | 40 |  |  | 80 | 320
|  | 7503-080 | FPA-1 Installed on support platform | 0 |  | 2008-07-08 | 2008-07-08 | 0
|  | 7503-110 | FPA-2 Installed on support platform | 0 |  | 2008-07-08 | 2008-07-08 | 0
|  | 7503-120 | Test movement of FPA-1& -2 & position checks. | 5 |  | 2008-07-09 | 2008-07-15 |  |  | 20 |  |  | 40 | 160
|  | 7503-130 | Install local Platforms around FPA-2 | 3 |  | 2008-07-11 | 2008-07-15 |  |  | 0 |  |  | 32 | 128 | 4 | 4
|  | 7503-060 | Install Lower PF 4,5&6 into prelim position | 2 |  | 2008-07-14 | 2008-07-15 | [5 empty] | 16 | 32
|  | 7503-150 | FPA-3 Installed on support platform | 0 |  | 2008-07-15 | 2008-07-15 | 0
|  | 7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 6 |  | 2008-07-16 | 2008-07-23 |  |  | 24 |  |  | 48 | 192
|  | 7503-030 | Install/Level FPA's and Spool Piece supports | 15 | 2 | 2008-06-03 | 2008-06-23 |  |  | 120 |  |  | 240 | 960
|  |  | Replace assembly structure with permanent structure | [8 empty] | 72 | 180 | 720 | 15 | 6
|  | 7503-090 | Install local Platforms around FPA-1 | 5 | 2 | 2008-07-17 | 2008-07-23 |  |  | 0 |  |  | 32 | 128 | 4 | 4
|  | 7503-170 | FPA Metrology Checks to Assure Alignment | 3 |  | 2008-07-24 | 2008-07-28 |  |  | 12 |  |  |  | 12
|  | 7503-190 | Install local Platforms around FPA-3 | 5 | 2 | 2008-07-29 | 2008-08-04 |  |  | 0 |  |  | 32 | 128 | 4 | 4
|  | 7503-180 | MC Interfaces: shim | 15 |  | 2008-08-05 | 2008-08-25 |  | 36 | 60 |  | 86 | 216 | 864 | 18 | 6 | shims provided by others; M&S for final sizing
|  |  | MC Interfaces: ream holes | [5 empty] | 72 |  |  | 230 | 576 | 2304 | 72 | 4 | 32 hole pairs x 18 interfaces x 1/4 day to set up and ream each hole with a two man crew, two crews; M&S for consumeable tools
|  |  | MC Interfaces: bolt together | [8 empty] | 29 | 72 | 288 | 36 | 6 | all materials provided by others
|  | 7503-200 | Mate-up and weld all VV-to-Spool interfaces | 15 |  | 2008-08-26 | 2008-09-16 | [5 empty] | 120 | 720
|  | 7503-210 | Fit-up all TF coils | 10 |  | 2008-09-17 | 2008-09-30 |  |  | 40 |  |  | 80 | 480
|  | 7503-240 | Bolt on preassembled pump duct | 5 |  | 2008-09-17 | 2008-09-23 | [5 empty] | 40 | 160
|  | 7503-240.1 | Install insulation boots | 5 | 2 | 2008-09-24 | 2008-09-30 | [6 empty] | 320
|  | 7503-240.2 | Install insulation | 2 | 2 | 2008-10-01 | 2008-10-02 | [6 empty] | 72
|  | 7503-270 | Raise lower PF 4,5&6 coils into final position | 6 |  | 2008-10-01 | 2008-10-08 |  |  | 24 |  |  | 48 | 192
|  | 7503-260 | PTP Pumpdown & leak check VV | 10 |  | 2008-10-03 | 2008-10-16 | [5 empty] | 120 | 480
|  | 7503-280 | Install Upper PF 4,5 & 6 coils | 6 |  | 2008-10-09 | 2008-10-16 |  |  | 24 |  |  | 48 | 192
|  | 7503-290 | Install PF Solenoid into position (U/L PF1,2,3) | 4 |  | 2008-10-17 | 2008-10-22 |  |  | 16 |  |  | 32 | 128 |  |  | All I&C in place on solenoid prior to arrival in C Test Cell (CTC)
|  | 7503-290A | Install trim coils | 5 |  | 2008-10-23 | 2008-10-29 |  |  | 16 |  |  | 32 | 128
|  |  | Install LN2 manifolds | [9 empty] | 80 | 320 | 10 | 4 | Fabrication by WBS 161; instl WG
|  | 7503-310 | Complete LN2 connections | 10 |  | 2008-10-30 | 2008-11-12 | [5 empty] | 80 | 320
|  | 7503-320 | Complete Elect Pwr connections | 10 | 2 | 2008-10-30 | 2008-11-12 | [5 empty] | 160 | 960 |  |  | Provided by WBS 162; instl WG
|  | 7503-321 | Complete mag diag & machine I&C | 10 | 2 | 2008-10-30 | 2008-11-12 | [5 empty] | 160 | 320 |  |  | Provided by WBS ?; instl WG
|  | 7503-340 | Install Cryostat Base, vapor barrie& port boots | 10 |  | 2008-11-13 | 2008-11-26 | [5 empty] | 80 | 320
|  | 730.1248 | ACC Review | 20 |  | 2008-11-20 | 2008-12-19 | 0
|  | 7503-350 | Install Cryostat upper section,VB and port boots | 10 |  | 2008-12-01 | 2008-12-12 | [5 empty] | 80 | 320
|  | 7503-360 | Install Midplane Cryostat sections and port boot | 15 |  | 2008-12-15 | 2009-01-13 | [5 empty] | 120 | 480
|  | 730.1249 | PSO Operational Readiness Assessment | 5 |  | 2008-12-22 | 2009-01-06 | 0
|  | 7503-370 | Install Cryostat Circulation Duct | 5 |  | 2009-01-14 | 2009-01-20 | [5 empty] | 40 | 160 |  |  | Cryo cooling system instl in WBS 623
|  | 730.8200 | PTP and Cooldown | 10 |  | 2009-01-21 | 2009-02-03 |  |  |  |  | 80 | 80 | 480
76 | Job: 7601 - Tooling Design & Fabrication | 713.020 | Lab Fab/Assy/Installation | 329 |  | 2007-10-01 | 2009-01-30 |  |  |  |  | 80 | 42 | 140
|  | 713.030 | Tooling,assy fixtures,misc equipt | 329 |  | 2007-10-01 | 2009-01-30 |  | 60
|  | 713.040 | General procurements | 329 |  | 2007-10-01 | 2009-01-30 |  | 45
|  | 713.050 | Welding tools, materials & equipt | 329 |  | 2007-10-01 | 2009-01-30 |  | 40
|  |  | Torque wrenches and multipliers | [5 empty] | 40 |  |  | 40
|  |  | Update Final Assembly Plan |  |  | 2007-05-01 | 2007-10-01 |  |  |  |  | 160
|  |  | Install e-beam mapping equipment | [8 empty] | 40 | 80 | 320 | 10 | 4 | WG
Grand Total | [7 empty] | 0 | 272.3 | 456 | 90 | 3625 | 7897.6 | 21087
EDP
2007-04-04
0815 hrs