## Sheet1
1
2
3 | Sum of BQ | [9 empty] | RES
4 | [10 empty] | $ | $k |  | hr | [6 empty] | met staff (budgeted in LOE) for ref only
5 | JJJJ | WBS4 | ACT | TITLE | ES | Viola ES | Viola EF | EF | OD | SHIFTS | ORNL35 | 41 | 81 | EA//EM | EE//SM | EM//EM | EM//TB | ORNLDM | ORNLEM | SH//TB | ZMET
6 | 1802 |  | 1802MAY | May cost incr | 2007-05-01 |  |  | 2007-05-29 | 20 |  |  |  | 15
7 |  | Total | [10 empty] | 15
8 |  | 2.00 | R1802-207 | Procedures written & approved | 2007-08-24 |  |  | 2007-09-13 | 14
9 |  |  | R1802-209 | JHA completed | 2007-09-14 |  |  | 2007-09-21 | 6
10 |  |  | R1802-211 | Training needs identified & released | 2007-09-24 |  |  | 2007-10-01 | 6
11 |  |  | R1802-213 | ACC review completed | 2007-10-02 |  |  | 2007-10-03 | 2
12 |  |  | R1802-215 | Pre-job brief completed | 2007-10-04 |  |  | 2007-10-04 | 1
13 |  |  | R1802-217 | Station 2 operational | 2007-10-05 |  |  | 2007-10-05 | 1
14 |  | 2.00 Total
15 |  | 3.00 | R1802-307 | Procedures written & approved | 2007-11-23 |  |  | 2007-12-10 | 10
16 |  |  | R1802-309 | JHA completed | 2007-12-11 |  |  | 2007-12-18 | 6
17 |  |  | R1802-311 | Training needs identified & released | 2007-12-19 |  |  | 2008-01-04 | 6
18 |  |  | R1802-313 | ACC review completed | 2008-01-07 |  |  | 2008-01-14 | 6
19 |  |  | R1802-315 | Pre-job brief completed | 2008-01-15 |  |  | 2008-01-22 | 6
20 |  | 3.00 Total
21 |  | 5.00 | R1802-507 | Procedures written & approved | 2008-05-29 |  |  | 2008-06-17 | 14
22 |  |  | R1802-509 | JHA completed | 2008-06-18 |  |  | 2008-06-25 | 6
23 |  |  | R1802-511 | Training needs identified & released | 2008-07-07 |  |  | 2008-07-14 | 6
24 |  |  | R1802-513 | ACC review completed | 2008-07-15 |  |  | 2008-07-23 | 7
25 |  |  | R1802-515 | Pre-job brief completed | 2008-07-24 |  |  | 2008-08-01 | 7
26 |  |  | R1802-519 | Fixtures installed | 2008-06-26 |  |  | 2008-07-03 | 6
27 |  | 5.00 Total
28 |  | A | 1802ORNL02 | ORNL Title III field period assy station 2 | 2007-08-14 |  |  | 2009-02-04 | 365 |  | 6 | [6 empty] | 591 | 591
29 |  |  | 1802ORNL03 | ORNL Title III field period assy station 3 | 2008-01-23 |  |  | 2009-05-19 | 333 |  | 6 | [6 empty] | 442 | 442
30 |  |  | 1802ORNL05 | ORNL Title III field period assy station 5 | 2008-08-04 |  |  | 2009-10-23 | 307 |  | 6 | [6 empty] | 444 | 444
31 |  |  | R1802-001 | Metrology Engr Super FY07 | 2007-05-01 |  |  | 2007-09-28 | 106 |  |  |  |  | 360
32 |  |  | R1802-003 | Metrology Engr Super FY08 | 2007-10-01 |  |  | 2008-09-30 | 250 |  |  |  |  | 863
33 |  |  | R1802-004 | Metrology Engr Super FY09 | 2008-10-01 |  |  | 2009-09-29 | 248 |  |  |  |  | 863
34 |  |  | R1802-004S | Metrology Engr Super FY09 (2n shft suprt .5 fte | 2009-02-26 |  |  | 2009-10-23 | 169 | 2 |  |  |  | 583.05
35 |  |  | R1802-005 | FPA Management FY07 | 2007-05-01 |  |  | 2007-09-28 | 106 |  |  | 5.7 |  |  |  | 719
36 |  |  | R1802-007 | FPA Management FY08 | 2007-10-01 |  |  | 2008-09-30 | 250 | [6 empty] | 1726
37 |  |  | R1802-008 | FPA Management FY09 | 2008-10-01 |  |  | 2009-09-29 | 248 | [6 empty] | 1726
38 |  |  | R1802-011 | Title III field period assy FY08 ORNL | 2007-10-01 |  |  | 2008-09-30 | 250 |  | 25 | [7 empty] | 400
39 |  |  | R1802-013 | HP Coverage in the TFTR TC LOE FY07 | 2007-05-01 |  |  | 2007-09-28 | 106 | [10 empty] | 539
40 |  |  | R1802-015 | HP Coverage in the TFTR TC LOE FY08 | 2007-10-01 |  |  | 2008-09-30 | 250 | [10 empty] | 1295
41 |  |  | R1802-016 | HP Coverage in the TFTR TC LOE FY09 | 2008-10-01 |  |  | 2009-05-11 | 150 | [10 empty] | 777
42 |  |  | R1810-098 | Station 3 complete |  |  |  | 2009-05-19 | 0
43 |  | A Total | [8 empty] | 43 | 5.7 |  | 2669.05 |  | 4171 |  | 1477 | 1877 | 2611
44 | 1802 Total | [9 empty] | 43 | 5.7 | 15 | 2669.05 |  | 4171 |  | 1477 | 1877 | 2611
45 | 1810 | S0P0 | R1801-004S | LOE Crane support, fixt setup (2nd shft 1.2 fte | 2009-02-26 |  |  | 2009-10-23 | 169 | 2 | [6 empty] | 1399.32
46 |  |  | R1810-001 | LOE Crane support, fixture setupfor FY07 | 2007-05-01 |  |  | 2007-09-28 | 106 | [7 empty] | 863
47 |  |  | R1810-003 | LOE Crane support, fixture setupfor FY08 | 2007-10-01 |  |  | 2008-09-30 | 250 | [7 empty] | 2071.2
48 |  |  | R1810-004 | LOE Crane support, fixture setupfor FY09 | 2008-10-01 |  |  | 2009-09-29 | 248 | [7 empty] | 2053.44
49 |  |  | R1810-005 | LOE Field Supervision for FY07 | 2007-05-01 |  |  | 2007-09-28 | 106 | [5 empty] | 719
50 |  |  | R1810-007 | LOE Field Supervision for FY08 | 2007-10-01 |  |  | 2008-09-30 | 250 | [5 empty] | 1726
51 |  |  | R1810-008 | LOE Field Supervision for FY09 | 2008-10-01 |  |  | 2009-09-29 | 248 | [5 empty] | 1726
52 |  |  | R1810-008S | LOE Field Supervision for 2nd shft 1.0 fte | 2009-02-26 |  |  | 2009-10-23 | 169 | 2 |  |  |  |  | 1166.1
53 |  |  | R1810-009 | LOE Metrology sprt FY07 1.5 fte EM & 1.0 fte TB | 2007-05-01 |  |  | 2007-09-28 | 106 | [6 empty] | 1097.1 | 731.4
54 |  |  | R1810-011 | LOE Metrology sprt FY08 1.5 fte EM & 1.0 fte TB | 2007-10-01 |  |  | 2008-09-30 | 250 | [6 empty] | 3500 | 2300
55 |  |  | R1810-012 | LOE Metrology sprt FY09 1.5 fte EM & 1.0 fte TB | 2008-10-01 |  |  | 2009-11-06 | 276 | [6 empty] | 1960 | 1300
56 |  |  | R1810-013 | Misc M&S FY07 | 2007-05-01 |  |  | 2007-09-28 | 106 |  |  | 15
57 |  |  | R1810-015 | Misc M&S FY08 | 2007-10-01 |  |  | 2008-09-30 | 250 |  |  | 36
58 |  |  | R1810-016 | Misc M&S FY09 | 2008-10-01 |  |  | 2009-11-06 | 276 |  |  | 38.64
59 |  |  | R1810-099 | Station 5 complete |  |  |  | 2009-10-23 | 0
60 |  | S0P0 Total | [9 empty] | 89.64 |  |  | 5337.1 | 6557.1 | 10718.36
61 |  | S1P1 | R1810-1105 | Instl cooling lines & Weld cooling/htg risers | 2007-06-01 |  | DONE | 2007-07-16 | 31 | 1 |  | 2 |  |  |  |  | 620
62 |  |  | R1810-1107 | Verify Instl of H/C lines,headers,manifolds | 2007-07-17 |  |  | 2007-07-23 | 5 | 1 | [6 empty] | 100
63 |  |  | R1810-1108 | Perform final acceptance testing (H/C flow test) | 2007-07-24 |  |  | 2007-07-30 | 5 | 1 |  | 4 |  |  |  |  | 100
64 |  |  | R1810-1109 | Loop termination & verification | 2007-12-07 | 2007-07-15 |  | 2008-01-10 | 18 | 1 | [6 empty] | 360
65 |  |  | R1810-1110 | Install Final Internal&Ext monuments & meas | 2008-01-11 |  |  | 2008-01-16 | 4 | 1 | [6 empty] | 80
66 |  |  | R1810-1111 | Final Scan | 2008-01-25 |  |  | 2008-01-30 | 4 | 1 | [6 empty] | 80
67 |  |  | R1810-1112 | Trim seal plates | 2007-07-31 |  |  | 2007-08-01 | 2 | 1 | [6 empty] | 40
68 |  |  | R1810-1113 | Prepare &transfer completed VV to holding area | 2008-02-14 |  |  | 2008-02-15 | 2 | 1 | [6 empty] | 40
69 |  |  | R1810-1114 | Install heater tape on removable ports | 2008-01-31 |  | 2008-04-10 | 2008-02-13 | 10 | 1 | [6 empty] | 200
70 |  | S1P1 Total | [9 empty] | 6 |  |  |  |  | 1620
71 |  | S1P2 | R1810-1203 | Misc Hardware | 2007-06-01 |  |  | 2007-09-28 | 84 |  |  | 2
72 |  |  | R1810-1208 | Perform final acceptance testing (H/C flow test) | 2008-02-25 |  |  | 2008-02-29 | 5 | 1 |  | 4 |  |  |  |  | 100
73 |  |  | R1810-1209 | Install cooling/htg lines to vac vsl | 2007-11-01 |  | DONE | 2007-11-21 | 15 | 1 | [6 empty] | 300
74 |  |  | R1810-1211 | Weld cooling/htg risers | 2007-11-22 |  | DONE | 2007-12-17 | 16 | 1 |  | 2 |  |  |  |  | 320
75 |  |  | R1810-1212 | Trim seal plates | 2008-03-03 |  |  | 2008-03-04 | 2 | 1 | [6 empty] | 40
76 |  |  | R1810-1213 | Verify Instl of H/C lines,headers,manifolds | 2008-02-18 |  |  | 2008-02-22 | 5 | 1 | [6 empty] | 100
77 |  |  | R1810-1214 | Install heater tape on removable ports | 2008-04-10 |  |  | 2008-04-23 | 10 | 1 | [6 empty] | 200
78 |  |  | R1810-1215 | Loop termination & verification | 2008-03-05 | 2007-08-15 |  | 2008-03-28 | 18 | 1 | [6 empty] | 360
79 |  |  | R1810-1216 | Install Final Internal&Ext monuments & meas | 2008-03-31 |  |  | 2008-04-03 | 4 | 1 | [6 empty] | 80
80 |  |  | R1810-1217 | Final Scan | 2008-04-04 |  |  | 2008-04-09 | 4 | 1 | [6 empty] | 80
81 |  |  | R1810-1219 | Prepare& transfer completed VV to holding area | 2008-04-24 |  |  | 2008-04-25 | 2 | 1 | [6 empty] | 40
82 |  | S1P2 Total | [9 empty] | 8 |  |  |  |  | 1620
83 |  | S1P3 | R1810-1303 | Misc Hardware | 2007-05-15 |  |  | 2009-02-03 | 427 |  |  | 2 |  |  |  |  | 0
84 |  |  | R1810-1304 | Layout diag &coolant paths on vessel | 2007-08-02 |  | DONE | 2007-08-17 | 12 | 1 | [6 empty] | 240
85 |  |  | R1810-1305 | Install heater tape on vertical ports | 2007-10-01 |  | 2007-06-20 | 2007-10-09 | 7 | 1 | [6 empty] | 140
92 |  |  | R1810-1314 | Install heater tape on removable ports | 2007-10-10 | 2008-04-23 |  | 2007-10-23 | 10 | 1 | [6 empty] | 200
90 |  |  | R1810-1312 | Trim seal plates | 2007-10-24 |  |  | 2007-10-25 | 2 | 1 | [6 empty] | 40
86 |  |  | R1810-1307 | Verify installation of heater tapes | 2007-10-26 | 2007-06-21 |  | 2007-10-26 | 1 | 1 | [6 empty] | 20
88 |  |  | R1810-1309 | Attach studs for coolant lines | 2007-10-29 | 2007-06-22 |  | 2007-10-31 | 3 | 1 | [6 empty] | 60
89 |  |  | R1810-1311 | Wind magnetic diagnostic sensors | 2007-12-18 | 2007-06-27 |  | 2008-01-15 | 14 | 1 | [6 empty] | 280
91 |  |  | R1810-1313 | Install precision magnetic diagnostic sensors | 2008-01-16 | 2007-07-11 |  | 2008-01-18 | 3 | 1 | [6 empty] | 60
93 |  |  | R1810-1315 | Verify installation magnetic diagnostic sensors | 2008-01-21 |  |  | 2008-01-24 | 4 | 1 | [6 empty] | 80
94 |  |  | R1810-1317 | Install local I&C (incl thermocouples) | 2008-10-01 |  |  | 2008-10-07 | 5 | 1 | [6 empty] | 100
95 |  |  | R1810-1319 | Verify installation of local I&C | 2008-10-08 |  |  | 2008-10-09 | 2 | 1 | [6 empty] | 40
96 |  |  | R1810-1321 | Install cooling/htg lines to vac vsl | 2008-10-10 |  |  | 2008-10-30 | 15 | 1 | [6 empty] | 300
97 |  |  | R1810-1323 | Weld cooling/htg risers | 2008-10-31 |  |  | 2008-11-21 | 16 | 1 | [6 empty] | 320
98 |  |  | R1810-1325 | Verify Instl of H/C lines,headers,manifolds | 2008-11-24 |  |  | 2008-12-02 | 5 | 1 | [6 empty] | 100
87 |  |  | R1810-1308 | Perform final acceptance testing (H/C flow test) | 2008-12-03 |  |  | 2008-12-09 | 5 | 1 | [6 empty] | 100
99 |  |  | R1810-1327 | Loop termination & verification | 2008-12-10 | 2007-09-15 |  | 2009-01-13 | 18 | 1 | [6 empty] | 360
100 |  |  | R1810-1328 | Install Final Internal&Ext monuments & meas | 2009-01-14 |  |  | 2009-01-19 | 4 | 1 | [6 empty] | 80
101 |  |  | R1810-1329 | Final Scan | 2009-01-20 |  |  | 2009-01-23 | 4 | 1 | [6 empty] | 80
102 |  |  | R1810-1331 | Prepare & transfer completed VV to holding area | 2009-01-26 |  |  | 2009-01-27 | 2 | 1 | [6 empty] | 40
103 |  | S1P3 Total | [9 empty] | 2 |  |  |  |  | 2640
104 |  | S1SP | R1810-1S03 | Attachdiagnostics, studs and coolant lines | 2009-01-28 |  |  | 2009-02-19 | 17 | 1 | [6 empty] | 340
105 |  |  | R1810-1S04 | Install Final Internal&Ext monuments & meas | 2009-02-20 |  |  | 2009-02-23 | 2 | 1 | [6 empty] | 40
106 |  | S1SP Total | [14 empty] | 380
107 |  | S2P1 | DOE-1 | Notify DOE of scheduled station 3 lifts |  |  |  | 2008-01-02 | 0 | 1
108 |  |  | DOE-2 | DOE review lift procedures | 2008-01-03 |  |  | 2008-02-13 | 30 | 1
109 |  |  | DOE-3 | DOE approval of scheduled station 3 lifts |  |  |  | 2008-02-13 | 0 | 1
110 |  |  | S21-10.01 | Install all wing support bladders | 2008-01-31 |  |  | 2008-02-01 | 2 | [7 empty] | 40
111 |  |  | S21-10.02 | Make local service runs/connections | 2008-01-31 |  |  | 2008-02-11 | 8 | [7 empty] | 160
112 |  |  | S21-10.03 | Inject stycast in all shim spaces | 2008-01-31 |  |  | 2008-01-31 | 1 | [7 empty] | 20
113 |  |  | S21-11.01 | Identify primary fiducials for positioning Sta 3 | 2008-01-11 |  |  | 2008-01-11 | 1 | [7 empty] | 20
114 |  |  | S21-11.03 | Measure bolt length on all tension fasteners | 2008-02-14 |  |  | 2008-02-13 | 0 | [7 empty] | 0
115 |  |  | S21-11.04 | Mark part for identification | 2008-02-14 |  |  | 2008-02-13 | 0 | [7 empty] | 0
116 |  |  | S21-11.05 | Install lift support beams | 2008-02-12 |  |  | 2008-02-13 | 2 | [7 empty] | 40
117 |  |  | S21-11.06 | Remove from stand & measure weight of assy | 2008-02-14 |  |  | 2008-02-14 | 1 | [7 empty] | 20
118 |  |  | S21-11.07 | Move A1-B1-C1 to holding area. | 2008-02-15 |  |  | 2008-02-14 | 0 | [7 empty] | 0
119 |  |  | S21-5.00 | BEGIN A-A Pre-assembly |  |  |  | 2007-08-02 | 0
120 |  |  | S21-5.01 | Place A2 "B" side down. Obtain fiduals | 2007-08-14 |  |  | 2007-08-15 | 2 | [7 empty] | 40
121 |  |  | S21-5.02 | Align to the conical seats locking into 8. | 2007-08-16 |  |  | 2007-08-16 | 1 | [11 empty] | 20
122 |  |  | S21-5.03 | Meas monuments on fixture & walls. | 2007-08-17 |  |  | 2007-08-20 | 2 | [11 empty] | 40
123 |  |  | S21-5.04 | Place shims on coil identical to A1-A2 fit up | 2007-08-21 |  |  | 2007-08-21 | 1 | [7 empty] | 10
124 |  |  | S21-5.05 | Install dial indicators on the MC to see deflec | 2007-08-22 |  |  | 2007-08-22 | 1 | [7 empty] | 40
125 |  |  | S21-5.06 | Lower mating A1 modular coil into position. | 2007-08-23 |  |  | 2007-08-23 | 1 | [7 empty] | 20
126 |  |  | S21-5.07 | Meas monuments bottom coil. Jack to .002ö | 2007-08-24 |  |  | 2007-08-24 | 1 | [7 empty] | 20
127 |  |  | S21-5.08 | Using 3 points, position as was done inA1A2 fit | 2007-08-27 |  |  | 2007-08-27 | 1 | [7 empty] | 20
128 |  |  | S21-5.09 | Torque to 50% | 2007-08-28 |  |  | 2007-08-29 | 2 | [7 empty] | 40
129 |  |  | S21-5.1 | Make "wiggle" test Tighten bolt and recheck. | 2007-08-30 |  |  | 2007-08-30 | 1 | [7 empty] | 20
130 |  |  | S21-5.11 | Meas tooling balls both coils. | 2007-08-31 |  |  | 2007-09-07 | 5 | [11 empty] | 100
131 |  |  | S21-5.12 | Adjust shims locally. Re-torque all studs to 50% | 2007-09-10 |  |  | 2007-09-12 | 3 | [7 empty] | 60
132 |  |  | S21-5.14 | Install A-A locator bushings | 2007-09-13 |  |  | 2007-09-14 | 2 | [7 empty] | 40
133 |  |  | S21-5.15 | Remove studs,nuts,shims. Identify shim locations | 2007-09-17 |  |  | 2007-09-17 | 1 | [7 empty] | 20
134 |  |  | S21-6.01 | Place Type A "A" side down. Obtain fiduals | 2007-09-18 |  |  | 2007-09-19 | 2 | [7 empty] | 40
135 |  |  | S21-6.02 | Align to the conical seats locking into 8. | 2007-09-20 |  |  | 2007-09-20 | 1 | [11 empty] | 20
136 |  |  | S21-6.03 | Meas monuments on fixture & walls. | 2007-09-21 |  |  | 2007-09-24 | 2 | [11 empty] | 40
137 |  |  | S21-6.04 | Place the an initial set shims on coil | 2007-09-25 |  |  | 2007-09-26 | 2 | [7 empty] | 40
138 |  |  | S21-6.041 | Stuff shim bag w/fiberglass & place on wing | 2007-09-27 |  |  | 2007-09-27 | 1 | [7 empty] | 5
139 |  |  | S21-6.05 | Lower the Type-B coil onto the Type-A coil. | 2007-09-28 |  |  | 2007-09-28 | 1 | [7 empty] | 20
140 |  |  | S21-6.06 | Measure monuments on A coil. Jack to .002ö | 2007-10-01 |  |  | 2007-10-01 | 1 | [7 empty] | 20
141 |  |  | S21-6.061 | instl dial indicators for x-y positioning | 2007-10-02 |  |  | 2007-10-02 | 1 | [7 empty] | 20
142 |  |  | S21-6.07 | Perform the X-Y positioning of the B coil. | 2007-10-03 |  |  | 2007-10-03 | 1 | [7 empty] | 20
143 |  |  | S21-6.08 | Install remaining metal shims torque to 50% | 2007-10-04 |  |  | 2007-10-05 | 2 | [7 empty] | 40
144 |  |  | S21-6.09 | Make "wiggle" test Tighten bolt and recheck. | 2007-10-08 |  |  | 2007-10-08 | 1 | [7 empty] | 20
145 |  |  | S21-6.1 | Measure the tooling balls on both coils. | 2007-10-09 |  |  | 2007-10-15 | 5 | [11 empty] | 100
146 |  |  | S21-6.11 | Loosen studs, adjust shims. Re-torque to 50%. | 2007-10-16 |  |  | 2007-10-18 | 3 | [7 empty] | 60
147 |  |  | S21-6.12 | Install alumina shims. Re-torque to 50%. | 2007-10-22 |  |  | 2007-10-22 | 1 | [7 empty] | 20
148 |  |  | S21-6.13 | Make "wiggle" test Tighten bolt and recheck. | 2007-10-23 |  |  | 2007-10-23 | 1 | [7 empty] | 20
149 |  |  | S21-6.14 | Measuretooling balls . The max devi .007ö . | 2007-10-24 |  |  | 2007-10-30 | 5 | [11 empty] | 100
150 |  |  | S21-6.15 | Loosen studs, adjust shims. Re-torque to 50%. | 2007-10-31 |  |  | 2007-11-02 | 3 | [7 empty] | 60
151 |  |  | S21-6.16 | Install bushing. Tighten back to 50% | 2007-11-05 |  |  | 2007-11-05 | 1 | [7 empty] | 30
152 |  |  | S21-6.17 | Complete tightening of flange bolts to 100%. | 2007-11-06 |  |  | 2007-11-06 | 1 | [7 empty] | 20
153 |  |  | S21-6.18 | Measuretooling balls . The max devi .007ö . | 2007-11-07 |  |  | 2007-11-08 | 2 | [11 empty] | 40
154 |  |  | S21-6.19 | Scan the ôBö flange of Type-B coil | 2007-11-09 |  |  | 2007-11-09 | 1 | [7 empty] | 20
155 |  |  | S21-7.01 | Place ôA/Bö assy, ôAö coil dwn, on 40deg fix. | 2007-11-12 |  |  | 2007-11-14 | 3 | [7 empty] | 60
156 |  |  | S21-7.02 | Align to the conical seats locking into a min of | 2007-11-15 |  |  | 2007-11-15 | 1 | [11 empty] | 20
157 |  |  | S21-7.03 | Measure the monuments on the fixture & the walls | 2007-11-16 |  |  | 2007-11-19 | 2 | [11 empty] | 40
158 |  |  | S21-7.04 | Place initial set metal shims on the coil | 2007-11-20 |  |  | 2007-11-21 | 2 | [7 empty] | 40
159 |  |  | S21-7.05 | Lower the Type-C coil onto the Type-B coil. | 2007-11-22 |  |  | 2007-11-22 | 1 | [7 empty] | 20
160 |  |  | S21-7.06 | Meas monuments on A coil to eval displacement. | 2007-11-23 |  |  | 2007-11-23 | 1 | [11 empty] | 20
161 |  |  | S21-7.07 | Perform the X-Y positioning of the coil. | 2007-11-26 |  |  | 2007-11-26 | 1 | [7 empty] | 20
162 |  |  | S21-7.08 | Install remaining metal shims torque to 50% | 2007-11-27 |  |  | 2007-11-28 | 2 | [7 empty] | 40
163 |  |  | S21-7.09 | "wiggle" test Tighten bolt and recheck. | 2007-12-03 |  |  | 2007-12-03 | 1 | [7 empty] | 20
164 |  |  | S21-7.1 | Measure the tooling balls on all coils. | 2007-12-04 |  |  | 2007-12-10 | 5 | [11 empty] | 100
165 |  |  | S21-7.11 | Adjust shims locally. Re-torque all studs to 50% | 2007-12-11 |  |  | 2007-12-13 | 3 | [7 empty] | 60
166 |  |  | S21-7.12 | Iinstall alumina shims. Re-torque all studs to | 2007-12-14 |  |  | 2007-12-14 | 1 | [7 empty] | 20
167 |  |  | S21-7.13 | "wiggle" test Tighten bolt and recheck. | 2007-12-17 |  |  | 2007-12-17 | 1 | [7 empty] | 20
168 |  |  | S21-7.14 | Measure the tooling balls on all coils. | 2007-12-18 |  |  | 2008-01-02 | 5 | [7 empty] | 100
169 |  |  | S21-7.15 | adjust shims locally. Re-torque all studs to 50 | 2008-01-03 |  |  | 2008-01-07 | 3 | [7 empty] | 60
170 |  |  | S21-7.16 | Install bushing. | 2008-01-08 |  |  | 2008-01-09 | 2 | [7 empty] | 30
171 |  |  | S21-7.17 | Complete tightening of flange bolts to 100%. | 2008-01-10 |  |  | 2008-01-10 | 1 | [7 empty] | 20
172 |  |  | S21-7.18 | Final metrology meas. Scan ôBö flangeType-C coil | 2008-01-14 |  |  | 2008-01-18 | 5 | [11 empty] | 100
173 |  |  | S21-8.01 | Tack weld inboard shims | 2008-01-21 |  |  | 2008-01-22 | 2 | [7 empty] | 40
174 |  |  | S21-9.01 | Install trim coil | 2008-01-23 |  |  | 2008-01-30 | 6 | [7 empty] | 120
175 |  | S2P1 Total | [14 empty] | 1755 |  |  |  | 740
176 |  | S2P2 | S23-A3B3C3 | Assemble/Align Mod-Coils A3/B3/C3 | 2008-02-15 |  |  | 2008-07-31 | 118 | [7 empty] | 1755 |  |  |  | 740
177 |  |  | S24-A4B4C4 | Assemble/Align Mod-Coils A4/B4/C4 | 2008-03-20 |  |  | 2008-07-10 | 79 | [7 empty] | 970 |  |  |  | 620
178 |  | S2P2 Total | [14 empty] | 2725 |  |  |  | 1360
179 |  | S2P3 | S25-A5B5C5 | Assemble/Align Mod-Coils A5/B5/C5 | 2008-09-02 |  |  | 2009-02-25 | 118 | [7 empty] | 1755 |  |  |  | 740
180 |  |  | S26-A6B6C6 | Assemble/Align Mod-Coils A6/B6/C6 | 2008-10-06 |  |  | 2009-02-04 | 79 | [7 empty] | 970 |  |  |  | 620
181 |  | S2P3 Total | [14 empty] | 2725 |  |  |  | 1360
182 |  | S2PM | S21-1.01 | Verify mating MC's A1,B1,C1 | 2007-05-01 |  |  | 2007-05-04 | 4 | [7 empty] | 80
183 |  |  | S21-1.02 | Epoxy paint all close fitting interfacing surfac | 2007-05-07 |  |  | 2007-05-09 | 3 | [7 empty] | 60
184 |  |  | S21-2.01 | Set A1 on pre-measured fixt, "B" side down | 2007-05-10 |  |  | 2007-05-10 | 1 | [7 empty] | 20
185 |  |  | S21-2.02 | Align to the conical seats locking into of 8 | 2007-05-11 |  |  | 2007-05-14 | 2 | [11 empty] | 40
186 |  |  | S21-2.03 | Estab global coord sys on mc geometry. Meas monu | 2007-05-15 |  |  | 2007-05-23 | 7 | [11 empty] | 140
187 |  |  | S21-2.04 | Meas tooling ball monuments on winding form. | 2007-05-24 |  |  | 2007-05-24 | 1 | [11 empty] | 20
188 |  |  | S21-2.05 | Scan the "A" flange of the Type-A1 coil. | 2007-05-25 |  |  | 2007-05-25 | 1 | [11 empty] | 20
189 |  |  | S21-2.07 | Remove A1 coil from stand | 2007-05-29 |  |  | 2007-05-29 | 1 | [7 empty] | 20
190 |  |  | S21-2.08 | Measure B1 "A" flange | 2007-05-30 |  |  | 2007-06-18 | 14 | [7 empty] | 40 |  |  |  | 220
191 |  |  | S21-2.11 | Measure C1 "A" flange | 2007-06-19 |  |  | 2007-07-06 | 13 | [7 empty] | 40 |  |  |  | 220
192 |  |  | S21-2.14 | Measure Type A1-A2 "A" flange | 2007-07-09 |  |  | 2007-07-25 | 13 | [7 empty] | 40 |  |  |  | 220
193 |  |  | S21-3.02 | Grind shims first article f/assy process qu | 2007-07-26 |  |  | 2007-07-31 | 4 | [7 empty] | 80
194 |  |  | S21-3.03 | Ready For Preassembly A1B1C1 |  |  |  | 2007-08-02 | 0
195 |  |  | S21-4.02 | Perform metrology set-up and checks | 2007-08-01 |  |  | 2007-08-02 | 2 | [11 empty] | 40
196 |  |  | S22-1.01 | Verify mating MC's of MCHP will come together | 2007-08-03 |  |  | 2007-08-08 | 4 | [7 empty] | 80
197 |  |  | S22-1.02 | Epoxy paint all close fitting interfacing surfac | 2007-08-09 |  |  | 2007-08-13 | 3 | [7 empty] | 60
198 |  |  | S22-2.08 | Set Type-B coil on fixt, ôBö side flange down. | 2007-08-14 |  |  | 2007-08-15 | 2 | [7 empty] | 40
199 |  |  | S22-2.09 | Steps 2.02 thru 2.04 scan the "A" side flange. | 2007-08-16 |  |  | 2007-08-22 | 5 | [11 empty] | 100
200 |  |  | S22-2.1 | Remove Type-B coil from stand and store coil. | 2007-08-23 |  |  | 2007-08-23 | 1 | [7 empty] | 20
201 |  |  | S22-2.11 | Set Type-C coil on fixt, ôBö side flange down. | 2007-08-24 |  |  | 2007-08-24 | 1 | [7 empty] | 20
202 |  |  | S22-2.12 | Steps 2.02 thru 2.04 scan the "A" side flange. | 2007-08-27 |  |  | 2007-08-31 | 5 | [11 empty] | 100
203 |  |  | S22-2.13 | Remove Type-C coil from stand and store coil. | 2007-09-04 |  |  | 2007-09-04 | 1 | [7 empty] | 20
204 |  |  | S22-3.02 | Compress alumina shims sort by thickness | 2007-09-05 |  |  | 2007-09-07 | 3 | [7 empty] | 60
205 |  |  | S22-4.02 | Perform metrology set-up and checks | 2007-09-10 |  |  | 2007-09-11 | 2 | [11 empty] | 40
206 |  |  | S22-4.03 | Ready For Preassembly A2B2C2 |  |  |  | 2007-09-11 | 0
207 |  |  | S23-1.01 | Verify mating MC's of MCHP will come together | 2007-09-12 |  |  | 2007-09-17 | 4 | [7 empty] | 80
208 |  |  | S23-1.02 | Epoxy paint all close fitting interfacing surfac | 2007-09-18 |  |  | 2007-09-20 | 3 | [7 empty] | 60
209 |  |  | S23-2.01 | Set the A3 coil on fixture, A side flange down | 2007-09-21 |  |  | 2007-09-21 | 1 | [7 empty] | 20
210 |  |  | S23-2.02 | Align to the conical seats locking into min of 8 | 2007-09-24 |  |  | 2007-09-25 | 2 | [11 empty] | 40
211 |  |  | S23-2.03 | Measure monuments on fixture and walls. | 2007-09-26 |  |  | 2007-10-04 | 7 | [11 empty] | 140
212 |  |  | S23-2.04 | Measure tooling ball monuments | 2007-10-05 |  |  | 2007-10-05 | 1 | [11 empty] | 20
213 |  |  | S23-2.05 | Scan the B flange of A3 | 2007-10-08 |  |  | 2007-10-08 | 1 | [11 empty] | 20
214 |  |  | S23-2.07 | Remove A3 move to holding area. | 2007-10-09 |  |  | 2007-10-09 | 1 | [7 empty] | 20
215 |  |  | S23-2.08 | Measure B3 "A" flange | 2007-10-10 |  |  | 2007-10-29 | 14 | [7 empty] | 40 |  |  |  | 220
216 |  |  | S23-2.11 | Measure C3 "A" flange | 2007-10-30 |  |  | 2007-11-15 | 13 | [7 empty] | 40 |  |  |  | 220
217 |  |  | S23-2.14 | Measure Type A3-A4 "A" flange | 2007-11-16 |  |  | 2007-12-06 | 13 | [7 empty] | 40 |  |  |  | 220
218 |  |  | S23-3.02 | Compress alumina shims sort by thickness | 2007-12-07 |  |  | 2007-12-12 | 4 | [7 empty] | 60
219 |  |  | S23-4.02 | Perform metrology set-up and checks | 2007-12-13 |  |  | 2007-12-14 | 2 | [11 empty] | 40
220 |  |  | S23-4.03 | Ready For Preassembly A3B3C3 | 2007-12-17 |  |  | 2007-12-14 | 0
221 |  |  | S24-1.01 | Verify mating MC's of MCHP will come together | 2007-12-17 |  |  | 2007-12-20 | 4 | [7 empty] | 80
222 |  |  | S24-1.02 | Epoxy paint all close fitting interfacing surfac | 2007-12-21 |  |  | 2008-01-03 | 3 | [7 empty] | 60
223 |  |  | S24-2.01 | Set the A4 coil on fixture, A side flange down | 2008-01-04 |  |  | 2008-01-04 | 1 | [7 empty] | 20
224 |  |  | S24-2.02 | Align to the conical seats locking into min of 8 | 2008-01-07 |  |  | 2008-01-08 | 2 | [11 empty] | 40
225 |  |  | S24-2.03 | Measure monuments on fixture and walls. | 2008-01-09 |  |  | 2008-01-10 | 2 | [11 empty] | 40
226 |  |  | S24-2.04 | Measure tooling ball monuments | 2008-01-11 |  |  | 2008-01-11 | 1 | [11 empty] | 20
227 |  |  | S24-2.05 | Scan the B flange of A4 | 2008-01-14 |  |  | 2008-01-14 | 1 | [11 empty] | 20
228 |  |  | S24-2.06 | Flip A4 "B" side dwn scan scan flange A | 2008-01-15 |  |  | 2008-01-21 | 5 | [7 empty] | 100
229 |  |  | S24-2.07 | Remove A4 move to holding area. | 2008-01-22 |  |  | 2008-01-22 | 1 | [7 empty] | 20
230 |  |  | S24-2.08 | Set B4 coil on fixt, B flange down. | 2008-01-23 |  |  | 2008-01-24 | 2 | [7 empty] | 40
231 |  |  | S24-2.09 | Steps 2.02 thru 2.04 scan the "A" side flange. | 2008-01-25 |  |  | 2008-01-31 | 5 | [11 empty] | 100
232 |  |  | S24-2.1 | Remove B4 from stand and store coil. | 2008-02-01 |  |  | 2008-02-01 | 1 | [7 empty] | 20
233 |  |  | S24-2.11 | Set C4 on fixt, B flange down. | 2008-02-04 |  |  | 2008-02-04 | 1 | [7 empty] | 20
234 |  |  | S24-2.12 | Steps 2.02 thru 2.04 scan the "A" side flange. | 2008-02-05 |  |  | 2008-02-11 | 5 | [11 empty] | 100
235 |  |  | S24-2.13 | Remove C4 coil from stand and store coil. | 2008-02-12 |  |  | 2008-02-12 | 1 | [7 empty] | 20
236 |  |  | S24-2.14 | Set MCHP A4 coil on fix, A flange dw | 2008-02-13 |  |  | 2008-02-13 | 1 | [7 empty] | 20
237 |  |  | S24-2.15 | Steps 2.02 thru 2.04scan the "B" side flange. | 2008-02-14 |  |  | 2008-02-20 | 5 | [11 empty] | 100
238 |  |  | S24-3.02 | Compress alumina shims sort by thickness | 2008-02-21 |  |  | 2008-02-26 | 4 | [7 empty] | 60
239 |  |  | S24-4.02 | Perform metrology set-up and checks | 2008-02-27 |  |  | 2008-02-28 | 2 | [11 empty] | 40
240 |  |  | S24-4.03 | Ready For Preassembly A4B4C4 | 2008-02-29 |  |  | 2008-02-28 | 0
241 |  |  | S25-1.01 | Verify mating MC's of MCHP will come together | 2008-02-29 |  |  | 2008-03-05 | 4 | [7 empty] | 80
242 |  |  | S25-1.02 | Epoxy paint all close fitting interfacing surfac | 2008-03-06 |  |  | 2008-03-10 | 3 | [7 empty] | 60
243 |  |  | S25-2.01 | Set the A5 coil on fixture, A side flange down | 2008-03-11 |  |  | 2008-03-11 | 1 | [7 empty] | 20
244 |  |  | S25-2.02 | Align to the conical seats locking into min of 8 | 2008-03-12 |  |  | 2008-03-13 | 2 | [11 empty] | 40
245 |  |  | S25-2.03 | Measure monuments on fixture and walls. | 2008-03-14 |  |  | 2008-03-24 | 7 | [11 empty] | 140
246 |  |  | S25-2.04 | Measure tooling ball monuments | 2008-03-25 |  |  | 2008-03-25 | 1 | [11 empty] | 20
247 |  |  | S25-2.05 | Scan the B flange of A5 | 2008-03-26 |  |  | 2008-03-26 | 1 | [11 empty] | 20
248 |  |  | S25-2.07 | Remove A5 move to holding area. | 2008-03-27 |  |  | 2008-03-27 | 1 | [7 empty] | 20
249 |  |  | S25-2.08 | Measure B5 "A" flange | 2008-03-28 |  |  | 2008-04-16 | 14 | [7 empty] | 40 |  |  |  | 220
250 |  |  | S25-2.11 | Measure C5 "A" flange | 2008-04-17 |  |  | 2008-05-05 | 13 | [7 empty] | 40 |  |  |  | 220
251 |  |  | S25-2.14 | Measure Type A5-A6 "A" flange | 2008-05-06 |  |  | 2008-05-22 | 13 | [7 empty] | 40 |  |  |  | 220
252 |  |  | S25-3.02 | Compress alumina shims sort by thickness | 2008-05-23 |  |  | 2008-05-29 | 4 | [7 empty] | 60
253 |  |  | S25-4.02 | Perform metrology set-up and checks | 2008-05-30 |  |  | 2008-06-02 | 2 | [11 empty] | 40
254 |  |  | S25-4.03 | Ready For Preassembly A5B5C5 | 2008-06-03 |  |  | 2008-06-02 | 0
255 |  |  | S26-1.01 | Verify mating MC's of MCHP will come together | 2008-06-03 |  |  | 2008-06-06 | 4 | [7 empty] | 80
256 |  |  | S26-1.02 | Epoxy paint all close fitting interfacing surfac | 2008-06-09 |  |  | 2008-06-11 | 3 | [7 empty] | 60
257 |  |  | S26-2.01 | Set the A6 coil on fixture, A side flange down | 2008-06-12 |  |  | 2008-06-12 | 1 | [7 empty] | 20
258 |  |  | S26-2.02 | Align to the conical seats locking into min of 8 | 2008-06-13 |  |  | 2008-06-16 | 2 | [11 empty] | 40
259 |  |  | S26-2.03 | Measure monuments on fixture and walls. | 2008-06-17 |  |  | 2008-06-18 | 2 | [11 empty] | 40
260 |  |  | S26-2.04 | Measure tooling ball monuments | 2008-06-19 |  |  | 2008-06-19 | 1 | [11 empty] | 20
261 |  |  | S26-2.05 | Scan the B flange of A6 | 2008-06-20 |  |  | 2008-06-20 | 1 | [11 empty] | 20
262 |  |  | S26-2.06 | Flip A6 "B" side dwn scan scan flange A | 2008-06-23 |  |  | 2008-06-27 | 5 | [7 empty] | 100
263 |  |  | S26-2.07 | Remove A6 move to holding area. | 2008-06-30 |  |  | 2008-06-30 | 1 | [7 empty] | 20
264 |  |  | S26-2.08 | Set B6 coil on fixt, B flange down. | 2008-07-01 |  |  | 2008-07-02 | 2 | [7 empty] | 40
265 |  |  | S26-2.09 | Steps 2.02 thru 2.04 scan the "A" side flange. | 2008-07-03 |  |  | 2008-07-10 | 5 | [11 empty] | 100
266 |  |  | S26-2.1 | Remove B6 from stand and store coil. | 2008-07-11 |  |  | 2008-07-11 | 1 | [7 empty] | 20
267 |  |  | S26-2.11 | Set C6 on fixt, B flange down. | 2008-07-14 |  |  | 2008-07-14 | 1 | [7 empty] | 20
268 |  |  | S26-2.12 | Steps 2.02 thru 2.04 scan the "A" side flange. | 2008-07-15 |  |  | 2008-07-21 | 5 | [11 empty] | 100
269 |  |  | S26-2.13 | Remove C6 coil from stand and store coil. | 2008-07-22 |  |  | 2008-07-22 | 1 | [7 empty] | 20
270 |  |  | S26-2.14 | Set MCHP A6 coil on fix, A flange dw | 2008-07-23 |  |  | 2008-07-23 | 1 | [7 empty] | 20
271 |  |  | S26-2.15 | Steps 2.02 thru 2.04scan the "B" side flange. | 2008-07-24 |  |  | 2008-07-30 | 5 | [11 empty] | 100
272 |  |  | S26-3.02 | Compress alumina shims sort by thickness | 2008-07-31 |  |  | 2008-08-05 | 4 | [7 empty] | 60
273 |  |  | S26-4.02 | Perform metrology set-up and checks | 2008-08-06 |  |  | 2008-08-07 | 2 | [11 empty] | 40
274 |  |  | S26-4.03 | Ready For Preassembly A6B6C6 | 2008-08-08 |  |  | 2008-08-07 | 0
275 |  | S2PM Total | [14 empty] | 2320 |  |  |  | 3920
276 |  | S2PR | R1810-2001 | Misc Hardware and hardware rework (1/2 fte loe) | 2007-05-01 |  |  | 2008-05-14 | 260 | 1 |  | 10 |  |  |  |  | 960
277 |  |  | R1810-2003 | Trial tensioning test on prototype | 2007-06-01 |  |  | 2007-06-05 | 3 | 1 |  | 3 |  |  |  |  | 40
278 |  |  | R1810-2005 | Trial bushing and shim test on prototype | 2007-06-01 |  |  | 2007-06-18 | 12 | 1 |  | 2 |  |  |  |  | 240
279 |  |  | R1810-2009 | Perform trial x-y-z alignments on A1-A2. | 2007-06-01 |  |  | 2007-06-11 | 7 | 1 |  | 2 |  |  |  |  | 140
280 |  |  | R1810-2010 | Perform developmental trials on A1-A2. | 2007-06-12 |  |  | 2007-07-24 | 30 | 1 |  | 2 |  |  |  |  | 600
281 |  |  | R1810-2011 | Alignment mechanisms, metro equipt &positioning | 2007-07-25 |  |  | 2007-08-01 | 6 | 1 |  | 40 |  |  |  |  | 120
282 |  |  | R1810-2013 | Procure alignment mechanisms, fiducials, lifting | 2007-06-01 |  |  | 2007-06-28 | 20 | 1 |  | 25 |  |  |  |  | 400
283 |  |  | R1810-2015 | Develop procedures for torquing bolts | 2007-06-01 |  |  | 2007-06-06 | 4 | 1 | [6 empty] | 80
284 |  |  | R1810-2017 | Determine fiducial types&locations | 2007-06-07 |  |  | 2007-06-21 | 11 | 1 |  | 2 |  |  |  |  | 220
285 |  |  | R1810-2019 | Procure monuments&related metrology equipment | 2007-06-01 |  |  | 2007-06-21 | 15 | 1 |  | 15 |  |  |  |  | 300
286 |  |  | R1810-2050 | Weld trials f/nose welding (in job 1421 | 2007-07-11 |  |  | 2007-07-30 | 14 | 1 |  | 70
287 |  | S2PR Total | [9 empty] | 171 |  |  |  |  | 3100
288 |  | S2PX | R1810-2002 | Test out Equip & Procedures | 2007-10-11 |  |  | 2007-10-19 | 7 | 1 | [6 empty] | 140
289 |  |  | R1810-2004 | Receive Drawings & Hardware (shims & Bolts) | 2007-08-16 |  |  | 2007-08-24 | 7 | 1 | [6 empty] | 140
290 |  |  | R1810-2006 | Surface grind set of metal shims for qualificat | 2007-09-04 |  |  | 2007-09-07 | 4 | 1 | [6 empty] | 240
291 |  |  | R1810-2021 | Tools&tooling available for FPA operations | 2007-08-17 |  |  | 2007-08-20 | 2 | 1 |  | 5 |  |  |  |  | 40
292 |  |  | R1810-2023 | Install FIRST Holding 20 deg fixture | 2007-05-01 |  |  | 2007-05-04 | 4 | 1 |  | 2 |  |  |  |  | 80
293 |  |  | R1810-2025 | Install SECOND Holding 20 deg fixture | 2007-08-01 |  |  | 2007-08-03 | 3 | 1 |  | 2 |  |  |  |  | 60
294 |  |  | R1810-2027 | Install THIRD Holding 20 deg fixture | 2007-08-06 |  |  | 2007-08-13 | 6 | 1 |  | 2 |  |  |  |  | 120
295 |  |  | R1810-2029 | Install LAST Holding 20 deg fixture | 2007-08-14 |  |  | 2007-08-16 | 3 | 1 |  | 2 |  |  |  |  | 60
296 |  |  | R1810-207 | Compress alumina shims and sort | 2007-10-12 |  |  | 2007-10-19 | 6 | 1 | [6 empty] | 120
297 |  |  | R1810-209 | Perform metrology setup & checks | 2007-09-17 |  |  | 2007-10-16 | 22 | 1 | [6 empty] | 100
298 |  |  | R1810-2108 | HARDWARE,DRAWINGS,& PROCURES AVAILABLE STATION 2 |  |  |  | 2007-10-19 | 0 | 1
299 |  | S2PX Total | [9 empty] | 13 |  |  |  |  | 1100
300 |  | S2PZ | S22-10.01 | Install all wing support bladders | 2008-02-13 |  |  | 2008-02-14 | 2 | [7 empty] | 40
301 |  |  | S22-10.02 | local service connections on each MC. | 2008-02-15 |  |  | 2008-02-26 | 8 | [7 empty] | 160
302 |  |  | S22-10.03 | Inject stycast to fill in all shim spaces | 2008-02-27 |  |  | 2008-02-27 | 1 | [7 empty] | 20
303 |  |  | S22-11.01 | Install or identify three primary fiducials | 2008-02-28 |  |  | 2008-02-28 | 1 | [7 empty] | 20
304 |  |  | S22-11.02 | Final metrology measurement of all fiducials. | 2008-02-29 |  |  | 2008-03-06 | 5 | [11 empty] | 100
305 |  |  | S22-11.03 | Tension tester measure bolt length | 2008-03-07 |  |  | 2008-03-07 | 1 | [7 empty] | 10
306 |  |  | S22-11.04 | Mark part for identification | 2008-03-10 |  |  | 2008-03-07 | 0 | [7 empty] | 0
307 |  |  | S22-11.05 | Install lift support beams | 2008-03-10 |  |  | 2008-03-11 | 2 | [7 empty] | 40
308 |  |  | S22-11.06 | Remove from stand Move A2-B2-C2 to holding area | 2008-03-12 |  |  | 2008-03-13 | 2 | [7 empty] | 40
309 |  |  | S22-6.01 | A2 ôAö flange dwn, 20deg fixt.Obtain fiduci | 2007-11-12 |  |  | 2007-11-12 | 1 | [7 empty] | 20
310 |  |  | S22-6.02 | Align to the conical seats locking into a min of | 2007-11-13 |  |  | 2007-11-13 | 1 | [11 empty] | 20
311 |  |  | S22-6.03 | Measure monuments on fixture and on the walls. | 2007-11-14 |  |  | 2007-11-15 | 2 | [11 empty] | 40
312 |  |  | S22-6.04 | Place alumina grind inboard weld shims on coil. | 2007-11-16 |  |  | 2007-11-19 | 2 | [7 empty] | 40
313 |  |  | S22-6.05 | Lower the Type-B coil onto the Type-A coil. | 2007-11-20 |  |  | 2007-11-20 | 1 | [7 empty] | 20
314 |  |  | S22-6.06 | Meas monuments on A coil. Jack to within .002ö | 2007-11-21 |  |  | 2007-11-21 | 1 | [11 empty] | 20
315 |  |  | S22-6.07 | Perform the X-Y positioning of the B coil. | 2007-11-22 |  |  | 2007-11-22 | 1 | [11 empty] | 20
316 |  |  | S22-6.08 | Install studs, supernuts, torque to 50% of final | 2007-11-23 |  |  | 2007-11-26 | 2 | [7 empty] | 40
317 |  |  | S22-6.09 | "wiggle" test Tighten bolt and recheck. | 2007-11-27 |  |  | 2007-11-27 | 1 | [7 empty] | 20
318 |  |  | S22-6.1 | Meas tooling balls on both coils. max devi .007ö | 2007-11-28 |  |  | 2007-12-06 | 5 | [11 empty] | 100
319 |  |  | S22-6.11 | Adjust shims locally. Re-torque all studs to 50% | 2007-12-07 |  |  | 2007-12-11 | 3 | [7 empty] | 60
320 |  |  | S22-6.12 | Install bushing. | 2007-12-12 |  |  | 2007-12-13 | 2 | [7 empty] | 30
321 |  |  | S22-6.13 | Complete tightening of flange bolts to 100%. | 2007-12-14 |  |  | 2007-12-14 | 1 | [7 empty] | 20
322 |  |  | S22-6.14 | Measure the tooling balls on both coils. | 2007-12-17 |  |  | 2007-12-19 | 3 | [11 empty] | 60
323 |  |  | S22-6.15 | Scan the ôBö flange of Type-B coil | 2007-12-20 |  |  | 2007-12-20 | 1 | [7 empty] | 20
324 |  |  | S22-7.01 | ôA/Bö assy ôAö coil dwn, 40deg fixt.Obtain fiduc | 2007-12-21 |  |  | 2008-01-02 | 2 | [7 empty] | 40
325 |  |  | S22-7.02 | Align to the conical seats locking into min of 8 | 2008-01-03 |  |  | 2008-01-03 | 1 | [11 empty] | 20
326 |  |  | S22-7.03 | Measure monuments on fixture and walls. | 2008-01-04 |  |  | 2008-01-07 | 2 | [11 empty] | 40
327 |  |  | S22-7.04 | Place alumin grind inboard weld shims on coil. | 2008-01-08 |  |  | 2008-01-09 | 2 | [7 empty] | 40
328 |  |  | S22-7.05 | Lower the Type-C coil onto the Type-B coil. | 2008-01-10 |  |  | 2008-01-10 | 1 | [7 empty] | 20
329 |  |  | S22-7.06 | Meas monuments on A coil for displacements. | 2008-01-11 |  |  | 2008-01-11 | 1 | [11 empty] | 20
330 |  |  | S22-7.07 | Perform the X-Y positioning of the coil. | 2008-01-14 |  |  | 2008-01-14 | 1 | [7 empty] | 20
331 |  |  | S22-7.08 | Install studs, supernuts, torque to 50% of fina | 2008-01-15 |  |  | 2008-01-16 | 2 | [7 empty] | 40
332 |  |  | S22-7.09 | "wiggle" test Tighten bolt and recheck. | 2008-01-17 |  |  | 2008-01-17 | 1 | [7 empty] | 20
333 |  |  | S22-7.1 | Measure the tooling balls on all coils. | 2008-01-18 |  |  | 2008-01-24 | 5 | [11 empty] | 100
334 |  |  | S22-7.11 | Install bushing. Replace nut and tighten to 50% | 2008-01-25 |  |  | 2008-01-25 | 1 | [7 empty] | 30
335 |  |  | S22-7.12 | Complete tightening of flange bolts to 100%. | 2008-01-28 |  |  | 2008-01-28 | 1 | [7 empty] | 20
336 |  |  | S22-7.13 | Measure the tooling balls on both coils. | 2008-01-29 |  |  | 2008-02-01 | 4 | [11 empty] | 80
337 |  |  | S22-8.01 | Tack weld all inboard shims to one flange | 2008-02-04 |  |  | 2008-02-04 | 1 | [7 empty] | 20
338 |  |  | S22-9.01 | Install trim coil | 2008-02-05 |  |  | 2008-02-12 | 6 | [7 empty] | 120
339 |  | S2PZ Total | [14 empty] | 970 |  |  |  | 620
340 |  | S3P0 | R1810-3102 | Misc M&S | 2008-04-03 |  |  | 2008-07-03 | 65 | 1 |  | 5
341 |  |  | R1810-3103 | Install station 3 platforms (8 required) | 2007-10-30 |  |  | 2007-11-02 | 4 | 1 |  | 10 |  |  |  |  | 112
342 |  |  | R1810-3104 | Procure 3 legged actuator system | 2007-10-01 |  |  | 2007-10-26 | 20 | 1 |  | 43
343 |  |  | R1810-3106 | Load test 3 ledded actuator system | 2007-10-29 |  |  | 2007-10-31 | 3 | 1 | [6 empty] | 96
344 |  |  | R1810-3107 | Test out station 3 equipment and procedures | 2007-11-05 |  |  | 2007-11-08 | 4 | 1 |  | 10
345 |  |  | R1810-3108 | Procure ,Fabricate 3 legged actuator lift fixtur | 2007-10-01 |  |  | 2007-10-26 | 20 | 1 |  | 6
346 |  |  | R1810-3109 | Begin assy of first field period assy | 2007-11-09 |  |  | 2007-11-12 | 2 | 1 |  | 40
347 |  |  | R1810-3112 | Load Test 3 legged actuator lift fixtur | 2007-10-29 |  |  | 2007-11-07 | 8 | 1 | [6 empty] | 128
348 |  |  | R1810-3150 | Fab New legs | 2007-10-01 |  |  | 2007-10-04 | 4 | 1 | [6 empty] | 64
349 |  | S3P0 Total | [9 empty] | 114 |  |  |  |  | 400
350 |  | S3P1 | R1810-2109 | Begin Station 3 | 2008-01-23 |  |  |  | 0 | 1
351 |  |  | S31-1.01 | Install Station 3 site monuments | 2008-01-23 |  |  | 2008-01-25 | 3 | 1 |  | 2 |  |  |  |  | 60
352 |  |  | S31-1.02 | Install floor mounted tracks and VV base support | 2008-01-28 |  |  | 2008-02-01 | 5 | 1 |  | 1 |  |  |  |  | 100
353 |  |  | S31-1.03 | Establish the MCHP CG location. | 2008-02-04 |  |  | 2008-02-05 | 2 | 1 | [6 empty] | 40
354 |  |  | S31-10.01 | transfer the unit to the transfer support frame | 2008-07-17 |  |  | 2008-07-18 | 2 | 1 | [6 empty] | 80
355 |  |  | S31-10.02 | Transfer Period 1 to Station 5 in NCSX TC | 2008-07-21 |  |  | 2008-07-21 | 1 | 1 | [6 empty] | 40
356 |  |  | S31-2.01 | Install MCHP support cart assemblies | 2008-02-06 |  |  | 2008-02-11 | 4 | 1 | [6 empty] | 80
357 |  |  | S31-2.02 | Verify cart motion. | 2008-02-12 |  |  | 2008-02-13 | 2 | 1 | [6 empty] | 40
358 |  |  | S31-2.03 | Install adjustor bar support weldment | 2008-02-14 |  |  | 2008-02-13 | 0 | 1 | [6 empty] | 0
359 |  |  | S31-2.04 | Position left MCHP on the cart assembly | 2008-02-15 |  |  | 2008-02-15 | 1 | 1 | [6 empty] | 20
360 |  |  | S31-2.05 | Secure left MCHP on support cart base. | 2008-02-18 |  |  | 2008-02-19 | 2 | 1 | [6 empty] | 40
361 |  |  | S31-2.06 | Measure monuments on left MCHP and walls | 2008-02-20 |  |  | 2008-02-26 | 5 | 1 | [6 empty] | 0 |  |  |  | 100
362 |  |  | S31-2.07 | Set positioning stop on the cart | 2008-02-27 |  |  | 2008-02-27 | 1 | 1 | [6 empty] | 20
363 |  |  | S31-3.01 | Move right base support cart to its final positi | 2008-02-28 |  |  | 2008-02-28 | 1 | 1 | [6 empty] | 10
364 |  |  | S31-3.02 | Lift the right side MCHP and position | 2008-03-14 |  |  | 2008-03-14 | 1 | 1 | [6 empty] | 20
365 |  |  | S31-3.03 | Temporary fasteners bring the parts together. | 2008-03-17 |  |  | 2008-03-14 | 0 | 1 | [6 empty] | 0
366 |  |  | S31-3.04 | AirLoc Wedgemount leveler to take load. | 2008-03-17 |  |  | 2008-03-14 | 0 | 1 | [6 empty] | 0
367 |  |  | S31-3.05 | Install temp scaffolding to install flange hw | 2008-03-17 |  |  | 2008-03-17 | 1 | 1 | [6 empty] | 20
368 |  |  | S31-3.06 | Install bolts and shims | 2008-03-18 |  |  | 2008-03-18 | 1 | 1 | [6 empty] | 20
369 |  |  | S31-3.07 | Tighten flange fasteners to 50% | 2008-03-19 |  |  | 2008-03-19 | 1 | 1 | [6 empty] | 20
370 |  |  | S31-3.08 | Perform metrology measurements | 2008-03-20 |  |  | 2008-03-26 | 5 | 1 | [6 empty] | 0 |  |  |  | 100
371 |  |  | S31-3.09 | Perform position adjust on right side MCHP | 2008-03-27 |  |  | 2008-03-28 | 2 | 1 | [6 empty] | 40
372 |  |  | S31-3.1 | Verify position of the VV support hanger | 2008-03-31 |  |  | 2008-04-02 | 3 | 1 | [6 empty] | 0 |  |  |  | 60
373 |  |  | S31-3.11 | Remove flange hardware and temp platforms | 2008-04-03 |  |  | 2008-04-03 | 1 | 1 | [6 empty] | 20
374 |  |  | S31-4.01 | EMeasure monuments on the MCHP's &walls. | 2008-04-04 |  |  | 2008-04-07 | 2 | 1 |  | 2 |  |  |  |  | 0 |  |  |  | 40
375 |  |  | S31-4.02 | Place all of the laser screens | 2008-04-08 |  |  | 2008-04-09 | 2 | 1 | [6 empty] | 40
376 |  |  | S31-4.03 | Determine laser alignment. | 2008-04-10 |  |  | 2008-04-10 | 1 | 1 | [6 empty] | 20
377 |  |  | S31-4.04 | mount the milar on the screens. | 2008-04-11 |  |  | 2008-04-11 | 1 | 1 | [6 empty] | 0
378 |  |  | S31-4.05 | Disengage MCHP's to move the left MCHP. | 2008-04-14 |  |  | 2008-04-14 | 1 | 1 | [6 empty] | 20
379 |  |  | S31-4.06 | Remove both MCHP's. | 2008-04-15 |  |  | 2008-04-16 | 2 | 1 | [6 empty] | 40
380 |  |  | S31-5.01 | Remove the adjustor bar support from left side. | 2008-04-17 |  |  | 2008-04-16 | 0 | 1 | [6 empty] | 0
381 |  |  | S31-5.02 | Install VV NBI port support stand. | 2008-04-17 |  |  | 2008-04-18 | 2 | 1 | [6 empty] | 40
382 |  |  | S31-5.03 | Install VVSA to base support | 2008-04-21 |  |  | 2008-04-21 | 1 | 1 | [6 empty] | 20
383 |  |  | S31-5.04 | Secure the VVSA to base & NBI port sprt stand. | 2008-04-22 |  |  | 2008-04-23 | 2 | 1 | [6 empty] | 40
384 |  |  | S31-6.01 | Install bumper protection components on the VV | 2008-04-24 |  |  | 2008-04-24 | 1 | 1 | [6 empty] | 10
385 |  |  | S31-6.02 | Position AirLoc Wedgemount in lower position. | 2008-04-25 |  |  | 2008-04-24 | 0 | 1 | [6 empty] | 0
386 |  |  | S31-6.03 | move the left MCHP over the VV. | 2008-04-25 |  |  | 2008-04-28 | 2 | 1 | [6 empty] | 40
387 |  |  | S31-6.04 | Re-install the left adjustor bar. | 2008-04-29 |  |  | 2008-04-28 | 0 | 1 | [6 empty] | 0
388 |  |  | S31-6.05 | Make adjustments to properly align MCHP. | 2008-04-29 |  |  | 2008-04-30 | 2 | 1 | [6 empty] | 40
389 |  |  | S31-6.06 | Transfer load to the AirLoc Wedgemount leveler. | 2008-05-01 |  |  | 2008-04-30 | 0 | 1 | [6 empty] | 0
390 |  |  | S31-6.07 | move the MCHP to the left 1/2". | 2008-05-01 |  |  | 2008-04-30 | 0 | 1 | [6 empty] | 0
391 |  |  | S31-7.01 | Position AirLoc Wedgemount lowered position. | 2008-05-01 |  |  | 2008-04-30 | 0 | 1 | [6 empty] | 0
392 |  |  | S31-7.02 | move the right MCHP over the VV | 2008-05-01 |  |  | 2008-05-02 | 2 | 1 | [6 empty] | 40
393 |  |  | S31-7.03 | move the left MCHP to its final position. | 2008-05-05 |  |  | 2008-05-05 | 1 | 1 | [6 empty] | 10
394 |  |  | S31-7.04 | engage the preinstalled Type-A flange bushings. | 2008-05-06 |  |  | 2008-05-06 | 1 | 1 | [6 empty] | 10
395 |  |  | S31-7.05 | Temporary fasteners bring the parts together. | 2008-05-07 |  |  | 2008-05-06 | 0 | 1 | [6 empty] | 0
396 |  |  | S31-7.06 | AirLoc Wedgemount leveler up to take the load. | 2008-05-07 |  |  | 2008-05-07 | 1 | 1 | [6 empty] | 10
397 |  |  | S31-7.07 | Remove laser screens | 2008-05-08 |  |  | 2008-05-07 | 0 | 1 | [6 empty] | 0
398 |  |  | S31-7.08 | Install temp scaffolding to install flange hw | 2008-05-08 |  |  | 2008-05-13 | 4 | 1 | [6 empty] | 80
399 |  |  | S31-7.09 | Install bolts, alumina and inboard weld shims. | 2008-05-14 |  |  | 2008-05-15 | 2 | 1 | [6 empty] | 40
400 |  |  | S31-7.1 | Tighten flange fasteners to 50% | 2008-05-16 |  |  | 2008-05-16 | 1 | 1 | [6 empty] | 20
401 |  |  | S31-7.11 | "wiggle" test Tighten bolt and recheck. | 2008-05-19 |  |  | 2008-05-19 | 1 | 1 | [6 empty] | 20
402 |  |  | S31-7.12 | Perform metrology measurements | 2008-05-20 |  |  | 2008-05-27 | 5 | 1 | [6 empty] | 0 |  |  |  | 100
403 |  |  | S31-7.13 | Perform position adjustments right side MCHP | 2008-05-28 |  |  | 2008-05-30 | 3 | 1 | [6 empty] | 60
404 |  |  | S31-7.14 | Remove SISSCO actuator from right MCHP. | 2008-06-02 |  |  | 2008-05-30 | 0 | 1 | [6 empty] | 0
405 |  |  | S31-7.15 | Install bushing. | 2008-06-02 |  |  | 2008-06-02 | 1 | 1 | [6 empty] | 10
406 |  |  | S31-7.16 | Tighten nuts 100%. & Measure | 2008-06-03 |  |  | 2008-06-03 | 1 | 1 | [6 empty] | 20
407 |  |  | S31-8.01 | partially weld the inboard shim. | 2008-06-04 |  |  | 2008-06-24 | 15 | 1 | [6 empty] | 300
408 |  |  | S31-8.02 | Final complete MC scan verify period alignment. | 2008-06-25 |  |  | 2008-07-01 | 5 | 1 | [6 empty] | 0 |  |  |  | 100
409 |  |  | S31-9.01 | Attach VV permanent vertical supports | 2008-07-02 |  |  | 2008-07-03 | 2 | 1 | [6 empty] | 40
410 |  |  | S31-9.02 | Attach temporary VV vertical supports | 2008-07-07 |  |  | 2008-07-07 | 1 | 1 | [6 empty] | 20
411 |  |  | S31-9.03 | Transfer load to vertical supports. | 2008-07-08 |  |  | 2008-07-08 | 1 | 1 | [6 empty] | 20
412 |  |  | S31-9.04 | Install VV lateral supports and align | 2008-07-09 |  |  | 2008-07-14 | 4 | 1 | [6 empty] | 80
413 |  |  | S31-9.05 | Prepare VVSA for transport. | 2008-07-15 |  |  | 2008-07-16 | 2 | 1 | [6 empty] | 40
414 |  | S3P1 Total | [9 empty] | 5 |  |  |  |  | 1800 |  |  |  | 500
415 |  | S3P2 | S32-1.01 | Install Station 3 site monuments | 2008-07-22 |  |  | 2008-07-24 | 3 | 1 |  | 2 |  |  |  |  | 60
416 |  |  | S32-1.02 | Install floor mounted tracks and VV base support | 2008-07-25 |  |  | 2008-07-31 | 5 | 1 |  | 1 |  |  |  |  | 100
417 |  |  | S32-1.03 | Establish the MCHP CG location. | 2008-08-01 |  |  | 2008-08-04 | 2 | 1 | [6 empty] | 40
418 |  |  | S32-10.01 | transfer the unit to the transfer support frame | 2009-01-09 |  |  | 2009-01-12 | 2 | 1 | [6 empty] | 80
419 |  |  | S32-10.02 | Transfer Period 2 to Station 5 in NCSX TC | 2009-01-13 |  |  | 2009-01-13 | 1 | 1 | [6 empty] | 40
420 |  |  | S32-2.01 | Install MCHP support cart assemblies | 2008-08-05 |  |  | 2008-08-08 | 4 | 1 | [6 empty] | 80
421 |  |  | S32-2.02 | Verify cart motion. | 2008-08-11 |  |  | 2008-08-12 | 2 | 1 | [6 empty] | 40
422 |  |  | S32-2.03 | Install adjustor bar support weldment | 2008-08-13 |  |  | 2008-08-12 | 0 | 1 | [6 empty] | 0
423 |  |  | S32-2.04 | Position left MCHP on the cart assembly | 2008-08-13 |  |  | 2008-08-13 | 1 | 1 | [6 empty] | 20
424 |  |  | S32-2.05 | Secure left MCHP on support cart base. | 2008-08-14 |  |  | 2008-08-15 | 2 | 1 | [6 empty] | 40
425 |  |  | S32-2.06 | Measure monuments on left MCHP and walls | 2008-08-18 |  |  | 2008-08-22 | 5 | 1 | [6 empty] | 0 |  |  |  | 100
426 |  |  | S32-2.07 | Set positioning stop on the cart | 2008-08-25 |  |  | 2008-08-25 | 1 | 1 | [6 empty] | 20
427 |  |  | S32-3.01 | Move right base support cart to its final positi | 2008-08-26 |  |  | 2008-08-26 | 1 | 1 | [6 empty] | 10
428 |  |  | S32-3.02 | Lift the right side MCHP and position | 2008-08-27 |  |  | 2008-08-27 | 1 | 1 | [6 empty] | 20
429 |  |  | S32-3.03 | Temporary fasteners bring the parts together. | 2008-08-28 |  |  | 2008-08-27 | 0 | 1 | [6 empty] | 0
430 |  |  | S32-3.04 | AirLoc Wedgemount leveler to take load. | 2008-08-28 |  |  | 2008-08-27 | 0 | 1 | [6 empty] | 0
431 |  |  | S32-3.05 | Install temp scaffolding to install flange hw | 2008-08-28 |  |  | 2008-08-28 | 1 | 1 | [6 empty] | 20
432 |  |  | S32-3.06 | Install bolts and shims | 2008-08-29 |  |  | 2008-08-29 | 1 | 1 | [6 empty] | 20
433 |  |  | S32-3.07 | Tighten flange fasteners to 50% | 2008-09-02 |  |  | 2008-09-02 | 1 | 1 | [6 empty] | 20
434 |  |  | S32-3.08 | Perform metrology measurements | 2008-09-03 |  |  | 2008-09-09 | 5 | 1 | [6 empty] | 0 |  |  |  | 100
435 |  |  | S32-3.09 | Perform position adjust on right side MCHP | 2008-09-10 |  |  | 2008-09-11 | 2 | 1 | [6 empty] | 40
436 |  |  | S32-3.1 | Verify position of the VV support hanger | 2008-09-12 |  |  | 2008-09-16 | 3 | 1 | [6 empty] | 0 |  |  |  | 60
437 |  |  | S32-3.11 | Remove flange hardware and temp platforms | 2008-09-17 |  |  | 2008-09-17 | 1 | 1 | [6 empty] | 20
438 |  |  | S32-4.01 | EMeasure monuments on the MCHP's &walls. | 2008-09-18 |  |  | 2008-09-19 | 2 | 1 |  | 2 |  |  |  |  | 0 |  |  |  | 40
439 |  |  | S32-4.02 | Place all of the laser screens | 2008-09-22 |  |  | 2008-09-23 | 2 | 1 | [6 empty] | 40
440 |  |  | S32-4.03 | Determine laser alignment. | 2008-09-24 |  |  | 2008-09-24 | 1 | 1 | [6 empty] | 20
441 |  |  | S32-4.04 | mount the milar on the screens. | 2008-09-25 |  |  | 2008-09-25 | 1 | 1 | [6 empty] | 0
442 |  |  | S32-4.05 | Disengage MCHP's to move the left MCHP. | 2008-09-26 |  |  | 2008-09-26 | 1 | 1 | [6 empty] | 20
443 |  |  | S32-4.06 | Remove both MCHP's. | 2008-09-29 |  |  | 2008-09-30 | 2 | 1 | [6 empty] | 40
444 |  |  | S32-5.01 | Remove the adjustor bar support from left side. | 2008-10-01 |  |  | 2008-09-30 | 0 | 1 | [6 empty] | 0
445 |  |  | S32-5.02 | Install VV NBI port support stand. | 2008-10-01 |  |  | 2008-10-02 | 2 | 1 | [6 empty] | 40
446 |  |  | S32-5.03 | Install VVSA to base support | 2008-10-03 |  |  | 2008-10-03 | 1 | 1 | [6 empty] | 20
447 |  |  | S32-5.04 | Secure the VVSA to base & NBI port sprt stand. | 2008-10-06 |  |  | 2008-10-07 | 2 | 1 | [6 empty] | 40
448 |  |  | S32-6.01 | Install bumper protection components on the VV | 2008-10-08 |  |  | 2008-10-08 | 1 | 1 | [6 empty] | 10
449 |  |  | S32-6.02 | Position AirLoc Wedgemount in lower position. | 2008-10-09 |  |  | 2008-10-08 | 0 | 1 | [6 empty] | 0
450 |  |  | S32-6.03 | move the left MCHP over the VV. | 2008-10-09 |  |  | 2008-10-10 | 2 | 1 | [6 empty] | 40
451 |  |  | S32-6.04 | Re-install the left adjustor bar. | 2008-10-13 |  |  | 2008-10-10 | 0 | 1 | [6 empty] | 0
452 |  |  | S32-6.05 | Make adjustments to properly align MCHP. | 2008-10-13 |  |  | 2008-10-14 | 2 | 1 | [6 empty] | 40
453 |  |  | S32-6.06 | Transfer load to the AirLoc Wedgemount leveler. | 2008-10-15 |  |  | 2008-10-14 | 0 | 1 | [6 empty] | 0
454 |  |  | S32-6.07 | move the MCHP to the left 1/2". | 2008-10-15 |  |  | 2008-10-14 | 0 | 1 | [6 empty] | 0
455 |  |  | S32-7.01 | Position AirLoc Wedgemount lowered position. | 2008-10-15 |  |  | 2008-10-14 | 0 | 1 | [6 empty] | 0
456 |  |  | S32-7.02 | move the right MCHP over the VV | 2008-10-15 |  |  | 2008-10-16 | 2 | 1 | [6 empty] | 40
457 |  |  | S32-7.03 | move the left MCHP to its final position. | 2008-10-17 |  |  | 2008-10-17 | 1 | 1 | [6 empty] | 10
458 |  |  | S32-7.04 | engage the preinstalled Type-A flange bushings. | 2008-10-20 |  |  | 2008-10-20 | 1 | 1 | [6 empty] | 10
459 |  |  | S32-7.05 | Temporary fasteners bring the parts together. | 2008-10-21 |  |  | 2008-10-20 | 0 | 1 | [6 empty] | 0
460 |  |  | S32-7.06 | AirLoc Wedgemount leveler up to take the load. | 2008-10-21 |  |  | 2008-10-21 | 1 | 1 | [6 empty] | 10
461 |  |  | S32-7.07 | Remove laser screens | 2008-10-22 |  |  | 2008-10-21 | 0 | 1 | [6 empty] | 0
462 |  |  | S32-7.08 | Install temp scaffolding to install flange hw | 2008-10-22 |  |  | 2008-10-27 | 4 | 1 | [6 empty] | 80
463 |  |  | S32-7.09 | Install bolts, alumina and inboard weld shims. | 2008-10-28 |  |  | 2008-10-29 | 2 | 1 | [6 empty] | 40
464 |  |  | S32-7.1 | Tighten flange fasteners to 50% | 2008-10-30 |  |  | 2008-10-30 | 1 | 1 | [6 empty] | 20
465 |  |  | S32-7.11 | "wiggle" test Tighten bolt and recheck. | 2008-10-31 |  |  | 2008-10-31 | 1 | 1 | [6 empty] | 20
466 |  |  | S32-7.12 | Perform metrology measurements | 2008-11-03 |  |  | 2008-11-07 | 5 | 1 | [6 empty] | 0 |  |  |  | 100
467 |  |  | S32-7.13 | Perform position adjustments right side MCHP | 2008-11-10 |  |  | 2008-11-12 | 3 | 1 | [6 empty] | 60
468 |  |  | S32-7.14 | Remove SISSCO actuator from right MCHP. | 2008-11-13 |  |  | 2008-11-12 | 0 | 1 | [6 empty] | 0
469 |  |  | S32-7.15 | Install bushing. | 2008-11-13 |  |  | 2008-11-13 | 1 | 1 | [6 empty] | 10
470 |  |  | S32-7.16 | Tighten nuts 100%. & Measure | 2008-11-14 |  |  | 2008-11-14 | 1 | 1 | [6 empty] | 20
471 |  |  | S32-8.01 | partially weld the inboard shim. | 2008-11-17 |  |  | 2008-12-09 | 15 | 1 | [6 empty] | 300
472 |  |  | S32-8.02 | Final complete MC scan verify period alignment. | 2008-12-10 |  |  | 2008-12-16 | 5 | 1 | [6 empty] | 0 |  |  |  | 100
473 |  |  | S32-9.01 | Attach VV permanent vertical supports | 2008-12-17 |  |  | 2008-12-18 | 2 | 1 | [6 empty] | 40
474 |  |  | S32-9.02 | Attach temporary VV vertical supports | 2008-12-19 |  |  | 2008-12-19 | 1 | 1 | [6 empty] | 20
475 |  |  | S32-9.03 | Transfer load to vertical supports. | 2008-12-22 |  |  | 2008-12-22 | 1 | 1 | [6 empty] | 20
476 |  |  | S32-9.04 | Install VV lateral supports and align | 2008-12-23 |  |  | 2009-01-06 | 4 | 1 | [6 empty] | 80
477 |  |  | S32-9.05 | Prepare VVSA for transport. | 2009-01-07 |  |  | 2009-01-08 | 2 | 1 | [6 empty] | 40
478 |  | S3P2 Total | [9 empty] | 5 |  |  |  |  | 1800 |  |  |  | 500
479 |  | S3P3 | S33-1.01 | Install Station 3 site monuments | 2009-01-14 |  |  | 2009-01-16 | 3 | 1 |  | 2 |  |  |  |  | 60
480 |  |  | S33-1.02 | Install floor mounted tracks and VV base support | 2009-01-19 |  |  | 2009-01-23 | 5 | 1 |  | 1 |  |  |  |  | 100
481 |  |  | S33-1.03 | Establish the MCHP CG location. | 2009-01-26 |  |  | 2009-01-27 | 2 | 1 | [6 empty] | 40
482 |  |  | S33-10.01 | transfer the unit to the transfer support frame | 2009-05-18 |  |  | 2009-05-18 | 1 | 2 | [6 empty] | 80
483 |  |  | S33-10.02 | Transfer Period 3 to Station 5 in NCSX TC | 2009-05-19 |  |  | 2009-05-19 | 1 | 2 | [6 empty] | 40
484 |  |  | S33-2.01 | Install MCHP support cart assemblies | 2009-01-28 |  |  | 2009-02-02 | 4 | 1 | [6 empty] | 80
485 |  |  | S33-2.02 | Verify cart motion. | 2009-02-03 |  |  | 2009-02-04 | 2 | 1 | [6 empty] | 40
486 |  |  | S33-2.03 | Install adjustor bar support weldment | 2009-02-05 |  |  | 2009-02-04 | 0 | 1 | [6 empty] | 0
487 |  |  | S33-2.04 | Position left MCHP on the cart assembly | 2009-02-26 |  |  | 2009-02-26 | 1 | 2 | [6 empty] | 20
488 |  |  | S33-2.05 | Secure left MCHP on support cart base. | 2009-02-27 |  |  | 2009-02-27 | 1 | 2 | [6 empty] | 40
489 |  |  | S33-2.06 | Measure monuments on left MCHP and walls | 2009-03-02 |  |  | 2009-03-03 | 2 | 2 | [6 empty] | 0 |  |  |  | 100
490 |  |  | S33-2.07 | Set positioning stop on the cart | 2009-03-05 |  |  | 2009-03-05 | 1 | 2 | [6 empty] | 20
491 |  |  | S33-3.01 | Move right base support cart to its final positi | 2009-03-06 |  |  | 2009-03-05 | 0 | 2 | [6 empty] | 0
492 |  |  | S33-3.02 | Lift the right side MCHP and position | 2009-03-06 |  |  | 2009-03-06 | 1 | 2 | [6 empty] | 30
493 |  |  | S33-3.03 | Temporary fasteners bring the parts together. | 2009-03-09 |  |  | 2009-03-06 | 0 | 2 | [6 empty] | 0
494 |  |  | S33-3.04 | AirLoc Wedgemount leveler to take load. | 2009-03-09 |  |  | 2009-03-06 | 0 | 2 | [6 empty] | 0
495 |  |  | S33-3.05 | Install temp scaffolding to install flange hw | 2009-03-09 |  |  | 2009-03-09 | 1 | 2 | [6 empty] | 20
496 |  |  | S33-3.06 | Install bolts and shims | 2009-03-10 |  |  | 2009-03-10 | 1 | 2 | [6 empty] | 20
497 |  |  | S33-3.07 | Tighten flange fasteners to 50% | 2009-03-11 |  |  | 2009-03-11 | 1 | 2 | [6 empty] | 20
498 |  |  | S33-3.08 | Perform metrology measurements | 2009-03-12 |  |  | 2009-03-12 | 1 | 2 | [6 empty] | 0 |  |  |  | 100
499 |  |  | S33-3.09 | Perform position adjust on right side MCHP | 2009-03-16 |  |  | 2009-03-16 | 1 | 2 | [6 empty] | 40
500 |  |  | S33-3.1 | Verify position of the VV support hanger | 2009-03-17 |  |  | 2009-03-17 | 1 | 2 | [6 empty] | 0 |  |  |  | 60
501 |  |  | S33-3.11 | Remove flange hardware and temp platforms | 2009-03-18 |  |  | 2009-03-18 | 1 | 2 | [6 empty] | 20
502 |  |  | S33-4.01 | EMeasure monuments on the MCHP's &walls. | 2009-03-19 |  |  | 2009-03-19 | 1 | 2 |  | 2 |  |  |  |  | 0 |  |  |  | 40
503 |  |  | S33-4.02 | Place all of the laser screens | 2009-03-20 |  |  | 2009-03-20 | 1 | 2 | [6 empty] | 40
504 |  |  | S33-4.03 | Determine laser alignment. | 2009-03-23 |  |  | 2009-03-23 | 1 | 2 | [6 empty] | 20
505 |  |  | S33-4.04 | mount the milar on the screens. | 2009-03-24 |  |  | 2009-03-24 | 1 | 2 | [6 empty] | 0
506 |  |  | S33-4.05 | Disengage MCHP's to move the left MCHP. | 2009-03-25 |  |  | 2009-03-25 | 1 | 2 | [6 empty] | 20
507 |  |  | S33-4.06 | Remove both MCHP's. | 2009-03-26 |  |  | 2009-03-26 | 1 | 2 | [6 empty] | 40
508 |  |  | S33-5.01 | Remove the adjustor bar support from left side. | 2009-03-27 |  |  | 2009-03-26 | 0 | 2 | [6 empty] | 0
509 |  |  | S33-5.02 | Install VV NBI port support stand. | 2009-03-27 |  |  | 2009-03-27 | 1 | 2 | [6 empty] | 40
510 |  |  | S33-5.03 | Install VVSA to base support | 2009-03-30 |  |  | 2009-03-30 | 1 | 2 | [6 empty] | 20
511 |  |  | S33-5.04 | Secure the VVSA to base & NBI port sprt stand. | 2009-03-31 |  |  | 2009-03-31 | 1 | 2 | [6 empty] | 40
512 |  |  | S33-6.01 | Install bumper protection components on the VV | 2009-04-01 |  |  | 2009-03-31 | 0 | 2 | [6 empty] | 0
513 |  |  | S33-6.02 | Position AirLoc Wedgemount in lower position. | 2009-04-01 |  |  | 2009-03-31 | 0 | 2 | [6 empty] | 0
514 |  |  | S33-6.03 | move the left MCHP over the VV. | 2009-04-01 |  |  | 2009-04-01 | 1 | 2 | [6 empty] | 50
515 |  |  | S33-6.04 | Re-install the left adjustor bar. | 2009-04-02 |  |  | 2009-04-01 | 0 | 2 | [6 empty] | 0
516 |  |  | S33-6.05 | Make adjustments to properly align MCHP. | 2009-04-02 |  |  | 2009-04-02 | 1 | 2 | [6 empty] | 40
517 |  |  | S33-6.06 | Transfer load to the AirLoc Wedgemount leveler. | 2009-04-03 |  |  | 2009-04-02 | 0 | 2 | [6 empty] | 0
518 |  |  | S33-6.07 | move the MCHP to the left 1/2". | 2009-04-03 |  |  | 2009-04-02 | 0 | 2 | [6 empty] | 0
519 |  |  | S33-7.01 | Position AirLoc Wedgemount lowered position. | 2009-04-03 |  |  | 2009-04-02 | 0 | 2 | [6 empty] | 0
520 |  |  | S33-7.02 | move the right MCHP over the VV | 2009-04-03 |  |  | 2009-04-03 | 1 | 2 | [6 empty] | 40
521 |  |  | S33-7.03 | move the left MCHP to its final position. | 2009-04-06 |  |  | 2009-04-06 | 1 | 2 | [6 empty] | 10
522 |  |  | S33-7.04 | engage the preinstalled Type-A flange bushings. | 2009-04-07 |  |  | 2009-04-07 | 1 | 2 | [6 empty] | 10
523 |  |  | S33-7.05 | Temporary fasteners bring the parts together. | 2009-04-08 |  |  | 2009-04-07 | 0 | 2 | [6 empty] | 0
524 |  |  | S33-7.06 | AirLoc Wedgemount leveler up to take the load. | 2009-04-08 |  |  | 2009-04-08 | 1 | 2 | [6 empty] | 10
525 |  |  | S33-7.07 | Remove laser screens | 2009-04-09 |  |  | 2009-04-08 | 0 | 2 | [6 empty] | 0
526 |  |  | S33-7.08 | Install temp scaffolding to install flange hw | 2009-04-09 |  |  | 2009-04-09 | 1 | 2 | [6 empty] | 80
527 |  |  | S33-7.09 | Install bolts, alumina and inboard weld shims. | 2009-04-13 |  |  | 2009-04-13 | 1 | 2 | [6 empty] | 40
528 |  |  | S33-7.1 | Tighten flange fasteners to 50% | 2009-04-14 |  |  | 2009-04-14 | 1 | 2 | [6 empty] | 20
529 |  |  | S33-7.11 | "wiggle" test Tighten bolt and recheck. | 2009-04-15 |  |  | 2009-04-15 | 1 | 2 | [6 empty] | 20
530 |  |  | S33-7.12 | Perform metrology measurements | 2009-04-16 |  |  | 2009-04-16 | 1 | 2 | [6 empty] | 0 |  |  |  | 100
531 |  |  | S33-7.13 | Perform position adjustments right side MCHP | 2009-04-20 |  |  | 2009-04-20 | 1 | 2 | [6 empty] | 60
532 |  |  | S33-7.14 | Remove SISSCO actuator from right MCHP. | 2009-04-22 |  |  | 2009-04-21 | 0 | 2 | [6 empty] | 0
533 |  |  | S33-7.15 | Install bushing. | 2009-04-22 |  |  | 2009-04-22 | 1 | 2 | [6 empty] | 10
534 |  |  | S33-7.16 | Tighten nuts 100%. & Measure | 2009-04-23 |  |  | 2009-04-23 | 1 | 2 | [6 empty] | 20
535 |  |  | S33-8.01 | partially weld the inboard shim. | 2009-04-24 |  |  | 2009-05-04 | 7 | 2 | [6 empty] | 300
536 |  |  | S33-8.02 | Final complete MC scan verify period alignment. | 2009-05-05 |  |  | 2009-05-07 | 3 | 2 | [6 empty] | 0 |  |  |  | 100
537 |  |  | S33-9.01 | Attach VV permanent vertical supports | 2009-05-08 |  |  | 2009-05-08 | 1 | 2 | [6 empty] | 40
538 |  |  | S33-9.02 | Attach temporary VV vertical supports | 2009-05-11 |  |  | 2009-05-11 | 1 | 2 | [6 empty] | 20
539 |  |  | S33-9.03 | Transfer load to vertical supports. | 2009-05-12 |  |  | 2009-05-12 | 1 | 2 | [6 empty] | 20
540 |  |  | S33-9.04 | Install VV lateral supports and align | 2009-05-13 |  |  | 2009-05-13 | 1 | 2 | [6 empty] | 80
541 |  |  | S33-9.05 | Prepare VVSA for transport. | 2009-05-15 |  |  | 2009-05-15 | 1 | 2 | [6 empty] | 40
542 |  | S3P3 Total | [9 empty] | 5 |  |  |  |  | 1800 |  |  |  | 500
543 | 1810 Total | [10 empty] | 418.64 |  |  | 5337.1 | 6557.1 | 37473.36 |  |  |  | 9500
544 | 1815 | S4P0 | R1810-5101 | MTM NCR hardware re-purchase | 2008-05-27 |  |  | 2008-06-30 | 25 | 1 |  | 42
545 |  |  | R1810-5102 | Monuments,reflectors,CCR's | 2008-06-03 |  |  | 2008-06-16 | 10 | 1 |  | 51.75
546 |  |  | R1810-5103 | metrology network in NCSX TC | 2008-06-17 |  |  | 2008-06-30 | 10 | 1 |  | 7 |  |  |  |  | 160
547 |  |  | R1810-5104 | Misc for tooling | 2008-07-21 |  |  | 2008-08-01 | 10 | 1
548 |  |  | R1810-5106 | Testout Sta 5 equipt & procedures | 2008-07-01 |  |  | 2008-07-08 | 5 | 1 | [6 empty] | 160
549 |  |  | R1810-5107 | Check 3 sled interfaces adjust holes | 2008-07-09 |  |  | 2008-07-24 | 12 | 1 | [6 empty] | 384
550 |  |  | R1810-5108 | Fixtures installed-final metrology | 2008-07-25 |  |  | 2008-08-01 | 6 | 1 | [6 empty] | 192
551 |  |  | R1810-5112 | Weld wire & welding supplies | 2008-05-27 |  |  | 2008-06-30 | 25 | 1 |  | 15
552 |  | S4P0 Total | [9 empty] | 115.75 |  |  |  |  | 896
553 |  | S4P1 | R1810-5109 | Begin Station 5 Operations |  |  |  | 2008-08-01 | 0 | 1
554 |  |  | S51-1.01 | cut off short dome | 2008-08-04 |  |  | 2008-08-05 | 2 | [7 empty] | 40
555 |  |  | S51-1.02 | Install insulation system around all ports. | 2008-08-06 |  |  | 2008-08-05 | 0 | [7 empty] | 0
556 |  |  | S51-1.03 | Install heat tape and theomocouples on all ports | 2008-08-06 |  |  | 2008-08-05 | 0 | [7 empty] | 0
557 |  |  | S51-10.01 | Install PF coil support structure | 2009-02-13 |  |  | 2009-02-24 | 8 | [7 empty] | 160
558 |  |  | S51-11.01 | Install tMC coolant manifold | 2009-02-25 |  |  | 2009-02-27 | 3 | [7 empty] | 60
559 |  |  | S51-11.02 | Connect MC coolant lines to the manifold | 2009-03-02 |  |  | 2009-03-27 | 20 | [7 empty] | 400
560 |  |  | S51-12.01 | Install Rogowski coils | 2009-03-30 |  |  | 2009-04-03 | 5 | [7 empty] | 100
561 |  |  | S51-13.01 | Obtain set of Period 1 align fiducial positions | 2009-04-06 |  |  | 2009-04-10 | 5 | [7 empty] | 0 |  |  |  | 100
562 |  |  | S51-13.02 | align to tooling balls on each MCHP | 2009-04-13 |  |  | 2009-04-13 | 1 | [7 empty] | 0 |  |  |  | 20
563 |  |  | S51-13.03 | bring the VV into proper alignment | 2009-04-14 |  |  | 2009-04-17 | 4 | [7 empty] | 80
564 |  |  | S51-13.04 | Install or identify three primary fiducials | 2009-04-20 |  |  | 2009-04-21 | 2 | [7 empty] | 40
565 |  |  | S51-13.05 | Make a final measurement of all fiducials | 2009-04-22 |  |  | 2009-04-23 | 2 | 2 | [6 empty] | 0 |  |  |  | 100
566 |  |  | S51-13.11 | Check Assembly (bolts, etc) | 2009-04-24 |  |  | 2009-04-28 | 3 | 2 | [6 empty] | 100
567 |  |  | S51-13.12 | Check Diagnostics (Loops, thermocouples) | 2009-04-29 |  |  | 2009-04-30 | 2 | 2 | [6 empty] | 100
568 |  |  | S51-13.13 | Check manifolds (pressure, flow, etc.) | 2009-05-01 |  |  | 2009-05-05 | 3 | 2 | [6 empty] | 100
569 |  |  | S51-13.14 | Check 6 modcoils (voltage etc) | 2009-05-06 |  |  | 2009-05-08 | 3 | 2 | [6 empty] | 120
570 |  |  | S51-13.15 | Check trim coils (voltage etc) | 2009-05-11 |  |  | 2009-05-12 | 2 | 2 | [6 empty] | 60
571 |  |  | S51-13.16 | Check TF coils (voltage etc) | 2009-05-13 |  |  | 2009-05-15 | 3 | 2 | [6 empty] | 120
572 |  |  | S51-14.01 | Install crane rigging to completed Period assy | 2009-05-18 |  |  | 2009-05-18 | 1 | 2 | [6 empty] | 40
573 |  |  | S51-14.02 | Remove platforms | 2009-05-19 |  |  | 2009-05-19 | 1 | 2 | [6 empty] | 20
574 |  |  | S51-14.03 | Transfer Period 1 to Station 6 in NCSX tTC. | 2009-05-20 |  |  | 2009-05-20 | 1 | 2 | [6 empty] | 40
575 |  |  | S51-2.01 | Install period support fixture | 2008-08-06 |  |  | 2008-08-07 | 2 | [7 empty] | 40
576 |  |  | S51-2.02 | Install FPA on support stand. | 2008-08-08 |  |  | 2008-08-11 | 2 | [7 empty] | 40
577 |  |  | S51-2.03 | Install external working platforms | 2008-08-12 |  |  | 2008-08-15 | 4 | [7 empty] | 80
578 |  |  | S51-2.04 | Install internal VV working platforms | 2008-08-18 |  |  | 2008-08-20 | 3 | [7 empty] | 60
579 |  |  | S51-3.01 | Install the domes (left and right side), | 2008-08-21 |  |  | 2008-08-22 | 2 | [7 empty] | 40
580 |  |  | S51-3.02 | Install small dome ports remaining circ ports. | 2008-08-25 |  |  | 2008-10-06 | 30 | 1 | [6 empty] | 600
581 |  |  | S51-3.03 | Leak check each port after it is welded. | 2008-09-16 |  |  | 2008-10-27 | 30 | 1 | [6 empty] | 600
582 |  |  | S51-4.01 | Install boots on ports except for the two port | 2008-10-16 |  |  | 2008-11-06 | 16 | 1 | [6 empty] | 320
583 |  |  | S51-5.01 | Install MC lead connections on each of the MC's | 2008-11-07 |  |  | 2008-11-07 | 1 | [7 empty] | 0
584 |  |  | S51-5.02 | Install MC coolant lines on each MC | 2008-11-10 |  |  | 2008-11-25 | 12 | [7 empty] | 240
585 |  |  | S51-5.03 | Platforms may need to be altered | 2008-11-26 |  |  | 2008-12-02 | 3 | [7 empty] | 60
586 |  |  | S51-6.01 | Rotate 2 TF coils over the MC on the right side | 2008-12-15 |  |  | 2008-12-16 | 2 | [7 empty] | 40
587 |  |  | S51-6.02 | Attach the temp support at end of Type-C MC | 2008-12-17 |  |  | 2008-12-17 | 1 | [7 empty] | 20
588 |  |  | S51-6.03 | Lower leveler pad disengage base of MC right sid | 2008-12-18 |  |  | 2008-12-17 | 0 | [7 empty] | 0
589 |  |  | S51-6.04 | Install TF support brackets | 2008-12-18 |  |  | 2008-12-19 | 2 | [7 empty] | 40
590 |  |  | S51-6.05 | Secure First TF assy | 2008-12-22 |  |  | 2008-12-22 | 1 | [7 empty] | 20
591 |  |  | S51-6.06 | Install TF support brackets | 2008-12-23 |  |  | 2009-01-02 | 2 | [7 empty] | 40
592 |  |  | S51-6.07 | Secure 2nd TF coil | 2009-01-05 |  |  | 2009-01-05 | 1 | [7 empty] | 20
593 |  |  | S51-6.08 | Install machine support plates | 2009-01-06 |  |  | 2009-01-08 | 3 | [7 empty] | 60
594 |  |  | S51-6.09 | Reinstall leveler pad | 2009-01-09 |  |  | 2009-01-08 | 0 | [7 empty] | 0
595 |  |  | S51-6.1 | Installed one side of the TF support brackets | 2009-01-09 |  |  | 2009-01-09 | 1 | [7 empty] | 20
596 |  |  | S51-7.01 | The TF installation on the left side | 2009-01-12 |  |  | 2009-01-28 | 13 | [7 empty] | 260
597 |  |  | S51-8.01 | Perform a fit-up check of the four TF coils | 2009-01-29 |  |  | 2009-02-04 | 5 | [7 empty] | 100
598 |  |  | S51-9.01 | Tack weld the left and right port 4's. | 2009-02-05 |  |  | 2009-02-06 | 2 | [7 empty] | 40
599 |  |  | S51-9.02 | Install boots on both port 4's. | 2009-02-09 |  |  | 2009-02-12 | 4 | [7 empty] | 80
600 |  | S4P1 Total | [14 empty] | 4400 |  |  |  | 220
601 |  | S4P2 | S52-1.01 | cut off short dome | 2009-01-14 |  |  | 2009-01-15 | 2 | [7 empty] | 40
602 |  |  | S52-1.02 | Install insulation system around all ports. | 2009-01-16 |  |  | 2009-01-15 | 0 | [7 empty] | 0
603 |  |  | S52-1.03 | Install heat tape and theomocouples on all ports | 2009-01-16 |  |  | 2009-01-15 | 0 | [7 empty] | 0
604 |  |  | S52-10.01 | Install PF coil support structure | 2009-07-06 |  |  | 2009-07-15 | 8 | [7 empty] | 160
605 |  |  | S52-11.01 | Install tMC coolant manifold | 2009-07-16 |  |  | 2009-07-20 | 3 | [7 empty] | 60
606 |  |  | S52-11.02 | Connect MC coolant lines to the manifold | 2009-07-21 |  |  | 2009-08-17 | 20 | [7 empty] | 400
607 |  |  | S52-12.01 | Install Rogowski coils | 2009-08-18 |  |  | 2009-08-24 | 5 | [7 empty] | 100
608 |  |  | S52-13.01 | Obtain set of Period 1 align fiducial positions | 2009-08-25 |  |  | 2009-08-31 | 5 | [7 empty] | 0 |  |  |  | 100
609 |  |  | S52-13.02 | align to tooling balls on each MCHP | 2009-09-01 |  |  | 2009-09-01 | 1 | [7 empty] | 0 |  |  |  | 20
610 |  |  | S52-13.03 | bring the VV into proper alignment | 2009-09-02 |  |  | 2009-09-08 | 4 | [7 empty] | 80
611 |  |  | S52-13.04 | Install or identify three primary fiducials | 2009-09-09 |  |  | 2009-09-10 | 2 | [7 empty] | 40
612 |  |  | S52-13.05 | Make a final measurement of all fiducials | 2009-09-11 |  |  | 2009-09-17 | 5 | [7 empty] | 0 |  |  |  | 100
613 |  |  | S52-13.11 | Check Assembly (bolts, etc) | 2009-09-18 |  |  | 2009-09-24 | 5 | [7 empty] | 100
614 |  |  | S52-13.12 | Check Diagnostics (Loops, thermocouples) | 2009-09-25 |  |  | 2009-10-01 | 5 | [7 empty] | 100
615 |  |  | S52-13.13 | Check manifolds (pressure, flow, etc.) | 2009-10-02 |  |  | 2009-10-08 | 5 | [7 empty] | 100
616 |  |  | S52-13.14 | Check 6 modcoils (voltage etc) | 2009-10-09 |  |  | 2009-10-16 | 6 | [7 empty] | 120
617 |  |  | S52-13.15 | Check trim coils (voltage etc) | 2009-10-19 |  |  | 2009-10-21 | 3 | [7 empty] | 60
618 |  |  | S52-13.16 | Check TF coils (voltage etc) | 2009-10-22 |  |  | 2009-10-29 | 6 | [7 empty] | 120
619 |  |  | S52-14.01 | Install crane rigging to completed Period assy | 2009-10-30 |  |  | 2009-11-02 | 2 | [7 empty] | 40
620 |  |  | S52-14.02 | Remove platforms | 2009-11-03 |  |  | 2009-11-03 | 1 | [7 empty] | 20
621 |  |  | S52-14.03 | Transfer Period 2 to Station 6 in NCSX tTC. | 2009-11-04 |  |  | 2009-11-05 | 2 | [7 empty] | 40
622 |  |  | S52-2.01 | Install period support fixture | 2009-01-16 |  |  | 2009-01-19 | 2 | [7 empty] | 40
623 |  |  | S52-2.02 | Install FPA on support stand. | 2009-01-20 |  |  | 2009-01-21 | 2 | [7 empty] | 40
624 |  |  | S52-2.03 | Install external working platforms | 2009-01-22 |  |  | 2009-01-27 | 4 | [7 empty] | 80
625 |  |  | S52-2.04 | Install internal VV working platforms | 2009-01-28 |  |  | 2009-01-30 | 3 | [7 empty] | 60
626 |  |  | S52-3.01 | Install the domes (left and right side), | 2009-02-02 |  |  | 2009-02-03 | 2 | [7 empty] | 40
627 |  |  | S52-3.02 | Install small dome ports remaining circ ports. | 2009-02-04 |  |  | 2009-03-17 | 30 | [7 empty] | 600
628 |  |  | S52-3.03 | Leak check each port after it is welded. | 2009-02-25 |  |  | 2009-04-07 | 30 | [7 empty] | 600
629 |  |  | S52-4.01 | Install boots on ports except for the two port | 2009-03-27 |  |  | 2009-04-17 | 16 | [7 empty] | 320
630 |  |  | S52-5.01 | Install MC lead connections on each of the MC's | 2009-04-20 |  |  | 2009-04-20 | 1 | [7 empty] | 0
631 |  |  | S52-5.02 | Install MC coolant lines on each MC | 2009-04-21 |  |  | 2009-05-06 | 12 | [7 empty] | 240
632 |  |  | S52-5.03 | Platforms may need to be altered | 2009-05-07 |  |  | 2009-05-11 | 3 | [7 empty] | 60
633 |  |  | S52-6.01 | Rotate 2 TF coils over the MC on the right side | 2009-05-12 |  |  | 2009-05-13 | 2 | [7 empty] | 40
634 |  |  | S52-6.02 | Attach the temp support at end of Type-C MC | 2009-05-14 |  |  | 2009-05-14 | 1 | [7 empty] | 20
635 |  |  | S52-6.03 | Lower leveler pad disengage base of MC right sid | 2009-05-15 |  |  | 2009-05-14 | 0 | [7 empty] | 0
636 |  |  | S52-6.04 | Install TF support brackets | 2009-05-15 |  |  | 2009-05-18 | 2 | [7 empty] | 40
637 |  |  | S52-6.05 | Secure First TF assy | 2009-05-19 |  |  | 2009-05-19 | 1 | [7 empty] | 20
638 |  |  | S52-6.06 | Install TF support brackets | 2009-05-20 |  |  | 2009-05-21 | 2 | [7 empty] | 40
639 |  |  | S52-6.07 | Secure 2nd TF coil | 2009-05-22 |  |  | 2009-05-22 | 1 | [7 empty] | 20
640 |  |  | S52-6.08 | Install machine support plates | 2009-05-26 |  |  | 2009-05-28 | 3 | [7 empty] | 60
641 |  |  | S52-6.09 | Reinstall leveler pad | 2009-05-29 |  |  | 2009-05-28 | 0 | [7 empty] | 0
642 |  |  | S52-6.1 | Installed one side of the TF support brackets | 2009-05-29 |  |  | 2009-05-29 | 1 | [7 empty] | 20
643 |  |  | S52-7.01 | The TF installation on the left side | 2009-06-01 |  |  | 2009-06-17 | 13 | [7 empty] | 260
644 |  |  | S52-8.01 | Perform a fit-up check of the four TF coils | 2009-06-18 |  |  | 2009-06-24 | 5 | [7 empty] | 100
645 |  |  | S52-9.01 | Tack weld the left and right port 4's. | 2009-06-25 |  |  | 2009-06-26 | 2 | [7 empty] | 40
646 |  |  | S52-9.02 | Install boots on both port 4's. | 2009-06-29 |  |  | 2009-07-02 | 4 | [7 empty] | 80
647 |  | S4P2 Total | [14 empty] | 4400 |  |  |  | 220
648 |  | S4P3 | R1810-5333 | Last field period assembled |  |  |  | 2009-10-23 | 0 | 2
649 |  |  | S53-1.01 | cut off short dome | 2009-05-21 |  |  | 2009-05-21 | 1 | 2 | [6 empty] | 40
650 |  |  | S53-1.02 | Install insulation system around all ports. | 2009-05-22 |  |  | 2009-05-21 | 0 | 2 | [6 empty] | 0
651 |  |  | S53-1.03 | Install heat tape and theomocouples on all ports | 2009-05-22 |  |  | 2009-05-21 | 0 | 2 | [6 empty] | 0
652 |  |  | S53-10.01 | Install PF coil support structure | 2009-08-20 |  |  | 2009-08-25 | 4 | 2 | [6 empty] | 160
653 |  |  | S53-11.01 | Install tMC coolant manifold | 2009-08-26 |  |  | 2009-08-27 | 2 | 2 | [6 empty] | 60
654 |  |  | S53-11.02 | Connect MC coolant lines to the manifold | 2009-08-28 |  |  | 2009-09-11 | 10 | 2 | [6 empty] | 400
655 |  |  | S53-12.01 | Install Rogowski coils | 2009-09-14 |  |  | 2009-09-16 | 3 | 2 | [6 empty] | 100
656 |  |  | S53-13.01 | Obtain set of Period 1 align fiducial positions | 2009-09-17 |  |  | 2009-09-18 | 2 | 2 | [6 empty] | 0 |  |  |  | 100
657 |  |  | S53-13.02 | align to tooling balls on each MCHP | 2009-09-21 |  |  | 2009-09-21 | 1 | 2 | [6 empty] | 0 |  |  |  | 20
658 |  |  | S53-13.03 | bring the VV into proper alignment | 2009-09-22 |  |  | 2009-09-23 | 2 | 2 | [6 empty] | 80
659 |  |  | S53-13.04 | Install or identify three primary fiducials | 2009-09-24 |  |  | 2009-09-24 | 1 | 2 | [6 empty] | 40
660 |  |  | S53-13.05 | Make a final measurement of all fiducials | 2009-09-25 |  |  | 2009-09-29 | 3 | 2 | [6 empty] | 0 |  |  |  | 100
661 |  |  | S53-13.11 | Check Assembly (bolts, etc) | 2009-09-30 |  |  | 2009-10-01 | 2 | 2 | [6 empty] | 100
662 |  |  | S53-13.12 | Check Diagnostics (Loops, thermocouples) | 2009-10-02 |  |  | 2009-10-06 | 3 | 2 | [6 empty] | 100
663 |  |  | S53-13.13 | Check manifolds (pressure, flow, etc.) | 2009-10-07 |  |  | 2009-10-08 | 2 | 2 | [6 empty] | 100
664 |  |  | S53-13.14 | Check 6 modcoils (voltage etc) | 2009-10-09 |  |  | 2009-10-13 | 3 | 2 | [6 empty] | 120
665 |  |  | S53-13.15 | Check trim coils (voltage etc) | 2009-10-14 |  |  | 2009-10-15 | 2 | 2 | [6 empty] | 60
666 |  |  | S53-13.16 | Check TF coils (voltage etc) | 2009-10-16 |  |  | 2009-10-20 | 3 | 2 | [6 empty] | 120
667 |  |  | S53-14.01 | Install crane rigging to completed Period assy | 2009-10-21 |  |  | 2009-10-21 | 1 | 2 | [6 empty] | 40
668 |  |  | S53-14.02 | Remove platforms | 2009-10-22 |  |  | 2009-10-22 | 1 | 2 | [6 empty] | 20
669 |  |  | S53-14.03 | Transfer Period 3 to Station 6 in NCSX tTC. | 2009-10-23 |  |  | 2009-10-23 | 1 | 2 | [6 empty] | 40
670 |  |  | S53-2.01 | Install period support fixture | 2009-05-22 |  |  | 2009-05-22 | 1 | 2 | [6 empty] | 40
671 |  |  | S53-2.02 | Install FPA on support stand. | 2009-05-26 |  |  | 2009-05-26 | 1 | 2 | [6 empty] | 40
672 |  |  | S53-2.03 | Install external working platforms | 2009-05-27 |  |  | 2009-05-28 | 2 | 2 | [6 empty] | 80
673 |  |  | S53-2.04 | Install internal VV working platforms | 2009-05-29 |  |  | 2009-06-01 | 2 | 2 | [6 empty] | 60
674 |  |  | S53-3.01 | Install the domes (left and right side), | 2009-06-02 |  |  | 2009-06-02 | 1 | 2 | [6 empty] | 40
675 |  |  | S53-3.02 | Install small dome ports remaining circ ports. | 2009-06-03 |  |  | 2009-06-23 | 15 | 2 | [6 empty] | 600
676 |  |  | S53-3.03 | Leak check each port after it is welded. | 2009-06-12 |  |  | 2009-07-02 | 15 | 2 | [6 empty] | 600
677 |  |  | S53-4.01 | Install boots on ports except for the two port | 2009-06-29 |  |  | 2009-07-09 | 8 | 2 | [6 empty] | 320
678 |  |  | S53-5.01 | Install MC lead connections on each of the MC's | 2009-07-10 |  |  | 2009-07-10 | 1 | 2 | [6 empty] | 0
679 |  |  | S53-5.02 | Install MC coolant lines on each MC | 2009-07-13 |  |  | 2009-07-20 | 6 | 2 | [6 empty] | 240
680 |  |  | S53-5.03 | Platforms may need to be altered | 2009-07-21 |  |  | 2009-07-22 | 2 | 2 | [6 empty] | 60
681 |  |  | S53-6.01 | Rotate 2 TF coils over the MC on the right side | 2009-07-23 |  |  | 2009-07-23 | 1 | 2 | [6 empty] | 40
682 |  |  | S53-6.02 | Attach the temp support at end of Type-C MC | 2009-07-24 |  |  | 2009-07-24 | 1 | 2 | [6 empty] | 20
683 |  |  | S53-6.03 | Lower leveler pad disengage base of MC right sid | 2009-07-27 |  |  | 2009-07-24 | 0 | 2 | [6 empty] | 0
684 |  |  | S53-6.04 | Install TF support brackets | 2009-07-27 |  |  | 2009-07-27 | 1 | 2 | [6 empty] | 40
685 |  |  | S53-6.05 | Secure First TF assy | 2009-07-28 |  |  | 2009-07-28 | 1 | 2 | [6 empty] | 20
686 |  |  | S53-6.06 | Install TF support brackets | 2009-07-29 |  |  | 2009-07-29 | 1 | 2 | [6 empty] | 40
687 |  |  | S53-6.07 | Secure 2nd TF coil | 2009-07-30 |  |  | 2009-07-30 | 1 | 2 | [6 empty] | 20
688 |  |  | S53-6.08 | Install machine support plates | 2009-07-31 |  |  | 2009-07-31 | 1 | 2 | [6 empty] | 60
689 |  |  | S53-6.09 | Reinstall leveler pad | 2009-08-03 |  |  | 2009-07-31 | 0 | 2 | [6 empty] | 0
690 |  |  | S53-6.1 | Installed one side of the TF support brackets | 2009-08-03 |  |  | 2009-08-03 | 1 | 2 | [6 empty] | 20
691 |  |  | S53-7.01 | The TF installation on the left side | 2009-08-04 |  |  | 2009-08-11 | 6 | 2 | [6 empty] | 260
692 |  |  | S53-8.01 | Perform a fit-up check of the four TF coils | 2009-08-12 |  |  | 2009-08-14 | 3 | 2 | [6 empty] | 100
693 |  |  | S53-9.01 | Tack weld the left and right port 4's. | 2009-08-17 |  |  | 2009-08-17 | 1 | 2 | [6 empty] | 40
694 |  |  | S53-9.02 | Install boots on both port 4's. | 2009-08-18 |  |  | 2009-08-19 | 2 | 2 | [6 empty] | 80
695 |  | S4P3 Total | [14 empty] | 4400 |  |  |  | 220
696 | 1815 Total | [10 empty] | 115.75 |  |  |  |  | 14096 |  |  |  | 660
697 | Grand Total | [9 empty] | 43 | 540.09 | 15 | 2669.05 | 5337.1 | 10728.1 | 51569.36 | 1477 | 1877 | 2611 | 10160
698
699
700
701
702
703

## FPA
1 | ACT | TITLE | ES | OD | EF | WBS2 | SHIFTS | JJJJ | WBS4 | ORDR | RES | RUT | BQ
4 | R1802-207 | Procedures written & approved | 2007-08-24 | 14 | 2007-09-13 | 18 |  | 1802 | 2.00 |  |  |  | 0
5 | R1802-209 | JHA completed | 2007-09-14 | 6 | 2007-09-21 | 18 |  | 1802 | 2.00 |  |  |  | 0
6 | R1802-211 | Training needs identified & released | 2007-09-24 | 6 | 2007-10-01 | 18 |  | 1802 | 2.00 |  |  |  | 0
7 | R1802-213 | ACC review completed | 2007-10-02 | 2 | 2007-10-03 | 18 |  | 1802 | 2.00 |  |  |  | 0
8 | R1802-215 | Pre-job brief completed | 2007-10-04 | 1 | 2007-10-04 | 18 |  | 1802 | 2.00 |  |  |  | 0
9 | R1802-217 | Station 2 operational | 2007-10-05 | 1 | 2007-10-05 | 18 |  | 1802 | 2.00 |  |  |  | 0
10 | R1802-307 | Procedures written & approved | 2007-11-23 | 10 | 2007-12-10 | 18 |  | 1802 | 3.00 | 11 |  |  | 0
11 | R1802-309 | JHA completed | 2007-12-11 | 6 | 2007-12-18 | 18 |  | 1802 | 3.00 | 12 |  |  | 0
12 | R1802-311 | Training needs identified & released | 2007-12-19 | 6 | 2008-01-04 | 18 |  | 1802 | 3.00 | 14 |  |  | 0
13 | R1802-313 | ACC review completed | 2008-01-07 | 6 | 2008-01-14 | 18 |  | 1802 | 3.00 | 15 |  |  | 0
14 | R1802-315 | Pre-job brief completed | 2008-01-15 | 6 | 2008-01-22 | 18 |  | 1802 | 3.00 | 16 |  |  | 0
15 | R1802-507 | Procedures written & approved | 2008-05-29 | 14 | 2008-06-17 | 18 |  | 1802 | 5.00 | 10 |  |  | 0
16 | R1802-509 | JHA completed | 2008-06-18 | 6 | 2008-06-25 | 18 |  | 1802 | 5.00 | 11 |  |  | 0
17 | R1802-519 | Fixtures installed | 2008-06-26 | 6 | 2008-07-03 | 18 |  | 1802 | 5.00 | 12 |  |  | 0
18 | R1802-511 | Training needs identified & released | 2008-07-07 | 6 | 2008-07-14 | 18 |  | 1802 | 5.00 | 13 |  |  | 0
19 | R1802-513 | ACC review completed | 2008-07-15 | 7 | 2008-07-23 | 18 |  | 1802 | 5.00 | 14 |  |  | 0
20 | R1802-515 | Pre-job brief completed | 2008-07-24 | 7 | 2008-08-01 | 18 |  | 1802 | 5.00 | 15 |  |  | 0
21 | 1802ORNL02 | ORNL Title III field period assy station 2 | 2007-08-14 | 365 | 2009-02-04 | 18 |  | 1802 | A | 10 | ORNLEM | hr | 591
22 | 1802ORNL02 | ORNL Title III field period assy station 2 | 2007-08-14 | 365 | 2009-02-04 | 18 |  | 1802 | A | 10 | ORNLDM | hr | 591
23 | 1802ORNL02 | ORNL Title III field period assy station 2 | 2007-08-14 | 365 | 2009-02-04 | 18 |  | 1802 | A | 10 | ORNL35 | $ | 6
24 | 1802ORNL03 | ORNL Title III field period assy station 3 | 2008-01-23 | 333 | 2009-05-19 | 18 |  | 1802 | A | 10 | ORNLEM | hr | 442
25 | 1802ORNL03 | ORNL Title III field period assy station 3 | 2008-01-23 | 333 | 2009-05-19 | 18 |  | 1802 | A | 10 | ORNL35 | $ | 6
26 | 1802ORNL03 | ORNL Title III field period assy station 3 | 2008-01-23 | 333 | 2009-05-19 | 18 |  | 1802 | A | 10 | ORNLDM | hr | 442
27 | 1802ORNL05 | ORNL Title III field period assy station 5 | 2008-08-04 | 307 | 2009-10-23 | 18 |  | 1802 | A | 10 | ORNLEM | hr | 444
28 | 1802ORNL05 | ORNL Title III field period assy station 5 | 2008-08-04 | 307 | 2009-10-23 | 18 |  | 1802 | A | 10 | ORNL35 | $ | 6
29 | 1802ORNL05 | ORNL Title III field period assy station 5 | 2008-08-04 | 307 | 2009-10-23 | 18 |  | 1802 | A | 10 | ORNLDM | hr | 444
30 | R1802-001 | Metrology Engr Super FY07 | 2007-05-01 | 106 | 2007-09-28 | 18 |  | 1802 | A | 10 | EA//EM | hr | 360
31 | R1802-003 | Metrology Engr Super FY08 | 2007-10-01 | 250 | 2008-09-30 | 18 |  | 1802 | A | 10 | EA//EM | hr | 863
32 | R1802-004 | Metrology Engr Super FY09 | 2008-10-01 | 248 | 2009-09-29 | 18 |  | 1802 | A | 10 | EA//EM | hr | 863
33 | R1802-004S | Metrology Engr Super FY09 (2n shft suprt .5 fte | 2009-02-26 | 169 | 2009-10-23 | 18 | 2 | 1802 | A | 10 | EA//EM | hr | 583.05
34 | R1802-005 | FPA Management FY07 | 2007-05-01 | 106 | 2007-09-28 | 18 |  | 1802 | A | 10 | EM//EM | hr | 719
35 | R1802-005 | FPA Management FY07 | 2007-05-01 | 106 | 2007-09-28 | 18 |  | 1802 | A | 10 | 41 | $k | 5.7
36 | R1802-007 | FPA Management FY08 | 2007-10-01 | 250 | 2008-09-30 | 18 |  | 1802 | A | 10 | EM//EM | hr | 1726
37 | R1802-008 | FPA Management FY09 | 2008-10-01 | 248 | 2009-09-29 | 18 |  | 1802 | A | 10 | EM//EM | hr | 1726
38 | R1802-011 | Title III field period assy FY08 ORNL | 2007-10-01 | 250 | 2008-09-30 | 18 |  | 1802 | A | 10 | ORNLEM | hr | 400
39 | R1802-011 | Title III field period assy FY08 ORNL | 2007-10-01 | 250 | 2008-09-30 | 18 |  | 1802 | A | 10 | ORNL35 | $ | 25
40 | R1802-013 | HP Coverage in the TFTR TC LOE FY07 | 2007-05-01 | 106 | 2007-09-28 | 18 |  | 1802 | A | 10 | SH//TB | hr | 539
41 | R1802-015 | HP Coverage in the TFTR TC LOE FY08 | 2007-10-01 | 250 | 2008-09-30 | 18 |  | 1802 | A | 10 | SH//TB | hr | 1295
42 | R1802-016 | HP Coverage in the TFTR TC LOE FY09 | 2008-10-01 | 150 | 2009-05-11 | 18 |  | 1802 | A | 10 | SH//TB | hr | 777
43 | R1810-098 | Station 3 complete |  | 0 | 2009-05-19 | 18 |  | 1802 | A | 11 |  |  | 0
44 | 1802MAY | May cost incr | 2007-05-01 | 20 | 2007-05-29 | 18 |  | 1802 |  | 14 | 81 | $k | 15
45 | R1801-004S | LOE Crane support, fixt setup (2nd shft 1.2 fte | 2009-02-26 | 169 | 2009-10-23 | 18 | 2 | 1810 | S0P0 |  | EM//TB | hr | 1399.32
46 | R1810-001 | LOE Crane support, fixture setupfor FY07 | 2007-05-01 | 106 | 2007-09-28 | 18 |  | 1810 | S0P0 |  | EM//TB | hr | 863
47 | R1810-003 | LOE Crane support, fixture setupfor FY08 | 2007-10-01 | 250 | 2008-09-30 | 18 |  | 1810 | S0P0 |  | EM//TB | hr | 2071.2
48 | R1810-004 | LOE Crane support, fixture setupfor FY09 | 2008-10-01 | 248 | 2009-09-29 | 18 |  | 1810 | S0P0 |  | EM//TB | hr | 2053.44
49 | R1810-005 | LOE Field Supervision for FY07 | 2007-05-01 | 106 | 2007-09-28 | 18 |  | 1810 | S0P0 |  | EE//SM | hr | 719
50 | R1810-007 | LOE Field Supervision for FY08 | 2007-10-01 | 250 | 2008-09-30 | 18 |  | 1810 | S0P0 |  | EE//SM | hr | 1726
51 | R1810-008 | LOE Field Supervision for FY09 | 2008-10-01 | 248 | 2009-09-29 | 18 |  | 1810 | S0P0 |  | EE//SM | hr | 1726
52 | R1810-008S | LOE Field Supervision for 2nd shft 1.0 fte | 2009-02-26 | 169 | 2009-10-23 | 18 | 2 | 1810 | S0P0 |  | EE//SM | hr | 1166.1
53 | R1810-009 | LOE Metrology sprt FY07 1.5 fte EM & 1.0 fte TB | 2007-05-01 | 106 | 2007-09-28 | 18 |  | 1810 | S0P0 |  | EM//EM | hr | 1097.1
54 | R1810-009 | LOE Metrology sprt FY07 1.5 fte EM & 1.0 fte TB | 2007-05-01 | 106 | 2007-09-28 | 18 |  | 1810 | S0P0 |  | EM//TB | hr | 731.4
55 | R1810-011 | LOE Metrology sprt FY08 1.5 fte EM & 1.0 fte TB | 2007-10-01 | 250 | 2008-09-30 | 18 |  | 1810 | S0P0 |  | EM//EM | hr | 3500
56 | R1810-011 | LOE Metrology sprt FY08 1.5 fte EM & 1.0 fte TB | 2007-10-01 | 250 | 2008-09-30 | 18 |  | 1810 | S0P0 |  | EM//TB | hr | 2300
57 | R1810-012 | LOE Metrology sprt FY09 1.5 fte EM & 1.0 fte TB | 2008-10-01 | 276 | 2009-11-06 | 18 |  | 1810 | S0P0 |  | EM//EM | hr | 1960
58 | R1810-012 | LOE Metrology sprt FY09 1.5 fte EM & 1.0 fte TB | 2008-10-01 | 276 | 2009-11-06 | 18 |  | 1810 | S0P0 |  | EM//TB | hr | 1300
59 | R1810-013 | Misc M&S FY07 | 2007-05-01 | 106 | 2007-09-28 | 18 |  | 1810 | S0P0 |  | 41 | $k | 15
60 | R1810-015 | Misc M&S FY08 | 2007-10-01 | 250 | 2008-09-30 | 18 |  | 1810 | S0P0 |  | 41 | $k | 36
61 | R1810-016 | Misc M&S FY09 | 2008-10-01 | 276 | 2009-11-06 | 18 |  | 1810 | S0P0 |  | 41 | $k | 38.64
62 | R1810-099 | Station 5 complete |  | 0 | 2009-10-23 | 18 |  | 1810 | S0P0 |  |  |  | 0
63 | R1810-1105 | Instl cooling lines & Weld cooling/htg risers | 2007-06-01 | 31 | 2007-07-16 | 18 | 1 | 1810 | S1P1 | 10 | EM//TB | hr | 620
64 | R1810-1105 | Instl cooling lines & Weld cooling/htg risers | 2007-06-01 | 31 | 2007-07-16 | 18 | 1 | 1810 | S1P1 | 10 | 41 | $k | 2
65 | R1810-1107 | Verify Instl of H/C lines,headers,manifolds | 2007-07-17 | 5 | 2007-07-23 | 18 | 1 | 1810 | S1P1 | 11 | EM//TB | hr | 100
66 | R1810-1108 | Perform final acceptance testing (H/C flow test) | 2007-07-24 | 5 | 2007-07-30 | 18 | 1 | 1810 | S1P1 | 12 | EM//TB | hr | 100
67 | R1810-1108 | Perform final acceptance testing (H/C flow test) | 2007-07-24 | 5 | 2007-07-30 | 18 | 1 | 1810 | S1P1 | 12 | 41 | $k | 4
68 | R1810-1112 | Trim seal plates | 2007-07-31 | 2 | 2007-08-01 | 18 | 1 | 1810 | S1P1 | 13 | EM//TB | hr | 40
69 | R1810-1109 | Loop termination & verification | 2007-12-07 | 18 | 2008-01-10 | 18 | 1 | 1810 | S1P1 | 14 | EM//TB | hr | 360
70 | R1810-1110 | Install Final Internal&Ext monuments & meas | 2008-01-11 | 4 | 2008-01-16 | 18 | 1 | 1810 | S1P1 | 15 | EM//TB | hr | 80
71 | R1810-1111 | Final Scan | 2008-01-25 | 4 | 2008-01-30 | 18 | 1 | 1810 | S1P1 | 16 | EM//TB | hr | 80
72 | R1810-1114 | Install heater tape on removable ports | 2008-01-31 | 10 | 2008-02-13 | 18 | 1 | 1810 | S1P1 | 17 | EM//TB | hr | 200
73 | R1810-1113 | Prepare &transfer completed VV to holding area | 2008-02-14 | 2 | 2008-02-15 | 18 | 1 | 1810 | S1P1 | 18 | EM//TB | hr | 40
74 | R1810-1203 | Misc Hardware | 2007-06-01 | 84 | 2007-09-28 | 18 |  | 1810 | S1P2 | 10 | 41 | $k | 2
75 | R1810-1209 | Install cooling/htg lines to vac vsl | 2007-11-01 | 15 | 2007-11-21 | 18 | 1 | 1810 | S1P2 | 13 | EM//TB | hr | 300
76 | R1810-1211 | Weld cooling/htg risers | 2007-11-22 | 16 | 2007-12-17 | 18 | 1 | 1810 | S1P2 | 14 | EM//TB | hr | 320
77 | R1810-1211 | Weld cooling/htg risers | 2007-11-22 | 16 | 2007-12-17 | 18 | 1 | 1810 | S1P2 | 14 | 41 | $k | 2
78 | R1810-1213 | Verify Instl of H/C lines,headers,manifolds | 2008-02-18 | 5 | 2008-02-22 | 18 | 1 | 1810 | S1P2 | 15 | EM//TB | hr | 100
79 | R1810-1208 | Perform final acceptance testing (H/C flow test) | 2008-02-25 | 5 | 2008-02-29 | 18 | 1 | 1810 | S1P2 | 16 | EM//TB | hr | 100
80 | R1810-1208 | Perform final acceptance testing (H/C flow test) | 2008-02-25 | 5 | 2008-02-29 | 18 | 1 | 1810 | S1P2 | 16 | 41 | $k | 4
81 | R1810-1212 | Trim seal plates | 2008-03-03 | 2 | 2008-03-04 | 18 | 1 | 1810 | S1P2 | 17 | EM//TB | hr | 40
82 | R1810-1215 | Loop termination & verification | 2008-03-05 | 18 | 2008-03-28 | 18 | 1 | 1810 | S1P2 | 18 | EM//TB | hr | 360
83 | R1810-1216 | Install Final Internal&Ext monuments & meas | 2008-03-31 | 4 | 2008-04-03 | 18 | 1 | 1810 | S1P2 | 19 | EM//TB | hr | 80
84 | R1810-1217 | Final Scan | 2008-04-04 | 4 | 2008-04-09 | 18 | 1 | 1810 | S1P2 | 20 | EM//TB | hr | 80
85 | R1810-1214 | Install heater tape on removable ports | 2008-04-10 | 10 | 2008-04-23 | 18 | 1 | 1810 | S1P2 | 21 | EM//TB | hr | 200
86 | R1810-1219 | Prepare& transfer completed VV to holding area | 2008-04-24 | 2 | 2008-04-25 | 18 | 1 | 1810 | S1P2 | 22 | EM//TB | hr | 40
87 | R1810-1303 | Misc Hardware | 2007-05-15 | 427 | 2009-02-03 | 18 |  | 1810 | S1P3 | 10 | EM//TB | hr | 0
88 | R1810-1303 | Misc Hardware | 2007-05-15 | 427 | 2009-02-03 | 18 |  | 1810 | S1P3 | 10 | 41 | $k | 2
89 | R1810-1304 | Layout diag &coolant paths on vessel | 2007-08-02 | 12 | 2007-08-17 | 18 | 1 | 1810 | S1P3 | 11 | EM//TB | hr | 240
90 | R1810-1305 | Install heater tape on vertical ports | 2007-10-01 | 7 | 2007-10-09 | 18 | 1 | 1810 | S1P3 | 11 | EM//TB | hr | 140
91 | R1810-1314 | Install heater tape on removable ports | 2007-10-10 | 10 | 2007-10-23 | 18 | 1 | 1810 | S1P3 | 12 | EM//TB | hr | 200
92 | R1810-1311 | Wind magnetic diagnostic sensors | 2007-12-18 | 14 | 2008-01-15 | 18 | 1 | 1810 | S1P3 | 13 | EM//TB | hr | 280
93 | R1810-1312 | Trim seal plates | 2007-10-24 | 2 | 2007-10-25 | 18 | 1 | 1810 | S1P3 | 14 | EM//TB | hr | 40
94 | R1810-1307 | Verify installation of heater tapes | 2007-10-26 | 1 | 2007-10-26 | 18 | 1 | 1810 | S1P3 | 15 | EM//TB | hr | 20
95 | R1810-1309 | Attach studs forcoolant lines | 2007-10-29 | 3 | 2007-10-31 | 18 | 1 | 1810 | S1P3 | 16 | EM//TB | hr | 60
96 | R1810-1313 | Install precision magnetic diagnostic sensors | 2008-01-16 | 3 | 2008-01-18 | 18 | 1 | 1810 | S1P3 | 17 | EM//TB | hr | 60
97 | R1810-1315 | Verify installation magnetic diagnostic sensors | 2008-01-21 | 4 | 2008-01-24 | 18 | 1 | 1810 | S1P3 | 18 | EM//TB | hr | 80
98 | R1810-1317 | Install local I&C (incl thermocouples) | 2008-10-01 | 5 | 2008-10-07 | 18 | 1 | 1810 | S1P3 | 19 | EM//TB | hr | 100
99 | R1810-1319 | Verify installation of local I&C | 2008-10-08 | 2 | 2008-10-09 | 18 | 1 | 1810 | S1P3 | 20 | EM//TB | hr | 40
100 | R1810-1321 | Install cooling/htg lines to vac vsl | 2008-10-10 | 15 | 2008-10-30 | 18 | 1 | 1810 | S1P3 | 21 | EM//TB | hr | 300
101 | R1810-1323 | Weld cooling/htg risers | 2008-10-31 | 16 | 2008-11-21 | 18 | 1 | 1810 | S1P3 | 22 | EM//TB | hr | 320
102 | R1810-1325 | Verify Instl of H/C lines,headers,manifolds | 2008-11-24 | 5 | 2008-12-02 | 18 | 1 | 1810 | S1P3 | 23 | EM//TB | hr | 100
103 | R1810-1308 | Perform final acceptance testing (H/C flow test) | 2008-12-03 | 5 | 2008-12-09 | 18 | 1 | 1810 | S1P3 | 24 | EM//TB | hr | 100
104 | R1810-1327 | Loop termination & verification | 2008-12-10 | 18 | 2009-01-13 | 18 | 1 | 1810 | S1P3 | 25 | EM//TB | hr | 360
105 | R1810-1328 | Install Final Internal&Ext monuments & meas | 2009-01-14 | 4 | 2009-01-19 | 18 | 1 | 1810 | S1P3 | 26 | EM//TB | hr | 80
106 | R1810-1329 | Final Scan | 2009-01-20 | 4 | 2009-01-23 | 18 | 1 | 1810 | S1P3 | 27 | EM//TB | hr | 80
107 | R1810-1331 | Prepare & transfer completed VV to holding area | 2009-01-26 | 2 | 2009-01-27 | 18 | 1 | 1810 | S1P3 | 28 | EM//TB | hr | 40
108 | R1810-1S03 | Attachdiagnostics, studs and coolant lines | 2009-01-28 | 17 | 2009-02-19 | 18 | 1 | 1810 | S1SP |  | EM//TB | hr | 340
109 | R1810-1S04 | Install Final Internal&Ext monuments & meas | 2009-02-20 | 2 | 2009-02-23 | 18 | 1 | 1810 | S1SP |  | EM//TB | hr | 40
110 | R1810-2003 | Trial tensioning test on prototype | 2007-06-01 | 3 | 2007-06-05 | 18 | 1 | 1810 | S2PR | 11 | EM//TB | hr | 40
111 | R1810-2003 | Trial tensioning test on prototype | 2007-06-01 | 3 | 2007-06-05 | 18 | 1 | 1810 | S2PR | 11 | 41 | $k | 3
112 | R1810-2005 | Trial bushing and shim test on prototype | 2007-06-01 | 12 | 2007-06-18 | 18 | 1 | 1810 | S2PR | 11 | EM//TB | hr | 240
113 | R1810-2005 | Trial bushing and shim test on prototype | 2007-06-01 | 12 | 2007-06-18 | 18 | 1 | 1810 | S2PR | 11 | 41 | $k | 2
114 | R1810-2009 | Perform trial x-y-z alignments on A1-A2. | 2007-06-01 | 7 | 2007-06-11 | 18 | 1 | 1810 | S2PR | 11 | EM//TB | hr | 140
115 | R1810-2009 | Perform trial x-y-z alignments on A1-A2. | 2007-06-01 | 7 | 2007-06-11 | 18 | 1 | 1810 | S2PR | 11 | 41 | $k | 2
116 | R1810-2010 | Perform developmental trials on A1-A2. | 2007-06-12 | 30 | 2007-07-24 | 18 | 1 | 1810 | S2PR | 11 | EM//TB | hr | 600
117 | R1810-2010 | Perform developmental trials on A1-A2. | 2007-06-12 | 30 | 2007-07-24 | 18 | 1 | 1810 | S2PR | 11 | 41 | $k | 2
118 | R1810-2011 | Alignment mechanisms, metro equipt &positioning | 2007-07-25 | 6 | 2007-08-01 | 18 | 1 | 1810 | S2PR | 11 | EM//TB | hr | 120
119 | R1810-2011 | Alignment mechanisms, metro equipt &positioning | 2007-07-25 | 6 | 2007-08-01 | 18 | 1 | 1810 | S2PR | 11 | 41 | $k | 40
120 | R1810-2013 | Procure alignment mechanisms, fiducials, lifting | 2007-06-01 | 20 | 2007-06-28 | 18 | 1 | 1810 | S2PR | 11 | EM//TB | hr | 400
121 | R1810-2013 | Procure alignment mechanisms, fiducials, lifting | 2007-06-01 | 20 | 2007-06-28 | 18 | 1 | 1810 | S2PR | 11 | 41 | $k | 25
122 | R1810-2015 | Develop procedures for torquing bolts | 2007-06-01 | 4 | 2007-06-06 | 18 | 1 | 1810 | S2PR | 11 | EM//TB | hr | 80
123 | R1810-2050 | Weld trials f/nose welding (in job 1421 | 2007-07-11 | 14 | 2007-07-30 | 18 | 1 | 1810 | S2PR | 12 | 41 | $k | 20
124 | R1810-2050 | Weld trials f/nose welding (in job 1421 | 2007-07-11 | 14 | 2007-07-30 | 18 | 1 | 1810 | S2PR | 12 | 41 | $k | 50
125 | R1810-2017 | Determine fiducial types&locations | 2007-06-07 | 11 | 2007-06-21 | 18 | 1 | 1810 | S2PR | 13 | EM//TB | hr | 220
126 | R1810-2017 | Determine fiducial types&locations | 2007-06-07 | 11 | 2007-06-21 | 18 | 1 | 1810 | S2PR | 13 | 41 | $k | 2
127 | R1810-2019 | Procure monuments&related metrology equipment | 2007-06-01 | 15 | 2007-06-21 | 18 | 1 | 1810 | S2PR | 14 | EM//TB | hr | 300
128 | R1810-2019 | Procure monuments&related metrology equipment | 2007-06-01 | 15 | 2007-06-21 | 18 | 1 | 1810 | S2PR | 14 | 41 | $k | 15
129 | R1810-2001 | Misc Hardware and hardware rework (1/2 fte loe) | 2007-05-01 | 260 | 2008-05-14 | 18 | 1 | 1810 | S2PR | 15 | 41 | $k | 10
130 | R1810-2001 | Misc Hardware and hardware rework (1/2 fte loe) | 2007-05-01 | 260 | 2008-05-14 | 18 | 1 | 1810 | S2PR | 15 | EM//TB | hr | 960
131 | R1810-2002 | Test out Equip & Procedures | 2007-10-11 | 7 | 2007-10-19 | 18 | 1 | 1810 | S2PX | 11 | EM//TB | hr | 140
132 | R1810-2023 | Install FIRST Holding 20 deg fixture | 2007-05-01 | 4 | 2007-05-04 | 18 | 1 | 1810 | S2PX | 11 | EM//TB | hr | 80
133 | R1810-2023 | Install FIRST Holding 20 deg fixture | 2007-05-01 | 4 | 2007-05-04 | 18 | 1 | 1810 | S2PX | 11 | 41 | $k | 2
134 | R1810-2025 | Install SECOND Holding 20 deg fixture | 2007-08-01 | 3 | 2007-08-03 | 18 | 1 | 1810 | S2PX | 11 | EM//TB | hr | 60
135 | R1810-2025 | Install SECOND Holding 20 deg fixture | 2007-08-01 | 3 | 2007-08-03 | 18 | 1 | 1810 | S2PX | 11 | 41 | $k | 2
136 | R1810-2027 | Install THIRD Holding 20 deg fixture | 2007-08-06 | 6 | 2007-08-13 | 18 | 1 | 1810 | S2PX | 11 | EM//TB | hr | 120
137 | R1810-2027 | Install THIRD Holding 20 deg fixture | 2007-08-06 | 6 | 2007-08-13 | 18 | 1 | 1810 | S2PX | 11 | 41 | $k | 2
138 | R1810-2029 | Install LAST Holding 20 deg fixture | 2007-08-14 | 3 | 2007-08-16 | 18 | 1 | 1810 | S2PX | 11 | EM//TB | hr | 60
139 | R1810-2029 | Install LAST Holding 20 deg fixture | 2007-08-14 | 3 | 2007-08-16 | 18 | 1 | 1810 | S2PX | 11 | 41 | $k | 2
140 | R1810-2004 | Receive Drawings & Hardware (shims & Bolts) | 2007-08-16 | 7 | 2007-08-24 | 18 | 1 | 1810 | S2PX | 12 | EM//TB | hr | 140
141 | R1810-2006 | Surface grind set of metal shims for qualificat | 2007-09-04 | 4 | 2007-09-07 | 18 | 1 | 1810 | S2PX | 12 | EM//TB | hr | 240
142 | R1810-207 | Compress alumina shims and sort | 2007-10-12 | 6 | 2007-10-19 | 18 | 1 | 1810 | S2PX | 12 | EM//TB | hr | 120
143 | R1810-209 | Perform metrology setup & checks | 2007-09-17 | 22 | 2007-10-16 | 18 | 1 | 1810 | S2PX | 12 | EM//TB | hr | 100
144 | R1810-2021 | Tools&tooling available for FPA operations | 2007-08-17 | 2 | 2007-08-20 | 18 | 1 | 1810 | S2PX | 13 | EM//TB | hr | 40
145 | R1810-2021 | Tools&tooling available for FPA operations | 2007-08-17 | 2 | 2007-08-20 | 18 | 1 | 1810 | S2PX | 13 | 41 | $k | 5
146 | R1810-2108 | HARDWARE,DRAWINGS,& PROCURES AVAILABLE STATION 2 |  | 0 | 2007-10-19 | 18 | 1 | 1810 | S2PX | 13 |  |  | 0
147 | S21-1.01 | Verify mating MC's A1,B1,C1 | 2007-05-01 | 4 | 2007-05-04 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 80
148 | S21-1.02 | Epoxy paint all close fitting interfacing surfac | 2007-05-07 | 3 | 2007-05-09 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 60
149 | S21-2.01 | Set A1 on pre-measured fixt, "B" side down | 2007-05-10 | 1 | 2007-05-10 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 20
150 | S21-2.02 | Align to the conical seats locking into of 8 | 2007-05-11 | 2 | 2007-05-14 | 18 |  | 1810 | S2PM | 11 | ZMET | met staff (budgeted in LOE) for ref only | 40
151 | S21-2.03 | Estab global coord sys on mc geometry. Meas monu | 2007-05-15 | 7 | 2007-05-23 | 18 |  | 1810 | S2PM | 11 | ZMET | met staff (budgeted in LOE) for ref only | 140
152 | S21-2.04 | Meas tooling ball monuments on winding form. | 2007-05-24 | 1 | 2007-05-24 | 18 |  | 1810 | S2PM | 11 | ZMET | met staff (budgeted in LOE) for ref only | 20
153 | S21-2.05 | Scan the "A" flange of the Type-A1 coil. | 2007-05-25 | 1 | 2007-05-25 | 18 |  | 1810 | S2PM | 11 | ZMET | met staff (budgeted in LOE) for ref only | 20
154 | S21-2.07 | Remove A1 coil from stand | 2007-05-29 | 1 | 2007-05-29 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 20
155 | S21-2.08 | Measure B1 "A" flange | 2007-05-30 | 14 | 2007-06-18 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 40
156 | S21-2.08 | Measure B1 "A" flange | 2007-05-30 | 14 | 2007-06-18 | 18 |  | 1810 | S2PM | 11 | ZMET | met staff (budgeted in LOE) for ref only | 220
157 | S21-2.11 | Measure C1 "A" flange | 2007-06-19 | 13 | 2007-07-06 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 40
158 | S21-2.11 | Measure C1 "A" flange | 2007-06-19 | 13 | 2007-07-06 | 18 |  | 1810 | S2PM | 11 | ZMET | met staff (budgeted in LOE) for ref only | 220
159 | S21-2.14 | Measure Type A1-A2 "A" flange | 2007-07-09 | 13 | 2007-07-25 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 40
160 | S21-2.14 | Measure Type A1-A2 "A" flange | 2007-07-09 | 13 | 2007-07-25 | 18 |  | 1810 | S2PM | 11 | ZMET | met staff (budgeted in LOE) for ref only | 220
161 | S21-3.02 | Grind shims first article f/assy process qu | 2007-07-26 | 4 | 2007-07-31 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 80
162 | S23-2.08 | Measure B3 "A" flange | 2007-10-10 | 14 | 2007-10-29 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 40
163 | S23-2.08 | Measure B3 "A" flange | 2007-10-10 | 14 | 2007-10-29 | 18 |  | 1810 | S2PM | 11 | ZMET | met staff (budgeted in LOE) for ref only | 220
164 | S23-2.11 | Measure C3 "A" flange | 2007-10-30 | 13 | 2007-11-15 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 40
165 | S23-2.11 | Measure C3 "A" flange | 2007-10-30 | 13 | 2007-11-15 | 18 |  | 1810 | S2PM | 11 | ZMET | met staff (budgeted in LOE) for ref only | 220
166 | S23-2.14 | Measure Type A3-A4 "A" flange | 2007-11-16 | 13 | 2007-12-06 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 40
167 | S23-2.14 | Measure Type A3-A4 "A" flange | 2007-11-16 | 13 | 2007-12-06 | 18 |  | 1810 | S2PM | 11 | ZMET | met staff (budgeted in LOE) for ref only | 220
168 | S25-2.08 | Measure B5 "A" flange | 2008-03-28 | 14 | 2008-04-16 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 40
169 | S25-2.08 | Measure B5 "A" flange | 2008-03-28 | 14 | 2008-04-16 | 18 |  | 1810 | S2PM | 11 | ZMET | met staff (budgeted in LOE) for ref only | 220
170 | S25-2.11 | Measure C5 "A" flange | 2008-04-17 | 13 | 2008-05-05 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 40
171 | S25-2.11 | Measure C5 "A" flange | 2008-04-17 | 13 | 2008-05-05 | 18 |  | 1810 | S2PM | 11 | ZMET | met staff (budgeted in LOE) for ref only | 220
172 | S25-2.14 | Measure Type A5-A6 "A" flange | 2008-05-06 | 13 | 2008-05-22 | 18 |  | 1810 | S2PM | 11 | EM//TB | hr | 40
173 | S25-2.14 | Measure Type A5-A6 "A" flange | 2008-05-06 | 13 | 2008-05-22 | 18 |  | 1810 | S2PM | 11 | ZMET | met staff (budgeted in LOE) for ref only | 220
174 | S21-4.02 | Perform metrology set-up and checks | 2007-08-01 | 2 | 2007-08-02 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
175 | S22-1.01 | Verify mating MC's of MCHP will come together | 2007-08-03 | 4 | 2007-08-08 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 80
176 | S22-1.02 | Epoxy paint all close fitting interfacing surfac | 2007-08-09 | 3 | 2007-08-13 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 60
177 | S22-2.08 | Set Type-B coil on fixt, ôBö side flange down. | 2007-08-14 | 2 | 2007-08-15 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 40
178 | S22-2.09 | Steps 2.02 thru 2.04 scan the "A" side flange. | 2007-08-16 | 5 | 2007-08-22 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 100
179 | S22-2.1 | Remove Type-B coil from stand and store coil. | 2007-08-23 | 1 | 2007-08-23 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
180 | S22-2.11 | Set Type-C coil on fixt, ôBö side flange down. | 2007-08-24 | 1 | 2007-08-24 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
181 | S22-2.12 | Steps 2.02 thru 2.04 scan the "A" side flange. | 2007-08-27 | 5 | 2007-08-31 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 100
182 | S22-2.13 | Remove Type-C coil from stand and store coil. | 2007-09-04 | 1 | 2007-09-04 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
183 | S22-3.02 | Compress alumina shims sort by thickness | 2007-09-05 | 3 | 2007-09-07 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 60
184 | S22-4.02 | Perform metrology set-up and checks | 2007-09-10 | 2 | 2007-09-11 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
185 | S23-1.01 | Verify mating MC's of MCHP will come together | 2007-09-12 | 4 | 2007-09-17 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 80
186 | S23-1.02 | Epoxy paint all close fitting interfacing surfac | 2007-09-18 | 3 | 2007-09-20 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 60
187 | S23-2.01 | Set the A3 coil on fixture, A side flange down | 2007-09-21 | 1 | 2007-09-21 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
188 | S23-2.02 | Align to the conical seats locking into min of 8 | 2007-09-24 | 2 | 2007-09-25 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
189 | S23-2.03 | Measure monuments on fixture and walls. | 2007-09-26 | 7 | 2007-10-04 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 140
190 | S23-2.04 | Measure tooling ball monuments | 2007-10-05 | 1 | 2007-10-05 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 20
191 | S23-2.05 | Scan the B flange of A3 | 2007-10-08 | 1 | 2007-10-08 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 20
192 | S23-2.07 | Remove A3 move to holding area. | 2007-10-09 | 1 | 2007-10-09 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
193 | S23-3.02 | Compress alumina shims sort by thickness | 2007-12-07 | 4 | 2007-12-12 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 60
194 | S23-4.02 | Perform metrology set-up and checks | 2007-12-13 | 2 | 2007-12-14 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
195 | S24-1.01 | Verify mating MC's of MCHP will come together | 2007-12-17 | 4 | 2007-12-20 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 80
196 | S24-1.02 | Epoxy paint all close fitting interfacing surfac | 2007-12-21 | 3 | 2008-01-03 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 60
197 | S24-2.01 | Set the A4 coil on fixture, A side flange down | 2008-01-04 | 1 | 2008-01-04 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
198 | S24-2.02 | Align to the conical seats locking into min of 8 | 2008-01-07 | 2 | 2008-01-08 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
199 | S24-2.03 | Measure monuments on fixture and walls. | 2008-01-09 | 2 | 2008-01-10 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
200 | S24-2.04 | Measure tooling ball monuments | 2008-01-11 | 1 | 2008-01-11 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 20
201 | S24-2.05 | Scan the B flange of A4 | 2008-01-14 | 1 | 2008-01-14 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 20
202 | S24-2.06 | Flip A4 "B" side dwn scan scan flange A | 2008-01-15 | 5 | 2008-01-21 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 100
203 | S24-2.07 | Remove A4 move to holding area. | 2008-01-22 | 1 | 2008-01-22 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
204 | S24-2.08 | Set B4 coil on fixt, B flange down. | 2008-01-23 | 2 | 2008-01-24 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 40
205 | S24-2.09 | Steps 2.02 thru 2.04 scan the "A" side flange. | 2008-01-25 | 5 | 2008-01-31 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 100
206 | S24-2.1 | Remove B4 from stand and store coil. | 2008-02-01 | 1 | 2008-02-01 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
207 | S24-2.11 | Set C4 on fixt, B flange down. | 2008-02-04 | 1 | 2008-02-04 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
208 | S24-2.12 | Steps 2.02 thru 2.04 scan the "A" side flange. | 2008-02-05 | 5 | 2008-02-11 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 100
209 | S24-2.13 | Remove C4 coil from stand and store coil. | 2008-02-12 | 1 | 2008-02-12 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
210 | S24-2.14 | Set MCHP A4 coil on fix, A flange dw | 2008-02-13 | 1 | 2008-02-13 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
211 | S24-2.15 | Steps 2.02 thru 2.04scan the "B" side flange. | 2008-02-14 | 5 | 2008-02-20 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 100
212 | S24-3.02 | Compress alumina shims sort by thickness | 2008-02-21 | 4 | 2008-02-26 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 60
213 | S24-4.02 | Perform metrology set-up and checks | 2008-02-27 | 2 | 2008-02-28 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
214 | S25-1.01 | Verify mating MC's of MCHP will come together | 2008-02-29 | 4 | 2008-03-05 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 80
215 | S25-1.02 | Epoxy paint all close fitting interfacing surfac | 2008-03-06 | 3 | 2008-03-10 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 60
216 | S25-2.01 | Set the A5 coil on fixture, A side flange down | 2008-03-11 | 1 | 2008-03-11 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
217 | S25-2.02 | Align to the conical seats locking into min of 8 | 2008-03-12 | 2 | 2008-03-13 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
218 | S25-2.03 | Measure monuments on fixture and walls. | 2008-03-14 | 7 | 2008-03-24 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 140
219 | S25-2.04 | Measure tooling ball monuments | 2008-03-25 | 1 | 2008-03-25 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 20
220 | S25-2.05 | Scan the B flange of A5 | 2008-03-26 | 1 | 2008-03-26 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 20
221 | S25-2.07 | Remove A5 move to holding area. | 2008-03-27 | 1 | 2008-03-27 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
222 | S25-3.02 | Compress alumina shims sort by thickness | 2008-05-23 | 4 | 2008-05-29 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 60
223 | S25-4.02 | Perform metrology set-up and checks | 2008-05-30 | 2 | 2008-06-02 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
224 | S26-1.01 | Verify mating MC's of MCHP will come together | 2008-06-03 | 4 | 2008-06-06 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 80
225 | S26-1.02 | Epoxy paint all close fitting interfacing surfac | 2008-06-09 | 3 | 2008-06-11 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 60
226 | S26-2.01 | Set the A6 coil on fixture, A side flange down | 2008-06-12 | 1 | 2008-06-12 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
227 | S26-2.02 | Align to the conical seats locking into min of 8 | 2008-06-13 | 2 | 2008-06-16 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
228 | S26-2.03 | Measure monuments on fixture and walls. | 2008-06-17 | 2 | 2008-06-18 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
229 | S26-2.04 | Measure tooling ball monuments | 2008-06-19 | 1 | 2008-06-19 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 20
230 | S26-2.05 | Scan the B flange of A6 | 2008-06-20 | 1 | 2008-06-20 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 20
231 | S26-2.06 | Flip A6 "B" side dwn scan scan flange A | 2008-06-23 | 5 | 2008-06-27 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 100
232 | S26-2.07 | Remove A6 move to holding area. | 2008-06-30 | 1 | 2008-06-30 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
233 | S26-2.08 | Set B6 coil on fixt, B flange down. | 2008-07-01 | 2 | 2008-07-02 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 40
234 | S26-2.09 | Steps 2.02 thru 2.04 scan the "A" side flange. | 2008-07-03 | 5 | 2008-07-10 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 100
235 | S26-2.1 | Remove B6 from stand and store coil. | 2008-07-11 | 1 | 2008-07-11 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
236 | S26-2.11 | Set C6 on fixt, B flange down. | 2008-07-14 | 1 | 2008-07-14 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
237 | S26-2.12 | Steps 2.02 thru 2.04 scan the "A" side flange. | 2008-07-15 | 5 | 2008-07-21 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 100
238 | S26-2.13 | Remove C6 coil from stand and store coil. | 2008-07-22 | 1 | 2008-07-22 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
239 | S26-2.14 | Set MCHP A6 coil on fix, A flange dw | 2008-07-23 | 1 | 2008-07-23 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 20
240 | S26-2.15 | Steps 2.02 thru 2.04scan the "B" side flange. | 2008-07-24 | 5 | 2008-07-30 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 100
241 | S26-3.02 | Compress alumina shims sort by thickness | 2008-07-31 | 4 | 2008-08-05 | 18 |  | 1810 | S2PM | 14 | EM//TB | hr | 60
242 | S26-4.02 | Perform metrology set-up and checks | 2008-08-06 | 2 | 2008-08-07 | 18 |  | 1810 | S2PM | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
243 | S21-3.03 | Ready For Preassembly A1B1C1 |  | 0 | 2007-08-02 | 18 |  | 1810 | S2PM | 15 |  |  | 0
244 | S22-4.03 | Ready For Preassembly A2B2C2 |  | 0 | 2007-09-11 | 18 |  | 1810 | S2PM | 15 |  |  | 0
245 | S23-4.03 | Ready For Preassembly A3B3C3 | 2007-12-17 | 0 | 2007-12-14 | 18 |  | 1810 | S2PM | 15 |  |  | 0
246 | S24-4.03 | Ready For Preassembly A4B4C4 | 2008-02-29 | 0 | 2008-02-28 | 18 |  | 1810 | S2PM | 15 |  |  | 0
247 | S25-4.03 | Ready For Preassembly A5B5C5 | 2008-06-03 | 0 | 2008-06-02 | 18 |  | 1810 | S2PM | 15 |  |  | 0
248 | S26-4.03 | Ready For Preassembly A6B6C6 | 2008-08-08 | 0 | 2008-08-07 | 18 |  | 1810 | S2PM | 15 |  |  | 0
249 | S21-5.00 | BEGIN A-A Pre-assembly |  | 0 | 2007-08-02 | 18 |  | 1810 | S2P1 | 11 |  |  | 0
250 | S21-5.01 | Place A2 "B" side down. Obtain fiduals | 2007-08-14 | 2 | 2007-08-15 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 40
251 | S21-5.02 | Align to the conical seats locking into 8. | 2007-08-16 | 1 | 2007-08-16 | 18 |  | 1810 | S2P1 | 11 | ZMET | met staff (budgeted in LOE) for ref only | 20
252 | S21-5.03 | Meas monuments on fixture & walls. | 2007-08-17 | 2 | 2007-08-20 | 18 |  | 1810 | S2P1 | 11 | ZMET | met staff (budgeted in LOE) for ref only | 40
253 | S21-5.04 | Place shims on coil identical to A1-A2 fit up | 2007-08-21 | 1 | 2007-08-21 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 10
254 | S21-5.05 | Install dial indicators on the MC to see deflec | 2007-08-22 | 1 | 2007-08-22 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 40
255 | S21-5.06 | Lower mating A1 modular coil into position. | 2007-08-23 | 1 | 2007-08-23 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
256 | S21-5.07 | Meas monuments bottom coil. Jack to .002ö | 2007-08-24 | 1 | 2007-08-24 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
257 | S21-5.08 | Using 3 points, position as was done inA1A2 fit | 2007-08-27 | 1 | 2007-08-27 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
258 | S21-5.09 | Torque to 50% | 2007-08-28 | 2 | 2007-08-29 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 40
259 | S21-5.1 | Make "wiggle" test Tighten bolt and recheck. | 2007-08-30 | 1 | 2007-08-30 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
260 | S21-5.11 | Meas tooling balls both coils. | 2007-08-31 | 5 | 2007-09-07 | 18 |  | 1810 | S2P1 | 11 | ZMET | met staff (budgeted in LOE) for ref only | 100
261 | S21-5.12 | Adjust shims locally. Re-torque all studs to 50% | 2007-09-10 | 3 | 2007-09-12 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 60
262 | S21-5.14 | Install A-A locator bushings | 2007-09-13 | 2 | 2007-09-14 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 40
263 | S21-5.15 | Remove studs,nuts,shims. Identify shim locations | 2007-09-17 | 1 | 2007-09-17 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
264 | S21-6.01 | Place Type A "A" side down. Obtain fiduals | 2007-09-18 | 2 | 2007-09-19 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 40
265 | S21-6.02 | Align to the conical seats locking into 8. | 2007-09-20 | 1 | 2007-09-20 | 18 |  | 1810 | S2P1 | 11 | ZMET | met staff (budgeted in LOE) for ref only | 20
266 | S21-6.03 | Meas monuments on fixture & walls. | 2007-09-21 | 2 | 2007-09-24 | 18 |  | 1810 | S2P1 | 11 | ZMET | met staff (budgeted in LOE) for ref only | 40
267 | S21-6.04 | Place the an initial set shims on coil | 2007-09-25 | 2 | 2007-09-26 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 40
268 | S21-6.041 | Stuff shim bag w/fiberglass & place on wing | 2007-09-27 | 1 | 2007-09-27 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 5
269 | S21-6.05 | Lower the Type-B coil onto the Type-A coil. | 2007-09-28 | 1 | 2007-09-28 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
270 | S21-6.06 | Measure monuments on A coil. Jack to .002ö | 2007-10-01 | 1 | 2007-10-01 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
271 | S21-6.061 | instl dial indicators for x-y positioning | 2007-10-02 | 1 | 2007-10-02 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
272 | S21-6.07 | Perform the X-Y positioning of the B coil. | 2007-10-03 | 1 | 2007-10-03 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
273 | S21-6.08 | Install remaining metal shims torque to 50% | 2007-10-04 | 2 | 2007-10-05 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 40
274 | S21-6.09 | Make "wiggle" test Tighten bolt and recheck. | 2007-10-08 | 1 | 2007-10-08 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
275 | S21-6.1 | Measure the tooling balls on both coils. | 2007-10-09 | 5 | 2007-10-15 | 18 |  | 1810 | S2P1 | 11 | ZMET | met staff (budgeted in LOE) for ref only | 100
276 | S21-6.11 | Loosen studs, adjust shims. Re-torque to 50%. | 2007-10-16 | 3 | 2007-10-18 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 60
277 | S21-6.12 | Install alumina shims. Re-torque to 50%. | 2007-10-22 | 1 | 2007-10-22 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
278 | S21-6.13 | Make "wiggle" test Tighten bolt and recheck. | 2007-10-23 | 1 | 2007-10-23 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
279 | S21-6.14 | Measuretooling balls . The max devi .007ö . | 2007-10-24 | 5 | 2007-10-30 | 18 |  | 1810 | S2P1 | 11 | ZMET | met staff (budgeted in LOE) for ref only | 100
280 | S21-6.15 | Loosen studs, adjust shims. Re-torque to 50%. | 2007-10-31 | 3 | 2007-11-02 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 60
281 | S21-6.16 | Install bushing. Tighten back to 50% | 2007-11-05 | 1 | 2007-11-05 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 30
282 | S21-6.17 | Complete tightening of flange bolts to 100%. | 2007-11-06 | 1 | 2007-11-06 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
283 | S21-6.18 | Measuretooling balls . The max devi .007ö . | 2007-11-07 | 2 | 2007-11-08 | 18 |  | 1810 | S2P1 | 11 | ZMET | met staff (budgeted in LOE) for ref only | 40
284 | S21-6.19 | Scan the ôBö flange of Type-B coil | 2007-11-09 | 1 | 2007-11-09 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
285 | S21-7.01 | Place ôA/Bö assy, ôAö coil dwn, on 40deg fix. | 2007-11-12 | 3 | 2007-11-14 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 60
286 | S21-7.02 | Align to the conical seats locking into a min of | 2007-11-15 | 1 | 2007-11-15 | 18 |  | 1810 | S2P1 | 11 | ZMET | met staff (budgeted in LOE) for ref only | 20
287 | S21-7.03 | Measure the monuments on the fixture & the walls | 2007-11-16 | 2 | 2007-11-19 | 18 |  | 1810 | S2P1 | 11 | ZMET | met staff (budgeted in LOE) for ref only | 40
288 | S21-7.04 | Place initial set metal shims on the coil | 2007-11-20 | 2 | 2007-11-21 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 40
289 | S21-7.05 | Lower the Type-C coil onto the Type-B coil. | 2007-11-22 | 1 | 2007-11-22 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
290 | S21-7.06 | Meas monuments on A coil to eval displacement. | 2007-11-23 | 1 | 2007-11-23 | 18 |  | 1810 | S2P1 | 11 | ZMET | met staff (budgeted in LOE) for ref only | 20
291 | S21-7.07 | Perform the X-Y positioning of the coil. | 2007-11-26 | 1 | 2007-11-26 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
292 | S21-7.08 | Install remaining metal shims torque to 50% | 2007-11-27 | 2 | 2007-11-28 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 40
293 | S21-7.09 | "wiggle" test Tighten bolt and recheck. | 2007-12-03 | 1 | 2007-12-03 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
294 | S21-7.1 | Measure the tooling balls on all coils. | 2007-12-04 | 5 | 2007-12-10 | 18 |  | 1810 | S2P1 | 11 | ZMET | met staff (budgeted in LOE) for ref only | 100
295 | S21-7.11 | adjust shims locally. Re-torque all studs to 50% | 2007-12-11 | 3 | 2007-12-13 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 60
296 | S21-7.12 | Iinstall alumina shims. Re-torque all studs to | 2007-12-14 | 1 | 2007-12-14 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
297 | S21-7.13 | "wiggle" test Tighten bolt and recheck. | 2007-12-17 | 1 | 2007-12-17 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
298 | S21-7.14 | Measure the tooling balls on all coils. | 2007-12-18 | 5 | 2008-01-02 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 100
299 | S21-7.15 | adjust shims locally. Re-torque all studs to 50 | 2008-01-03 | 3 | 2008-01-07 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 60
300 | S21-7.16 | Install bushing. | 2008-01-08 | 2 | 2008-01-09 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 30
301 | S21-7.17 | Complete tightening of flange bolts to 100%. | 2008-01-10 | 1 | 2008-01-10 | 18 |  | 1810 | S2P1 | 11 | EM//TB | hr | 20
302 | DOE-1 | Notify DOE of scheduled station 3 lifts |  | 0 | 2008-01-02 | 18 | 1 | 1810 | S2P1 | 12 |  |  | 0
303 | DOE-2 | DOE review lift procedures | 2008-01-03 | 30 | 2008-02-13 | 18 | 1 | 1810 | S2P1 | 12 |  |  | 0
304 | DOE-3 | DOE approval of scheduled station 3 lifts |  | 0 | 2008-02-13 | 18 | 1 | 1810 | S2P1 | 12 |  |  | 0
305 | S21-11.01 | Identify primary fiducials for positioning Sta 3 | 2008-01-11 | 1 | 2008-01-11 | 18 |  | 1810 | S2P1 | 12 | EM//TB | hr | 20
306 | S21-7.18 | Final metrology meas. Scan ôBö flangeType-C coil | 2008-01-14 | 5 | 2008-01-18 | 18 |  | 1810 | S2P1 | 12 | ZMET | met staff (budgeted in LOE) for ref only | 100
307 | S21-8.01 | Tack weld inboard shims | 2008-01-21 | 2 | 2008-01-22 | 18 |  | 1810 | S2P1 | 12 | EM//TB | hr | 40
308 | S21-9.01 | Install trim coil | 2008-01-23 | 6 | 2008-01-30 | 18 |  | 1810 | S2P1 | 12 | EM//TB | hr | 120
309 | S21-10.01 | Install all wing support bladders | 2008-01-31 | 2 | 2008-02-01 | 18 |  | 1810 | S2P1 | 13 | EM//TB | hr | 40
310 | S21-10.02 | Make local service runs/connections | 2008-01-31 | 8 | 2008-02-11 | 18 |  | 1810 | S2P1 | 13 | EM//TB | hr | 160
311 | S21-10.03 | Inject stycast in all shim spaces | 2008-01-31 | 1 | 2008-01-31 | 18 |  | 1810 | S2P1 | 13 | EM//TB | hr | 20
312 | S21-11.03 | Measure bolt length on all tension fasteners | 2008-02-14 | 0 | 2008-02-13 | 18 |  | 1810 | S2P1 | 13 | EM//TB | hr | 0
313 | S21-11.04 | Mark part for identification | 2008-02-14 | 0 | 2008-02-13 | 18 |  | 1810 | S2P1 | 13 | EM//TB | hr | 0
314 | S21-11.05 | Install lift support beams | 2008-02-12 | 2 | 2008-02-13 | 18 |  | 1810 | S2P1 | 13 | EM//TB | hr | 40
315 | S21-11.06 | Remove from stand & measure weight of assy | 2008-02-14 | 1 | 2008-02-14 | 18 |  | 1810 | S2P1 | 13 | EM//TB | hr | 20
316 | S21-11.07 | Move A1-B1-C1 to holding area. | 2008-02-15 | 0 | 2008-02-14 | 18 |  | 1810 | S2P1 | 13 | EM//TB | hr | 0
317 | S22-6.01 | A2 ôAö flange dwn, 20deg fixt.Obtain fiduci | 2007-11-12 | 1 | 2007-11-12 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 20
318 | S22-6.02 | Align to the conical seats locking into a min of | 2007-11-13 | 1 | 2007-11-13 | 18 |  | 1810 | S2PZ | 14 | ZMET | met staff (budgeted in LOE) for ref only | 20
319 | S22-6.03 | Measure monuments on fixture and on the walls. | 2007-11-14 | 2 | 2007-11-15 | 18 |  | 1810 | S2PZ | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
320 | S22-6.04 | Place alumina grind inboard weld shims on coil. | 2007-11-16 | 2 | 2007-11-19 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 40
321 | S22-6.05 | Lower the Type-B coil onto the Type-A coil. | 2007-11-20 | 1 | 2007-11-20 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 20
322 | S22-6.06 | Meas monuments on A coil. Jack to within .002ö | 2007-11-21 | 1 | 2007-11-21 | 18 |  | 1810 | S2PZ | 14 | ZMET | met staff (budgeted in LOE) for ref only | 20
323 | S22-6.07 | Perform the X-Y positioning of the B coil. | 2007-11-22 | 1 | 2007-11-22 | 18 |  | 1810 | S2PZ | 14 | ZMET | met staff (budgeted in LOE) for ref only | 20
324 | S22-6.08 | Install studs, supernuts, torque to 50% of final | 2007-11-23 | 2 | 2007-11-26 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 40
325 | S22-6.09 | "wiggle" test Tighten bolt and recheck. | 2007-11-27 | 1 | 2007-11-27 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 20
326 | S22-6.1 | Meas tooling balls on both coils. max devi .007ö | 2007-11-28 | 5 | 2007-12-06 | 18 |  | 1810 | S2PZ | 14 | ZMET | met staff (budgeted in LOE) for ref only | 100
327 | S22-6.11 | adjust shims locally. Re-torque all studs to 50% | 2007-12-07 | 3 | 2007-12-11 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 60
328 | S22-6.12 | Install bushing. | 2007-12-12 | 2 | 2007-12-13 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 30
329 | S22-6.13 | Complete tightening of flange bolts to 100%. | 2007-12-14 | 1 | 2007-12-14 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 20
330 | S22-6.14 | Measure the tooling balls on both coils. | 2007-12-17 | 3 | 2007-12-19 | 18 |  | 1810 | S2PZ | 14 | ZMET | met staff (budgeted in LOE) for ref only | 60
331 | S22-6.15 | Scan the ôBö flange of Type-B coil | 2007-12-20 | 1 | 2007-12-20 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 20
332 | S22-7.01 | ôA/Bö assy ôAö coil dwn, 40deg fixt.Obtain fiduc | 2007-12-21 | 2 | 2008-01-02 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 40
333 | S22-7.02 | Align to the conical seats locking into min of 8 | 2008-01-03 | 1 | 2008-01-03 | 18 |  | 1810 | S2PZ | 14 | ZMET | met staff (budgeted in LOE) for ref only | 20
334 | S22-7.03 | Measure monuments on fixture and walls. | 2008-01-04 | 2 | 2008-01-07 | 18 |  | 1810 | S2PZ | 14 | ZMET | met staff (budgeted in LOE) for ref only | 40
335 | S22-7.04 | Place alumin grind inboard weld shims on coil. | 2008-01-08 | 2 | 2008-01-09 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 40
336 | S22-7.05 | Lower the Type-C coil onto the Type-B coil. | 2008-01-10 | 1 | 2008-01-10 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 20
337 | S22-7.06 | Meas monuments on A coil for displacements. | 2008-01-11 | 1 | 2008-01-11 | 18 |  | 1810 | S2PZ | 14 | ZMET | met staff (budgeted in LOE) for ref only | 20
338 | S22-7.07 | Perform the X-Y positioning of the coil. | 2008-01-14 | 1 | 2008-01-14 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 20
339 | S22-7.08 | Install studs, supernuts, torque to 50% of fina | 2008-01-15 | 2 | 2008-01-16 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 40
340 | S22-7.09 | "wiggle" test Tighten bolt and recheck. | 2008-01-17 | 1 | 2008-01-17 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 20
341 | S22-7.1 | Measure the tooling balls on all coils. | 2008-01-18 | 5 | 2008-01-24 | 18 |  | 1810 | S2PZ | 14 | ZMET | met staff (budgeted in LOE) for ref only | 100
342 | S22-7.11 | Install bushing. Replace nut and tighten to 50% | 2008-01-25 | 1 | 2008-01-25 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 30
343 | S22-7.12 | Complete tightening of flange bolts to 100%. | 2008-01-28 | 1 | 2008-01-28 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 20
344 | S22-7.13 | Measure the tooling balls on both coils. | 2008-01-29 | 4 | 2008-02-01 | 18 |  | 1810 | S2PZ | 14 | ZMET | met staff (budgeted in LOE) for ref only | 80
345 | S22-8.01 | Tack weld all inboard shims to one flange | 2008-02-04 | 1 | 2008-02-04 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 20
346 | S22-9.01 | Install trim coil | 2008-02-05 | 6 | 2008-02-12 | 18 |  | 1810 | S2PZ | 14 | EM//TB | hr | 120
347 | S22-10.01 | Install all wing support bladders | 2008-02-13 | 2 | 2008-02-14 | 18 |  | 1810 | S2PZ | 16 | EM//TB | hr | 40
348 | S22-10.02 | local service connections on each MC. | 2008-02-15 | 8 | 2008-02-26 | 18 |  | 1810 | S2PZ | 16 | EM//TB | hr | 160
349 | S22-10.03 | Inject stycast to fill in all shim spaces | 2008-02-27 | 1 | 2008-02-27 | 18 |  | 1810 | S2PZ | 16 | EM//TB | hr | 20
350 | S22-11.01 | Install or identify three primary fiducials | 2008-02-28 | 1 | 2008-02-28 | 18 |  | 1810 | S2PZ | 16 | EM//TB | hr | 20
351 | S22-11.02 | Final metrology measurement of all fiducials. | 2008-02-29 | 5 | 2008-03-06 | 18 |  | 1810 | S2PZ | 16 | ZMET | met staff (budgeted in LOE) for ref only | 100
352 | S22-11.03 | Tension tester measure bolt length | 2008-03-07 | 1 | 2008-03-07 | 18 |  | 1810 | S2PZ | 16 | EM//TB | hr | 10
353 | S22-11.04 | Mark part for identification | 2008-03-10 | 0 | 2008-03-07 | 18 |  | 1810 | S2PZ | 16 | EM//TB | hr | 0
354 | S22-11.05 | Install lift support beams | 2008-03-10 | 2 | 2008-03-11 | 18 |  | 1810 | S2PZ | 16 | EM//TB | hr | 40
355 | S22-11.06 | Remove from stand Move A2-B2-C2 to holding area | 2008-03-12 | 2 | 2008-03-13 | 18 |  | 1810 | S2PZ | 16 | EM//TB | hr | 40
356 | S23-A3B3C3 | Assemble/Align Mod-Coils A3/B3/C3 | 2008-02-15 | 118 | 2008-07-31 | 18 |  | 1810 | S2P2 |  | EM//TB | hr | 1755
357 | S23-A3B3C3 | Assemble/Align Mod-Coils A3/B3/C3 | 2008-02-15 | 118 | 2008-07-31 | 18 |  | 1810 | S2P2 |  | ZMET | met staff (budgeted in LOE) for ref only | 740
358 | S24-A4B4C4 | Assemble/Align Mod-Coils A4/B4/C4 | 2008-03-20 | 79 | 2008-07-10 | 18 |  | 1810 | S2P2 |  | EM//TB | hr | 970
359 | S24-A4B4C4 | Assemble/Align Mod-Coils A4/B4/C4 | 2008-03-20 | 79 | 2008-07-10 | 18 |  | 1810 | S2P2 |  | ZMET | met staff (budgeted in LOE) for ref only | 620
360 | S25-A5B5C5 | Assemble/Align Mod-Coils A5/B5/C5 | 2008-09-02 | 118 | 2009-02-25 | 18 |  | 1810 | S2P3 |  | EM//TB | hr | 1755
361 | S25-A5B5C5 | Assemble/Align Mod-Coils A5/B5/C5 | 2008-09-02 | 118 | 2009-02-25 | 18 |  | 1810 | S2P3 |  | ZMET | met staff (budgeted in LOE) for ref only | 740
362 | S26-A6B6C6 | Assemble/Align Mod-Coils A6/B6/C6 | 2008-10-06 | 79 | 2009-02-04 | 18 |  | 1810 | S2P3 |  | EM//TB | hr | 970
363 | S26-A6B6C6 | Assemble/Align Mod-Coils A6/B6/C6 | 2008-10-06 | 79 | 2009-02-04 | 18 |  | 1810 | S2P3 |  | ZMET | met staff (budgeted in LOE) for ref only | 620
364 | R1810-3102 | Misc M&S | 2008-04-03 | 65 | 2008-07-03 | 18 | 1 | 1810 | S3P0 | 10 | 41 | $k | 5
365 | R1810-3103 | Install station 3 platforms (8 required) | 2007-10-30 | 4 | 2007-11-02 | 18 | 1 | 1810 | S3P0 | 11 | EM//TB | hr | 112
366 | R1810-3103 | Install station 3 platforms (8 required) | 2007-10-30 | 4 | 2007-11-02 | 18 | 1 | 1810 | S3P0 | 11 | 41 | $k | 10
367 | R1810-3104 | Procure 3 legged actuator system | 2007-10-01 | 20 | 2007-10-26 | 18 | 1 | 1810 | S3P0 | 12 | 41 | $k | 43
368 | R1810-3106 | Load test 3 ledded actuator system | 2007-10-29 | 3 | 2007-10-31 | 18 | 1 | 1810 | S3P0 | 13 | EM//TB | hr | 96
369 | R1810-3108 | Procure ,Fabricate 3 legged actuator lift fixtur | 2007-10-01 | 20 | 2007-10-26 | 18 | 1 | 1810 | S3P0 | 14 | 41 | $k | 6
370 | R1810-3112 | Load Test 3 legged actuator lift fixtur | 2007-10-29 | 8 | 2007-11-07 | 18 | 1 | 1810 | S3P0 | 15 | EM//TB | hr | 128
371 | R1810-3150 | Fab New legs | 2007-10-01 | 4 | 2007-10-04 | 18 | 1 | 1810 | S3P0 | 16 | EM//TB | hr | 64
372 | R1810-3107 | Test out station 3 equipment and procedures | 2007-11-05 | 4 | 2007-11-08 | 18 | 1 | 1810 | S3P0 | 17 | 41 | $k | 10
373 | R1810-3109 | Begin assy of first field period assy | 2007-11-09 | 2 | 2007-11-12 | 18 | 1 | 1810 | S3P0 | 17 | 41 | $k | 40
374 | R1810-2109 | Begin Station 3 | 2008-01-23 | 0 |  | 18 | 1 | 1810 | S3P1 | 01 |  |  | 0
375 | S31-1.01 | Install Station 3 site monuments | 2008-01-23 | 3 | 2008-01-25 | 18 | 1 | 1810 | S3P1 | 11 | 41 | $k | 2
376 | S31-1.01 | Install Station 3 site monuments | 2008-01-23 | 3 | 2008-01-25 | 18 | 1 | 1810 | S3P1 | 11 | EM//TB | hr | 60
377 | S31-1.02 | Install floor mounted tracks and VV base support | 2008-01-28 | 5 | 2008-02-01 | 18 | 1 | 1810 | S3P1 | 12 | 41 | $k | 1
378 | S31-1.02 | Install floor mounted tracks and VV base support | 2008-01-28 | 5 | 2008-02-01 | 18 | 1 | 1810 | S3P1 | 12 | EM//TB | hr | 100
379 | S31-1.03 | Establish the MCHP CG location. | 2008-02-04 | 2 | 2008-02-05 | 18 | 1 | 1810 | S3P1 | 15 | EM//TB | hr | 40
380 | S31-2.01 | Install MCHP support cart assemblies | 2008-02-06 | 4 | 2008-02-11 | 18 | 1 | 1810 | S3P1 | 16 | EM//TB | hr | 80
381 | S31-2.02 | Verify cart motion. | 2008-02-12 | 2 | 2008-02-13 | 18 | 1 | 1810 | S3P1 | 17 | EM//TB | hr | 40
382 | S31-2.03 | Install adjustor bar support weldment | 2008-02-14 | 0 | 2008-02-13 | 18 | 1 | 1810 | S3P1 | 18 | EM//TB | hr | 0
383 | S31-2.04 | Position left MCHP on the cart assembly | 2008-02-15 | 1 | 2008-02-15 | 18 | 1 | 1810 | S3P1 | 19 | EM//TB | hr | 20
384 | S31-2.05 | Secure left MCHP on support cart base. | 2008-02-18 | 2 | 2008-02-19 | 18 | 1 | 1810 | S3P1 | 20 | EM//TB | hr | 40
385 | S31-2.06 | Measure monuments on left MCHP and walls | 2008-02-20 | 5 | 2008-02-26 | 18 | 1 | 1810 | S3P1 | 21 | EM//TB | hr | 0
386 | S31-2.06 | Measure monuments on left MCHP and walls | 2008-02-20 | 5 | 2008-02-26 | 18 | 1 | 1810 | S3P1 | 21 | ZMET | met staff (budgeted in LOE) for ref only | 100
387 | S31-2.07 | Set positioning stop on the cart | 2008-02-27 | 1 | 2008-02-27 | 18 | 1 | 1810 | S3P1 | 22 | EM//TB | hr | 20
388 | S31-3.01 | Move right base support cart to its final positi | 2008-02-28 | 1 | 2008-02-28 | 18 | 1 | 1810 | S3P1 | 23 | EM//TB | hr | 10
389 | S31-3.02 | Lift the right side MCHP and position | 2008-03-14 | 1 | 2008-03-14 | 18 | 1 | 1810 | S3P1 | 24 | EM//TB | hr | 20
390 | S31-3.03 | Temporary fasteners bring the parts together. | 2008-03-17 | 0 | 2008-03-14 | 18 | 1 | 1810 | S3P1 | 25 | EM//TB | hr | 0
391 | S31-3.04 | AirLoc Wedgemount leveler to take load. | 2008-03-17 | 0 | 2008-03-14 | 18 | 1 | 1810 | S3P1 | 26 | EM//TB | hr | 0
392 | S31-3.05 | Install temp scaffolding to install flange hw | 2008-03-17 | 1 | 2008-03-17 | 18 | 1 | 1810 | S3P1 | 27 | EM//TB | hr | 20
393 | S31-3.06 | Install bolts and shims | 2008-03-18 | 1 | 2008-03-18 | 18 | 1 | 1810 | S3P1 | 28 | EM//TB | hr | 20
394 | S31-3.07 | Tighten flange fasteners to 50% | 2008-03-19 | 1 | 2008-03-19 | 18 | 1 | 1810 | S3P1 | 29 | EM//TB | hr | 20
395 | S31-3.08 | Perform metrology measurements | 2008-03-20 | 5 | 2008-03-26 | 18 | 1 | 1810 | S3P1 | 30 | EM//TB | hr | 0
396 | S31-3.08 | Perform metrology measurements | 2008-03-20 | 5 | 2008-03-26 | 18 | 1 | 1810 | S3P1 | 30 | ZMET | met staff (budgeted in LOE) for ref only | 100
397 | S31-3.09 | Perform position adjust on right side MCHP | 2008-03-27 | 2 | 2008-03-28 | 18 | 1 | 1810 | S3P1 | 31 | EM//TB | hr | 40
398 | S31-3.1 | Verify position of the VV support hanger | 2008-03-31 | 3 | 2008-04-02 | 18 | 1 | 1810 | S3P1 | 32 | EM//TB | hr | 0
399 | S31-3.1 | Verify position of the VV support hanger | 2008-03-31 | 3 | 2008-04-02 | 18 | 1 | 1810 | S3P1 | 32 | ZMET | met staff (budgeted in LOE) for ref only | 60
400 | S31-3.11 | Remove flange hardware and temp platforms | 2008-04-03 | 1 | 2008-04-03 | 18 | 1 | 1810 | S3P1 | 33 | EM//TB | hr | 20
401 | S31-4.01 | EMeasure monuments on the MCHP's &walls. | 2008-04-04 | 2 | 2008-04-07 | 18 | 1 | 1810 | S3P1 | 34 | EM//TB | hr | 0
402 | S31-4.01 | EMeasure monuments on the MCHP's &walls. | 2008-04-04 | 2 | 2008-04-07 | 18 | 1 | 1810 | S3P1 | 34 | ZMET | met staff (budgeted in LOE) for ref only | 40
403 | S31-4.01 | EMeasure monuments on the MCHP's &walls. | 2008-04-04 | 2 | 2008-04-07 | 18 | 1 | 1810 | S3P1 | 34 | 41 | $k | 2
404 | S31-4.02 | Place all of the laser screens | 2008-04-08 | 2 | 2008-04-09 | 18 | 1 | 1810 | S3P1 | 35 | EM//TB | hr | 40
405 | S31-4.03 | Determine laser alignment. | 2008-04-10 | 1 | 2008-04-10 | 18 | 1 | 1810 | S3P1 | 36 | EM//TB | hr | 20
406 | S31-4.04 | mount the milar on the screens. | 2008-04-11 | 1 | 2008-04-11 | 18 | 1 | 1810 | S3P1 | 37 | EM//TB | hr | 0
407 | S31-4.05 | Disengage MCHP's to move the left MCHP. | 2008-04-14 | 1 | 2008-04-14 | 18 | 1 | 1810 | S3P1 | 38 | EM//TB | hr | 20
408 | S31-4.06 | Remove both MCHP's. | 2008-04-15 | 2 | 2008-04-16 | 18 | 1 | 1810 | S3P1 | 39 | EM//TB | hr | 40
409 | S31-5.01 | Remove the adjustor bar support from left side. | 2008-04-17 | 0 | 2008-04-16 | 18 | 1 | 1810 | S3P1 | 40 | EM//TB | hr | 0
410 | S31-5.02 | Install VV NBI port support stand. | 2008-04-17 | 2 | 2008-04-18 | 18 | 1 | 1810 | S3P1 | 41 | EM//TB | hr | 40
411 | S31-5.03 | Install VVSA to base support | 2008-04-21 | 1 | 2008-04-21 | 18 | 1 | 1810 | S3P1 | 42 | EM//TB | hr | 20
412 | S31-5.04 | Secure the VVSA to base & NBI port sprt stand. | 2008-04-22 | 2 | 2008-04-23 | 18 | 1 | 1810 | S3P1 | 43 | EM//TB | hr | 40
413 | S31-6.01 | Install bumper protection components on the VV | 2008-04-24 | 1 | 2008-04-24 | 18 | 1 | 1810 | S3P1 | 44 | EM//TB | hr | 10
414 | S31-6.02 | Position AirLoc Wedgemount in lower position. | 2008-04-25 | 0 | 2008-04-24 | 18 | 1 | 1810 | S3P1 | 45 | EM//TB | hr | 0
415 | S31-6.03 | move the left MCHP over the VV. | 2008-04-25 | 2 | 2008-04-28 | 18 | 1 | 1810 | S3P1 | 46 | EM//TB | hr | 40
416 | S31-6.04 | Re-install the left adjustor bar. | 2008-04-29 | 0 | 2008-04-28 | 18 | 1 | 1810 | S3P1 | 47 | EM//TB | hr | 0
417 | S31-6.05 | Make adjustments to properly align MCHP. | 2008-04-29 | 2 | 2008-04-30 | 18 | 1 | 1810 | S3P1 | 48 | EM//TB | hr | 40
418 | S31-6.06 | Transfer load to the AirLoc Wedgemount leveler. | 2008-05-01 | 0 | 2008-04-30 | 18 | 1 | 1810 | S3P1 | 49 | EM//TB | hr | 0
419 | S31-6.07 | move the MCHP to the left 1/2". | 2008-05-01 | 0 | 2008-04-30 | 18 | 1 | 1810 | S3P1 | 50 | EM//TB | hr | 0
420 | S31-7.01 | Position AirLoc Wedgemount lowered position. | 2008-05-01 | 0 | 2008-04-30 | 18 | 1 | 1810 | S3P1 | 51 | EM//TB | hr | 0
421 | S31-7.02 | move the right MCHP over the VV | 2008-05-01 | 2 | 2008-05-02 | 18 | 1 | 1810 | S3P1 | 52 | EM//TB | hr | 40
422 | S31-7.03 | move the left MCHP to its final position. | 2008-05-05 | 1 | 2008-05-05 | 18 | 1 | 1810 | S3P1 | 53 | EM//TB | hr | 10
423 | S31-7.04 | engage the preinstalled Type-A flange bushings. | 2008-05-06 | 1 | 2008-05-06 | 18 | 1 | 1810 | S3P1 | 54 | EM//TB | hr | 10
424 | S31-7.05 | Temporary fasteners bring the parts together. | 2008-05-07 | 0 | 2008-05-06 | 18 | 1 | 1810 | S3P1 | 55 | EM//TB | hr | 0
425 | S31-7.06 | AirLoc Wedgemount leveler up to take the load. | 2008-05-07 | 1 | 2008-05-07 | 18 | 1 | 1810 | S3P1 | 56 | EM//TB | hr | 10
426 | S31-7.07 | Remove laser screens | 2008-05-08 | 0 | 2008-05-07 | 18 | 1 | 1810 | S3P1 | 57 | EM//TB | hr | 0
427 | S31-7.08 | Install temp scaffolding to install flange hw | 2008-05-08 | 4 | 2008-05-13 | 18 | 1 | 1810 | S3P1 | 58 | EM//TB | hr | 80
428 | S31-7.09 | Install bolts, alumina and inboard weld shims. | 2008-05-14 | 2 | 2008-05-15 | 18 | 1 | 1810 | S3P1 | 59 | EM//TB | hr | 40
429 | S31-7.1 | Tighten flange fasteners to 50% | 2008-05-16 | 1 | 2008-05-16 | 18 | 1 | 1810 | S3P1 | 60 | EM//TB | hr | 20
430 | S31-7.11 | "wiggle" test Tighten bolt and recheck. | 2008-05-19 | 1 | 2008-05-19 | 18 | 1 | 1810 | S3P1 | 61 | EM//TB | hr | 20
431 | S31-7.12 | Perform metrology measurements | 2008-05-20 | 5 | 2008-05-27 | 18 | 1 | 1810 | S3P1 | 62 | EM//TB | hr | 0
432 | S31-7.12 | Perform metrology measurements | 2008-05-20 | 5 | 2008-05-27 | 18 | 1 | 1810 | S3P1 | 62 | ZMET | met staff (budgeted in LOE) for ref only | 100
433 | S31-7.13 | Perform position adjustments right side MCHP | 2008-05-28 | 3 | 2008-05-30 | 18 | 1 | 1810 | S3P1 | 63 | EM//TB | hr | 60
434 | S31-7.14 | Remove SISSCO actuator from right MCHP. | 2008-06-02 | 0 | 2008-05-30 | 18 | 1 | 1810 | S3P1 | 64 | EM//TB | hr | 0
435 | S31-7.15 | Install bushing. | 2008-06-02 | 1 | 2008-06-02 | 18 | 1 | 1810 | S3P1 | 65 | EM//TB | hr | 10
436 | S31-7.16 | Tighten nuts 100%. & Measure | 2008-06-03 | 1 | 2008-06-03 | 18 | 1 | 1810 | S3P1 | 66 | EM//TB | hr | 20
437 | S31-8.01 | partially weld the inboard shim. | 2008-06-04 | 15 | 2008-06-24 | 18 | 1 | 1810 | S3P1 | 67 | EM//TB | hr | 300
438 | S31-8.02 | Final complete MC scan verify period alignment. | 2008-06-25 | 5 | 2008-07-01 | 18 | 1 | 1810 | S3P1 | 68 | EM//TB | hr | 0
439 | S31-8.02 | Final complete MC scan verify period alignment. | 2008-06-25 | 5 | 2008-07-01 | 18 | 1 | 1810 | S3P1 | 68 | ZMET | met staff (budgeted in LOE) for ref only | 100
440 | S31-9.01 | Attach VV permanent vertical supports | 2008-07-02 | 2 | 2008-07-03 | 18 | 1 | 1810 | S3P1 | 69 | EM//TB | hr | 40
441 | S31-9.02 | Attach temporary VV vertical supports | 2008-07-07 | 1 | 2008-07-07 | 18 | 1 | 1810 | S3P1 | 70 | EM//TB | hr | 20
442 | S31-9.03 | Transfer load to vertical supports. | 2008-07-08 | 1 | 2008-07-08 | 18 | 1 | 1810 | S3P1 | 71 | EM//TB | hr | 20
443 | S31-9.04 | Install VV lateral supports and align | 2008-07-09 | 4 | 2008-07-14 | 18 | 1 | 1810 | S3P1 | 72 | EM//TB | hr | 80
444 | S31-9.05 | Prepare VVSA for transport. | 2008-07-15 | 2 | 2008-07-16 | 18 | 1 | 1810 | S3P1 | 73 | EM//TB | hr | 40
445 | S31-10.01 | transfer the unit to the transfer support frame | 2008-07-17 | 2 | 2008-07-18 | 18 | 1 | 1810 | S3P1 | 74 | EM//TB | hr | 80
446 | S31-10.02 | Transfer Period 1 to Station 5 in NCSX TC | 2008-07-21 | 1 | 2008-07-21 | 18 | 1 | 1810 | S3P1 | 75 | EM//TB | hr | 40
447 | S32-1.01 | Install Station 3 site monuments | 2008-07-22 | 3 | 2008-07-24 | 18 | 1 | 1810 | S3P2 | 11 | 41 | $k | 2
448 | S32-1.01 | Install Station 3 site monuments | 2008-07-22 | 3 | 2008-07-24 | 18 | 1 | 1810 | S3P2 | 11 | EM//TB | hr | 60
449 | S32-1.02 | Install floor mounted tracks and VV base support | 2008-07-25 | 5 | 2008-07-31 | 18 | 1 | 1810 | S3P2 | 12 | 41 | $k | 1
450 | S32-1.02 | Install floor mounted tracks and VV base support | 2008-07-25 | 5 | 2008-07-31 | 18 | 1 | 1810 | S3P2 | 12 | EM//TB | hr | 100
451 | S32-1.03 | Establish the MCHP CG location. | 2008-08-01 | 2 | 2008-08-04 | 18 | 1 | 1810 | S3P2 | 15 | EM//TB | hr | 40
452 | S32-2.01 | Install MCHP support cart assemblies | 2008-08-05 | 4 | 2008-08-08 | 18 | 1 | 1810 | S3P2 | 16 | EM//TB | hr | 80
453 | S32-2.02 | Verify cart motion. | 2008-08-11 | 2 | 2008-08-12 | 18 | 1 | 1810 | S3P2 | 17 | EM//TB | hr | 40
454 | S32-2.03 | Install adjustor bar support weldment | 2008-08-13 | 0 | 2008-08-12 | 18 | 1 | 1810 | S3P2 | 18 | EM//TB | hr | 0
455 | S32-2.04 | Position left MCHP on the cart assembly | 2008-08-13 | 1 | 2008-08-13 | 18 | 1 | 1810 | S3P2 | 19 | EM//TB | hr | 20
456 | S32-2.05 | Secure left MCHP on support cart base. | 2008-08-14 | 2 | 2008-08-15 | 18 | 1 | 1810 | S3P2 | 20 | EM//TB | hr | 40
457 | S32-2.06 | Measure monuments on left MCHP and walls | 2008-08-18 | 5 | 2008-08-22 | 18 | 1 | 1810 | S3P2 | 21 | EM//TB | hr | 0
458 | S32-2.06 | Measure monuments on left MCHP and walls | 2008-08-18 | 5 | 2008-08-22 | 18 | 1 | 1810 | S3P2 | 21 | ZMET | met staff (budgeted in LOE) for ref only | 100
459 | S32-2.07 | Set positioning stop on the cart | 2008-08-25 | 1 | 2008-08-25 | 18 | 1 | 1810 | S3P2 | 22 | EM//TB | hr | 20
460 | S32-3.01 | Move right base support cart to its final positi | 2008-08-26 | 1 | 2008-08-26 | 18 | 1 | 1810 | S3P2 | 23 | EM//TB | hr | 10
461 | S32-3.02 | Lift the right side MCHP and position | 2008-08-27 | 1 | 2008-08-27 | 18 | 1 | 1810 | S3P2 | 24 | EM//TB | hr | 20
462 | S32-3.03 | Temporary fasteners bring the parts together. | 2008-08-28 | 0 | 2008-08-27 | 18 | 1 | 1810 | S3P2 | 25 | EM//TB | hr | 0
463 | S32-3.04 | AirLoc Wedgemount leveler to take load. | 2008-08-28 | 0 | 2008-08-27 | 18 | 1 | 1810 | S3P2 | 26 | EM//TB | hr | 0
464 | S32-3.05 | Install temp scaffolding to install flange hw | 2008-08-28 | 1 | 2008-08-28 | 18 | 1 | 1810 | S3P2 | 27 | EM//TB | hr | 20
465 | S32-3.06 | Install bolts and shims | 2008-08-29 | 1 | 2008-08-29 | 18 | 1 | 1810 | S3P2 | 28 | EM//TB | hr | 20
466 | S32-3.07 | Tighten flange fasteners to 50% | 2008-09-02 | 1 | 2008-09-02 | 18 | 1 | 1810 | S3P2 | 29 | EM//TB | hr | 20
467 | S32-3.08 | Perform metrology measurements | 2008-09-03 | 5 | 2008-09-09 | 18 | 1 | 1810 | S3P2 | 30 | EM//TB | hr | 0
468 | S32-3.08 | Perform metrology measurements | 2008-09-03 | 5 | 2008-09-09 | 18 | 1 | 1810 | S3P2 | 30 | ZMET | met staff (budgeted in LOE) for ref only | 100
469 | S32-3.09 | Perform position adjust on right side MCHP | 2008-09-10 | 2 | 2008-09-11 | 18 | 1 | 1810 | S3P2 | 31 | EM//TB | hr | 40
470 | S32-3.1 | Verify position of the VV support hanger | 2008-09-12 | 3 | 2008-09-16 | 18 | 1 | 1810 | S3P2 | 32 | EM//TB | hr | 0
471 | S32-3.1 | Verify position of the VV support hanger | 2008-09-12 | 3 | 2008-09-16 | 18 | 1 | 1810 | S3P2 | 32 | ZMET | met staff (budgeted in LOE) for ref only | 60
472 | S32-3.11 | Remove flange hardware and temp platforms | 2008-09-17 | 1 | 2008-09-17 | 18 | 1 | 1810 | S3P2 | 33 | EM//TB | hr | 20
473 | S32-4.01 | EMeasure monuments on the MCHP's &walls. | 2008-09-18 | 2 | 2008-09-19 | 18 | 1 | 1810 | S3P2 | 34 | EM//TB | hr | 0
474 | S32-4.01 | EMeasure monuments on the MCHP's &walls. | 2008-09-18 | 2 | 2008-09-19 | 18 | 1 | 1810 | S3P2 | 34 | ZMET | met staff (budgeted in LOE) for ref only | 40
475 | S32-4.01 | EMeasure monuments on the MCHP's &walls. | 2008-09-18 | 2 | 2008-09-19 | 18 | 1 | 1810 | S3P2 | 34 | 41 | $k | 2
476 | S32-4.02 | Place all of the laser screens | 2008-09-22 | 2 | 2008-09-23 | 18 | 1 | 1810 | S3P2 | 35 | EM//TB | hr | 40
477 | S32-4.03 | Determine laser alignment. | 2008-09-24 | 1 | 2008-09-24 | 18 | 1 | 1810 | S3P2 | 36 | EM//TB | hr | 20
478 | S32-4.04 | mount the milar on the screens. | 2008-09-25 | 1 | 2008-09-25 | 18 | 1 | 1810 | S3P2 | 37 | EM//TB | hr | 0
479 | S32-4.05 | Disengage MCHP's to move the left MCHP. | 2008-09-26 | 1 | 2008-09-26 | 18 | 1 | 1810 | S3P2 | 38 | EM//TB | hr | 20
480 | S32-4.06 | Remove both MCHP's. | 2008-09-29 | 2 | 2008-09-30 | 18 | 1 | 1810 | S3P2 | 39 | EM//TB | hr | 40
481 | S32-5.01 | Remove the adjustor bar support from left side. | 2008-10-01 | 0 | 2008-09-30 | 18 | 1 | 1810 | S3P2 | 40 | EM//TB | hr | 0
482 | S32-5.02 | Install VV NBI port support stand. | 2008-10-01 | 2 | 2008-10-02 | 18 | 1 | 1810 | S3P2 | 41 | EM//TB | hr | 40
483 | S32-5.03 | Install VVSA to base support | 2008-10-03 | 1 | 2008-10-03 | 18 | 1 | 1810 | S3P2 | 42 | EM//TB | hr | 20
484 | S32-5.04 | Secure the VVSA to base & NBI port sprt stand. | 2008-10-06 | 2 | 2008-10-07 | 18 | 1 | 1810 | S3P2 | 43 | EM//TB | hr | 40
485 | S32-6.01 | Install bumper protection components on the VV | 2008-10-08 | 1 | 2008-10-08 | 18 | 1 | 1810 | S3P2 | 44 | EM//TB | hr | 10
486 | S32-6.02 | Position AirLoc Wedgemount in lower position. | 2008-10-09 | 0 | 2008-10-08 | 18 | 1 | 1810 | S3P2 | 45 | EM//TB | hr | 0
487 | S32-6.03 | move the left MCHP over the VV. | 2008-10-09 | 2 | 2008-10-10 | 18 | 1 | 1810 | S3P2 | 46 | EM//TB | hr | 40
488 | S32-6.04 | Re-install the left adjustor bar. | 2008-10-13 | 0 | 2008-10-10 | 18 | 1 | 1810 | S3P2 | 47 | EM//TB | hr | 0
489 | S32-6.05 | Make adjustments to properly align MCHP. | 2008-10-13 | 2 | 2008-10-14 | 18 | 1 | 1810 | S3P2 | 48 | EM//TB | hr | 40
490 | S32-6.06 | Transfer load to the AirLoc Wedgemount leveler. | 2008-10-15 | 0 | 2008-10-14 | 18 | 1 | 1810 | S3P2 | 49 | EM//TB | hr | 0
491 | S32-6.07 | move the MCHP to the left 1/2". | 2008-10-15 | 0 | 2008-10-14 | 18 | 1 | 1810 | S3P2 | 50 | EM//TB | hr | 0
492 | S32-7.01 | Position AirLoc Wedgemount lowered position. | 2008-10-15 | 0 | 2008-10-14 | 18 | 1 | 1810 | S3P2 | 51 | EM//TB | hr | 0
493 | S32-7.02 | move the right MCHP over the VV | 2008-10-15 | 2 | 2008-10-16 | 18 | 1 | 1810 | S3P2 | 52 | EM//TB | hr | 40
494 | S32-7.03 | move the left MCHP to its final position. | 2008-10-17 | 1 | 2008-10-17 | 18 | 1 | 1810 | S3P2 | 53 | EM//TB | hr | 10
495 | S32-7.04 | engage the preinstalled Type-A flange bushings. | 2008-10-20 | 1 | 2008-10-20 | 18 | 1 | 1810 | S3P2 | 54 | EM//TB | hr | 10
496 | S32-7.05 | Temporary fasteners bring the parts together. | 2008-10-21 | 0 | 2008-10-20 | 18 | 1 | 1810 | S3P2 | 55 | EM//TB | hr | 0
497 | S32-7.06 | AirLoc Wedgemount leveler up to take the load. | 2008-10-21 | 1 | 2008-10-21 | 18 | 1 | 1810 | S3P2 | 56 | EM//TB | hr | 10
498 | S32-7.07 | Remove laser screens | 2008-10-22 | 0 | 2008-10-21 | 18 | 1 | 1810 | S3P2 | 57 | EM//TB | hr | 0
499 | S32-7.08 | Install temp scaffolding to install flange hw | 2008-10-22 | 4 | 2008-10-27 | 18 | 1 | 1810 | S3P2 | 58 | EM//TB | hr | 80
500 | S32-7.09 | Install bolts, alumina and inboard weld shims. | 2008-10-28 | 2 | 2008-10-29 | 18 | 1 | 1810 | S3P2 | 59 | EM//TB | hr | 40
501 | S32-7.1 | Tighten flange fasteners to 50% | 2008-10-30 | 1 | 2008-10-30 | 18 | 1 | 1810 | S3P2 | 60 | EM//TB | hr | 20
502 | S32-7.11 | "wiggle" test Tighten bolt and recheck. | 2008-10-31 | 1 | 2008-10-31 | 18 | 1 | 1810 | S3P2 | 61 | EM//TB | hr | 20
503 | S32-7.12 | Perform metrology measurements | 2008-11-03 | 5 | 2008-11-07 | 18 | 1 | 1810 | S3P2 | 62 | EM//TB | hr | 0
504 | S32-7.12 | Perform metrology measurements | 2008-11-03 | 5 | 2008-11-07 | 18 | 1 | 1810 | S3P2 | 62 | ZMET | met staff (budgeted in LOE) for ref only | 100
505 | S32-7.13 | Perform position adjustments right side MCHP | 2008-11-10 | 3 | 2008-11-12 | 18 | 1 | 1810 | S3P2 | 63 | EM//TB | hr | 60
506 | S32-7.14 | Remove SISSCO actuator from right MCHP. | 2008-11-13 | 0 | 2008-11-12 | 18 | 1 | 1810 | S3P2 | 64 | EM//TB | hr | 0
507 | S32-7.15 | Install bushing. | 2008-11-13 | 1 | 2008-11-13 | 18 | 1 | 1810 | S3P2 | 65 | EM//TB | hr | 10
508 | S32-7.16 | Tighten nuts 100%. & Measure | 2008-11-14 | 1 | 2008-11-14 | 18 | 1 | 1810 | S3P2 | 66 | EM//TB | hr | 20
509 | S32-8.01 | partially weld the inboard shim. | 2008-11-17 | 15 | 2008-12-09 | 18 | 1 | 1810 | S3P2 | 67 | EM//TB | hr | 300
510 | S32-8.02 | Final complete MC scan verify period alignment. | 2008-12-10 | 5 | 2008-12-16 | 18 | 1 | 1810 | S3P2 | 68 | EM//TB | hr | 0
511 | S32-8.02 | Final complete MC scan verify period alignment. | 2008-12-10 | 5 | 2008-12-16 | 18 | 1 | 1810 | S3P2 | 68 | ZMET | met staff (budgeted in LOE) for ref only | 100
512 | S32-9.01 | Attach VV permanent vertical supports | 2008-12-17 | 2 | 2008-12-18 | 18 | 1 | 1810 | S3P2 | 69 | EM//TB | hr | 40
513 | S32-9.02 | Attach temporary VV vertical supports | 2008-12-19 | 1 | 2008-12-19 | 18 | 1 | 1810 | S3P2 | 70 | EM//TB | hr | 20
514 | S32-9.03 | Transfer load to vertical supports. | 2008-12-22 | 1 | 2008-12-22 | 18 | 1 | 1810 | S3P2 | 71 | EM//TB | hr | 20
515 | S32-9.04 | Install VV lateral supports and align | 2008-12-23 | 4 | 2009-01-06 | 18 | 1 | 1810 | S3P2 | 72 | EM//TB | hr | 80
516 | S32-9.05 | Prepare VVSA for transport. | 2009-01-07 | 2 | 2009-01-08 | 18 | 1 | 1810 | S3P2 | 73 | EM//TB | hr | 40
517 | S32-10.01 | transfer the unit to the transfer support frame | 2009-01-09 | 2 | 2009-01-12 | 18 | 1 | 1810 | S3P2 | 74 | EM//TB | hr | 80
518 | S32-10.02 | Transfer Period 2 to Station 5 in NCSX TC | 2009-01-13 | 1 | 2009-01-13 | 18 | 1 | 1810 | S3P2 | 75 | EM//TB | hr | 40
519 | S33-1.01 | Install Station 3 site monuments | 2009-01-14 | 3 | 2009-01-16 | 18 | 1 | 1810 | S3P3 | 11 | 41 | $k | 2
520 | S33-1.01 | Install Station 3 site monuments | 2009-01-14 | 3 | 2009-01-16 | 18 | 1 | 1810 | S3P3 | 11 | EM//TB | hr | 60
521 | S33-1.02 | Install floor mounted tracks and VV base support | 2009-01-19 | 5 | 2009-01-23 | 18 | 1 | 1810 | S3P3 | 12 | 41 | $k | 1
522 | S33-1.02 | Install floor mounted tracks and VV base support | 2009-01-19 | 5 | 2009-01-23 | 18 | 1 | 1810 | S3P3 | 12 | EM//TB | hr | 100
523 | S33-1.03 | Establish the MCHP CG location. | 2009-01-26 | 2 | 2009-01-27 | 18 | 1 | 1810 | S3P3 | 15 | EM//TB | hr | 40
524 | S33-2.01 | Install MCHP support cart assemblies | 2009-01-28 | 4 | 2009-02-02 | 18 | 1 | 1810 | S3P3 | 16 | EM//TB | hr | 80
525 | S33-2.02 | Verify cart motion. | 2009-02-03 | 2 | 2009-02-04 | 18 | 1 | 1810 | S3P3 | 17 | EM//TB | hr | 40
526 | S33-2.03 | Install adjustor bar support weldment | 2009-02-05 | 0 | 2009-02-04 | 18 | 1 | 1810 | S3P3 | 18 | EM//TB | hr | 0
527 | S33-2.04 | Position left MCHP on the cart assembly | 2009-02-26 | 1 | 2009-02-26 | 18 | 2 | 1810 | S3P3 | 19 | EM//TB | hr | 20
528 | S33-2.05 | Secure left MCHP on support cart base. | 2009-02-27 | 1 | 2009-02-27 | 18 | 2 | 1810 | S3P3 | 20 | EM//TB | hr | 40
529 | S33-2.06 | Measure monuments on left MCHP and walls | 2009-03-02 | 2 | 2009-03-03 | 18 | 2 | 1810 | S3P3 | 21 | EM//TB | hr | 0
530 | S33-2.06 | Measure monuments on left MCHP and walls | 2009-03-02 | 2 | 2009-03-03 | 18 | 2 | 1810 | S3P3 | 21 | ZMET | met staff (budgeted in LOE) for ref only | 100
531 | S33-2.07 | Set positioning stop on the cart | 2009-03-05 | 1 | 2009-03-05 | 18 | 2 | 1810 | S3P3 | 22 | EM//TB | hr | 20
532 | S33-3.01 | Move right base support cart to its final positi | 2009-03-06 | 0 | 2009-03-05 | 18 | 2 | 1810 | S3P3 | 23 | EM//TB | hr | 0
533 | S33-3.02 | Lift the right side MCHP and position | 2009-03-06 | 1 | 2009-03-06 | 18 | 2 | 1810 | S3P3 | 24 | EM//TB | hr | 30
534 | S33-3.03 | Temporary fasteners bring the parts together. | 2009-03-09 | 0 | 2009-03-06 | 18 | 2 | 1810 | S3P3 | 25 | EM//TB | hr | 0
535 | S33-3.04 | AirLoc Wedgemount leveler to take load. | 2009-03-09 | 0 | 2009-03-06 | 18 | 2 | 1810 | S3P3 | 26 | EM//TB | hr | 0
536 | S33-3.05 | Install temp scaffolding to install flange hw | 2009-03-09 | 1 | 2009-03-09 | 18 | 2 | 1810 | S3P3 | 27 | EM//TB | hr | 20
537 | S33-3.06 | Install bolts and shims | 2009-03-10 | 1 | 2009-03-10 | 18 | 2 | 1810 | S3P3 | 28 | EM//TB | hr | 20
538 | S33-3.07 | Tighten flange fasteners to 50% | 2009-03-11 | 1 | 2009-03-11 | 18 | 2 | 1810 | S3P3 | 29 | EM//TB | hr | 20
539 | S33-3.08 | Perform metrology measurements | 2009-03-12 | 1 | 2009-03-12 | 18 | 2 | 1810 | S3P3 | 30 | EM//TB | hr | 0
540 | S33-3.08 | Perform metrology measurements | 2009-03-12 | 1 | 2009-03-12 | 18 | 2 | 1810 | S3P3 | 30 | ZMET | met staff (budgeted in LOE) for ref only | 100
541 | S33-3.09 | Perform position adjust on right side MCHP | 2009-03-16 | 1 | 2009-03-16 | 18 | 2 | 1810 | S3P3 | 31 | EM//TB | hr | 40
542 | S33-3.1 | Verify position of the VV support hanger | 2009-03-17 | 1 | 2009-03-17 | 18 | 2 | 1810 | S3P3 | 32 | EM//TB | hr | 0
543 | S33-3.1 | Verify position of the VV support hanger | 2009-03-17 | 1 | 2009-03-17 | 18 | 2 | 1810 | S3P3 | 32 | ZMET | met staff (budgeted in LOE) for ref only | 60
544 | S33-3.11 | Remove flange hardware and temp platforms | 2009-03-18 | 1 | 2009-03-18 | 18 | 2 | 1810 | S3P3 | 33 | EM//TB | hr | 20
545 | S33-4.01 | EMeasure monuments on the MCHP's &walls. | 2009-03-19 | 1 | 2009-03-19 | 18 | 2 | 1810 | S3P3 | 34 | EM//TB | hr | 0
546 | S33-4.01 | EMeasure monuments on the MCHP's &walls. | 2009-03-19 | 1 | 2009-03-19 | 18 | 2 | 1810 | S3P3 | 34 | ZMET | met staff (budgeted in LOE) for ref only | 40
547 | S33-4.01 | EMeasure monuments on the MCHP's &walls. | 2009-03-19 | 1 | 2009-03-19 | 18 | 2 | 1810 | S3P3 | 34 | 41 | $k | 2
548 | S33-4.02 | Place all of the laser screens | 2009-03-20 | 1 | 2009-03-20 | 18 | 2 | 1810 | S3P3 | 35 | EM//TB | hr | 40
549 | S33-4.03 | Determine laser alignment. | 2009-03-23 | 1 | 2009-03-23 | 18 | 2 | 1810 | S3P3 | 36 | EM//TB | hr | 20
550 | S33-4.04 | mount the milar on the screens. | 2009-03-24 | 1 | 2009-03-24 | 18 | 2 | 1810 | S3P3 | 37 | EM//TB | hr | 0
551 | S33-4.05 | Disengage MCHP's to move the left MCHP. | 2009-03-25 | 1 | 2009-03-25 | 18 | 2 | 1810 | S3P3 | 38 | EM//TB | hr | 20
552 | S33-4.06 | Remove both MCHP's. | 2009-03-26 | 1 | 2009-03-26 | 18 | 2 | 1810 | S3P3 | 39 | EM//TB | hr | 40
553 | S33-5.01 | Remove the adjustor bar support from left side. | 2009-03-27 | 0 | 2009-03-26 | 18 | 2 | 1810 | S3P3 | 40 | EM//TB | hr | 0
554 | S33-5.02 | Install VV NBI port support stand. | 2009-03-27 | 1 | 2009-03-27 | 18 | 2 | 1810 | S3P3 | 41 | EM//TB | hr | 40
555 | S33-5.03 | Install VVSA to base support | 2009-03-30 | 1 | 2009-03-30 | 18 | 2 | 1810 | S3P3 | 42 | EM//TB | hr | 20
556 | S33-5.04 | Secure the VVSA to base & NBI port sprt stand. | 2009-03-31 | 1 | 2009-03-31 | 18 | 2 | 1810 | S3P3 | 43 | EM//TB | hr | 40
557 | S33-6.01 | Install bumper protection components on the VV | 2009-04-01 | 0 | 2009-03-31 | 18 | 2 | 1810 | S3P3 | 44 | EM//TB | hr | 0
558 | S33-6.02 | Position AirLoc Wedgemount in lower position. | 2009-04-01 | 0 | 2009-03-31 | 18 | 2 | 1810 | S3P3 | 45 | EM//TB | hr | 0
559 | S33-6.03 | move the left MCHP over the VV. | 2009-04-01 | 1 | 2009-04-01 | 18 | 2 | 1810 | S3P3 | 46 | EM//TB | hr | 50
560 | S33-6.04 | Re-install the left adjustor bar. | 2009-04-02 | 0 | 2009-04-01 | 18 | 2 | 1810 | S3P3 | 47 | EM//TB | hr | 0
561 | S33-6.05 | Make adjustments to properly align MCHP. | 2009-04-02 | 1 | 2009-04-02 | 18 | 2 | 1810 | S3P3 | 48 | EM//TB | hr | 40
562 | S33-6.06 | Transfer load to the AirLoc Wedgemount leveler. | 2009-04-03 | 0 | 2009-04-02 | 18 | 2 | 1810 | S3P3 | 49 | EM//TB | hr | 0
563 | S33-6.07 | move the MCHP to the left 1/2". | 2009-04-03 | 0 | 2009-04-02 | 18 | 2 | 1810 | S3P3 | 50 | EM//TB | hr | 0
564 | S33-7.01 | Position AirLoc Wedgemount lowered position. | 2009-04-03 | 0 | 2009-04-02 | 18 | 2 | 1810 | S3P3 | 51 | EM//TB | hr | 0
565 | S33-7.02 | move the right MCHP over the VV | 2009-04-03 | 1 | 2009-04-03 | 18 | 2 | 1810 | S3P3 | 52 | EM//TB | hr | 40
566 | S33-7.03 | move the left MCHP to its final position. | 2009-04-06 | 1 | 2009-04-06 | 18 | 2 | 1810 | S3P3 | 53 | EM//TB | hr | 10
567 | S33-7.04 | engage the preinstalled Type-A flange bushings. | 2009-04-07 | 1 | 2009-04-07 | 18 | 2 | 1810 | S3P3 | 54 | EM//TB | hr | 10
568 | S33-7.05 | Temporary fasteners bring the parts together. | 2009-04-08 | 0 | 2009-04-07 | 18 | 2 | 1810 | S3P3 | 55 | EM//TB | hr | 0
569 | S33-7.06 | AirLoc Wedgemount leveler up to take the load. | 2009-04-08 | 1 | 2009-04-08 | 18 | 2 | 1810 | S3P3 | 56 | EM//TB | hr | 10
570 | S33-7.07 | Remove laser screens | 2009-04-09 | 0 | 2009-04-08 | 18 | 2 | 1810 | S3P3 | 57 | EM//TB | hr | 0
571 | S33-7.08 | Install temp scaffolding to install flange hw | 2009-04-09 | 1 | 2009-04-09 | 18 | 2 | 1810 | S3P3 | 58 | EM//TB | hr | 80
572 | S33-7.09 | Install bolts, alumina and inboard weld shims. | 2009-04-13 | 1 | 2009-04-13 | 18 | 2 | 1810 | S3P3 | 59 | EM//TB | hr | 40
573 | S33-7.1 | Tighten flange fasteners to 50% | 2009-04-14 | 1 | 2009-04-14 | 18 | 2 | 1810 | S3P3 | 60 | EM//TB | hr | 20
574 | S33-7.11 | "wiggle" test Tighten bolt and recheck. | 2009-04-15 | 1 | 2009-04-15 | 18 | 2 | 1810 | S3P3 | 61 | EM//TB | hr | 20
575 | S33-7.12 | Perform metrology measurements | 2009-04-16 | 1 | 2009-04-16 | 18 | 2 | 1810 | S3P3 | 62 | EM//TB | hr | 0
576 | S33-7.12 | Perform metrology measurements | 2009-04-16 | 1 | 2009-04-16 | 18 | 2 | 1810 | S3P3 | 62 | ZMET | met staff (budgeted in LOE) for ref only | 100
577 | S33-7.13 | Perform position adjustments right side MCHP | 2009-04-20 | 1 | 2009-04-20 | 18 | 2 | 1810 | S3P3 | 63 | EM//TB | hr | 60
578 | S33-7.14 | Remove SISSCO actuator from right MCHP. | 2009-04-22 | 0 | 2009-04-21 | 18 | 2 | 1810 | S3P3 | 64 | EM//TB | hr | 0
579 | S33-7.15 | Install bushing. | 2009-04-22 | 1 | 2009-04-22 | 18 | 2 | 1810 | S3P3 | 65 | EM//TB | hr | 10
580 | S33-7.16 | Tighten nuts 100%. & Measure | 2009-04-23 | 1 | 2009-04-23 | 18 | 2 | 1810 | S3P3 | 66 | EM//TB | hr | 20
581 | S33-8.01 | partially weld the inboard shim. | 2009-04-24 | 7 | 2009-05-04 | 18 | 2 | 1810 | S3P3 | 67 | EM//TB | hr | 300
582 | S33-8.02 | Final complete MC scan verify period alignment. | 2009-05-05 | 3 | 2009-05-07 | 18 | 2 | 1810 | S3P3 | 68 | EM//TB | hr | 0
583 | S33-8.02 | Final complete MC scan verify period alignment. | 2009-05-05 | 3 | 2009-05-07 | 18 | 2 | 1810 | S3P3 | 68 | ZMET | met staff (budgeted in LOE) for ref only | 100
584 | S33-9.01 | Attach VV permanent vertical supports | 2009-05-08 | 1 | 2009-05-08 | 18 | 2 | 1810 | S3P3 | 69 | EM//TB | hr | 40
585 | S33-9.02 | Attach temporary VV vertical supports | 2009-05-11 | 1 | 2009-05-11 | 18 | 2 | 1810 | S3P3 | 70 | EM//TB | hr | 20
586 | S33-9.03 | Transfer load to vertical supports. | 2009-05-12 | 1 | 2009-05-12 | 18 | 2 | 1810 | S3P3 | 71 | EM//TB | hr | 20
587 | S33-9.04 | Install VV lateral supports and align | 2009-05-13 | 1 | 2009-05-13 | 18 | 2 | 1810 | S3P3 | 72 | EM//TB | hr | 80
588 | S33-9.05 | Prepare VVSA for transport. | 2009-05-15 | 1 | 2009-05-15 | 18 | 2 | 1810 | S3P3 | 73 | EM//TB | hr | 40
589 | S33-10.01 | transfer the unit to the transfer support frame | 2009-05-18 | 1 | 2009-05-18 | 18 | 2 | 1810 | S3P3 | 74 | EM//TB | hr | 80
590 | S33-10.02 | Transfer Period 3 to Station 5 in NCSX TC | 2009-05-19 | 1 | 2009-05-19 | 18 | 2 | 1810 | S3P3 | 75 | EM//TB | hr | 40
591 | R1810-5101 | MTM NCR hardware re-purchase | 2008-05-27 | 25 | 2008-06-30 | 18 | 1 | 1815 | S4P0 | 10 | 41 | $k | 42
592 | R1810-5102 | Monuments,reflectors,CCR's | 2008-06-03 | 10 | 2008-06-16 | 18 | 1 | 1815 | S4P0 | 11 | 41 | $k | 51.75
593 | R1810-5103 | metrology network in NCSX TC | 2008-06-17 | 10 | 2008-06-30 | 18 | 1 | 1815 | S4P0 | 12 | EM//TB | hr | 160
594 | R1810-5103 | metrology network in NCSX TC | 2008-06-17 | 10 | 2008-06-30 | 18 | 1 | 1815 | S4P0 | 12 | 41 | $k | 7
595 | R1810-5104 | Misc for tooling | 2008-07-21 | 10 | 2008-08-01 | 18 | 1 | 1815 | S4P0 | 13 |  |  | 0
596 | R1810-5112 | Weld wire & welding supplies | 2008-05-27 | 25 | 2008-06-30 | 18 | 1 | 1815 | S4P0 | 14 | 41 | $k | 15
597 | R1810-5106 | Testout Sta 5 equipt & procedures | 2008-07-01 | 5 | 2008-07-08 | 18 | 1 | 1815 | S4P0 | 15 | EM//TB | hr | 160
598 | R1810-5107 | Check 3 sled interfaces adjust holes | 2008-07-09 | 12 | 2008-07-24 | 18 | 1 | 1815 | S4P0 | 16 | EM//TB | hr | 384
599 | R1810-5108 | Fixtures installed-final metrology | 2008-07-25 | 6 | 2008-08-01 | 18 | 1 | 1815 | S4P0 | 17 | EM//TB | hr | 192
600 | R1810-5109 | Begin Station 5 Operations |  | 0 | 2008-08-01 | 18 | 1 | 1815 | S4P1 | 01 |  |  | 0
601 | S51-1.01 | cut off short dome | 2008-08-04 | 2 | 2008-08-05 | 18 |  | 1815 | S4P1 | 11 | EM//TB | hr | 40
602 | S51-1.02 | Install insulation system around all ports. | 2008-08-06 | 0 | 2008-08-05 | 18 |  | 1815 | S4P1 | 12 | EM//TB | hr | 0
603 | S51-1.03 | Install heat tape and theomocouples on all ports | 2008-08-06 | 0 | 2008-08-05 | 18 |  | 1815 | S4P1 | 13 | EM//TB | hr | 0
604 | S51-2.01 | Install period support fixture | 2008-08-06 | 2 | 2008-08-07 | 18 |  | 1815 | S4P1 | 14 | EM//TB | hr | 40
605 | S51-2.02 | Install FPA on support stand. | 2008-08-08 | 2 | 2008-08-11 | 18 |  | 1815 | S4P1 | 15 | EM//TB | hr | 40
606 | S51-2.03 | Install external working platforms | 2008-08-12 | 4 | 2008-08-15 | 18 |  | 1815 | S4P1 | 16 | EM//TB | hr | 80
607 | S51-2.04 | Install internal VV working platforms | 2008-08-18 | 3 | 2008-08-20 | 18 |  | 1815 | S4P1 | 17 | EM//TB | hr | 60
608 | S51-3.01 | Install the domes (left and right side), | 2008-08-21 | 2 | 2008-08-22 | 18 |  | 1815 | S4P1 | 18 | EM//TB | hr | 40
609 | S51-3.02 | Install small dome ports remaining circ ports. | 2008-08-25 | 30 | 2008-10-06 | 18 | 1 | 1815 | S4P1 | 19 | EM//TB | hr | 600
610 | S51-3.03 | Leak check each port after it is welded. | 2008-09-16 | 30 | 2008-10-27 | 18 | 1 | 1815 | S4P1 | 20 | EM//TB | hr | 600
611 | S51-4.01 | Install boots on ports except for the two port | 2008-10-16 | 16 | 2008-11-06 | 18 | 1 | 1815 | S4P1 | 21 | EM//TB | hr | 320
612 | S51-5.01 | Install MC lead connections on each of the MC's | 2008-11-07 | 1 | 2008-11-07 | 18 |  | 1815 | S4P1 | 22 | EM//TB | hr | 0
613 | S51-5.02 | Install MC coolant lines on each MC | 2008-11-10 | 12 | 2008-11-25 | 18 |  | 1815 | S4P1 | 23 | EM//TB | hr | 240
614 | S51-5.03 | Platforms may need to be altered | 2008-11-26 | 3 | 2008-12-02 | 18 |  | 1815 | S4P1 | 24 | EM//TB | hr | 60
615 | S51-6.01 | Rotate 2 TF coils over the MC on the right side | 2008-12-15 | 2 | 2008-12-16 | 18 |  | 1815 | S4P1 | 25 | EM//TB | hr | 40
616 | S51-6.02 | Attach the temp support at end of Type-C MC | 2008-12-17 | 1 | 2008-12-17 | 18 |  | 1815 | S4P1 | 26 | EM//TB | hr | 20
617 | S51-6.03 | Lower leveler pad disengage base of MC right sid | 2008-12-18 | 0 | 2008-12-17 | 18 |  | 1815 | S4P1 | 27 | EM//TB | hr | 0
618 | S51-6.04 | Install TF support brackets | 2008-12-18 | 2 | 2008-12-19 | 18 |  | 1815 | S4P1 | 28 | EM//TB | hr | 40
619 | S51-6.05 | Secure First TF assy | 2008-12-22 | 1 | 2008-12-22 | 18 |  | 1815 | S4P1 | 29 | EM//TB | hr | 20
620 | S51-6.06 | Install TF support brackets | 2008-12-23 | 2 | 2009-01-02 | 18 |  | 1815 | S4P1 | 30 | EM//TB | hr | 40
621 | S51-6.07 | Secure 2nd TF coil | 2009-01-05 | 1 | 2009-01-05 | 18 |  | 1815 | S4P1 | 31 | EM//TB | hr | 20
622 | S51-6.08 | Install machine support plates | 2009-01-06 | 3 | 2009-01-08 | 18 |  | 1815 | S4P1 | 32 | EM//TB | hr | 60
623 | S51-6.09 | Reinstall leveler pad | 2009-01-09 | 0 | 2009-01-08 | 18 |  | 1815 | S4P1 | 33 | EM//TB | hr | 0
624 | S51-6.1 | Installed one side of the TF support brackets | 2009-01-09 | 1 | 2009-01-09 | 18 |  | 1815 | S4P1 | 34 | EM//TB | hr | 20
625 | S51-7.01 | The TF installation on the left side | 2009-01-12 | 13 | 2009-01-28 | 18 |  | 1815 | S4P1 | 35 | EM//TB | hr | 260
626 | S51-8.01 | Perform a fit-up check of the four TF coils | 2009-01-29 | 5 | 2009-02-04 | 18 |  | 1815 | S4P1 | 36 | EM//TB | hr | 100
627 | S51-9.01 | Tack weld the left and right port 4's. | 2009-02-05 | 2 | 2009-02-06 | 18 |  | 1815 | S4P1 | 37 | EM//TB | hr | 40
628 | S51-9.02 | Install boots on both port 4's. | 2009-02-09 | 4 | 2009-02-12 | 18 |  | 1815 | S4P1 | 38 | EM//TB | hr | 80
629 | S51-10.01 | Install PF coil support structure | 2009-02-13 | 8 | 2009-02-24 | 18 |  | 1815 | S4P1 | 39 | EM//TB | hr | 160
630 | S51-11.01 | Install tMC coolant manifold | 2009-02-25 | 3 | 2009-02-27 | 18 |  | 1815 | S4P1 | 40 | EM//TB | hr | 60
631 | S51-11.02 | Connect MC coolant lines to the manifold | 2009-03-02 | 20 | 2009-03-27 | 18 |  | 1815 | S4P1 | 41 | EM//TB | hr | 400
632 | S51-12.01 | Install Rogowski coils | 2009-03-30 | 5 | 2009-04-03 | 18 |  | 1815 | S4P1 | 42 | EM//TB | hr | 100
633 | S51-13.01 | Obtain set of Period 1 align fiducial positions | 2009-04-06 | 5 | 2009-04-10 | 18 |  | 1815 | S4P1 | 43 | EM//TB | hr | 0
634 | S51-13.01 | Obtain set of Period 1 align fiducial positions | 2009-04-06 | 5 | 2009-04-10 | 18 |  | 1815 | S4P1 | 43 | ZMET | met staff (budgeted in LOE) for ref only | 100
635 | S51-13.02 | align to tooling balls on each MCHP | 2009-04-13 | 1 | 2009-04-13 | 18 |  | 1815 | S4P1 | 44 | EM//TB | hr | 0
636 | S51-13.02 | align to tooling balls on each MCHP | 2009-04-13 | 1 | 2009-04-13 | 18 |  | 1815 | S4P1 | 44 | ZMET | met staff (budgeted in LOE) for ref only | 20
637 | S51-13.03 | bring the VV into proper alignment | 2009-04-14 | 4 | 2009-04-17 | 18 |  | 1815 | S4P1 | 45 | EM//TB | hr | 80
638 | S51-13.04 | Install or identify three primary fiducials | 2009-04-20 | 2 | 2009-04-21 | 18 |  | 1815 | S4P1 | 46 | EM//TB | hr | 40
639 | S51-13.05 | Make a final measurement of all fiducials | 2009-04-22 | 2 | 2009-04-23 | 18 | 2 | 1815 | S4P1 | 47 | EM//TB | hr | 0
640 | S51-13.05 | Make a final measurement of all fiducials | 2009-04-22 | 2 | 2009-04-23 | 18 | 2 | 1815 | S4P1 | 47 | ZMET | met staff (budgeted in LOE) for ref only | 100
641 | S51-13.11 | Check Assembly (bolts, etc) | 2009-04-24 | 3 | 2009-04-28 | 18 | 2 | 1815 | S4P1 | 48 | EM//TB | hr | 100
642 | S51-13.12 | Check Diagnostics (Loops, thermocouples) | 2009-04-29 | 2 | 2009-04-30 | 18 | 2 | 1815 | S4P1 | 49 | EM//TB | hr | 100
643 | S51-13.13 | Check manifolds (pressure, flow, etc.) | 2009-05-01 | 3 | 2009-05-05 | 18 | 2 | 1815 | S4P1 | 50 | EM//TB | hr | 100
644 | S51-13.14 | Check 6 modcoils (voltage etc) | 2009-05-06 | 3 | 2009-05-08 | 18 | 2 | 1815 | S4P1 | 51 | EM//TB | hr | 120
645 | S51-13.15 | Check trim coils (voltage etc) | 2009-05-11 | 2 | 2009-05-12 | 18 | 2 | 1815 | S4P1 | 52 | EM//TB | hr | 60
646 | S51-13.16 | Check TF coils (voltage etc) | 2009-05-13 | 3 | 2009-05-15 | 18 | 2 | 1815 | S4P1 | 53 | EM//TB | hr | 120
647 | S51-14.01 | Install crane rigging to completed Period assy | 2009-05-18 | 1 | 2009-05-18 | 18 | 2 | 1815 | S4P1 | 54 | EM//TB | hr | 40
648 | S51-14.02 | Remove platforms | 2009-05-19 | 1 | 2009-05-19 | 18 | 2 | 1815 | S4P1 | 55 | EM//TB | hr | 20
649 | S51-14.03 | Transfer Period 1 to Station 6 in NCSX tTC. | 2009-05-20 | 1 | 2009-05-20 | 18 | 2 | 1815 | S4P1 | 56 | EM//TB | hr | 40
650 | S52-1.01 | cut off short dome | 2009-01-14 | 2 | 2009-01-15 | 18 |  | 1815 | S4P2 | 11 | EM//TB | hr | 40
651 | S52-1.02 | Install insulation system around all ports. | 2009-01-16 | 0 | 2009-01-15 | 18 |  | 1815 | S4P2 | 12 | EM//TB | hr | 0
652 | S52-1.03 | Install heat tape and theomocouples on all ports | 2009-01-16 | 0 | 2009-01-15 | 18 |  | 1815 | S4P2 | 13 | EM//TB | hr | 0
653 | S52-2.01 | Install period support fixture | 2009-01-16 | 2 | 2009-01-19 | 18 |  | 1815 | S4P2 | 14 | EM//TB | hr | 40
654 | S52-2.02 | Install FPA on support stand. | 2009-01-20 | 2 | 2009-01-21 | 18 |  | 1815 | S4P2 | 15 | EM//TB | hr | 40
655 | S52-2.03 | Install external working platforms | 2009-01-22 | 4 | 2009-01-27 | 18 |  | 1815 | S4P2 | 16 | EM//TB | hr | 80
656 | S52-2.04 | Install internal VV working platforms | 2009-01-28 | 3 | 2009-01-30 | 18 |  | 1815 | S4P2 | 17 | EM//TB | hr | 60
657 | S52-3.01 | Install the domes (left and right side), | 2009-02-02 | 2 | 2009-02-03 | 18 |  | 1815 | S4P2 | 18 | EM//TB | hr | 40
658 | S52-3.02 | Install small dome ports remaining circ ports. | 2009-02-04 | 30 | 2009-03-17 | 18 |  | 1815 | S4P2 | 19 | EM//TB | hr | 600
659 | S52-3.03 | Leak check each port after it is welded. | 2009-02-25 | 30 | 2009-04-07 | 18 |  | 1815 | S4P2 | 20 | EM//TB | hr | 600
660 | S52-4.01 | Install boots on ports except for the two port | 2009-03-27 | 16 | 2009-04-17 | 18 |  | 1815 | S4P2 | 21 | EM//TB | hr | 320
661 | S52-5.01 | Install MC lead connections on each of the MC's | 2009-04-20 | 1 | 2009-04-20 | 18 |  | 1815 | S4P2 | 22 | EM//TB | hr | 0
662 | S52-5.02 | Install MC coolant lines on each MC | 2009-04-21 | 12 | 2009-05-06 | 18 |  | 1815 | S4P2 | 23 | EM//TB | hr | 240
663 | S52-5.03 | Platforms may need to be altered | 2009-05-07 | 3 | 2009-05-11 | 18 |  | 1815 | S4P2 | 24 | EM//TB | hr | 60
664 | S52-6.01 | Rotate 2 TF coils over the MC on the right side | 2009-05-12 | 2 | 2009-05-13 | 18 |  | 1815 | S4P2 | 25 | EM//TB | hr | 40
665 | S52-6.02 | Attach the temp support at end of Type-C MC | 2009-05-14 | 1 | 2009-05-14 | 18 |  | 1815 | S4P2 | 26 | EM//TB | hr | 20
666 | S52-6.03 | Lower leveler pad disengage base of MC right sid | 2009-05-15 | 0 | 2009-05-14 | 18 |  | 1815 | S4P2 | 27 | EM//TB | hr | 0
667 | S52-6.04 | Install TF support brackets | 2009-05-15 | 2 | 2009-05-18 | 18 |  | 1815 | S4P2 | 28 | EM//TB | hr | 40
668 | S52-6.05 | Secure First TF assy | 2009-05-19 | 1 | 2009-05-19 | 18 |  | 1815 | S4P2 | 29 | EM//TB | hr | 20
669 | S52-6.06 | Install TF support brackets | 2009-05-20 | 2 | 2009-05-21 | 18 |  | 1815 | S4P2 | 30 | EM//TB | hr | 40
670 | S52-6.07 | Secure 2nd TF coil | 2009-05-22 | 1 | 2009-05-22 | 18 |  | 1815 | S4P2 | 31 | EM//TB | hr | 20
671 | S52-6.08 | Install machine support plates | 2009-05-26 | 3 | 2009-05-28 | 18 |  | 1815 | S4P2 | 32 | EM//TB | hr | 60
672 | S52-6.09 | Reinstall leveler pad | 2009-05-29 | 0 | 2009-05-28 | 18 |  | 1815 | S4P2 | 33 | EM//TB | hr | 0
673 | S52-6.1 | Installed one side of the TF support brackets | 2009-05-29 | 1 | 2009-05-29 | 18 |  | 1815 | S4P2 | 34 | EM//TB | hr | 20
674 | S52-7.01 | The TF installation on the left side | 2009-06-01 | 13 | 2009-06-17 | 18 |  | 1815 | S4P2 | 35 | EM//TB | hr | 260
675 | S52-8.01 | Perform a fit-up check of the four TF coils | 2009-06-18 | 5 | 2009-06-24 | 18 |  | 1815 | S4P2 | 36 | EM//TB | hr | 100
676 | S52-9.01 | Tack weld the left and right port 4's. | 2009-06-25 | 2 | 2009-06-26 | 18 |  | 1815 | S4P2 | 37 | EM//TB | hr | 40
677 | S52-9.02 | Install boots on both port 4's. | 2009-06-29 | 4 | 2009-07-02 | 18 |  | 1815 | S4P2 | 38 | EM//TB | hr | 80
678 | S52-10.01 | Install PF coil support structure | 2009-07-06 | 8 | 2009-07-15 | 18 |  | 1815 | S4P2 | 39 | EM//TB | hr | 160
679 | S52-11.01 | Install tMC coolant manifold | 2009-07-16 | 3 | 2009-07-20 | 18 |  | 1815 | S4P2 | 40 | EM//TB | hr | 60
680 | S52-11.02 | Connect MC coolant lines to the manifold | 2009-07-21 | 20 | 2009-08-17 | 18 |  | 1815 | S4P2 | 41 | EM//TB | hr | 400
681 | S52-12.01 | Install Rogowski coils | 2009-08-18 | 5 | 2009-08-24 | 18 |  | 1815 | S4P2 | 42 | EM//TB | hr | 100
682 | S52-13.01 | Obtain set of Period 1 align fiducial positions | 2009-08-25 | 5 | 2009-08-31 | 18 |  | 1815 | S4P2 | 43 | EM//TB | hr | 0
683 | S52-13.01 | Obtain set of Period 1 align fiducial positions | 2009-08-25 | 5 | 2009-08-31 | 18 |  | 1815 | S4P2 | 43 | ZMET | met staff (budgeted in LOE) for ref only | 100
684 | S52-13.02 | align to tooling balls on each MCHP | 2009-09-01 | 1 | 2009-09-01 | 18 |  | 1815 | S4P2 | 44 | EM//TB | hr | 0
685 | S52-13.02 | align to tooling balls on each MCHP | 2009-09-01 | 1 | 2009-09-01 | 18 |  | 1815 | S4P2 | 44 | ZMET | met staff (budgeted in LOE) for ref only | 20
686 | S52-13.03 | bring the VV into proper alignment | 2009-09-02 | 4 | 2009-09-08 | 18 |  | 1815 | S4P2 | 45 | EM//TB | hr | 80
687 | S52-13.04 | Install or identify three primary fiducials | 2009-09-09 | 2 | 2009-09-10 | 18 |  | 1815 | S4P2 | 46 | EM//TB | hr | 40
688 | S52-13.05 | Make a final measurement of all fiducials | 2009-09-11 | 5 | 2009-09-17 | 18 |  | 1815 | S4P2 | 47 | EM//TB | hr | 0
689 | S52-13.05 | Make a final measurement of all fiducials | 2009-09-11 | 5 | 2009-09-17 | 18 |  | 1815 | S4P2 | 47 | ZMET | met staff (budgeted in LOE) for ref only | 100
690 | S52-13.11 | Check Assembly (bolts, etc) | 2009-09-18 | 5 | 2009-09-24 | 18 |  | 1815 | S4P2 | 48 | EM//TB | hr | 100
691 | S52-13.12 | Check Diagnostics (Loops, thermocouples) | 2009-09-25 | 5 | 2009-10-01 | 18 |  | 1815 | S4P2 | 49 | EM//TB | hr | 100
692 | S52-13.13 | Check manifolds (pressure, flow, etc.) | 2009-10-02 | 5 | 2009-10-08 | 18 |  | 1815 | S4P2 | 50 | EM//TB | hr | 100
693 | S52-13.14 | Check 6 modcoils (voltage etc) | 2009-10-09 | 6 | 2009-10-16 | 18 |  | 1815 | S4P2 | 51 | EM//TB | hr | 120
694 | S52-13.15 | Check trim coils (voltage etc) | 2009-10-19 | 3 | 2009-10-21 | 18 |  | 1815 | S4P2 | 52 | EM//TB | hr | 60
695 | S52-13.16 | Check TF coils (voltage etc) | 2009-10-22 | 6 | 2009-10-29 | 18 |  | 1815 | S4P2 | 53 | EM//TB | hr | 120
696 | S52-14.01 | Install crane rigging to completed Period assy | 2009-10-30 | 2 | 2009-11-02 | 18 |  | 1815 | S4P2 | 54 | EM//TB | hr | 40
697 | S52-14.02 | Remove platforms | 2009-11-03 | 1 | 2009-11-03 | 18 |  | 1815 | S4P2 | 55 | EM//TB | hr | 20
698 | S52-14.03 | Transfer Period 2 to Station 6 in NCSX tTC. | 2009-11-04 | 2 | 2009-11-05 | 18 |  | 1815 | S4P2 | 56 | EM//TB | hr | 40
699 | R1810-5333 | Last field period assembled |  | 0 | 2009-10-23 | 18 | 2 | 1815 | S4P3 |  |  |  | 0
700 | S53-1.01 | cut off short dome | 2009-05-21 | 1 | 2009-05-21 | 18 | 2 | 1815 | S4P3 | 11 | EM//TB | hr | 40
701 | S53-1.02 | Install insulation system around all ports. | 2009-05-22 | 0 | 2009-05-21 | 18 | 2 | 1815 | S4P3 | 12 | EM//TB | hr | 0
702 | S53-1.03 | Install heat tape and theomocouples on all ports | 2009-05-22 | 0 | 2009-05-21 | 18 | 2 | 1815 | S4P3 | 13 | EM//TB | hr | 0
703 | S53-2.01 | Install period support fixture | 2009-05-22 | 1 | 2009-05-22 | 18 | 2 | 1815 | S4P3 | 14 | EM//TB | hr | 40
704 | S53-2.02 | Install FPA on support stand. | 2009-05-26 | 1 | 2009-05-26 | 18 | 2 | 1815 | S4P3 | 15 | EM//TB | hr | 40
705 | S53-2.03 | Install external working platforms | 2009-05-27 | 2 | 2009-05-28 | 18 | 2 | 1815 | S4P3 | 16 | EM//TB | hr | 80
706 | S53-2.04 | Install internal VV working platforms | 2009-05-29 | 2 | 2009-06-01 | 18 | 2 | 1815 | S4P3 | 17 | EM//TB | hr | 60
707 | S53-3.01 | Install the domes (left and right side), | 2009-06-02 | 1 | 2009-06-02 | 18 | 2 | 1815 | S4P3 | 18 | EM//TB | hr | 40
708 | S53-3.02 | Install small dome ports remaining circ ports. | 2009-06-03 | 15 | 2009-06-23 | 18 | 2 | 1815 | S4P3 | 19 | EM//TB | hr | 600
709 | S53-3.03 | Leak check each port after it is welded. | 2009-06-12 | 15 | 2009-07-02 | 18 | 2 | 1815 | S4P3 | 20 | EM//TB | hr | 600
710 | S53-4.01 | Install boots on ports except for the two port | 2009-06-29 | 8 | 2009-07-09 | 18 | 2 | 1815 | S4P3 | 21 | EM//TB | hr | 320
711 | S53-5.01 | Install MC lead connections on each of the MC's | 2009-07-10 | 1 | 2009-07-10 | 18 | 2 | 1815 | S4P3 | 22 | EM//TB | hr | 0
712 | S53-5.02 | Install MC coolant lines on each MC | 2009-07-13 | 6 | 2009-07-20 | 18 | 2 | 1815 | S4P3 | 23 | EM//TB | hr | 240
713 | S53-5.03 | Platforms may need to be altered | 2009-07-21 | 2 | 2009-07-22 | 18 | 2 | 1815 | S4P3 | 24 | EM//TB | hr | 60
714 | S53-6.01 | Rotate 2 TF coils over the MC on the right side | 2009-07-23 | 1 | 2009-07-23 | 18 | 2 | 1815 | S4P3 | 25 | EM//TB | hr | 40
715 | S53-6.02 | Attach the temp support at end of Type-C MC | 2009-07-24 | 1 | 2009-07-24 | 18 | 2 | 1815 | S4P3 | 26 | EM//TB | hr | 20
716 | S53-6.03 | Lower leveler pad disengage base of MC right sid | 2009-07-27 | 0 | 2009-07-24 | 18 | 2 | 1815 | S4P3 | 27 | EM//TB | hr | 0
717 | S53-6.04 | Install TF support brackets | 2009-07-27 | 1 | 2009-07-27 | 18 | 2 | 1815 | S4P3 | 28 | EM//TB | hr | 40
718 | S53-6.05 | Secure First TF assy | 2009-07-28 | 1 | 2009-07-28 | 18 | 2 | 1815 | S4P3 | 29 | EM//TB | hr | 20
719 | S53-6.06 | Install TF support brackets | 2009-07-29 | 1 | 2009-07-29 | 18 | 2 | 1815 | S4P3 | 30 | EM//TB | hr | 40
720 | S53-6.07 | Secure 2nd TF coil | 2009-07-30 | 1 | 2009-07-30 | 18 | 2 | 1815 | S4P3 | 31 | EM//TB | hr | 20
721 | S53-6.08 | Install machine support plates | 2009-07-31 | 1 | 2009-07-31 | 18 | 2 | 1815 | S4P3 | 32 | EM//TB | hr | 60
722 | S53-6.09 | Reinstall leveler pad | 2009-08-03 | 0 | 2009-07-31 | 18 | 2 | 1815 | S4P3 | 33 | EM//TB | hr | 0
723 | S53-6.1 | Installed one side of the TF support brackets | 2009-08-03 | 1 | 2009-08-03 | 18 | 2 | 1815 | S4P3 | 34 | EM//TB | hr | 20
724 | S53-7.01 | The TF installation on the left side | 2009-08-04 | 6 | 2009-08-11 | 18 | 2 | 1815 | S4P3 | 35 | EM//TB | hr | 260
725 | S53-8.01 | Perform a fit-up check of the four TF coils | 2009-08-12 | 3 | 2009-08-14 | 18 | 2 | 1815 | S4P3 | 36 | EM//TB | hr | 100
726 | S53-9.01 | Tack weld the left and right port 4's. | 2009-08-17 | 1 | 2009-08-17 | 18 | 2 | 1815 | S4P3 | 37 | EM//TB | hr | 40
727 | S53-9.02 | Install boots on both port 4's. | 2009-08-18 | 2 | 2009-08-19 | 18 | 2 | 1815 | S4P3 | 38 | EM//TB | hr | 80
728 | S53-10.01 | Install PF coil support structure | 2009-08-20 | 4 | 2009-08-25 | 18 | 2 | 1815 | S4P3 | 39 | EM//TB | hr | 160
729 | S53-11.01 | Install tMC coolant manifold | 2009-08-26 | 2 | 2009-08-27 | 18 | 2 | 1815 | S4P3 | 40 | EM//TB | hr | 60
730 | S53-11.02 | Connect MC coolant lines to the manifold | 2009-08-28 | 10 | 2009-09-11 | 18 | 2 | 1815 | S4P3 | 41 | EM//TB | hr | 400
731 | S53-12.01 | Install Rogowski coils | 2009-09-14 | 3 | 2009-09-16 | 18 | 2 | 1815 | S4P3 | 42 | EM//TB | hr | 100
732 | S53-13.01 | Obtain set of Period 1 align fiducial positions | 2009-09-17 | 2 | 2009-09-18 | 18 | 2 | 1815 | S4P3 | 43 | EM//TB | hr | 0
733 | S53-13.01 | Obtain set of Period 1 align fiducial positions | 2009-09-17 | 2 | 2009-09-18 | 18 | 2 | 1815 | S4P3 | 43 | ZMET | met staff (budgeted in LOE) for ref only | 100
734 | S53-13.02 | align to tooling balls on each MCHP | 2009-09-21 | 1 | 2009-09-21 | 18 | 2 | 1815 | S4P3 | 44 | EM//TB | hr | 0
735 | S53-13.02 | align to tooling balls on each MCHP | 2009-09-21 | 1 | 2009-09-21 | 18 | 2 | 1815 | S4P3 | 44 | ZMET | met staff (budgeted in LOE) for ref only | 20
736 | S53-13.03 | bring the VV into proper alignment | 2009-09-22 | 2 | 2009-09-23 | 18 | 2 | 1815 | S4P3 | 45 | EM//TB | hr | 80
737 | S53-13.04 | Install or identify three primary fiducials | 2009-09-24 | 1 | 2009-09-24 | 18 | 2 | 1815 | S4P3 | 46 | EM//TB | hr | 40
738 | S53-13.05 | Make a final measurement of all fiducials | 2009-09-25 | 3 | 2009-09-29 | 18 | 2 | 1815 | S4P3 | 47 | EM//TB | hr | 0
739 | S53-13.05 | Make a final measurement of all fiducials | 2009-09-25 | 3 | 2009-09-29 | 18 | 2 | 1815 | S4P3 | 47 | ZMET | met staff (budgeted in LOE) for ref only | 100
740 | S53-13.11 | Check Assembly (bolts, etc) | 2009-09-30 | 2 | 2009-10-01 | 18 | 2 | 1815 | S4P3 | 48 | EM//TB | hr | 100
741 | S53-13.12 | Check Diagnostics (Loops, thermocouples) | 2009-10-02 | 3 | 2009-10-06 | 18 | 2 | 1815 | S4P3 | 49 | EM//TB | hr | 100
742 | S53-13.13 | Check manifolds (pressure, flow, etc.) | 2009-10-07 | 2 | 2009-10-08 | 18 | 2 | 1815 | S4P3 | 50 | EM//TB | hr | 100
743 | S53-13.14 | Check 6 modcoils (voltage etc) | 2009-10-09 | 3 | 2009-10-13 | 18 | 2 | 1815 | S4P3 | 51 | EM//TB | hr | 120
744 | S53-13.15 | Check trim coils (voltage etc) | 2009-10-14 | 2 | 2009-10-15 | 18 | 2 | 1815 | S4P3 | 52 | EM//TB | hr | 60
745 | S53-13.16 | Check TF coils (voltage etc) | 2009-10-16 | 3 | 2009-10-20 | 18 | 2 | 1815 | S4P3 | 53 | EM//TB | hr | 120
746 | S53-14.01 | Install crane rigging to completed Period assy | 2009-10-21 | 1 | 2009-10-21 | 18 | 2 | 1815 | S4P3 | 54 | EM//TB | hr | 40
747 | S53-14.02 | Remove platforms | 2009-10-22 | 1 | 2009-10-22 | 18 | 2 | 1815 | S4P3 | 55 | EM//TB | hr | 20
748 | S53-14.03 | Transfer Period 3 to Station 6 in NCSX tTC. | 2009-10-23 | 1 | 2009-10-23 | 18 | 2 | 1815 | S4P3 | 56 | EM//TB | hr | 40