NCSX

Manufacturing Facility Operations Plan

NCSX-PLAN-MFOP-01-dB

Draft B

13 October 2005

Prepared by: __________________________________________________________________________

J. Chrzanowski, Coil Manufacturing Facility Manager

Prepared by:___________________________________________________________________________

M. Viola, Field Period Assembly Manager

Concur: ______________________________________________________________________________

T. Brown, Field Period Assembly WBS Manager (WBS 18_

Concur: ______________________________________________________________________________

B. Nelson, RLM for Stellarator Core Systems (WBS 1)

Concur: ______________________________________________________________________________

S. Raftopoulos, Lead Metrology Engineer

Concur: ______________________________________________________________________________

B. Stratton, Dimensional Control Coordinator

Concur: ______________________________________________________________________________

W. Slavin, Industrial Hygiene

Concur: ______________________________________________________________________________

J. Levine, ES&H

Concur: ______________________________________________________________________________

J. Malsbury, Quality Assurance

Approved by: _________________________________________________________________________

L. Dudek, RLM for On-site Fabrication

Record of Revisions

| Revision | Date | ECP | Description of Change |
| --- | --- | --- | --- |
| Rev. 0 | 8/29/05 | - | Initial issue. Supersedes NCSX-PLAN-MCFOP-01 |

Table of Contents

1	Scope	- 1 -

2	Applicable Documents	- 1 -

3	Description of Major Components and Assemblies	- 2 -

3.1	Modular Coils	- 2 -

3.2	Toroidal Field (TF) Coils	- 3 -

3.3	Coil Support Structures	- 5 -

3.4	External Trim Coils	- 5 -

3.5	Vacuum Vessel Initial Assembly	- 6 -

3.6	Modular Coil Sub-assembly (MCSA)	- 6 -

3.7	TF Coil 3-Coil Module	- 7 -

3.8	Field Period Assembly	- 7 -

3.9	Station Logbook	- 22 -

3.10	Daily Summary Report	- 22 -

3.11	Radiation Controlled Area:	- 24 -

3.12	Quality Control during Manufacturing	- 26 -

3.13	Measurements	- 26 -

Table of Figures

Figure 1-Modular Coil Types	Error! Bookmark not defined.

Figure 2- Twisted Racetrack Coil	Error! Bookmark not defined.

Figure 3- Toroidal Field Coil	Error! Bookmark not defined.

Figure 4 Complete Stellarator Core Field Period	- 8 -

Figure 5 TFTR Loading Station	- 9 -

Figure 6-NCSX Manufacturing Facility	- 10 -

Figure 6 Vacuum Vessel Support	- 12 -

Figure 7- Flow Plan for MC Fabrication	- 14 -

Figure 8- Flow Plan for TRC Fabrication	- 15 -

Figure 9- Flow Plan for TF Coil Fabrication	- 15 -

Figure 9- Flow Plan for Coil VPI Fabrication	- 16 -

Figure 11 - Field Period Assembly Plan Outline	- 18 -

Figure 10-NCSX Manufacturing Facility Organizational Chart	- 20 -

Table of Tables

Table 1 Typical components to be lifted and weights	- 9 -

# Scope

The National Compact Stellarator Experiment (NCSX) Modular and Toroidal Field Coils will be manufactured and field periods assembled at the Princeton Plasma Physics Laboratory (PPPL) for the NCSX Project.  This work will be done in the NCSX Manufacturing Facility which is housed in the test cell formerly used for the Tokamak Fusion Test Reactor (TFTR).  This document describes the general operations plan that will be used during the manufacturing of coils and assembly of the field periods.  It describes:

Work to be accomplished;

The facility and work stations;

The work flow;

Roles and responsibilities;

Facility operating guidelines;

Safety and quality controls.

This plan supersedes the Coil Manufacturing Facility Operations Plan (NCSX-PLAN-CMFOP-01-00). Separate Manufacturing, Inspection, and Test/Quality Assurance (MIT/QA) Plans and supporting procedures will be developed for the modular coil and TF coil manufacturing and field period assembly.

# Applicable Documents

| Document Number | Title |
| --- | --- |
| ES&H Documents |
| ES&H 5008 | PPPL Environmental, Safety and Health Manual |
| ESH-004 | Job Hazard Analysis |
| ESH-008 | Access to Radiological Areas (RCA’s) |
| NEPA 1283 | Modular/TF Coil Development and Production |
| Manufacturing, Inspection, Test and Quality Assurance Plans |
| NCSX-MIT/QA-131-01-00 | Mfg., Inspection, Test/QA Plan for Toroidal Field Coils |
| NCSX-MIT/QA-142-01-00 | Mfg., Inspection, Test/QA Plan for Modular Coils |
| NCSX-MIT/QA-185-01-00 | Mfg., Inspection, Test/QA Plan for Field Period Assembly |
| Component Specifications |
| NCSX-CSPEC-121-02 | Vacuum Vessel Sub-assembly |
| NCSX-CSPEC-131-02 | Toroidal Field Coil Conductor |
| NCSX-CSPEC-131-03 | Toroidal Field Coil Wedge Casting |
| NCSX-CSPEC-133-XX | External Trim Coils |
| NCSX-CSPEC-142-03 | Modular Coil Conductor |
| NCSX-CSPEC-141-03 | Modular Coil Winding Forms |
| NCSX-CSPEC-15-XX | Coil Support Structure |
| Fabrication Specifications |
| NCSX-CSPEC-131-01 | Toroidal Field Coil Assembly |
| NCSX-CSPEC-142-05 | Modular Coil Type C Assembly |
| NCSX-CSPEC-142-XX | Modular Coil Type A Assembly |
| NCSX-CSPEC-142-XX | Modular Coil Type B Assembly |
| NCSX-CSPEC-142-XX | Modular Coil Half-period Assembly |
| NCSX-CSPEC-185-XX | Initial Vacuum Vessel Assembly |
| NCSX-CSPEC-185-XX | TF Half-period Assembly |
| NCSX-CSPEC-185-XX | Initial Field Period Assembly |
| NCSX-CSPEC-185-XX | Final Field Period Assembly |
| Work Planning Forms |
| WP-1038 | Work Planning Form for Winding Production Mod Coil |
| WP-1188 | Work Planning Form for Twisted Racetrack Coil |
| WP-1227 | Work Planning Form for Winding Production TF Coils |
| WP-1224 | Work Planning Form for Field Period Assembly |
| Manufacturing Facility Procedures |
| D-NCSX-OP-EO-41 | NCSX Coil Manufacturing Facility Emergency Response |

# Description of Major Components and Assemblies

## Modular Coils

The modular coils consist of three field periods with 6 coils per period for a total of 18 coils.  Due to symmetry, only three different coil shapes are required to make up the complete coil set.  Each modular coil is constructed by winding pre-insulated rectangular compacted copper cable onto a stainless steel cast winding form. The modular coil winding forms are being provided by Energy Industries of Ohio (EIO) in accordance with the product specification for the modular coil winding forms (NCSX-CSPEC-141-03).

Each coil consists of two double pancake windings.  Once wound, the entire coil is vacuum-pressure impregnated (VPI) with epoxy. Individual coil assemblies – one of each coil type – are bolted together to form a 3-coil module.  3-coil modules are slid over each end of a 120° vacuum vessel sub-assembly (VVSA) and bolted together as part of assembling a field period.  The three different modular coil types are shown in Figure 1 below.  The modular coil assemblies will manufactured in the NCSX Manufacturing Facility in accordance with the product specification for each coil type (NCSX-CSPEC-142-XX for Type A coils, NCSX-CSPEC-142-XX for Type B coils, and NCSX-CSPEC-142-05 for Type C coils).

Figure 1 - Modular coil types

## Toroidal Field (TF) Coils

The Toroidal Field (TF) Coil System consist of 18 identical, equally spaced coils. Each TF coil has 12 turns and is constructed by winding pre-insulated rectangular hollow core copper conductors onto a winding mandrel. Once wound, the coils are ground wrapped with fiberglass tape, placed in a vacuum mold and epoxy impregnated (VPI) in the autoclave. Wedge castings will then be installed.  During post VPI testing and operation, the coil set will be pre-cooled to cryogenic temperatures using nitrogen gas.  Figure 2 shows a TF coil assembly and a cross-section view through the nose region.  The TF conductor will be supplied by Outokumpu of Finland in accordance with the product specification for the TF conductor (NCSX-CSPEC-131-02).  The wedge castings will be fabricated in accordance with the product specification for the wedge castings (NCSX-CSPEC-131-03).  The TF coil assemblies will be fabricated in the NCSX Manufacturing Facility in accordance with the product specification for the TF coil assembly (NCSX-CSPEC-131-01).

Figure 2 – TF coil assembly and cross-section

### Vacuum Vessel Sub-assembly (VVSA)

The vacuum vessel sub-assembly (VVSA) is a 120° segment of the vacuum vessel and includes a vacuum vessel period assembly, port extensions, spacer, and port covers and seals.  These elements are shown in Figure 3.  The three VVSAs will be fabricated by Major Tool and Machine in accordance with the product specification for the VVSA (NCSX-CSPEC-121-02).

Figure 3 - Vacuum vessel sub-assembly components

## Coil Support Structures

The coil support structures provide structural support for the TF and PF coils.  The coil support structures consist of two shelves – one above the modular coils and one below the modular coils.  The upper and lower support structures are connected through the structural shell of the modular coils.  The coil support structures are shown in Figure 4 with (left frame) and without (right frame) the modular coils.  The coil support structures will be fabricated in accordance with the product specification (NCSX-CSPEC-15-XX) and assembled on-site at PPPL.

Figure 4 - Coil support structures

## External Trim Coils

The external trim coils are used to null out field errors with a low poloidal mode number.  The design of the trim coils is still evolving.  An early concept is shown in Figure 5.  The external trim coils are the small, beige-colored coils with trapezoidal shapes.  The external trim coils will be fabricated in accordance with their product specification (NCSX-CSPEC-133-XX).

Figure 5 – External trim coil concept

## Initial Vacuum Vessel Assembly

The Initial Vacuum Vessel Assembly (IVVA) consists of a single vacuum vessel period assembly (part of the VVSA) with coolant tubes and headers and magnetic diagnostics installed.  The IVVA will be assembled in Station V1 in the NCSX Manufacturing Facility in accordance with its product specification (NCSX-CSPEC-185-XX).  A picture of the IVVA with the magnetic flux loops and coolant tubes being installed is shown in Figure 6.

Figure 6 – A completed IVVA

## Modular Coil Half-period Assembly (MCHPA)

The modular coils will be assembled in 3-coil modules known as Modular Coil Half-period Assemblies (MCHPAs).  Each MCHPA will have one coil assembly of each type.  The MCHPAs will be assembled in Station V2 in the NCSX Manufacturing Facility in accordance with their product specification (NCSX-CSPEC-185-XX).  A picture of a MCHPA being assembled in Station V2 is shown in Figure 7.

Figure 7 - Modular coil half-period assembly (MCHPA) being assembled in Station V2

## TF Coil Half-period Assembly (TFHPA)

The TF coils will be assembled in 3-coil modules known as TF Coil Half-period Assemblies (TFHPAs).  Each TFHPA will have 60° segments of the coil support structures installed above and below the TF coils.  Temporary supports are provided as part of the TFHPA to connect the coil support structure segments.  These temporary supports are removed later when the coil support structures are mounted to the modular coils.  The TFHPAs will be assembled in Station ? in the NCSX Manufacturing Facility in accordance with the TFHPA product specification (NCSX-CSPEC-185-XX).  A picture of a TFHPA being assembled in Station V2 is shown in Figure 8.

Figure 8 – A completed TF Half-period Assembly (TFHPA)

## Initial Field Period Assembly

The Initial Field Period Assembly (IFPA) is comprised of an Initial Vacuum Vessel Assembly (IVVA) with two Modular Coil Half-period Assemblies (MCHPAs) installed over the IVVA and joined together.  When completed, the IVVA will be supported off the modular coils and all of the port extensions are installed except for Port 4.  In preparation for installing the pourable thermal insulation, the boots to seal the port extensions to the modular coil shell are also installed.  The IFPAs will be assembled in Station V3 in the NCSX Manufacturing Facility in accordance with the IFPA product specification (NCSX-CSPEC-185-XX).

## Final Field Period Assembly

The Final Field Period Assembly (FFPA) is comprised of an Initial Field Period Assembly (IFPA) with two TF Coil Half-period Assemblies (TFHPAs) installed and joined together.  When completed, the modular coils will be attached to the Coil Support Structure on the top and bottom.  Port 4 extensions will be installed completing the port installations.  Trim coils will also be installed.  The FFPAs will be assembled in Station V4 in the NCSX Manufacturing Facility in accordance with the IFPA product specification (NCSX-CSPEC-185-XX).  The completed FFPA will be ready for transport to the NCSX Test Cell.

Figure 9 - Completed Final Field Period Assembly (FFPA)

The Field Period Assembly area will make use of the crane primarily for picking up major components such as the Vacuum Vessel, Modular Coil, TF Coil and the completed Field Period Assembly. When components arrive from the vendor they will be inspected for damage, lifted off the truck and placed in an area designated for receiving inspection. All necessary documentation will be reviewed and any additional testing will be performed. When the component has passed the receiving inspection test it will be lifted to the appropriate fixture in the assembly area.

When a Field Period Assembly is completed it will be lifted from the fixture in the assembly area and set on a truck for shipment as shown in Figure 9. The Field Period Assembly will be driven a short distance on site to the NCSX test cell.

The crane is not expected to be used for day-to-day assembly. Local fixtures will be used for assembly. Typical lifts and the weights are shown in Table 1.  After a lift has been performed the crane will be released for other operations needed in the TFTR Test Cell.

Figure 11 TFTR Loading Station

Table 1 Typical components to be lifted and weights

| Description | Weight |
| --- | --- |
| Vacuum Vessel | 6,400 lbs |
| M1 Coil | 7,100 lbs |
| M2 Coil | 6,700 lbs |
| M3 Coil | 7,100 lbs |
| Half period Modular Coil | 21,000 lbs x 2 |
| Half period TF Coil | 11,000 lbs x 2 |
| Field Period Assembly | 70,400 lbs |

# Facilities and Work Stations

The Twisted Racetrack (TRC), Modular (MC) and Toroidal Field (TF) Coils are fabricated in the vacated TFTR Test Cell at D-site. The coil testing facility as well as the coil storage area is located in the Test Cell basement. The NCSX Coil Manufacturing Facility (CMF) has adequate climate control needed for comfort and tolerance control and crane capabilities.  There are a total of six [7] workstations associated with the manufacturing of the MC, TRC and TF coils.  The facility will from here on be identified as the “NCSX Coil Manufacturing Facility” (Error! Reference source not found.). The basement area will be identified as the NCSX Coil Test Facility and the NCSX Coil Storage Area.

Figure 12-NCSX Manufacturing Facility

## Facilities Description

The Manufacturing facility (formerly known as the TFTR test cell), shown in Figure 6, is approximately 114 ft wide by 150 ft. long. The modular coil area will occupy the North side of the building.  The Field Period Assembly will be located around the modular coil area in the east and south side of the building. PPPL will coordinate the cleanup and installation of fixtures that will be used for Field Period Assembly. Utilities such as instrument air, power and data ports will be installed or upgraded based on the needs of each fixture, but at the present time the utilities appear adequate.  Data ports will be installed as needed, primarily to collect the metrology data that will be generated during the assembly processes. The building crane will be shared with the modular coil assembly.

### Crane Capacity

The manufacturing facility has an overhead trolley crane with (2) hooks.

Load capacity: Large hook- 110 Ton;	 Small hook/ 25 Ton

### Climate Control

The coil manufacturing facility environment will be maintained at a constant 70 degrees F +/- 5 degrees with 50% relative humidity +/- 10%

Work Space

Test Cell has over 14,000 square feet of floor space that will be shared between the coil manufacturing facility, field period assembly activities plus the remaining neutral beams from TFTR. The coil winding facility will need a minimum of 3500 square feet of floor space.

Work Station Descriptions

Modular Coils: There are a total of [5] workstations associated with the production of the Modular Coils.  Stations 1, 2, 4 and 5 are located in the Coil Manufacturing Facility (CMF).  Station No. 7 is located in the basement.

Twisted Racetrack Coils: There are a total of [3] workstations associated with the production of the TRC.  Stations 2 and 5 are located in the Coil Manufacturing Facility (CMF).  Station No. 7 is located in the basement.

Toroidal Field Coils: There are [4] workstations associated with the production of the TF coils. Stations 3, 5 and 6 are located in the Coil Manufacturing Facility (CMF).  Station No. 7 is located in the basement.

Field Period Assembly (FPA): There are [5] workstations associated with the assembly. These workstations are labeled V1– V5 to differentiate from the coil stations.

Station No. 1a & b- Winding Form Preparation and Post VPI

Modular Coils: [Winding Form Prep]: At this station [1a] the modular coil winding forms are mounted to the turning fixture support rings.  The assembled MC form and support ring are then installed into the [1b] turning fixture. There the winding forms are inspected and cleaned.  The poloidal break will be electrically tested and sealed, the coil clamp studs are welded in position, initial metrology and inspections performed and the inner copper cladding is installed.

[Post VPI]:Once the coil has been epoxy impregnated (VPI) at station 5, it will return to station 1b for cleanup, installation of final coil clamps and final room temperature electrical testing.

Stations 2 & 4- Coil Winding and Mold Preparation

Modular Coils: At these (2) stations the pre-insulated copper cable conductors are wound onto the stainless steel winding forms [castings].  Work at this station includes winding, adjusting the coil centroid using the Romer (CCM), the installation of the Groundwrap insulation as well as completion [brazing] of the coil leads.  Once the Groundwrap has been completed, the outer chill plates, outer diagnostics, and “Bag Mold” are installed. These (2) stations are enclosed with a ceiling and walls to better control the cleanliness of the winding environment.  The rooms are provided with positive pressure that may be utilized to reduce any outside contamination.

Twisted Racetrack Coil: At station 2 all winding form preparations as well as coil winding and post VPI activities will be performed on the TRC.

Station No. 3- Coil Winding and Mold Preparation

Toroidal Field Coils: At this station the TF coils are wound onto a winding mandrel using insulated extruded copper conductor.  Work at this station includes application of turn insulation, conductor brazing, joint testing as well as completion of the coil leads.  Once the coil has been wound, the coil is then moved to stands within the cleanroom, for application of the groundwrap insulation. The coil is then placed into a vacuum mold in preparation for VPI activities. This station is enclosed with a ceiling and walls to better control the cleanliness of the winding environment.  The room is provided with positive pressure that may be used to reduce any outside contamination.

Station No. 5- Autoclave/VPI

This station is comprised of the autoclave [vacuum/pressure oven], epoxy mixing station and epoxy control/delivery manifold for performing the epoxy vacuum-pressure-impregnation of the TRC, MC and TF coils.

Station No. 6- TF Wedge Casting Assembly:

At this station a matching pair of stainless steel wedge castings is assembled to the TF Coil to make up the TF Coil Subassembly.  This operation occurs after VPI is complete and the coil is cured therefore a clean room is not required.  The wedge castings are adhered to the coil within a steel alignment fixture to precisely locate the mating surfaces of the castings with respect to the current center of the coils.  Note: This will occur following any cold testing.

Station No. 7- NCSX Coil Test Facility

This station is located in the Test Cell basement.  This facility will be used to electrically test the coils at liquid nitrogen temperatures to ensure their integrity.

Station No. V1 – VVSA receipt Inspection, diagnostic loop and cooling tube installation Facility

The Field Period Assembly will begin with the assembly of the vacuum vessel. This station is comprised of two trunions that will support the VVSA in a rotisserie style. The Diagnostic loops will be installed using small tabs spot welded to the vessel surface and then the cooling tubes will be installed with studs welded to the surface and clamps applied.

Figure 13 Vacuum Vessel Support

Station No. V2 – Modular Coil Assembly

This station is comprised of a tilting platform that will allow the modular coils to be aligned and bolted together.

Station No. V3 – Modular Coil and Port Extension Installation

This station is comprised of a support that will hold the vacuum vessel vertical and allow the modular coils to be rotated (screwed) onto each end of the VVSA, one at a time.  Then the ports will be aligned and welded on. From this point forward, the Assembly will be called the Field Period Assembly.

Station No. V4 – TF Coil and Trim Coil Installation

This station is comprised of a support for the Field Period Assembly and a large column that will be used to support the TF Coils and rotate them onto the Field Period Assembly.

Station No. V5 – Storage and Transportation Preparation

This station is space set aside for minor intermediate operations or storage both between stations and in preparation for transportation to the NCSX Test Cell.

Manufacturing Inspection & Test/Quality Assurance Plan

The Manufacturing Inspection & Test/Quality Assurance Plans (MIT/QA) govern all manufacturing activities.  These documents describe the steps required to successfully manufacture, inspect and test the NCSX coils and assemble the FPA. The (MIT/QA) plan document numbers NCSX-MIT/QA-142-01-01 (Modular Coils) and NCSX-MIT/QA-131-01-00 (TF Coils) identify procedures, test plans, Field Packages etc. necessary to complete the production of the NCSX coils. NCSX-MIT/QA-183-01-00 (FPA) identifies procedures, test plans, Field Packages etc. necessary to complete the assembly of the field periods.

Figure 14- Flow Plan for MC Fabrication

Flow Plan of the Manufacturing Operations

Figure 12- Flow Plan for MC Fabrication provides the general flow plan outlining the operation of this facility for the Modular Coils. Figure 13- Flow Plan for TRC Fabrication provides the general flow plan outlining the operation of this facility for the Twisted Racetrack Coil.  Error! Reference source not found. provides the general flow plan outlining the operation of this facility for the Toroidal Field Coils.

Figure 15- Flow Plan for TRC Fabrication

Figure 16- Flow Plan for TF Coil Fabrication

Figure 17- Flow Plan for Coil VPI Fabrication

Figure 181 - Field Period Assembly Plan Outline

Responsibilities during Manufacturing

This section identifies by discipline, those individuals who staff the manufacturing facility.  Figure 17-NCSX Manufacturing Facility Organizational Chart is an overall organization chart for the Modular Coil Manufacturing Facility.  The subsections, which follow, provide a brief description of each position on that organization chart.

Manufacturing Facility Managers

The Coil Manufacturing Facility Manager is responsible for the overall operation of the NCSX Coil Manufacturing Facility and successful completion of the coils.  Duties include managing the Field Supervisors, heading daily startup meetings and ensuring that both Integrated Safety Management (ISM) and risk management are incorporated in all aspects of the manufacturing activities.

Field Supervisors

The Field Supervisors (FS) report to the Manufacturing Facility Manager and are responsible for managing the lead technicians and field crews.  FS may have a primary station responsibility as well as sharing the overall supervisory responsibilities. In addition they are responsible for ensuring that ISM and risk management are incorporated in all aspects of the manufacturing activities.

Lift Engineer

The Lift Engineer shall monitor and retain overall responsibility for the hoisting and rigging of Critical non-repetitive lifts.

Coil Test Director

This Coil Test Director is the engineer responsible for coordinating the testing of each coil in the Coil Test Station located in the Test Cell Basement.

Lead Technicians

The lead technicians are responsible for supervising the field crew activities at each workstation.  They are also responsible for communicating all questions and/or concerns to the Field Supervisor filling the station log book on a daily basis and for ensuring that ISM and risk management are incorporated in all aspects of the manufacturing activities.  The Lead Technician reports to the Field Supervisors.

Field Crews

The field crews report to the Lead Technicians and are responsible for performing the manufacturing activities as identified in the MIT/QA Plan and procedures to successfully complete the fabrication of the NCSX Coils and FPA.  They are also responsible for ensuring that ISM is incorporated in all aspects of the manufacturing activities

Health Physics Representative

The Health Physics Representative is responsible for coordinating with the Field Supervisors all health physics issues associated with work being performed in the Coil Manufacturing Facility (Test Cell).

[Note:  The Manufacturing Facility is located in a Radiation Controlled Area (RCA) requiring HP coverage to ensure that activities conform to PPPL HP policy.]

Industrial Hygiene Representative

The Industrial Hygiene (IH) Representative is responsible for reviewing and approving Job Hazard Analysis (JHA) surveys and issuing Confined Space Work Permits.  He/she provides IH technical support to the field supervisors, lead technicians and field crews.

Figure 19-NCSX Manufacturing Facility Organizational Chart

Dimensional Control/Metrology Representative(s)

The Dimensional Control and Metrology Representatives are responsible for defining ensuring that the centroid of the coil windings is located within the specified tolerance and critical FPA alignments are made.  These individuals define, guide participate and approve of the measurements performed during coil fabrication.

Construction Safety Representative

The Construction Safety Representative is responsible for reviewing and ensuring that all field activities are being performed safely and in accord with PPPL safety requirements.  Responsibilities include working with field supervisors, lead technicians and field crews, making recommendations for types of safety equipment to be used and how to perform work more safely.

Quality Control Representative

QC shall work as an independent group, reviewing field activities to ensure that procedures are being followed and that necessary travelers and data sheets are completed in a timely fashion.  The QC representative shall apprise the Field Supervisors and Manufacturing Facility Manager of any concerns.

General Facility Operating Guidelines

The following sections provide a brief overview of the operating guidelines for the NCSX Coil Manufacturing Facility.

Field Supervisors

Shall be appointed by the Manufacturing Facility Managers and will supervise all field operations.  Additionally during the MC and TF Coil production, a Field Supervisor will be on duty in the NCSX Coil Manufacturing Facility during working hours.

House-Keeping/Cleanliness Rules

“Good House-Keeping” is an essential element to the success of the manufacturing of the modular coils.  The following steps will be taken to enforce this practice.

No food, gum, smoking or beverage will be allowed in the NCSX Coil manufacturing facility. (Radiation Controlled Area “RCA”)

The coil winding and molding preparation stations [Work Stations #2-4] are housed in a clean environment with walls, ceiling and filtered airflow.

Only personnel associated with the coil manufacturing activities may enter Work Stations #2-4 unless approved by the Manufacturing Field Manager or Field Supervisors.  Approved names will be posted outside each station.

Step-off pads will be used at the entrances of workstations 2-4, to minimize transport of foreign particulate and dirt into the work area.  In addition, some sort of approved protection may be worn over street shoes such as booties or other approved foot coverage while in these areas.

It is recommended that lab coats or Tyvex suits be worn by the crew during the winding and molding operations.

Latex, rubber or cotton lint-free gloves will be required to be worn during the handling of insulated conductor, insulation, fillers or other components used in the construction of the modular coils.

The manufacturing stations will be cleaned daily by the coil work crew at the end of each shift.

Markers and Pencils:

The use of lead pencils or non-approved markers is prohibited in the fabrication stations. “Sharpie” permanent markers are the only markers that may be used without prior approval by the Field Supervisor.

Chips and Filings:

Extreme care must be taken when using files, grinders, etc. that could generate metal chips or filings.  Surrounding areas must be protected from these activities.  This type of work should be minimized near the coils whenever possible.

Hard hats

Hard hats are not required in the NCSX Manufacturing Facility unless the facility crane is in use.  The following rules shall be followed if the crane is in use:

NCSX Manufacturing Facility Hard Hat Rules

While the overhead crane is powered up (crane lights are on), all personnel under or within 5 feet of the BRIDGE of the crane MUST be wearing hard hats.  This includes walking under the bridge to enter or exit the Facility.

If the crane is in a powered down mode (lights are off), but there is a load suspended from the crane, all personnel under the TROLLEY of the crane must be wearing hard hats.

Crane operators must sound horn when powering up the crane.  The person responsible for the lift must perform a visual inspection to ensure that all personnel under the bridge of the crane don hard hats before the crane is operated. This includes checking ALL clean rooms if the bridge is over that area of the facility.  If the crane bridge is moving through the facility, the person responsible for the lift must ensure that all personnel in the path are wearing hard hats before the crane travels.

The person in charge of the lift must also ensure that there are signs and/or barriers outside the facility indicating that the crane is in use, and that hard hats are required.

Station Logbook

Each workstation will have a “Station Logbook” that will be filled in on a daily basis by the Lead Technician.  Entries will include technical data associated with that station, daily progress, as well as problems and solutions that may arise.

Daily Summary Report

A daily summary report, outlining the day’s activities, will be issued by the Field Supervisor on duty at the end of the shift.  This report will briefly outline the day’s accomplishments as well as manufacturing issues he feels should be included.  This report will be e-mailed to the NCSX project management. Note: These daily reports will begin once full production of the modular and TF coils starts.

Safety and Training Requirements

Integrated Safety Management (ISM)

ISM principles will be used throughout the coil manufacturing process and field period assembly. It is a “Common sense approach to Doing Work Safely”. There are seven guiding principles for safety management:

Line management responsibility for safety

Clear roles and responsibilities

Competence commensurate with responsibilities

Balanced priorities

Identification of safety standards and requirements

Hazard controls tailored to work being performed

Operations authorization

Job Hazard Analysis Surveys and Safety Meetings

JHA’s will be generated to identify existing or potential workplace hazards and to evaluate the risk of worker injury or illness associated with job tasks. (Reference document ESH-004 “Job Hazard Analysis”)  The JHA’s will be reviewed by the IH representative for accuracy as well as completeness.  It will be reviewed with all activity participants at the Pre-Job briefings.

Safety meetings will be conducted on a regular basis to ensure that the focus on safety is a foremost priority.

Safety Walk-Through’s

Daily safety walk-throughs will be performed by Industrial Hygiene, by Construction Safety and by field supervisors with the intention of identifying and correcting unsafe conditions or activities in the manufacturing area.

Training

Training of personnel is “Key” to completing the NCSX fieldwork safely.  Courses will be required for all personnel, instructing them in the proper use of tools and equipment; personal protective equipment (PPE’s); and general laboratory policy and safety requirements.  All personnel entering the Manufacturing Facility must be Radiation Safety Qualified, must wear current radiation dosimetry, and must sign the Radiation Work Permit (RWP)/Access Log daily.  Visitors may only enter if escorted by an individual RAD Safety qualified with a visitor’s radiation badge.  A manufacturing training matrix identifies the training required for the individual working in the manufacturing facility.

Personal Protective Equipment [PPE’s]

The PPPL Industrial Hygiene and Construction Safety representatives will work together with the Manufacturing Facility Manager to identify the necessary and correct personal protective equipment needed to ensure a healthy and safe work environment for the work force.

Radiation Controlled Area:

The NCSX manufacturing facility is located in a Radiation Controlled Area (RCA). As a result, all personnel entering or working in the area must be radiation qualified, read and sign the RWP, or be escorted by a qualified escort.

Food and Beverage

No food, gum, or beverage is allowed in the Manufacturing Facility because it is located in an RCA.

Emergency Response Procedure

In the event of abnormal conditions in the NCSX Manufacturing Facility, procedure “D-NCSX-OP-EO-41” identifies what actions should be taken. Abnormal conditions are identified as conditions which, if not corrected, could result in injury to personnel or damage to equipment.  All employees working in the coil manufacturing facility will be required to read the emergency response procedure.

Meetings and Communication

Communication between management and the field crews is essential to ensure a successful and cohesive working group.  In addition to the meetings described below, other meetings may be held “as required” to keep the work crew informed of laboratory or safety related items.

Daily Startup Meetings

There will be a Daily Startup Meeting to review inter-actions, planning, scheduling, safety and commitments for all activities associated with the Coil Manufacturing Facility.   Additional meetings will be held between shifts for the purpose of exchanging information.

Time: The meetings will be held in the AM Monday thru Friday prior to the start of field activities and will address the day’s scheduled activities.

Location: The meetings will normally be held in the WCC trailer conference room at D-site.  Location of meeting may also be in the field.

Chairman: One of the Manufacturing Facility Managers (MFM) or his designee (Field Supervisor) will chair this meeting.

Attendees should include the MFM, Field Supervisors, Lead Technicians, Field Crews, Health Physics Representative, Industrial Hygiene Representative, Quality Control Representative and Construction Safety Representative.  This list may change depending upon the tasks being performed that day.

Safety Meetings

There will be safety meetings typically every other week to discuss particular safety issues associated with the manufacturing of the modular coils and/or general safety related topics. (These meetings will commence once the production of the modular coils has begun)

Time: The meetings will be held at 11:00 AM every other Tuesday and will address safety issues.

Location:  The meetings will generally be held in the WCC trailer conference room at D-site.  However, they may be held in other areas as deemed appropriate for the topic being discussed.

Chairman: Either a safety representative or a field supervisor will chair the meetings, as required.

Attendees should include the Field Supervisors, Lead Technicians, Field Crews, Health Physics Representative, Industrial Hygiene Representative, Quality Control Representative and Construction Safety Representative.  This list may change depending upon the topic of the meeting that day.

Pre-Job Briefings

Pre-job briefings are held prior to the start of any new work activity.  The purpose of the briefing is to discuss specific work activities, responsibilities of the participants, a review of the JHA/safety issues, and to respond to all questions and concerns.  In addition a review of post job briefings from previous, similar type operations may be appropriate.  The participants at these briefings should include all individuals who will be involved with the activity including lead technician, field crews, and supervisors.  Representatives from construction safety, Industrial Hygiene, Health Physics and Quality Control should be included as appropriate to the job.

Post-Job Briefings

A post-job briefing is held at the conclusion of a work activity.  These briefings will be held at each station for every NCSX coil. The purpose of the briefing is to discuss the completed work activities.  It should include lessons learned including technique problems, improvements and safety related issues. Minutes from the post job briefings will be kept and filed with the run copy of the procedure.  This information will be shared as deemed appropriate at the pre-job briefing of the next similar type operation.  The participants at these briefings should include all individuals involved with the completed activity or procedure. It should include the lead technician, field crews, and supervisors.  Representatives from construction safety, Industrial Hygiene, Health Physics and Quality Control will be included as appropriate to the job.

Documentation

Document Control

All NCSX associated documents used for manufacturing the NCSX coils will be under NCSX Project document control.  Any modifications to the procedures will be implemented using ENG-030.

Field Packages

Each coil will have a separate “Coil Field Package” that will follow the coil from station to station and each VVSA will have a corresponding “VVSA field package”.  It will include all of the process procedures, QC inspection reports, photographs, test results, and measurements used to document completion of major activities.  The Field Package will be further discussed in the MIT/QA plan.

The Lead Technician, Field Supervisor and or Quality Control representative will document all critical completions in the procedure.  This will be completed using the signer’s initials identifying the approver.

The signoffs in the procedures will be filled out in a timely fashion once a particular activity has been completed.

Documents Retention and Storage

If paper documents, they should be stored in the Ops Center. If electronic documents, they will be stored on the NCSX web site. Per the NCSX Docs and Records Plan, they need to be retained until the machine is dismantled and disposed.

Quality Assurance/Quality Control Requirements

Quality Control during Manufacturing

Quality control during the manufacturing process will be the responsibility of all parties involved in the manufacturing (Field supervisors, technicians, and Quality Control representative)

Measurements

Measurements and tests will typically be performed by the work crews and engineering.  The QC representative should be made aware of planned tests and measurements, but unless required by the procedures, need not be present.

Other Quality Control Representative Responsibilities

The QC representative will review the field activities on a daily basis; checking for completion of documentation as well as compliance with the approved procedures.

The QC representative will be a required signature on the procedure verifying that the station activities have been completed and that the coil may move to the next station.

The QC representative will report to the laboratory appointed NCSX Quality Assurance representative.  He/she will also inform the Coil Facility Manager of any issues or concerns that may be uncovered.

# Comments

Modified format and style to be consistent with project guidelines

Simplified this section some..

Do we need a NEPA for field period assembly?

I took out all references to the Twisted Racetrack Coil - that is history.

Should we add all of our manufacturing procedures to this list?

We do not appear to have a Station identified to assemble the TF coil half-period assemblies.

Need to confirm that the boot installation allows adequate radial play for machine assembly.

# Text boxes

Controlled Document

This is a controlled document.  Check the NCSX Engineering Web prior to use to assure that this document is current.

Station 6

TF coil/Wedge Cast.

(1) Lead Tech. + [1] crew

Field Supervisor*

Tom Meighan

Field Supervisor*

Mike Kalish

Station 5

VPI

(1) Lead Tech. + [2] crew

Stations 2, 3 & 4 Winding stations

(3) Lead Techs + [4] crew

Material Receipt

Station #2 activities include:

-Transport VPI’d coil back to Station #2 Turning fixture

-Install Final Coil Clamps

-Perform room temperature tests [Electrical]

Manpower:  2 technicians per station

# Station No.6

Coil Testing

Cold test the modular coil [TC Basement]

# Station No.2

Post VPI

# Station No.2

-Winding Form Prep.  -Coil Winding

- Install of Mold

# Station No.5

VPI/Autoclave Station

Station #5 activities include:

-Install TRC Coil into autoclave

-VPI

-Cleanup

Manpower:  3 technicians per station

Station #2 activities include:

-Mount WF to support ring		-Coil winding/positioning

-Measure/inspect WF surfaces 	-Ground wrapping

-Install clamp studs		-Final coil positioning

-Clean & mold release WF		-Install chill plates

-Install winding clamps		-Install bag mold

-Install inner cladding   	                 -Vacuum leak check bag

Manpower:  2 technicians per station

Station 1

Winding Form Preparation

(1) Lead Tech. + [1] crew

Field Supervisor*

Jim Chrzanowski

Field Supervisor*

Steve Raftopoulos

Dimensional Control/Metrology Representative (Stratton/Raftopoulos)

Quality Control Representative

* Note:  Designates primary station responsibility as well as sharing overall field management responsibilities.

Indicates a communication link, and not a management link between the participants

NCSX WBS13 Manager

Mike Kalish

NCSX WBS14 Manager

Dave Williamson

PPPL Responsible Line Manager

Larry Dudek

Health Physics (HP) Representative

Industrial Hygiene Representative

Coil Manufacturing Facility Manager

Jim Chrzanowski

Field Period Assembly Manager

Mike Viola

Construction Safety Representative

Material Receipt

  - VVSA receipt & inspection

  - Cooling Tubes receipt & inspection

  - Misc. hardware inspection guidelines

Procedure No.

NCSX-PROC- FPA -QA

- VVSA Preparation

  - Locate diagnostic loops

  - Install templates

  - Install Diag Loops

  - Locate cooling tubes

  - Install tube clamp studs

  - Perform measurements

# Station No. V1

VVSA loops and tubes

Procedure No.

NCSX-PROC- FPA -001

Procedure No.

NCSX-PROC- FPA -002

# Station No. V2

MC Assembly

- MC Assembly

  - Align and assembly 3 MC sets

- Install MC Assembly and port extension

  - Align and Install VVSA

  - Install first 3 MC sets

  - Install Second 3 MC sets

  - Align and bolt together

  - Align and Weld Port extension

Procedure No.

NCSX-PROC- FPA -003

# Station No. V3

Install MC and port extension

- Assemble and Install TF Coils and Trim Coils

  - Assemble two 3 TF coil sets

  - Install Field Period

  - Install one 3 coil set onto TF fixture

  - Roll Coils on

  - Install second 3 coil set onto TF fixture

  - Roll Coils on

  - Install Trim Coils

Procedure No.

NCSX-PROC- FPA -004

# Station No. V4

Install TF and Trim Coil

- Final Prep for Transport

  - Perform Final Measurements

  - Install transportation supports

  - Load on truck

Station No. V5

Final Prep for transport

Procedure No.

NCSX-PROC- FPA -005

Send to NCSX Test Cell

Stations V1-V5

FPA

(1) Lead Tech. + [2] crew

Field Supervisor*

John Edwards