PPPL Quality Notes for the Week of 1/23/06

Tuesday Teleconference 9 AM EST

(877) 952-1506, Passcode: 833648

- Closed Items:

  - EIO submitted a revised MTM C-1 data package that addressed all PPPL comments.

  - PPPL issued RFD 14-012 on 1/17 to reduce tolerances based on MTM input. RFD addresses:

    - As-built positioning on flange and tee holes

    - Out of round port hole cut-outs.

    - Relaxing tee height tolerance.

- Pending from EIO:

  - (EIO, MTK) Update MetalTek CA 1538 for B-1 Thin wall condition.  Initial CA only states that there are problems and says there will be an update as evaluation progresses. Note from EIO: (Open - HOT) On 1/20 MTK submitted CA 1538, an interim report highlighting the results of the 3D ScanCo report indicating that there is scant stock in some areas of the castings.  EIO is seeking to secure a more detailed summary of the thin area and the minimum wall thickness found.  MTK projects completion of their investigation by 1/31; however, until then, they are looking to secure permission to commence rework of the B pattern for areas not related to the thin wall condition (in order to meet the aggressive schedule set forth on 1/14).    This issue is considered “HOT” for discussion at the QA meeting on 1/24. Rework of pattern includes??? Need clarification from EIO of what rework needs permission.  EIO/MTK probably needs expedited disposition. Roy is sending the 3DScanCo report and a link to their website. Areas include flange, tee, and wall, at minimum.  MTK may add weld to tee to assure that part can be located in casting. Rework probably includes modifying tee to ensure that later B-Types do not have tee problem. Rework to address areas where EIO wants improvement should not need PPPL permission.

Status:

  - (EIO, MTM) Provide a copy of the updated MTM process outline incorporating recent changes

Status: (Open) Discussed at meeting on 1/6 with MTM. Final plan will take a while as changes are taking place. PPPL requested interim processing plan(s) and stated that reviews would be for major issues only. PPPL wants a living document, not a “historical artifact.” MTM agreed to make this available.  Due by 1/23.  MTM working it, EIO hasn’t seen it yet.

  - (EIO, MTM,MTK) Complete corrective action (RT) for dispositioned MTM NC 18776 (C3) addressing rejectable LPI indications found during machining.

Status: (Open) C-3 NC 18776 will remain open until radiograph of ~18” of the adjacent flange region has been accomplished and it is verified that those regions are free of unacceptable indications. This was discussed with MTM at the meeting on 1/6. Subsequently PPPL, ORNL, and MTM discussed and agreed on more specific locations for the two radiographs.  NCSX will submit a mark up of the photo describing where the X-ray shots should be made.   PPPL sent slide 1/23

  - (EIO, MTM) Develop a UT Technique and submit the procedure and procedure qualification for examining the high stress areas of the casting.
Status: (Open) EIO Weekly has end of February as the due date.  In the interim, RT of the high stress area will be performed.

  - (EIO, MTM) Change requests and Process Outline changes regarding items discussed at 1/4, 5, & 6 meeting.

    - Revised IDC that shows CMM inspection of every other hole on Tee.  All holes will still be inspected for cleanliness and thread integrity.

Status: (Open)  due 1/23

    - Revised IDC that shows hand tool inspection of poloidal break dimensions.

Status: (Open)  due 1/23

    - Propose port cut-out deviation requests for the Type A & B MCWF’s.

Status: (Open)  per EIO, sent to PPPL for review Type C sent, A&B are still needed

  - (EIO, MTM) Provide comments on draft NCSX-CSPEC-141-03-11 which includes the following changes based on the 1/4, 5, & 6 meeting.

Status: (Open) Due 1/20, extended to 1/25

    - Reduced inspection grid for dimensional verification.

    - Relaxed surface finish at extended wing.

    - Relaxed tee stud and poloidal break inspection technique.

    - Reduced magnetic permeability measurements (also resulted in change to SOW dropping the requirement to provide a grid).

    - Provided an alternative to individual lot testing of weld filler material (ref. NC 18831).

(EIO, MTM) MTM comments on the draft table of coordinates for Type C MCWF dimensional inspection.  Also provided in IGES format on 1/17.

Status: (Open)  need date from MTM

- Pending from PPPL

  - Revise drawings to incorporate changes shown below resulting from 1/4, 5, & 6 meeting and to incorporate RFD 14-012 changes.

Status: (Open) due 1/31.

    - Drawing change for new conical feature to replace spherical seats.

    - Change to reference dimensions where tolerances are not needed.

    - Drawing change increasing tolerance at extended wing.

    - Provide inspection points for each MCWF Type.  Note Draft table & IGES file for Type C sent to MTM for comment.   See 2.7.PPPL is awaiting feedback from EIO – does MTM want full inspection data (flanges, outer shell, etc.) for C-types?

  - PPPL to submit a mark up of the photo describing where the X-ray shots for corrective action on MTM NC 18776 (addressing C3 rejectable LPI indications found during machining) should be made.   PPPL sent yesterday

  - Disposition final MetalTek CA1323 (provided today) - for erroneous reported chemistry (sulfur and phosphorous values for C-1 through C-4, A-1 & 11 shims, and Manganese on those castings, plus C-5).  Note that C-1 & C-2 packages will not be complete until this NCR is closed.

  - Disposition MetalTek CA 1537 (provided today) for B-1 Chemistry. Note that CA includes a request to increase allowable Phosphorous levels.

  - Disposition CA 1347 (provided today) which documents the outcome of EIO investigation into the A-1 casting thin wall and actions to ensure wall thickness consistency on subsequent castings. Min wall verification on A-2, A-3

  - Additional CA (1536, addressing Manganese noncoformances) was supposed to be included. It has now been added to the FTP site.

- New Specification & Drawing Changes:

  - RFD 14-012 issued.  This document makes tolerance changes on drawing SE141-116 that are based on EIO/MTM feedback on the C-1 and C-2 MCWF’s.  PPPL has a due date of 1/31/06 to update the drawing. The changes are:

1. 	Increase profile of datums –E- and –D- flanges from .020” to .030”

2. 	Break down the .020 profile of the T section to the following:

a. Profile of top surface of T = .100”

b. Leave sides of T as profile of .010” per PPPL request.

3. 	Increase profile below the VPI groove from .100” to .200” PPPL to check on whether an updated gage drawing was transmitted to EIO

4. 	Increase true position of 96 holes in T section from .010” to .060”

5. 	Increase true position of holes in –E- and –D- flanges from .010” to .060” and change nominal hole size from 1.88” to 1.885” +/- .003”.