PPPL Quality Notes for the Week of 1/2/06

Tuesday Teleconference 9 AM EST

(877) 952-1506, Passcode: 833648

- Closed Items:

  - A-1 chemical analysis page for documentation package has been updated and posted. It needs to be included in the documentation package and the values reflected on the spreadsheet.  Closed 12/19.

  - G-11 flat sheet certification listed as round bar in MTM portion of C-2 documentation package is considered correct by EIO since flat sheet used to machine round bar. Closed 12/19.

  - PPPL approved revised MetalTek casting Quality Plan dated 12-05-05 on 12/22.

  - Dispositioned MTM NC 18830 addressing elongation below spec on Metrode material was provided to EIO on 12/19.

(all 4 items agreed upon)

- Pending from EIO:

  - (EIO, MTK) Update MetalTek CA1323 - for erroneous reported chemistry (sulfur and phosphorous values for C-1 through C-4, A-1 & 11 shims, and Manganese on those castings, plus C-5).  As of 11/22, MTK did not like the initial results from Stellalloy button and wants to obtain more test results prior to utilizing button for calibration of spectrograph. Note that C-1 & C-2 packages will not be complete until this NCR is closed. Also, preliminary information suggests that 2-3 castings may be slightly out of range for P & Mn.

Status from EIO: (Open) NCR is in review at MTK and is expected at EIO after 1/4//05. Will use new button for all new calibrations.  Will release updated data today.

  - (EIO, MTM) Address comments from PPPL review (12/8) of revised MTM C-1 data package.

Status: (Open) New package posted for PPPL review 12/13, however, as noted below by EIO, it is not complete. EIO does not have new package from MTK (file was erroneously overwritten).  Frank will send the 12/13 pkg. to Roy.  3 0f 4 items not addressed in this pkg- Roy will check status with MTK- Frank will review.

    - For C-1 and future castings, provide completed shop travelers or process sheets

Status from EIO: (Open) Not added.  Mike will discuss with Kevin & add in.

    - Include missing C-1 certifications for weld material, identified as Items #8 & #9 (mc106164.tif) in the TOC.

Status from EIO:  (Open) Metrode cert added but cryogenic test results missing.

    - The Table of Contents (TOC) lists certifications to be added later for the casting and for the shim.  These certifications are actually the first part of the package.

Status from EIO: (Open - No update)

    - NC17452 for a tool gouge is not in the package

Status from EIO: (Open - No update) To be added

  - (EIO, MTK) Update of CA 1347 with the outcome of EIO investigation into the A-1 casting thin wall and actions to ensure wall thickness consistency on subsequent castings.  Note: still open, awaiting A2 and A3 measurements to confirm dimensional consistency.

Status from EIO: (Open) Dimensional data from A-2 are under review at MTK.  The root cause analysis in process at EIO.  Preliminary conversations with MTK indicate that the same results are being found on A-3 and can be expected for the remaining A castings.  The topic is proposed for further discussion in mid January when review of dimensional data from A-2 is completed and initial data on A-4 becomes available.  Weekly report notes the doc. Pkg. will be posted soon, and Nancy notes that MTK’s root cause analysis will be available soon.

  - (EIO, MTM) Provide a copy of the updated MTM process outline incorporating recent changes

Status from EIO: (Open - no update from 12/23/05 report) MTM has updated the internal process plan to incorporate all changes associated with Spec rev 10, which will be available for EIO and PPPL review during the visit on 1/4 - 1/6.  They have requested to submit the formal process plan after the UT procedure and the revised machining processes are approved and in-place. The proposed date for submission is 2/28/06. Nancy notes that the shop is working to the update but has not submitted it yet because of administrative concerns  (ie, MTM wants to prove process before finalizing it;  desire to reduce administrative burden).  MTM will discuss this during our visit tomorrow.

  - (EIO) Report on lessons learned and/or corrective actions for the two (2) C-2 LPI indications found at MTM.

Status from EIO (Open) EIO is working on the corrective action and root cause analysis, which will summarize team activities to avoid similar problems in the future.  Paper work to be submitted for discussion at upcoming telecon on 1/3/06.  EIO will forward to Frank shortly.

  - (EIO, MTM,MTK) Complete corrective action (RT, UT) for dispositioned MTM NC 18776 (C3) addressing rejectable LPI indications found during machining. Also report any lessons learned and/or actions to prevent recurrence including possible relation to item # 2.10 (above), the original C-6 porosity and/or the A-3 surface porosity.

Status from EIO: Topic of why these weren’t identified during NDT testing at the foundry was addressed during Telecon with PPPL on 12/21.   C-3 NCR will remain open until radiograph of ~18” of the adjacent flange region has been accomplished and it is verified that those regions are free of unacceptable indications.

PPPL: EIO Lessons Learned discussed.    MTM plans to use UT on C4 and is developing a procedure.

  - (EIO, MTM) Develop a UT Technique and submit the procedure and procedure qualification for examining the high stress areas of the casting.
Status from EIO (Open - No update from 12/23/05 report) Kevin Bowling has committed to having a UT procedure to EIO by 2/3/06. 12/23, demonstration of various transducers & test probes that will be needed to inspect the coils was provided by supplier. Once the correct probes are determined, MTM will need to purchase these and write a specific procedure for the castings. If implemented, C-4 looks to be the 1st casting where we will use UT inspection.  See above.

- Pending from PPPL

  - Disposition NC 18831 regarding missing actual RT test results for Metrode weld wire. Results from another lot were submitted to PPPL on 12/1 for possible acceptance in lieu of actual results from lot used which are not available.

Status: (Open) NCR under discussion at PPPL.  Disposition to be provided by 1/10/06.

  - RFD needs to be incorporated into the SE141-137 and SE141-138 bearing plate drawings.

- New Specification & Drawing Changes:

Phil noted that the A and B bearing plate drawings were completed and should be posted this morning and will advise EIO through Larry.