PPPL Quality Notes for the Week of November 14, 2005

Teleconference Tuesday 9 AM EST (877) 952-1506, Passcode: 833648

Closed Items:

Dispositioned MTK CA 1423, for noncompliant chemistry of Metrode Lot # WO21735 and Metrode Lot # WO19711 weld material, signed and returned to EIO 11/8.

Dispositioned MTK CA 1379 addressing unsuccessful A-1 Casting weld filler metal test and the subsequent re-test.

Closed MTM C-1 NCR NC 17452 (flange face gouge weld repair) with added PPPL note that post-weld NDT was performed with satisfactory results.  Note:  Frank notes that after weld repairs NDT should be performed ASAP.  In this case, it was performed as a final inspection.

Note:  The B1 casting was poured on Friday night, 11/11.

Pending from EIO:

Update MetalTek CA1323 - for erroneous reported chemistry (sulfur and phosphorous values for C-1 through C-4, A-1, & 11 shims and Manganese on those castings, plus C-5).  As of 10/25 MTK is awaiting return of the new Stellalloy standard from the 2nd lab.  Note:   Chuck will update by 11/21.

For the C-3 & A-1 documents, update MetalTek chemistry in the documentation packages and spreadsheets to report the post-PM MetalTek Product Analysis with the Wisconsin Centrifugal results as validation. (ref. 2.2, above). As of 11/10, the C-1 & C-2 packages are updated and posted. Note:  Just waiting for C3 & A1 to be updated.

Address comments from PPPL review (10/13) of MTM C-1 data package. The first 3 are items for inclusion in the updated MTM C-1 documentation package. The other 2 concern documentation for C-2 and on.  Note:  Nancy believes Kevin is waiting for PPPL to return the NCRs.

Provide corrected electrical inspection results for C-1. Document posted 10/28. This needs to be incorporated into the C-1 documentation package.

For C-1 and future castings, provide completed shop travelers or process sheets. C-1 document posted 10/28. This needs to be incorporated into the C-1 documentation package.

Include missing C-1 certifications for weld material, identified as Items #8 & #9 (mc106164.tif & mc106579.tif) in the TOC, and for G11 flat sheet, item #10, (mc107081.tif) in the digital package.

For future castings, report surface finish for the “L” sections of the Tee (125 requirement) separately from the rest of machined areas (250 requirement).  Report location and extent for all out of tolerance areas separately.

For future castings, include surface inspection grid. For magnetic permeability, agreed to have DCMA witness and have photos taken in progress.  This will not be complete mapping.  Dimensional inspection grid should be apparent from results.

Update of CA 1347 with the outcome of EIO investigation into the A-1 casting thin wall and actions to ensure wall thickness consistency on subsequent castings. Note:  still open, awaiting A2 and A3 measurements to confirm dimensional consistency.

Provide a copy of the issued 9/28/05 revision of MetalTek casting Quality Plan (conditionally approved - 10/11 email), with the noted changes. Will follow issuance of Rev.10 of NCSX-CSPEC-141-03. Note:  Awaiting Rev. 10 of the spec.

Provide a copy of the updated MTM process outline incorporating recent changes. Will follow issuance of Rev.10 of NCSX-CSPEC-141-03  Note:  Awaiting Rev. 10 of the spec.

EIO/MTM input on PPPL C-1 NCR’s 3618, 3619, 3620, & 3621. Due 11/9   Input for 3617 provided on 11/10 in form of MTM internal NCR.  Note:  Roy to check status with Kevin.

MTM NCR addressing elongation below specification requirements for Metrode ER316Mnnf, Batch # W020132, used to repair C-1.   Note:  Awaiting NCR yet.

Room temperature tensile test results for Metrode ER316Mnnf, Batch # W020132, MTM used to repair C-1.  Note:  MTM just needs to perform room temperature tests and then a NCR not necessary.

Results of MTK review of what caused the porosity in C-6.  Note:  Possible root causes are insufficient burn-out of mold; core wash not being adequately dried; atmospheric moisture; metal gas.  Actual root cause not apparent – therefore MTK plans to attack all potential causes.  A draft procedure change is being prepared increasing the time for mold drying. All agreed that, since C6 was scrapped, a NCR is not necessary – this is now simply an EIO internal matter to investigate causes and corrective actions to avoid this condition in future pours. A2 also exhibits some gas, but not nearly as severe (it had 15 internal defects – way down from previous castings).

Note on sequencing:  Will start machining A1 before all Cs are completed – probably after C5.  C6 will be the next casting poured – scheduled for delivery to MTM by 1/30/06.   B1 will be machined before all As are completed – probably after A5.

Pending from PPPL

Review and disposition MTM C1 NCR NC 18297 for dimensional nonconformances. Revised copy received 11/10.  Note:  Will process by 11/18.

Review and disposition MTM C1 NCR NC 18315 for missing dimensional inspection data. Revised copy received 11/10.  Note:  Will process by 11/18.

Disposition outstanding PPPL C-1 NCRs: (requires EIO input – see 2.6, above)  NOteP  MTM provided on 3617 NCSX will process by 11/18.   – still awaiting the other four.

PPPL 3617 - MTM hole numbering,

PPPL 3618 - MTM PB Fasteners,

PPPL 3619 – Cooling Tube hole drilling,

PPPL 3620 – PB Shim contour,

PPPL 3621 – MTM back spot face/thru-hole interference.

Review MetalTek special process personnel qualifications. DCMA has reviewed these. PPPL will also review, but with lower priority than other items on this list. Note:  Frank will review – low priority;  all agree timing is not critical.

Advance review of preliminary MetalTek documentation packages for:

C-2, Review updated version posted 11/8 addressing PPPL comments.

A-1 and C-3. Note still under development and not currently posted for review Roy notes a new C3 posting will be performed today.

Specification and drawing changes.  Revision 10 of NCSX-CSPEC-141-03 was in the signature cycle, but is being held until the radiography discussions are completed.  These items are in process:

PPPL to follow up on tolerance update on Sheet 10 of 141-116, zone D2.  Need to get drawing posted and notify EIO through Larry and added to drawing change list in the spec.  Note:  drawing updated and will be formally transmitted with spec revison.

Discussion of Radiography Inspection Requirements and possibility of UT in lieu of RT should result in spec changes. The team was requested to comment on the Strawman revision below which will permit the use of both radiographic and UT inspections.  Note   Roy (Kevin)  needs to get UT and radiography personnel qualification .  Nancy suggests that maybe this can be addressed in the meantime.

#### Radiographic Inspection

Each casting shall be free of internal radiographic indications of defects as defined in MSS SP 54 for radiography.  Defects exceeding these limits shall be repaired per Section Error! Reference source not found. (Repairs

#### 3.1.1.7  Inspection for Internal Defects in the High Stress Area

Each casting shall be free of indications of internal defects exceeding 0.080” (major dimension) in the web region of the Tee in the   High Stress Areas (as defined in Appendix A - Error! Reference source not found. ).  Radiographic inspection  or radiographic inspection  in combination with  ultrasonic (UT) inspections hall  be used.  Radiographic inspection shall be  as defined in MSS SP 54 .  UT inspection shall be performed in accordance with procedures and personnel qualifications  submitted to NCSX for approval prior to use.    Defects exceeding inspection limits shall be repaired per Section Error! Reference source not found.  if performed prior to any significant amount of machining has been performed.  Defects exceeding those limits which are identified after the winding form is significantly machined (i.e. to within 0.25” of final dimensions) shall be reported on an NCR for evaluation.  Repairs  at that stage shall only be made if formally approved in the disposition of the NCR, and as defined in the NCR disposition.   .