PPPL Quality Notes for the Week of December 5, 2005

Teleconference Tuesday 9 AM EST (877) 952-1506, Passcode: 833648

Closed Items:

PPPL transmitted dispositioned & closed MTM C1 NCR NC 18297 for dimensional nonconformances on 11/28 and NCR NC 18315 for missing dimensional inspection data transmitted 12/1.

Copies of dispositioned PPPL C-1 NCRs transmitted to EIO for information.

PPPL 3617 – Misnumbered racetrack

PPPL 3618 - MTM PB Fasteners

PPPL 3619 – Cooling Tube hole drilling

PPPL 3620 – PB Shim contour

PPPL 3621 – MTM back spot face/thru-hole interference

PPPL reviewed the 11/15/05 C-2 Documentation package from MetalTek and returned 4 minor comments on 12/2

Results of MTK review of what caused porosity in C-6.  Action satisfied by QA teleconference on 11/29.

Pending from EIO:

(EIO, MTK) Update MetalTek CA1323 - for erroneous reported chemistry (sulfur and phosphorous values for C-1 through C-4, A-1, & 11 shims and Manganese on those castings, plus C-5).  MTK did not like initial results from Stellalloy button and wants to obtain more test results prior to utilizing button for calibration of spectrograph.

Status: (Open) Chuck states that the specimen is at a 3rd lab awaiting testing – will update on schedule at next week’s QA meeting. New button is expected back from 3rd lab by 12/12

(EIO) For A-1, update MetalTek chemistry in the documentation package and spreadsheets to report the post-PM MetalTek Product Analysis with the Wisconsin Centrifugal results as validation. As of 11/10, the C-1, C-2 & preliminary C-3 packages are updated and posted.

Status: (Open) Chemistries are being updated – should be complete by 12/6. MetalTek portion of A-1documentation package will be completed over w/o 12/26

(EIO, MTM) Address comments from PPPL review (10/13) of MTM C-1 data package. The first 3 are items for inclusion in the updated MTM C-1 documentation package. The other 2 concern documentation for C-2 and on.

Status: (Open) MTM received final NCR from EIO on 12/2. MTM to complete C-1 over weekend & get new copy of C-1 doc package posted to EIO doc package for review by 12/5. Package posted on ftp site on 12/5

Add corrected electrical inspection results for C-1 to documentation package.

Add completed shop travelers or process sheets to the C-1 documentation package.

Add missing C-1 certifications for weld material, identified as Items #8 & #9 (mc106164.tif & mc106579.tif) in the TOC, and for G11 flat sheet, item #10, (mc107081.tif) to the digital package.

For future castings, report surface finish for the “L” sections of the Tee (125 requirement) separately from the rest of machined areas (250 requirement).  Report location and extent for all out of tolerance areas separately. NOTE – This has been incorporated into C-2 – CMM inspection reports will be available by 12/7. This should close out this note

For future castings, include surface inspection grid. For magnetic permeability, agreed to have DCMA witness and have photos taken in progress.  This will not be complete mapping.  Dimensional inspection grid should be apparent from results.

Status – This has been incorporated into C-2 – Successful review of inspection reports for C-2 should close out this note

(EIO, MTK) Update of CA 1347 with the outcome of EIO investigation into the A-1 casting thin wall and actions to ensure wall thickness consistency on subsequent castings. Note:  still open, awaiting A2 and A3 measurements to confirm dimensional consistency.  Preliminary measurements of A-3 to be taken when the casting returns from MQS on 11/28/05.

Status: (Open) Preliminary measurements of A-3 to be taken. MTK – will do by 12/9

(EIO) Provide a copy of the issued 9/28/05 revision of MetalTek casting Quality Plan (conditionally approved - 10/11 email), with the noted changes.

Status: (Open) New revision sent to EIO on 12/2. Currently under review   To be submitted this week

(EIO, MTM) Provide a copy of the updated MTM process outline incorporating recent changes.

Status: (Open -No update) MTM to complete by    12/9

(EIO, MTM) MTM NCR addressing elongation below specification requirements for Metrode ER316Mnnf, Batch # W020132, used to repair C-1.

Status: (Open) MTM to supply by   12/9

(EIO, MTM, PPPL) Room temperature tensile test results for Metrode ER316Mnnf, Batch # W020132, MTM used to repair C-1.

Status: (Open) Actual results from this batch of weld wire are not available from Metrode. Metrode did supply MTM with actual results obtained from a previous lot. As this is a standard weld wire for Metrode, EIO has submitted these results to PPPL for review on 12/1 in lieu of creating new test bars or an NCR. (see 3.2 below) NCR by 12/9

(EIO) Corrections need to be made to C-2 doc package to reflect comments from PPPL on 12/2
Status: (New) Most corrections will be made w/o 12/5 with the exception of replacing CA 1323 with a finalized copy. By 12/9

(MTM) NCR addressing 3 rejectable LPI indications found in final inspection of C-2 
Received NC18776 this morning – corrected copy w/ serial number, needed.  Only the large vee-shaped indication in the tee area was reported.  The other 2 areas will be ground and if removed without violating minimum wall, will not require an NCR.

Pending from PPPL

Review MetalTek special process personnel qualifications. 
Status: DCMA has reviewed these. PPPL will also review, but with lower priority than other items on this list.

Actual results from a previous Metrode weld wire lot were submitted to PPPL on 12/1 for possible acceptance in lieu of actual results from lot used which are not available
Status: (New) Submitted 12/1 NCR due

Specification and drawing changes.  NONE

C-3 LPI bleed-outs (NC18715)– MetalTek to look into gas.  EIO, Pete, to give PPPL the RT shot ID (Drawing location is SE141-116, Sht. 4, F-5), MTM will look at, and likely perform, UT inspection after this machining is completed later this week.  MTM is concerned that any welding, especially after this machining step is complete, will cause significant movement.

Mike (MTM) will check on status of UT technique development.

C-2 is still on CMM.  Inspection was completed, but data review showed that the required grid was not obtained.  Additional inspections were done evening of 12/5 and that data is under review now.  Documentation package should be to EIO tomorrow.