# Week of 3/13/06

PPPL MCWF Quality Notes

Tuesday Teleconference 3/14 9 AM EST (877) 952-1506, Passcode: 833648

- Closed Items:

- Pending from EIO:

  - (EIO, MTM) Develop a UT Technique and submit the procedure and procedure qualification for examining the high stress areas of the casting.

 Status: (Open) Due date is end of February.  In the interim, RT of the high stress area will be performed. MTM plans to validate the UT technique on C-4 in conjunction with RT.   Repeatability issues have arisen. The UT equipment manufacturer was in to help.

  - (EIO) Provide final documentation packages for completed MCWF’s.

    - C-2 (includes RT film)

Status: (Open) – Sections are updated, now they will be merged or an index added. Films were sent with C-3 films. C-2 will be posted later this week.

    - C-3 (includes RT film)

Status: (Open) –Films already provided. Dimensional NC 19314 (3.7  below) disposition needed before MTM can submit

  - (EIO, MTK) Initiate RFD for casting areas where it is proposed to not inspect and not repair. 

 Status: (Open) Initial approach discussed 2/16.  Update expected by 2/22.  This has been delayed as making the template is more complicated than expected. No change

  - (EIO, MTM) Updated NC19209, requesting RT of C-4 weld repair be waived, with documentation of post-weld inspections.

 Status (Open) Update received 3/8, but did not include documentation of post-weld inspections.  MTM will update with reports from the work performed the attached or a statement to that effect..

  - (EIO, MTM) Update NC 18607 to show that corrective action has been accomplished 

 Status (Open) To be included in MTM portion of C-3 doc package. The documentation of corrective action will clearly be tied to the NC – either on that form or separate document with references.

  - (EIO, MTM) Update NC 18654 to show that corrective action has been accomplished 

 Status (Open) To be included in MTM portion of C-3 doc package. The documentation of corrective action will clearly be tied to the NC – either on that form or separate document with references.

  - (EIO, MTK) Update CA 1625 (A-1 linear indication) after machining. 

Status (Open) MTM to document condition after machining for MTK evaluation. This area has not yet been machined.

  - (EIO, MTM) Address actions to prevent recurrence of issues (listed below—not all may need specific actions) discussed in 3/7/06 C-3 Results from Visual Inspection teleconference. PPPL has to generate NCR’S will work with EIO on the dispositions

    - Modify CMM inspection to include poloidal break (to detect shifts such as seen on C-3).

    - Better identify surface divots – especially those on tee edges.

    - Remove steel bushings.

    - Watch for rust indications –possible permeability issues.

    - Assure cooling line holes are clear

    - Verify 2” clearance on flange holes. 2”H x 3” dia. Gage will not fit in most holes.  PPPL needs to specify exactly what sockets and tooling will be used.  This needs to be addressed today or tomorrow because MTM is ready to finish machining on C-4. MTM will check again with a tapered gage based on the washer. 2 7/8” (or 2 ¾”?) dia. at bottom for ½” then expands to 3” dia. for another 1 ½”- The gage will center on hole.

Status (Open) new

  - (EIO, MTK) Notify PPPL about when additional test coupons will be shipped.  EIO to investigate.

Status (New) Update to be reported at next QA meeting. Film, test coupons & extra material by end of next week

  - (EIO, MTM) Provide NCR for C-5 flange thickness concern raised by MTM in the 3/7 teleconference.

Status (New) flange may be shifted so “best fit” makes flange too thin when there‘s actually enough cast thickness. NCR is due by 3/22. NCSX can probably accept the nonconforming condition for C-5 since the stresses are low in that region.

- Pending from PPPL

  - Process EIO’s proposed RFD for C-Type MCWF port cut-out deviation received 2/17.

 Status: (Open) by 3/17

  - Process NC19269 for LPI indications found on C-3. 

 Status: (Open) in transmittal cycle-will be sent by3-15.Sent 3/13

  - Disposition NC19321 with weld repair approach, including waiving RT, for gouge on C-4.  Note: MTM confirmed that the CMM will get at least 4 points, so profile will be assured.

  Status: (Open) by 3/17

  - Provide ECN or drawing update showing revised poloidal break tolerances as discussed on 2/27. MTM can hold 0.002” for bushings, but seeks something closer to the .013” measured on C-3 for the break gap. Perhaps, for the poloidal break flange fit-up, 0.005” through and 0.015” at edges – edge defined as no more that 1/8” penetration - would be practical. 

 Status: (Open) wording in process – will provide by 3/15

  - Process EIO’s NC 19233 & 19234 for bearing plate permeability
Status: (Open) Under discussion – Permeability was ranging as high as 1.05 – New readings found on the A & B style are ranging 1.15 – 1.2.  MTM reported that grinding was unsuccessful and will try solution anneal.  EIO has also initiated a request to Metal Tek for quote to cast Stellalloy bearing plates.  MTM will also investigate use of Stellalloy cut-outs from A-types or whether or not they can find certified compliant material.

PPPL to check on acceptable alternative materials such as 304 or 17 -4ph material and what condition is required for the plates (Kevin notes that for 17 -4, lower hardness is better). Solution anneal did not reduce permeability.  MTK quote due 3/15. PPPL to check on acceptability of alternative material.  MTM checking on available 17-4. EIO will have a proposal based on Stellalloy shortly .

  - Evaluate revised document of corrective actions for MetalTek CA 1538 for B-1 Thin wall condition. Actions include adding stock to Core Box #9, weld repair of the thin flange area, and further evaluation/possible action regarding wing interference areas.

 Status: (Open) posted 3/5 - PPPL will download & process. by 3/17

  - Process NC 19314 for C-3 dimensional deviations.

Status: (Open) ORNL says all are acceptable – PPPL to disposition and process. by 3/17

  - PPPL approval of final C-1 documentation package is needed.

Status: (Open) by 3/17

  - PPPL to evaluate C-5 flange thickness concern raised by MTM in the 3/7 teleconference. 

Status: (New) The topic was addressed during the weekly QA meeting on 3/7 and further information was provided by Mike Griffith later that day.  PPPL to consider requirements and advise.  EIO needs to submit NCR (see 2.10).

Flange reference dimension on C castings (1.38)

- New Specification & Drawing Changes: none

MCWF Inspection Point change- MTM requested a different reference system and pointed out that PPPL did not specify all points. PPPL will post by Wednesday 3/22

¼” thermocouple for A casting – PPPL provided relief by tapering.  MTM to propose new location, but wants some guidance from PPPL on new position.

Note: Frank will not make the trip to MTM.  Tentatively, Collin Phelps, PPPL QC, will visit MTM next Wednesday, Thursday, and Friday.