# Week of 3/20/06

PPPL MCWF Quality Notes

Tuesday Teleconference 3/21 9 AM EST (877) 952-1506, Passcode: 833648

- Closed Items:

  - NC19209 was updated with documentation of post-weld inspections and is now closed.

  - Closed and dispositioned NC19269 for LPI indications found on C-3 was transmitted to EIO.

- Pending from EIO:

  - (EIO, MTM) Develop a UT Technique and submit the procedure and procedure qualification for examining the high stress areas of the casting.

 Status: (Open) Due date is end of February.  In the interim, RT of the high stress area will be performed.   Repeatability issues have arisen. The UT equipment manufacturer was in to help. MTM plans to validate the UT technique on C-4 in conjunction with RT. MTM will attempt trying it on C-4 later this week.

  - (EIO) Provide final documentation packages for completed MCWF’s.

    - C-3 (includes RT film)

Status: (Open) –Films already provided. MTM needs dispositioned NC 19314 for dimensional discrepancies.

  - (EIO, MTK) Initiate RFD for casting areas where it is proposed to not inspect and not repair. 

 Status: (Open) Initial approach discussed 2/16.  Update expected by 2/22.  This has been delayed as making the template is more complicated than expected.

  - (EIO, MTM) Update NC 18607 to show that corrective action has been accomplished 

 Status (Open) To be included in MTM portion of C-3 doc package. The documentation of corrective action will clearly be tied to the NC – either on that form or separate document with references.

  - (EIO, MTM) Update NC 18654 to show that corrective action has been accomplished 

 Status (Open) To be included in MTM portion of C-3 doc package. The documentation of corrective action will clearly be tied to the NC – either on that form or separate document with references.

  - (EIO, MTK) Update CA 1625 (A-1 linear indication) after machining. 

Status (Open) MTM to document condition after machining for MTK evaluation.  MTM reports that another 0.050 inches needs to be removed. Will take about another 1.5 weeks

  - (EIO, MTM) Address actions to prevent recurrence of issues (listed below—not all may need specific actions) discussed in 3/7/06 C-3 Results from Visual Inspection teleconference.

    - Modify CMM inspection to include poloidal break (to detect shifts such as seen on C-3). MTM added points, but did not change the wording of the process sheets.

    - Better identify surface divots – especially those on tee edges.

    - Remove steel bushings.

    - Watch for rust indications –possible permeability issues.  MTM notes that they checked the permeability for rust stains on the type A and B the castings which are in storage at MTM and could not duplicate high permeability results.

    - Assure cooling line holes are clear

    - Verify 2” clearance on flange holes. 2”H x 3” dia. gage will not fit in most holes. MTM checked again with a tapered gage based on the washer. 2 7/8” dia. at bottom for ½” then expands to 3” dia. for another 1 ½”- The gage centered on hole. Most holes now pass. The balance will be remediated  MTM notes that this took a fair amount of grinding on C-4.

Status (Open) new

  - (EIO, MTK) Notify PPPL about when additional test coupons will be shipped.  EIO to investigate.

Status (Open) Due to ship by 3/24.

  - (EIO, MTM) Provide NCR for C-5 flange thickness concern raised by MTM in the 3/7 teleconference. Flange may be shifted so “best fit” makes flange too thin when there‘s actually enough cast thickness.

Status (Open) NCR due by 3/22

- Pending from PPPL

  - Process EIO’s proposed RFD for C-Type MCWF port cut-out deviation received 2/17.

 Status: (Open) in signature cycle- to EIO by 3/22

  - Disposition NC19321 with weld repair approach, including waiving RT, for gouge on C-4.  Note: MTM confirmed that the CMM will get at least 4 points, so profile will be assured.

  Status: (Open) due from PPPL by 3/22 .  Note, add signature block for EIO to signify that it has been completed.

  - Provide CSPEC update addressing revised poloidal break inspection/tolerances. Poloidal break flange fit-up, 0.005” through and 0.015” at edges – edge defined as no more that 1/8” penetration. 

 Status: (Open) Rapid response guidance sent 3/16.  Wording for next CSPEC revision is in process.

  - Process EIO’s NC 19233 & 19234 for bearing plate permeability

Status: (Open) Response using EIO quote for Stellalloy plates in progress – to EIO by 3/22

  - Evaluate revised document of corrective actions for MetalTek CA 1538 for B-1 Thin wall condition. Actions include adding stock to Core Box #9, weld repair of the thin flange area, and further evaluation/possible action regarding wing interference areas.

 Status: (Open) in signature cycle- to EIO by 3/22

  - Process NC 19314 for C-3 dimensional deviations.

Status: (Open) ORNL says all are acceptable – PPPL to disposition and process by 3/24

  - PPPL approval of final C-1 documentation package is needed.

Status: (Open) due from PPPL by 3/23

  - Review submitted final C-2 documentation package. Films were sent with C-3 films.

Status: (Open) – target date: 3/29.

  - PPPL to provide guidance on Type A MCWF thermocouple hole placement. 

Status: (Open) – Rapid response guidance drafted and sent on 3/20.

- New Specification & Drawing Changes: none