PPPL Quality Notes for the Week of August 15, 2005

TUESDAY CALL AT 9AM EDT 1-877-952-1506, ACCESS CODE: 833648

Pete D, Chuck R, Nancy H, Roy S, Phil H, Frank M, Larry S

- Closed Items:

Radiographic Technique Sheets for the Type C castings have been received and accepted.   (E-5)

Pending from EIO:

Corrective action – additional 4 side bend tests (at room temperature) and 1 tension test – for MTM nonconformance report NC17399.  - Due ASAP (5/24/05) and prior to weld repair on any castings other than C1 – estimated date as of 8/12 it is just after 8/17.  (E-3)

Outcome of EIO investigation into the cause of the thin A-1 casting wall and actions to ensure wall thickness consistency on subsequent Type A castings, as well as, to minimize the chances of recurrence on the Type B casting. (E-6)

Lawton and SCANCO to verify that the “bad” area scan is accurate - DONE

MTK will measure the A1 after radiography and HT with their Romer arm.

EIO to report determination of root cause and action(s) to ensure acceptable future Type A & B castings.

Update MetalTek CA1323 regarding erroneous values reported for sulfur and phosphorous to reflect investigation results and manufacturer’s inputs and explanations. (E-7)

St. Louis Testing data for 11 10 shims needs to be added.  Target:  ? was 8/9  NOTES:  All 11 were poured from the same heat.    Today, EIO sent chemistry for ( -6)  shim, but it doesn’t say it covers the batch.  PPPL is looking for 1 certification that covers the entire heat, and have the heat number identified.  This will then apply to  all 11 shims.  MTM should receive a copy of the certification also since they are doing weld qualification tests.  Chuck will resolve.

MetalTek to add information on how specification ranges were set (based on what information), whether it appears the spectrometer card failed recently or back when the specification ranges were set, and results of manufacturer’s check of the spectrometer.   Results of mfg. check due by 8/19 .    Notes:  Chuck states date is still good.  Needs to talk to Joe about the issue of how the specification ranges were set.

MetalTek to provide results of independent verification of constituents, other than Sulfur and Phosphorous, for at least 2 of the 4 castings (C-2, C-3, C-4, or A-1). Product Analysis on C3 was done for most constituents using MTK spectrometer.  Future castings, starting with C5, will have independent analysis of all elements.  (E-8)  Notes: Samples are at Wisconsin Centrifugal now – awaiting results. Chuck will get back to Pete with estimated date today.

Update MetalTek documentation packages to substitute corrected certifications, replace NCR’s with closed copies showing PPPL signatures, and update spreadsheet per 7/20/05 action items email. Most pieces (all but the final inspection report for the C-1 Shim) have been updated and supplied to PPPL. These need to be incorporated into the documentation package.  Expect updated C-1 doc. package by 8/19  (E-9)  Notes:  2 inspection reports will be included – 1 for the shim, 1 for the casting.

NCR, preferably with close-up photos, from MTM for new gouges on C-1 casting. (E-11) Notes:  Can’t get photos until machining is done, but will issue NCR at the end of the week, probably based on drawings showing location and details of gouges.

MetalTek ITP with list of the appropriate revision for each applicable, approved procedure.   Notes:  Pete has an update from Chuck yesterday.  Pete says the only issue is sand blasting:  it’s a prerequisite for LPI, not a procedure.  Frank says it’s a process, since it’s a deviation from the standard.  Chuck agrees – will submit revised ITP today.

Radiographic Technique sheet for the Type A castings.

Notes:  Due technique sheet for Type A’s – Chuck states we should have it by 8/26.

Pending from PPPL

Response to information provided 6/21/05 regarding the different cryogenic yield test results from the 2 different labs for the C-1 casting alloys and the plan to have RT tensile and all CVN performed by St. Louis lab.  Response/closure will be based on DCMA witness of a cryogenic CVN test at St. Louis Testing – currently scheduled for Tuesday 8/9. (E-1)  Status: CVN witnessed on 8/9 and found acceptable.  Notes:  CLOSED.  Frank asks if Chuck will keep Rosa informed of future tests so she can perform spot checks.

Review revised MTM portion of the MIT/QA Plan addressing welding due to defects found during NDE (received 8/12) estimated completion is 8/17 (E-2)  Notes  PPPL will approve by 8/17.

Disposition of CA1347 for wall thickness below tolerance on A-1. (E-6)  Notes:  PPPL will submit with “USE AS IS” by 8/17.

Disposition and sign-off of CA1324 for major weld repairs on A-1. (E-6)    Notes:  PPPL will disposition by 8/19.

MISCELLANEOUS:

Roy will visit MTK on 8/23 – Frank will also be there on that date.  Next week’s QA meeting will go on at 9 AM EDT.

Phil will visit MTK on the morning of 8/31 and will visit MTM on the morning of 9/1.

Nancy notes the A1 will be re-scanned  - probably after heat treat, but the pattern may not- SCANCO thinks they have sufficient data from the original scan.  MTK is not so sure that the original data is sufficient, so this is still an open issue.  (If re-scanned, it will most likely be done by MTK and probably only in the “bad” region.)

MTM moved to the 4th setup!