# Week of 5/15/06

PPPL MCWF Quality Notes

Tuesday Teleconference 5/16 9 AM EST (877) 952-1506, Passcode: 833648

- Closed Items:

  - Signed, closed NC19475 (C-4 misc. discrepancies) revision 1, was sent to EIO on 5/9.

- Pending from EIO:

  - (EIO) Provide final documentation packages for completed MCWF’s.

    - C-2 (reopened)
Status: (Open) PPPL on reviewing package noted missing documents  
1) The weld map does not correspond to the attached photos. NOTE - EIO is searching old records for photos submitted – Some submitted on 7/28/05 were replacements for earlier (unclear photos). EIO is constructing a table pointing to other, existing photos, for repairs listed as on the missing photos. 
2) The data package is missing NCR CA 1320 Note – will add after resolving above
3) The data package is missing NC’s 18830 & 18831.  These are for weld wire and elongations that were not to specification.  This weld wire was used to repair C-2 (8/05) before the CSPEC was changed in 11/15/05 and so the NCR’s should also be in the C-2 package.

    - C-3 (reopened)
Status: (Open) EIO will add MetalTek CA 1581.

    - C-4

Status: (Open) –Films already provided. NCR 19475 Rev.1 was needed and was provided to EIO on 5/9.

    - C-5

Status: (New) – Doc package in preparation Awaiting MTM portion

  - (EIO, MTK/MTM) Update CA 1625 (A-1 linear indication) after machining. 
Status (Open) Looks like it’s cleaning up. An NCR will be issued after LPI. Photos are on the EIO FTP site.   NCR will be coming from MTM if there is a rejection at LPI.   A second NCR will come from MTK on the source of the defect.

  - (EIO, MTK) Update CA 1671 (for A6 test results below spec for elongation) with inspection and analysis results.  
Status (Open) – MetalTek updated the CA on 5/5 to state that the plates had flaws.  Per discussion on 5/8 with PPPL, MetalTek will update again to include photographs with individual plate identification. MTK sent one half of a fractured test bar back to lab to prepare sample for photo macrograph. Lab lost sample and cannot photograph it. MTK will send other half for photo.  MTK expects close-out by 5/23.

  - (EIO) Investigate and take steps to mitigate source of ferromagnetic contamination seen on C-4 & B-1. Report back so that PPPL can disposition NCR 3633.
Status: (In-Progress) – CA in process of being written. MetalTek sent their Severn gauge back for calibration and found that it was off by 0.01 (0.005 above calibration limit). MetalTek is leaning toward burned in sand (which contains iron oxide) being the source and the inaccurate gage being the reason it wasn’t found sooner. 
MetalTek also agreed that “final” magnetic permeability check will be done after all processing (per MTS) and on a clean surface (per Severn instructions & MetalTek procedure). 
MetalTek personnel are at MTM checking permeability and grinding high spots. CA1695 was provided 5/16.  MTK used a magnet and detected imbedded particles present in the mold sand and in the garnet blast grit.  MTK feels part of the situation was due to the inaccurate gauge, part due to the process, and part due to “environmental contamination”.  MTK’s crew is cleaning up castings at MTM now.  CA 1695 will need to be updated as we see if the problem continues or not. It should include a statement that Mag perm will be done on clean surface after all processing.

  - (EIO, MTM) Disposition rejected SS316 bearing plate material documented on EIO’s NC 19233 & 19234.
Status: (Open) Scheduled to ship w/o 5/15. Type A & C bearing plates have been re-poured.

  - (EIO, MTM) Document Corrective Action to close NC 19783 (A-1Tee hole counter-bore depths).
Status: (New)

  - (EIO, MTM) Document Corrective Action to close NC19710 (C-5 weld repairs w/o RT)
Status: (New)

- Pending from PPPL

  - Provide updated requirements documents incorporating the following changes:

    - CSPEC update addressing revised poloidal break inspection/tolerances. Poloidal break flange fit-up, 0.005” through and 0.015” at edges – edge defined as no more that 1/8” penetration. 
Status: (Open) Rapid response guidance sent 3/16.  Wording for next CSPEC revision is in process.

    - PPPL to incorporate guidance on Type A MCWF thermocouple hole placement provided 3/20 into requirements documents. 
Status: (Open) – EIO has delivered marked up drawings with proposed locations.

  - Process EIO CA for C-4 features compliant to SE141-116, Rev. 7, but not to Rev. 8. 
Status: (In-Progress) On 5/2 MTM submitted updated CA which was accepted by Peter Djordjevich of EIO and forwarded to PPPL for informational purposes.  The matter of whether or not MTM’s suggestion to have NCSX circulate drawings for review and initialing prior to formal distribution is being reviewed by PPPL for feasibility. CA to be revised to add that MTM/EIO will notify PPPL of drawing changes that conflict with their understanding of agreements. PPPL will continue to discuss drawing changes in QA teleconferences and will add a note on change transmittals requesting that the drawings be reviewed for discussion during the teleconference.

- Discussion Topics for Teleconference:

  - New Specification & Drawing Changes

    - Type A Flange hole interferences were addressed on RFD-14-018.

Note that This RFD also includes a modification by the NCSX Project for all the Type A MCWF flange holes. The minimum stud clearance required behind the tapped holes shall not be less than ¼” to ensure full thread engagement.

MTM –inspection points provided do not include points for top of tee or Side E inner cast surfaces.  They are needed for the imminent CMM inspection of A-1.