# Week of 5/8/06

PPPL MCWF Quality Notes

No Tuesday Teleconference 5/9 9 AM EST (877) 952-1506, Passcode: 833648

- Closed Items:

- Pending from EIO:

  - (EIO) Provide final documentation packages for completed MCWF’s.

    - C-2 (reopened)
Status: (Open) PPPL on reviewing package noted missing documents  
1) The weld map does not correspond to the attached photos. NOTE -  EIO is searching old records for photos submitted – Some submitted on 7/28/05 were replacements for earlier (unclear photos)
2) The data package is missing NCR CA 1320 Note – will add after resolving above
3) The data package is missing NC’s 18830 & 18831.  These are for weld wire and elongations that were not to specification.  This weld wire was used to repair C-2 (8/05) before the CSPEC was changed in 11/15/05 and so the NCR’s should also be in the C-2 package.

    - C-3 (reopened)
Status: (Open) Comment from PPPL in process at EIO:

MetalTek CA 1581 should be part of their documentation package.  Note – EIO will add week off 5/8

    - C-4

Status: (Open) –Films already provided. Need open NCR 19475 Rev.1 (3.2 below) to complete

    - C-5

Status: (New) – Doc package in preparation

  - (EIO, MTK) Update CA 1625 (A-1 linear indication) after machining. 
Status (Open) Updated by MTM on 5/8- Looks like it’s cleaning up and will be acceptable as-is.  An NCR will be issued after LPI. Photos are on the EIO FTP site.

  - (EIO, MTK)   (EIO, MTK) Update CA 1671 (for A6 test results below spec for elongation) with inspection and analysis results.  
Status (Open) – MetalTek updated the CA on 5/5 to state that the plates had flaws.  Per discussion on 5/8 with PPPL, MetalTek will update again to include photographs with individual plate identification.

  - (EIO) Investigate and take steps to mitigate source of ferromagnetic contamination seen on C-4 & B-1. Report back so that PPPL can disposition NCR 3633.
Status: (In-Progress) – EIO & MetalTek to get together to look at grey spots, either at MetalTek or at MTM.  MetalTek has examined the first bearing plates and confirmed some, but not all of the high perm. spots.  MetalTek also sandblasted one plate and all high perm spots passed a 1.02 check, while 9 of 10 passed a 1.01 check. PPPL found another 30 spots of high permeability on receipt inspection of C-5. For discussion:
- Results of EIO 5/1 team teleconference.
- If not part of the previous, MetalTek discuss the extended corrosion checks in prototype phase that strongly suggested that the Stellalloy does not rust.
- MetalTek DCMA is witnessing a magnetic permeability check through LPI developer, which is followed by grinding of Permeability spots and LPI indications. MetalTek’s “final” magnetic permeability check, that should be witnessed by DCMA, should be after all processing (per MTS) and on a clean surface.
- MTK sent their Severn gauge back for calibration and found that it was off by 0.01 (0.005 above calibration limit).  This is thought to account for a large part of the issue.  MetalTek will submit a report of their activities, including the visit to  MTM on 5/15, investigating the permeability issue. MetalTek discussed this with PPPL on 5/8 and is leaning toward burned in sand being the source and the inaccurate gage being the reason it wasn’t found sooner.

  - (EIO, MTM) Disposition rejected SS316 bearing plate material documented on EIO’s NC 19233 & 19234.
Status: (Open) Will close after 316 bearing plate material is shipped back to PPPL, which will be after Stellalloy bearing plates are in use. The bearing plates are currently being cast for the C and B style coils.  Additionally, the first plates received at MTM were found to have magnetic permeability higher than the CSPEC limit and are under review at MTK.

- Pending from PPPL

  - Provide updated requirements documents incorporating the following changes:

    - CSPEC update addressing revised poloidal break inspection/tolerances. Poloidal break flange fit-up, 0.005” through and 0.015” at edges – edge defined as no more that 1/8” penetration. 
Status: (Open) Rapid response guidance sent 3/16.  Wording for next CSPEC revision is in process.

    - PPPL to incorporate guidance on Type A MCWF thermocouple hole placement provided 3/20 into requirements documents. 
Status: (Open) – EIO has delivered marked up drawings with proposed locations

  - Return signed NC19475 (C-4 misc. discrepancies) revision 1, posted 3/29, to EIO.  
Status (Open) – This also has the info on the thin flange region noted in 3.4.  PPPL is overdue – planned to get it to EIO by 4/25.

  - Review updated CA 1671 (for A6 test results below spec for elongation) with inspection and analysis results.  
Status (Open) –

  - Process EIO CA for C-4 features compliant to SE141-116, Rev. 7, but not to Rev. 8. 
Status: (In-Progress) On 5/2 MTM submitted updated CA which was accepted by Peter Djordjevich of EIO and forwarded to PPPL for informational purposes.  The matter of whether or not MTM’s suggestion to have NCSX circulate drawings for review and initialing prior to formal distribution is being reviewed by PPPL for feasibility.

- Discussion Topics for Teleconference:

  - New Specification & Drawing Changes-None

  - Possible meeting at PPPL to discuss potential changes to Type B MCWF that could help expedite machining process.

  - Type A Flange hole interferences (RFD-14-018) status/recommendations. E-mail from PPPL/ORNL dated 5/4 with Slides on the Type A flange hole changes - Intralink models SE140-130.ASM and SE140-150.ASM show the changes without actually modifying the parts. MTM was investigating other alternatives.  PPPL will require MTM to define exactly how MTM proposes to make the change on -1 in lieu of filling the holes with weld and drilling & tapping them.  Topic remains open for discussion.