# Week of 6/12/06

PPPL MCWF Quality Notes

Tuesday Teleconference 6/13 9 AM EST (877) 952-1506, Passcode: 833648

- Closed Items:

- Pending from EIO:

  - (EIO) Provide final documentation packages for completed MCWF’s.

    - C-4
Status: (Open- No Update) –EIO needs has MTM portion (by 6/6) Preliminary copy sent to PPPL 6/12.

    - C-5
Status: (Open- No Update) – EIO needs has MTM portion (by 6/6)

    - A-1
Status: (New) – In-progress at MTM

  - (EIO) Investigate and take steps to mitigate source of ferromagnetic contamination seen on C-4, B-1 and subsequent castings. Report back with update to CA 1695 so that PPPL can disposition NCR 3633.
Status: (In-Progress) –MTK will clean-up B-1 & A-2, inaccessible at the previous visit, when they are accessible.  Aiming for 12/21

  - (EIO, MTM) Document Corrective Action to close NC 19783 (A-1Tee hole counter-bore depths).
Status: (Open)  MTM is waiting for PPPL input (3.2) regarding their investigation into mag perm of hardware before manufacturing the required bushings.

  - (EIO, MTM) Document Corrective Action to close NC19710 (C-5 weld repairs w/o RT)
Status: (Open - No update)  Rework router/update after A-1 ships. By 6/13 Update sent 6/12

  - (EIO, MTM) Provide Stellalloy bearing plates and replacement fasteners for MCWF’s C-1 through C-5. (Needed to close NCR’s 3618 & 3651.)
Status: (Open) MTM has not yet received all fasteners & bearing plates are not yet machined.  MTM will determine a ship date. In progress, but no ship date yet – possibly with A-2

  - (EIO, MTM) MTM will add an IDC torque check of poloidal break hardware.
Status: (New) will see on A-2

  - (EIO, MTK) Clarify MCWF Type A RT Technique Sheet so that locations can be matched to films.
Status: (New) EIO sent casting model photos that should help on 6/10.  These didn’t arrive, so were re-sent to PPPL today.  MTK will add photos, using the model, to identify locations on the casting.

- Pending from PPPL

  - Provide updated requirements documents incorporating the following changes:

    - CSPEC update addressing revised poloidal break inspection/tolerances. Poloidal break flange fit-up, 0.005” through and 0.015” at edges – edge defined as no more that 1/8” penetration. 
Status: (Open- No Update) Rapid response guidance sent 3/16.  Wording for next CSPEC revision is in process.

    - PPPL to incorporate guidance on Type A MCWF thermocouple hole placement provided 3/20 into requirements documents. 
Status: (Open- No Update) – EIO has delivered marked up drawings with proposed locations.   ECN-5218R2 implements this change, which is described by RFD-14-017.  Change will appear in drawing SE141-114, Rev-7, which should be issued, along with SE141-115, Rev.8, before 6/16.

    - PPPL to correct drawing SE-141-114, Rev. 6 - the dimensions shown in Sect. Q-Q are the correct ones, and the remnant incorrect dimensions will be deleted.
Status: (New) –An ECN is required.  ECN-5218R2 also covers this change

    - ECN needed to capture changes discussed on 6/9 regarding Type B thermocouple hole, VI bleeder hole, thru/tapped holes, & port cut-out. 
Status: (New) –ECN-5218R2 in progress.

    - ECN needed to address hole added to poloidal break. 
Status: (New) –   ECN-5218R2 covers this also.  Drawing SE141-058 was at Rev-2, with ECN-5112(RFD-14-019), "add lifting holes", pending.  We will make this change and the new hole and issue it as Rev-3 by 6/16.

  - PPPL will check and advise MTM on Bushings with acceptable magnetic permeability.
Status: (Open) PPPL may run magnetization curves in hope of raising the permeability limits. We briefly discussed using the rejected Stellalloy bearing plates.  Phil & Mike will see if that is worth pursuing.

  - Review C-2 & C-3 documentation packages posted 5/31
Status: (Open).6/16

  - Disposition (mark) rejected SS316 bearing plate material and then close EIO’s NC 19233 & 19234.
Status: (Open).  PPPL to verify that all plates are marked with their permeability.

  - Review updated CA 1671 (for A6 test results below spec for elongation) with inspection and analysis results.  
Status (Open) – in progress – Phil has been discussing with Brad, but no signed disposition yet.

- Discussion Topics for Teleconference:

  - New Specification & Drawing Changes

    - The Type A inspection points file has been updated to rev. 2. Type-A tee base inspection points titled type-a-tee-nq.txt and type-a-tee-mp.txt has been added to zip file type-a-insp-points-r2. There are two points per side, located 1/2-in apart and slightly below the vpi groove at every tee hole. The coordinate system is rotated 10-deg about z-axis from CSO.

    - Arrange to be at MTM for A-2 inspection on 6/26.