# Week of 7/10/06

PPPL MCWF Quality Notes

Tuesday Teleconference 7/11 9 AM EST (877) 952-1506, Passcode: 833648

- Closed Items:

- Pending from EIO:

  - (EIO) Provide final documentation packages for completed MCWF’s.

    - C-4
Status: (Open) – PPPL feedback on preliminary copy provided 6/26. EIO to complete & resubmit by 7/14

    - C-5
Status: (Open) – PPPL feedback on preliminary copy provided late 6/30/06. EIO to complete & resubmit by 7/14

    - A-1
Status: (Open) – In-progress at MTM. Awaiting purchase/receipt of bushings

    - A-2
Status: (New) – in progress at EIO

  - (EIO, MTK) Investigate and take steps to mitigate source of ferromagnetic contamination seen on C-4, B-1 and subsequent castings. Report back with update to CA 1695 so that PPPL can disposition NCR 3633.
Status: (In-Progress) – MTK inspected and cleaned-up A-2 on 6/19.  B-1 was not accessible at the time - Inspection/Clean-up will be done by MTM as part of final.6/30 update still has TBD’s.MTK will update today.

  - (EIO, MTM) Document Corrective Action to close NC 19783 (A-1Tee hole counter-bore depths).
Status: (Open) PPPL sent EIO/MTM direction on 6/20 to use 316 material regardless of the permeability.  MTM to initiate manufacture of the bushings. PPPL needs them mid-August. MTM has received one quote, but is still awaiting responses from three other sources, including PPPL recommended source.

  - (EIO, MTM) Provide Stellalloy bearing plates and replacement fasteners for MCWF’s C-1 through C-5. (Needed to close NCR’s 3618 & 3651)
Status: (Open) Replacement hardware received.  MTM is working on the plates - most of the plates are being machined as a group, so they will ship when all are done - probably with A-3.

- Pending from PPPL

  - Revise CSPEC to incorporate the following changes:

    - CSPEC update addressing revised poloidal break inspection/tolerances. Poloidal break flange fit-up, 0.005” through and 0.015” at edges – edge defined as no more that 1/8” penetration. 
Status: (Open) Rapid response guidance sent 3/16. Target date for Rev. 12 is 7/28.

    - CSPEC revision to update the inspection points.
Status: (Open) Rapid response guidance sent 5/16. Target date for Rev. 12 is 7/28.

  - Review updated CA 1671 (for A6 test results below spec for elongation) with inspection and analysis results.  
Status (Open) – in progress

  - Review additional photos (model) for Type A technique posted 7/7.
Status: (Open) 7/17 target

  - Review additional data for Type B technique mailed to PPPL last week.
Status: (Open) Photos not received as of 7/10/06.Initial info is in the mail.  Photos will follow by 7/17 – in progress at MTK.

  - MTM to obtain ingredients information for Sherwin penetrant (seen on A-1 PB insulator).
Status: (Open) Initial contact of Sherwin got no response. MTM will pursue. In the interim, MTM has sent the MSDS which only lists alcohol as a hazardous substance. EIO has taken lead to re-contact Sherwin – Will try to update by 7/11 QA meeting Info now at ORNL for evaluation

- Discussion Topics for Teleconference:

  - New Specification & Drawing Changes

The production winding form folder of the manufacturing ftp site has been updated with the addition of an IGES file (typeb-new-vpi-holes) that shows the new VPI bleed holes for the Type-B modular coils.

MTM was able to overlay the bleed holes onto the B casting (as shown below) and did not see any issues with moving them to this location.  PPPL input/concurrence with this approach is sought.  It is recommended that the topic be added to next week’s QA telecon. Looks OK, PPPL to send formal change.

  - Plans for EIO to visit PPPL in mid August for a Program Review are currently underway.  If there are any particular items of interest for the agenda/review, please let EIO/Phil know.

A-3 Final Inspection – Tues/Wed 7/25, 7/26.

A-3 NCR coming. 141-114, Sht. 5, Hole 17 is 2.057”, rather than 1.885”.