# Week of 7/17/06

PPPL MCWF Quality Notes

Tuesday Teleconference 7/18 9 AM EST (877) 952-1506, Passcode: 833648

- Closed Items:

  - MetalTek CA 1695, addressing the ferromagnetic contamination seen on C-4, B-1 and subsequent castings has been updated.

  - MetalTek has provided additional photos (of the model) for the Type A technique. This will aid in identifying film locations.

- Pending from EIO:

  - (EIO) Provide final documentation packages for completed MCWF’s.

    - C-4
Status: (Open) –In progress posted 7/17

    - C-5
Status: (Open) –EIO to complete & resubmit by 7/21

    - A-1
Status: (Open) – In-progress at MTM. Expected 7/21

    - A-2
Status: (New) – in progress at EIO Expected 7/21

  - (EIO, MTM) Document Corrective Action to close NC 19783 (A-1Tee hole counter-bore depths).
Status: (Open) PPPL sent EIO/MTM direction on 6/20 to use 316 material regardless of the permeability.  MTM has initiated manufacture of the bushings and will deliver by mid-August. NC will be closed on delivery.

  - (EIO, MTM) Provide Stellalloy bearing plates and replacement fasteners for MCWF’s C-1 through C-5. (Needed to close NCR’s 3618 & 3651)
Status: (Open) MTM is preparing to ship all hardware (including old magnetic hardware) with A-3.  MTM also submitted information related to the 1” drive socket to PPPL per request.

  - (EIO, MTM) Document Corrective Action to close NC 20124 for oversized hole on A-3.
Status: (Open) –

- Pending from PPPL

  - Revise CSPEC to incorporate the following changes:

    - CSPEC update addressing revised poloidal break inspection/tolerances. Poloidal break flange fit-up, 0.005” through and 0.015” at edges – edge defined as no more than 1/8” penetration. 
Status: (Open) Rapid response guidance sent 3/16. Target date for Rev. 12 is 7/28.

    - CSPEC revision to update the inspection points.
Status: (Open) Rapid response guidance sent 5/16. Target date for Rev. 12 is 7/28.

    - Modify high stress area? (Tee hole designators and possible location changes)

  - Review updated CA 1671 (for A6 test results below spec for elongation) with inspection and analysis results.  
Status (Open) – verified in progress on 7/17

  - Review additional data for Type B technique mailed to PPPL last week.
Status: (Open) Mail not received as of 7/17/06. Emailed photos received 7/17. Can PPPL borrow the models? Posted on ftp site - RT_B_SHOts.pdf

  - MTM to obtain ingredients information for Sherwin penetrant (seen on A-1 PB insulator).
Status: (Open) EIO sent Sherwin info, which is now at ORNL for evaluation. PPPL to follow up

- Discussion Topics for Teleconference:

  - New Specification & Drawing Changes - None

  - Plans for EIO to visit PPPL in mid August for a Program Review are currently underway.  If there are any particular items of interest for the agenda/review, please let Nancy or Phil know.