## EIO Monthly Report 1-3-05
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: January 3, 2005
| Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05
Patterns
Pattern A complete | 2005-02-10 | 2005-02-25 | 255125 |  | 10% | 18%
Pattern B complete | 2005-04-12 |  | 255125 |  | 2% | 7%
Major Tool Tooling Complete | 2005-02-15 |  | 555000 |  | 25% | 50%
Materials (MetalTek) | 2005-12-31 |  | 744746 |  | 5% | 17.6%
C1
MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-10 | 140808 |  | 0
MTM - machining/inspection | 2005-05-15 | 2005-05-26 | 154912
Receive at PPPL | 2005-05-16 | 2005-05-27
C2
MTK-casting | 2005-04-20 |  | 140808
MTM - machining/inspection | 2005-07-13 |  | 154912
Receive at PPPL | 2005-07-14
A1
MTK-casting | 2005-05-20 | 2005-06-08 | 140808
MTM - machining/inspection | 2005-08-12 | 2005-08-31 | 154912
Receive at PPPL | 2005-08-15 | 2005-09-02
C3
MTK-casting | 2005-06-20 |  | 140808
MTM - machining/inspection | 2005-09-14 |  | 154912
Receive at PPPL | 2005-09-15
B1
MTK-casting | 2005-07-21 |  | 140808
MTM - machining/inspection | 2005-10-13 |  | 154912
Receive at PPPL | 2005-10-14
A2
MTK-casting | 2005-08-17 |  | 140808
MTM - machining/inspection | 2005-11-14 |  | 154912
Receive at PPPL | 2005-11-15
A3
MTK-casting | 2005-09-16 | 2005-09-15 | 140808
MTM - machining/inspection | 2005-12-14 |  | 154912
Receive at PPPL | 2005-12-15
A4
MTK-casting | 2005-10-17 | 2005-10-05 | 140808
MTM - machining/inspection | 2006-01-13 |  | 154912
Receive at PPPL | 2006-01-16
A5
MTK-casting | 2005-11-16 | 2005-10-26 | 140808
MTM - machining/inspection | 2006-02-14 |  | 154912
Receive at PPPL | 2006-02-15
A6
MTK-casting | 2005-12-14 | 2005-11-15 | 140808
MTM - machining/inspection | 2006-03-14 |  | 154912
Receive at PPPL | 2006-03-15
B2
MTK-casting | 2006-01-13 | 2005-12-08 | 140808
MTM - machining/inspection | 2006-04-13 |  | 154912
Receive at PPPL | 2006-04-14
B3
MTK-casting | 2006-02-13 | 2006-01-05 | 140808
MTM - machining/inspection | 2006-05-12 |  | 154912
Receive at PPPL | 2006-05-15
B4
MTK-casting | 2006-03-16 | 2006-01-25 | 140808
MTM - machining/inspection | 2006-06-14 |  | 154912
Receive at PPPL | 2006-06-15
B5
MTK-casting | 2006-03-28 | 2006-02-15 | 140808
MTM - machining/inspection | 2006-06-26 |  | 154912
Receive at PPPL | 2006-06-27
B6
MTK-casting | 2006-04-14 | 2006-03-08 | 140808
MTM - machining/inspection | 2006-07-13
Receive at PPPL | 2006-07-14 |  | 154912
C4
MTK-casting | 2006-05-16 | 2006-03-31 | 140808
MTM - machining/inspection | 2006-08-14 |  | 154912
Receive at PPPL | 2006-08-15
C5
MTK-casting | 2006-05-30 | 2006-04-24 | 140808
MTM - machining/inspection | 2006-08-28 |  | 154912
Receive at PPPL | 2006-08-29
C6
MTK-casting | 2006-06-16 | 2006-05-14 | 140808
MTM - machining/inspection | 2006-09-14 |  | 154912
Receive at PPPL | 2006-09-15
EIO Project Mgt. 24 mos. |  |  | 908828 | 8.333% | 12.5% | 16.6%
Note on A5: Nancy Horton: Note 2) in e-mail: Several upfront milestones under the heading of "Patterns" have been initiated and some progress toward delivery has been accomplished as follows: Pattern A: Solidification modeling, modeling of the top half of the drag core box, as well as some gluing of the pattern. Pattern B: Stock Model complete and Solidification Modeling underway. Major Tool Tooling: Programming and internal drawings for fixtures A, B and C are complete. Fabrication of the C fixture is more than 10% complete. Materials: Metal Tek reports that they will procure metal in 17 lots. To date, they have procured 3 of the 17 lots.
Note on C13: Nancy Horton: Note 7 in e-mail: The first hardware deliverable under this contract will be the NCSX Winding Form referred to as C-1. Early effort toward the production of C-1 was performed under concurrent EIO contract S-04341-F, Change Order 5. The two key milestones under that change order were accomplished during December: Delivery of the completed pattern to Metal Tek and casting Coil C-1 through shakeout. With the initial success of the C-1 casting, we are still working toward the extremely ambitious 25 week schedule which was used for the projected schedule delivery date for C-1. As noted last month, this is a target which depends on many favorable advantages occurring during the course of production. In fact, our team's proposed baseline schedule for producing a winding form is 27 weeks: 15 weeks for casting the part, followed by 12 weeks for machining.
Note on C79: Nancy Horton: Note 9 in e-mail: The projected dates for completion of castings at Metal Tek were based on the assumption that once full-scale production of the 18 castings commences, Metal Tek projects that they will be able to produce and deliver one casting every three weeks. Therefore, if delays are experienced in the early stages of production, there is ample opportunity for recovery and acceleration over the remainder of the production period. The projected schedule change in completion of the A Pattern will have a corresponding impact on these dates. As noted, these dates will be reevaluated after the meeting on 1/18/05.
Note on G8: Nancy Horton: Note 5 from e-mail: At 50% complete, Major Tool is entitled to bill $350,000 for upfront costs.
Note on G9: Nancy Horton: Note 6 from e-mail: Metal Tek is entitled to bill for metal as they buy it. At this point, they will have spent and will bill for approximately $130,000 out of the total.
Note on D3: Nancy Horton: Note 1 from e-mail: For this spreadsheet, "Task Values" were based on rounded calculations which when totaled, result in a deviation from the bottom line negotiated price. Billings will reflect the agreed upon prices in EIO contract.
Note on G7: Nancy Horton: Note 4 from e-mail: The estimate of %Complete includes schedule and effort related to solidification modeling which is performed under Metal Tek's contract (not part of the $255,125). Lawton reports that they are about 1-2% started on fabrication of B pattern.
Note on G6: Nancy Horton: Nancy Horton: Note 3b from e-mail: The estimate of %Complete includes schedule and effort related to solidification modeling which is performed under Metal Tek's contract (not part of the $255,125). Lawton reports that they are about 8-10% complete with the A pattern.
Note on C6: Nancy Horton: Note 3a from e-mail: Due to complexities encountered during Solidification modeling, and Lawton's experience building the C Pattern, the completion date for A pattern is projected out to the end of February. Lawton has given their commitment to make every effort to improve upon this schedule if possible. This impacts the projected delivery schedule of A-1 casting to PPPL.
Note on C21: Nancy Horton: Note 8 from e-mail: The required leadtime for Pattern A will not only impact the schedule delivery date of A-1; it may also impact the delivery dates for the remaining coils, as Metal Tek projections have previously been based on a 3 week minimum leadtime between castings. Therefore, the topic of delivery order will be included on the Agenda for the meeting in St. Louis on 1/18/05, to address each company's concerns and considerations, as well as to ensure that this is still PPPL's preferred delivery sequence. Baseline and/or projected delivery schedules will be modified in next month's report, based on agreements reached at the meeting.

## EIO Monthly Report 12-3-04
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: December 3, 2004
| Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05
Patterns
Pattern A complete | 2005-02-10 |  |  |  | 10%
Pattern B complete | 2005-04-12 |  |  |  | 2%
Major Tool Tooling Complete | 2005-02-15 |  |  |  | 25%
Materials (MetalTek) |  |  |  |  | 5%
C1
MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-10 |  |  | 0
MTM - machining/inspection | 2005-05-15 | 2005-05-26
Receive at PPPL | 2005-05-16 | 2005-05-27
C2
MTK-casting | 2005-04-20
MTM - machining/inspection | 2005-07-13
Receive at PPPL | 2005-07-14
A1
MTK-casting | 2005-05-20
MTM - machining/inspection | 2005-08-12
Receive at PPPL | 2005-08-15
C3
MTK-casting | 2005-06-20
MTM - machining/inspection | 2005-09-14
Receive at PPPL | 2005-09-15
B1
MTK-casting | 2005-07-21
MTM - machining/inspection | 2005-10-13
Receive at PPPL | 2005-10-14
A2
MTK-casting | 2005-08-17
MTM - machining/inspection | 2005-11-14
Receive at PPPL | 2005-11-15
A3
MTK-casting | 2005-09-16 | 2005-09-15
MTM - machining/inspection | 2005-12-14
Receive at PPPL | 2005-12-15
A4
MTK-casting | 2005-10-17 | 2005-10-05
MTM - machining/inspection | 2006-01-13
Receive at PPPL | 2006-01-16
A5
MTK-casting | 2005-11-16 | 2005-10-26
MTM - machining/inspection | 2006-02-14
Receive at PPPL | 2006-02-15
A6
MTK-casting | 2005-12-14 | 2005-11-15
MTM - machining/inspection | 2006-03-14
Receive at PPPL | 2006-03-15
B2
MTK-casting | 2006-01-13 | 2005-12-08
MTM - machining/inspection | 2006-04-13
Receive at PPPL | 2006-04-14
B3
MTK-casting | 2006-02-13 | 2006-01-05
MTM - machining/inspection | 2006-05-12
Receive at PPPL | 2006-05-15
B4
MTK-casting | 2006-03-16 | 2006-01-25
MTM - machining/inspection | 2006-06-14
Receive at PPPL | 2006-06-15
B5
MTK-casting | 2006-03-28 | 2006-02-15
MTM - machining/inspection | 2006-06-26
Receive at PPPL | 2006-06-27
B6
MTK-casting | 2006-04-14 | 2006-03-08
MTM - machining/inspection | 2006-07-13
Receive at PPPL | 2006-07-14
C4
MTK-casting | 2006-05-16 | 2006-03-31
MTM - machining/inspection | 2006-08-14
Receive at PPPL | 2006-08-15
C5
MTK-casting | 2006-05-30 | 2006-04-24
MTM - machining/inspection | 2006-08-28
Receive at PPPL | 2006-08-29
C6
MTK-casting | 2006-06-16 | 2006-05-14
MTM - machining/inspection | 2006-09-14
Receive at PPPL | 2006-09-15
EIO Project Mgt. 24 mos. |  |  |  | 8.333% | 12.5%
Note on A5: Nancy Horton: Note 1) in e-mail: Several upfront milestones, under the heading of Patterns, have been initiated and some progress toward delivery has been accomplished. These include solidification modeling for Pattern A, along with some purchase of wood and other materials for the fabrication of both A and B patterns, preparation of the machining fixtures for winding form C, and purchase of the required materials to cast the parts, including metal. Significant progress toward completion of these tasks is expected in the upcoming months of December and January.
Note on C13: Nancy Horton: Note 2) in e-mail: The first hardware deliverable under this contract will be the NCSX Winding Form referred to as C-1. Early effort toward the production of C-1 is primarily being accomplished under concurrent EIO contract S-04341-F, Change Order 5. A key milestone toward production of C-1, fabrication of the hard tool pattern, was completed last week and final inspection and shipment to Metal Tek is anticipated on December 6, 2004. A second major accomplishment toward the development of C-1, set-up and pouring of the casting, is anticipated to commence in the upcoming week with scheduled completion on or before December 24, 2004. An extremely ambitious 25 week schedule has been used for the projected schedule delivery date for C-1. This is a target which depends on many favorable advantages occurring during the course of production. In fact, our team's proposed baseline schedule for producing a winding form is 27 weeks: 15 weeks for casting the part, followed by 12 weeks for machining. As production gets underway, we will have better knowledge of the opportunities and challenges which will impact delivery.
Note on C79: Nancy Horton: Note 3) in e-mail: Once full-scale production of the 18 castings commences, Metal Tek has projected that they will be able to produce and deliver one casting every three weeks. Therefore, if delays are experienced in the early stages of production, there is ample opportunity for recovery and acceleration over the remainder of the production period.