## EIO Monthly Report 12-5-05
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: December 5, 2005
Casting Delivery Sequence |  | Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05 | % compl. 2/05 | % compl. 3/05 | % Complete 4/05 | % Complete 5/05 | % Complete 6/05 | % Complete 7/05 | % Complete 8/05 | % Complete 9/05 | % Complete 10/05 | % Complete 11/05 | % Complete 12/05 | Cost Accrual
Patterns
| Pattern A complete | 2005-02-10 | 2005-04-01 | 255125 |  | 10% | 18% | 25% | 40% | 98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 255125
| Pattern B complete | 2005-04-12 | 2005-07-01 | 255125 |  | 2% | 7% | 10% | 10% | 15% | 17% | 20% | 25% | 40% | 95% | 97% | 97% | 97% | 247471.25
| Major Tool Tooling Complete | 2005-02-15 | 2005-03-14 | 555000 |  | 25% | 50% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 555000
| Materials (MetalTek) | 2005-12-31 |  | 744746 |  | 5% | 17.6% | 18% | 67% | 67% | 67% | 67% | 67% | 67% | 100% | 100% | 100% | 100% | 744746
1 | C1
| MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-31 | 140808 |  | 0 | 0 | 75% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 140808
| MTM - machining/inspection | 2005-05-15 | 2005-09-30 | 154912 |  | 0 | 0 | 0 |  | 10% | 30% | 65% | 70% | 80% | 90% | 100% | 100% | 100% | 154912
| Receive at PPPL | 2005-05-16 | 2005-10-03 | [11 empty] | 35% | 100% | 100% | 100%
2 | C2
| MTK-casting | 2005-04-20 | 2005-06-27 | 140808 |  |  |  |  | 5% | 10% | 25% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 140808
| MTM - machining/inspection | 2005-07-13 | 2005-12-09 | 154912 | [8 empty] | 5% | 30% | 70% | 75% | 85% | 98% | 151813.76
| Receive at PPPL | 2005-07-14 | 2005-12-12 | [11 empty] | 10% | 15% | 15% | 15%
3 | C3
| MTK-casting | 2005-06-20 | 2005-09-21 | 140808 | [7 empty] | 10% | 50% | 65% | 90% | 100% | 100% | 100% | 140808
| MTM - machining/inspection | 2005-09-14 | 2005-01-22 | 154912 | [11 empty] | 5% | 25% | 60% | 92947.2
| Receive at PPPL | 2005-09-15 | 2005-01-23
4 | C4
| MTK-casting | 2006-05-16 | 2005-10-31 | 140808 | [8 empty] | 40% | 55% | 75% | 85% | 100% | 100% | 140808
| MTM - machining/inspection | 2006-08-14 | 2006-02-10 | 154912 | [11 empty] | 5% | 7% | 15% | 23236.8
| Receive at PPPL | 2006-08-15 | 2006-02-12
5 | C5
| MTK-casting | 2006-05-30 | 2005-11-26 | 140808 | [9 empty] | 35% | 50% | 75% | 80% | 100% | 140808
| MTM - machining/inspection | 2006-08-28 | 2006-03-03 | 154912 | [11 empty] | 2% | 2% | 5% | 7745.6
| Receive at PPPL | 2006-08-29 | 2006-03-06
6 | A1
| MTK-casting | 2005-05-20 | 2005-09-06 | 140808 | [6 empty] | 5% | 20% | 60% | 80% | 99% | 100% | 100% | 100% | 140808
| MTM - machining/inspection | 2005-08-12 | 2006-03-27 | 154912 | [11 empty] | 10% | 10% | 10% | 15491.2
| Receive at PPPL | 2005-08-15 | 2006-03-28
7 | C6
| MTK-casting | 2006-06-16 | 2006-02-01 | 140808 | [9 empty] | 2% | 35% | 65% | 5% | 50% | 70404
| MTM - machining/inspection | 2006-09-14 | 2006-04-25 | 154912
| Receive at PPPL | 2006-09-15 | 2006-04-26
8 | A2
| MTK-casting | 2005-08-17 | 2005-12-30 | 140808 | [10 empty] | 2% | 50% | 55% | 80% | 112646.4
| MTM - machining/inspection | 2005-11-14 | 2006-05-13 | 154912
| Receive at PPPL | 2005-11-15 | 2006-05-15
9 | A3
| MTK-casting | 2005-07-21 | 2005-01-27 | 140808 | [11 empty] | 2% | 50% | 60% | 84484.8
| MTM - machining/inspection | 2005-10-13 | 2006-06-03 | 154912
| Receive at PPPL | 2005-10-14 | 2006-06-05
10 | A4
| MTK-casting | 2005-10-17 | 2006-02-28 | 140808 | [13 empty] | 5% | 7040.4
| MTM - machining/inspection | 2006-01-13 | 2006-06-21 | 154912
| Receive at PPPL | 2006-01-16 | 2006-06-22
11 | A5
| MTK-casting | 2006-01-13 | 2006-03-20 | 140808 | [13 empty] | 0%
| MTM - machining/inspection | 2006-04-13 | 2006-07-10 | 154912
| Receive at PPPL | 2006-04-14 | 2006-07-11
12 | B1
| MTK-casting | 2005-09-16 | 2006-01-16 | 140808 | [11 empty] | 5% | 20% | 55% | 77444.4
| MTM - machining/inspection | 2005-12-14 | 2006-07-31 | 154912
| Receive at PPPL | 2005-12-15 | 2006-08-01
13 | A6
| MTK-casting | 2005-11-16 | 2006-04-10 | 140808
| MTM - machining/inspection | 2006-02-14 | 2006-08-14 | 154912
| Receive at PPPL | 2006-02-15 | 2006-08-15
14 | B2
| MTK-casting | 2005-12-14 | 2006-04-30 | 140808
| MTM - machining/inspection | 2006-03-14 | 2006-08-28 | 154912
| Receive at PPPL | 2006-03-15 | 2006-08-29
15 | B3
| MTK-casting | 2006-02-13 | 2006-05-20 | 140808
| MTM - machining/inspection | 2006-05-12 | 2006-09-11 | 154912
| Receive at PPPL | 2006-05-15 | 2006-09-12
16 | B4
| MTK-casting | 2006-03-16 | 2006-06-07 | 140808
| MTM - machining/inspection | 2006-06-14 | 2006-09-25 | 154912
| Receive at PPPL | 2006-06-15 | 2006-09-26
17 | B5
| MTK-casting | 2006-03-28 | 2006-07-02 | 140808
| MTM - machining/inspection | 2006-06-26 | 2006-10-09 | 154912
| Receive at PPPL | 2006-06-27 | 2006-10-10
18 | B6
| MTK-casting | 2006-04-14 | 2006-07-20 | 140808
| MTM - machining/inspection | 2006-07-13 | 2006-10-23 | 154912
| Receive at PPPL | 2006-07-14 | 2006-10-24
| EIO Project Mgt. 24 mos. |  |  | 908828 | 8.333% | 12.5% | 16.6% | 21% | 25% | 29% | 33.3% | 37.5% | 42% | 45% | 50% | 54% | 58% | 62% | 563473.36
TOTAL | [18 empty] | 4008830.17
Note on E3: Nancy Horton: For this spreadsheet, "Task Values" were based on rounded calculations which when totaled, result in a deviation from the bottom line negotiated price. Billings will reflect the agreed upon prices in EIO contract.
Note on D11: Nancy Horton: Reference: C-1 was poured on 12/20/04. C-1 casting shipped on 3/31/05 and was placed in the fixture at MTM on 4/1/05.
Note on D15: Nancy Horton: Ref: C-2 was poured on 4/15/05. 6/27/05 reflects the actual date C-2 casting was shipped from MTK. This was 5 days ahead of previously projected schedule of 7/1/05.
Note on A3: Nancy Horton: Ref: As of 11/15/05, the projected machining/delivery sequence of the castings is: C-1 C-2 C-3 C-4 C-5 A-1 C-6 A-2 A-3 A-4 A-5 B-1 A-6 B-2 B-3 B-4 B-5 B-6
Note on D20: Nancy Horton: Ref: Revised projected delivery date for C-3 is based on an 18 week machining leadtime
Note on D32: Nancy Horton: Note 6 from e-mail: Machining of A-1 will commence after C-5. Projected machining start date is 1/3/06. Delivery schedule for A-1 is based on a 12 week leadtime.
Note on D23: Nancy Horton: Ref: C-4 was poured on 7/12/05. 10/31/05 reflects the actual ship date to MTM
Note on D27: Nancy Horton: Ref: C-5 was poured on 8/8/05
Note on D35: Nancy Horton: Ref: C-6 was poured on 8/31/05 and scrapped on 10/28/05. C-6 was re-poured on 11/28/05. MTK is working to expedite the part ahead of A-4
Note on D3: Nancy Horton: Note 1 from e-mail: Delivery projections have been updated to reflect the desired machining sequence. For this month's report, the contract period of performance was extended to reflect incorporation of PPPL request for deviations. The RFD is still under negotiation.
Note on D19: Nancy Horton: Ref: C-3 was poured on 6/10/05 and was delivered to MTM on 9/21/05
Note on D31: Nancy Horton: Ref: A-1 was poured on 5/24/05
Note on Q35: Nancy Horton: reference: C-6 ws X-rayed in October and deemed unacceptable.
Note on D24: Nancy Horton: Delivery schedule for C-4 is based on a 15 week machining leadtime and reflects an expectation of continued learning
Note on D39: Nancy Horton: Ref: A-2 was poured on 9/27/05
Note on D55: Nancy Horton: Ref: B-1 was poured on 11/11/05.
Note on D75: Nancy Horton: Ref: Assumes pour date no later than 4/25/06
Note on D79: Nancy Horton: Ref: Assumes pour date no later than 5/15/06
Note on D71: Nancy Horton: Ref: Assumes pour date of 4/4/06
Note on D67: Nancy Horton: Ref: Assumes pour date of 3/14/06
Note on D63: Nancy Horton: Ref: Assumes pour date of 2/20/06
Note on D59: Nancy Horton: Ref: Assumes pour date of 1/31/06
Note on D51: Nancy Horton: Ref: Assumes pour date of 1/10/06
Note on D47: Nancy Horton: Scheduled to pour 12/20/05
Note on D43: Nancy Horton: Ref: A-3 was poured on 10/14
Note on S7: Nancy K. Horton: note 2 from e-mail: B pattern is 100% complete; however, Cost of the pattern includes first article scan at Metal Tek. Scan is scheduled to commence on 12/5. This figure will remain open until B-1 is successfully scanned..
Note on S16: Nancy K. Horton: note 3 from e-mail: As of 12/5, final inspections on C-2 are being conducted. Part is scheduled to ship to PPPL on 12/9/05.
Note on S17: Nancy K. Horton: note 4 from e-mail: A second shipping crate for C-2 has been built. Crates will rotate with each shipment.
Note on S28: Nancy K. Horton: note 8 from e-mail: C-5 was received at MTM on 11/28 and by 12/3 was set-up in preparation for roughing on the Lucas.
Note on D28: Nancy K. Horton: C-5 was received at MTM on 11/28/05. Projected delivery schedule is based on a 14 week leadtime.
Note on D40: Nancy K. Horton: Projected completion date is based on a 12 week machining schedule. Machining to commence no later than 2/20/06 - 3 weeks after C-6.
Note on D16: Nancy K. Horton: Revised projection for completion of C-2 reflects a 23 week leadtime for machining
Note on D12: Nancy K. Horton: Machining leadtime ws 26 weeks.
Note on D36: Nancy K. Horton: Projected delivery schedule for C-6 is 12 weeks.
Note on D44: Nancy K. Horton: Projected completion date is based on a 12 week machining schedule. Machining to commence no later than 3/13/06 - 3 weeks after A-2.
Note on D48: Nancy K. Horton: Projected completion date is based on a 12 week machining schedule. Machining to commence no later than 3/31/06 - 3 weeks after A-3.
Note on D52: Nancy K. Horton: Projected completion date is based on a 12 week machining schedule. Machining to commence no later than 4/20/06 - 3 weeks after A-4.
Note on D56: Nancy K. Horton: Projected completion date is based on a 12 week machining schedule. Machining to commence no later than 5/10/06 - 2.5 weeks after A-5.
Note on D60: Nancy K. Horton: Projected completion date is based on a 12 week machining schedule. Machining to commence no later than 5/24/06 - 2 weeks after B-1.
Note on D64: Nancy K. Horton: Projected completion date is based on a 12 week machining schedule. Machining to commence no later than 6/8/06 - 2 weeks after A-6.
Note on D68: Nancy K. Horton: Projected completion date is based on a 12 week machining schedule. Machining to commence no later than 6/20/06 - 2 weeks after B-2.
Note on D72: Nancy K. Horton: Projected completion date is based on a 12 week machining schedule. Machining to commence no later than 7/5/06 - 2 weeks after B-3.
Note on D76: Nancy K. Horton: Projected completion date is based on a 12 week machining schedule. Machining to commence no later than 7/20/06 - 2 weeks after B-4.
Note on D80: Nancy K. Horton: Projected completion date is based on a 12 week machining schedule. Machining to commence no later than 8/3/06 - 2 weeks after B-5.
Note on S20: Nancy K. Horton: note 5 from e-mail: C-3 is currently on the 3-Axis machine. It is scheduled to move to the U-5 on 12/9.
Note on S24: Nancy K. Horton: note 6 from e-mail: C-4 has been roughed on the Lucas and is now waiting to be moved to the 3-axis machine when C-3 is complete.
Note on S35: Nancy K. Horton: note 9 from e-mail: A new C-6 was poured on 11/28.
Note on S32: Nancy K. Horton: Reference: Machining of A-1 scheduled to commence at the beginning of the New Year.
Note on D57: Nancy K. Horton: 8/1 is now the projected date when PPPL will have one of each type of casting in-house.
Note on S27: Nancy K. Horton: note 7 from e-mail: C-5 was shipped from Metal Tek on 11/26 and received by Major Tool on 11/28.
Note on S39: Nancy K. Horton: note 10 from e-mail: A-2 is in weld upgrade.
Note on S43: Nancy K. Horton: note 11 from e-mail: A-3 is now in weld upgrade and is scheduled to ship to Major Tool in January.
Note on S47: Nancy K. Horton: note 12 from e-mail: Set-up for A-4 is underway. The part is scheduled to pour on 12/20.
Note on S55: Nancy K. Horton: note 13 from e-mail: B-1 was poured on 11/11. The part is scheduled to be scanned the week of 12/5.

## EIO Monthly Report 11-4-05
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: November 4, 2005
Casting Delivery Sequence |  | Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05 | % compl. 2/05 | % compl. 3/05 | % Complete 4/05 | % Complete 5/05 | % Complete 6/05 | % Complete 7/05 | % Complete 8/05 | % Complete 9/05 | % Complete 10/05 | % Complete 11/05 | Cost Accrual
Patterns
| Pattern A complete | 2005-02-10 | 2005-04-01 | 255125 |  | 10% | 18% | 25% | 40% | 98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 255125
| Pattern B complete | 2005-04-12 | 2005-07-01 | 255125 |  | 2% | 7% | 10% | 10% | 15% | 17% | 20% | 25% | 40% | 95% | 97% | 97% | 247471.25
| Major Tool Tooling Complete | 2005-02-15 | 2005-03-14 | 555000 |  | 25% | 50% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 555000
| Materials (MetalTek) | 2005-12-31 |  | 744746 |  | 5% | 17.6% | 18% | 67% | 67% | 67% | 67% | 67% | 67% | 100% | 100% | 100% | 744746
1 | C1
| MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-31 | 140808 |  | 0 | 0 | 75% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 140808
| MTM - machining/inspection | 2005-05-15 | 2005-09-30 | 154912 |  | 0 | 0 | 0 |  | 10% | 30% | 65% | 70% | 80% | 90% | 100% | 100% | 154912
| Receive at PPPL | 2005-05-16 | 2005-10-03 | [11 empty] | 35% | 100% | 100%
2 | C2
| MTK-casting | 2005-04-20 | 2005-06-27 | 140808 |  |  |  |  | 5% | 10% | 25% | 50% | 100% | 100% | 100% | 100% | 100% | 140808
| MTM - machining/inspection | 2005-07-13 | 2005-11-18 | 154912 | [8 empty] | 5% | 30% | 70% | 75% | 85% | 131675.2
| Receive at PPPL | 2005-07-14 | 2005-11-20 | [11 empty] | 10% | 15% | 15%
3 | A1
| MTK-casting | 2005-05-20 | 2005-09-06 | 140808 | [6 empty] | 5% | 20% | 60% | 80% | 99% | 100% | 100% | 140808
| MTM - machining/inspection | 2005-08-12 | 2006-05-01 | 154912 | [11 empty] | 10% | 10% | 15491.2
| Receive at PPPL | 2005-08-15 | 2006-05-02
4 | C3
| MTK-casting | 2005-06-20 | 2005-09-21 | 140808 | [7 empty] | 10% | 50% | 65% | 90% | 100% | 100% | 140808
| MTM - machining/inspection | 2005-09-14 | 2005-12-22 | 154912 | [11 empty] | 5% | 25% | 38728
| Receive at PPPL | 2005-09-15 | 2005-12-23
5 | C4
| MTK-casting | 2006-05-16 | 2005-10-31 | 140808 | [8 empty] | 40% | 55% | 75% | 85% | 100% | 140808
| MTM - machining/inspection | 2006-08-14 | 2006-01-22 | 154912 | [11 empty] | 5% | 7% | 10843.84
| Receive at PPPL | 2006-08-15 | 2006-01-23
6 | C5
| MTK-casting | 2006-05-30 | 2005-11-18 | 140808 | [9 empty] | 35% | 50% | 75% | 80% | 112646.4
| MTM - machining/inspection | 2006-08-28 | 2006-02-10 | 154912 | [11 empty] | 2% | 2% | 3098.24
| Receive at PPPL | 2006-08-29 | 2006-02-12
7 | C6
| MTK-casting | 2006-06-16 | 2006-02-01 | 140808 | [9 empty] | 2% | 35% | 65% | 5% | 7040.4
| MTM - machining/inspection | 2006-09-14 | 2006-04-25 | 154912
| Receive at PPPL | 2006-09-15 | 2006-04-26
8 | A2
| MTK-casting | 2005-08-17 | 2005-11-30 | 140808 | [10 empty] | 2% | 50% | 55% | 77444.4
| MTM - machining/inspection | 2005-11-14 | 2006-02-25 | 154912
| Receive at PPPL | 2005-11-15 | 2006-02-26
9 | A3
| MTK-casting | 2005-07-21 | 2005-12-20 | 140808 | [11 empty] | 2% | 50% | 70404
| MTM - machining/inspection | 2005-10-13 | 2006-03-13 | 154912
| Receive at PPPL | 2005-10-14 | 2006-03-15
10 | B1
| MTK-casting | 2005-09-16 | 2006-01-16 | 140808 | [11 empty] | 5% | 20% | 28161.6
| MTM - machining/inspection | 2005-12-14 | 2006-04-11 | 154912
| Receive at PPPL | 2005-12-15 | 2006-04-12
11 | A4
| MTK-casting | 2005-10-17 | 2006-02-20 | 140808
| MTM - machining/inspection | 2006-01-13 | 2006-05-17 | 154912
| Receive at PPPL | 2006-01-16 | 2006-05-19
12 | A5
| MTK-casting | 2006-01-13 | 2006-03-14 | 140808
| MTM - machining/inspection | 2006-04-13 | 2006-06-05 | 154912
| Receive at PPPL | 2006-04-14 | 2006-06-07
13 | A6
| MTK-casting | 2005-11-16 | 2006-04-05 | 140808
| MTM - machining/inspection | 2006-02-14 | 2006-06-27 | 154912
| Receive at PPPL | 2006-02-15 | 2006-06-28
14 | B2
| MTK-casting | 2005-12-14 | 2006-04-25 | 140808
| MTM - machining/inspection | 2006-03-14 | 2006-07-18 | 154912
| Receive at PPPL | 2006-03-15 | 2006-07-20
15 | B3
| MTK-casting | 2006-02-13 | 2006-05-15 | 140808
| MTM - machining/inspection | 2006-05-12 | 2006-08-08 | 154912
| Receive at PPPL | 2006-05-15 | 2006-08-10
16 | B4
| MTK-casting | 2006-03-16 | 2006-06-07 | 140808
| MTM - machining/inspection | 2006-06-14 | 2006-08-28 | 154912
| Receive at PPPL | 2006-06-15 | 2006-08-30
17 | B5
| MTK-casting | 2006-03-28 | 2006-06-25 | 140808
| MTM - machining/inspection | 2006-06-26 | 2006-09-15 | 154912
| Receive at PPPL | 2006-06-27 | 2006-09-16
18 | B6
| MTK-casting | 2006-04-14 | 2006-07-20 | 140808
| MTM - machining/inspection | 2006-07-13 | 2006-10-09 | 154912
| Receive at PPPL | 2006-07-14 | 2006-10-10
| EIO Project Mgt. 24 mos. |  |  | 908828 | 8.333% | 12.5% | 16.6% | 21% | 25% | 29% | 33.3% | 37.5% | 42% | 45% | 50% | 54% | 58% | 527120.24
TOTAL | [17 empty] | 3683947.77
Note on E3: Nancy Horton: For this spreadsheet, "Task Values" were based on rounded calculations which when totaled, result in a deviation from the bottom line negotiated price. Billings will reflect the agreed upon prices in EIO contract.
Note on D11: Nancy Horton: Reference: C-1 was poured on 12/20/04. C-1 casting shipped on 3/31/05 and was placed in the fixture at MTM on 4/1/05.
Note on D15: Nancy Horton: Ref: C-2 was poured on 4/15/05. 6/27/05 reflects the actual date C-2 casting was shipped from MTK. This was 5 days ahead of previously projected schedule of 7/1/05.
Note on A3: Nancy Horton: Ref: PPPL has granted the EIO team flexibility in establishing the most advantageous casting sequence, considering criteria such as learning and production efficiency. Nonetheless, the team will endeavor to deliver one of each type casting to PPPL as soon as practical, all things considered. The schedule reflected in the spreadsheet reflects the most likely sequencing option at this time.
Note on D24: Nancy Horton: Ref: 12/22 reflects the latest delivery projection based on a 12 week machining schedule commencing on 10/04.
Note on D20: Nancy Horton: Note 6 from e-mail: In this scenario, the projected start date for A-1 is after A-3 and B-1. Machining would commence on 2/5/06 for projected completion by 5/1/06. The EIO team is taking a closer look at the schedule and may make further sequencing revisions to capitalize on learning.
Note on D27: Nancy Horton: Ref: C-4 was poured on 7/12/05. 10/31/05 reflects the actual ship date to MTM
Note on D31: Nancy Horton: Ref: C-5 was poured on 8/8/05
Note on D35: Nancy Horton: Ref: C-6 was poured on 8/31/05 and scrapped on 10/28/05. Revised delivery schedule assumes a new pour date of 11/25/05
Note on D3: Nancy Horton: Note 1 from e-mail: Delivery projections have been updated to reflect a possible scenario. EIO team members are currently evaluating a number of different options and implementing efficiencies in order to establish the most effective schedule within the contract period of performance. For this exercise, the contract period of performance was extended by 3 weeks to reflect incorporation of PPPL request for deviations. The RFD is still under negotiation.
Note on D23: Nancy Horton: Ref: C-3 was poured on 6/10/05 and was delivered to MTM on 9/21/05
Note on D19: Nancy Horton: Ref: A-1 was poured on 5/24/05
Note on Q35: Nancy Horton: reference: C-6 ws X-rayed in October and deemed unacceptable.
Note on D28: Nancy Horton: Ref: Revised projection based on a 12 week machining schedule after receipt of casting
Note on R7: Nancy Horton: note 2 from e-mail: B pattern is 100% complete; however, Cost of the pattern includes first article scan at Metal Tek, so this figure will remain open until after B-1 is poured and scanned.
Note on R13: Nancy Horton: note 3 from e-mail: C-1 was delivered to PPPL on 10/3/05
Note on R17: Nancy Horton: note 5 from e-mail: Draft C-2 doc package has been posted to EIO ftp for advance review. Shipping crate for C-1 will be returned to support shipment of C-2.
Note on R20: Nancy Horton: Reference: While programming for A is nearly complete, the casting will be machined after C-3 and possibly even after all of the C's have commenced machining
Note on R23: Nancy Horton: note 7 from e-mail: C-3 was completed on 9/20 and delivered to MTM on 9/21/05
Note on R27: Nancy Horton: note 9 from e-mail: C-4 was shipped to MTM on 10/31/05
Note on R28: Nancy Horton: note 10 from e-mail: As of 11/4/05, MTM reported that they had commenced set-up and x-ray of the part. According to their internal schedule, the part was approximately 2% complete. The figure of 7% includes applicable learning from C-1 and C-2.
Note on R31: Nancy Horton: note 11 from e-mail: C-5 is still undergoing weld upgrade. The part returned from X-ray on 11/4/05 with only 3 rejected views, so it should proceed through final stages in the upcoming weeks.
Note on R32: Nancy Horton: Ref: 2% reflects applicable learning from C-1 and preparation for receipt of C-5
Note on R35: Nancy Horton: note 12 from e-mail: The first "C-6" casting poured on 8/31/05 was determined unacceptable for upgrade after X-ray and will be scrapped. Another pour will be scheduled after B-1. The revised % complete does not reflect the previous effort put forth on the scrapped casting.
Note on R47: Nancy Horton: note 15 from e-mail: B-1 Mold is ready and part is scheduled to pour 11/8/05.
Note on D39: Nancy Horton: Ref: A-2 was poured on 9/27/05)
Note on D47: Nancy Horton: Ref: B-1 is scheduled to pour 11/8/05.
Note on D75: Nancy Horton: Ref: Assumes pour date no later than 4/20/06
Note on D79: Nancy Horton: Ref: Assumes pour date no later than 5/10/06
Note on D71: Nancy Horton: Ref: Assumes pour date of 3/31/06
Note on D67: Nancy Horton: Ref: Assumes pour date of 3/10/06
Note on D63: Nancy Horton: Ref: Assumes pour date of 2/15/06
Note on D59: Nancy Horton: Ref: Assumes pour date of 1/25/06
Note on D55: Nancy Horton: Ref: Assumes pour date of 1/5/06
Note on D51: Nancy Horton: Ref: Assumes pour date of 12/15/06
Note on D43: Nancy Horton: Ref: A-3 was poured on 10/14
Note on R16: Nancy Horton: note 4 from e-mail: MTM has commenced the 4th of 5 set-ups. Delivery is now projected for 11/18/05
Note on R24: Nancy Horton: note 8 from e-mail: C-3 finished the first week of semi-finishing operations and continues to make excellent progress.
Note on R43: Nancy Horton: note 14 from e-mail: A-3 was poured on 10/14.
Note on R39: Nancy Horton: note 13 from e-mail: A-2 was shipped to MQS on 11/4 for initial NDT

## EIO Monthly Report 10-1-05
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: October 4, 2005
Casting Delivery Sequence |  | Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05 | % compl. 2/05 | % compl. 3/05 | % Complete 4/05 | % Complete 5/05 | % Complete 6/05 | % Complete 7/05 | % Complete 8/05 | % Complete 9/05 | % Complete 10/05 | Fiscal Year End Cost Accrual
Patterns
| Pattern A complete | 2005-02-10 | 2005-04-01 | 255125 |  | 10% | 18% | 25% | 40% | 98% | 100% | 100% | 100% | 100% | 100% | 100% | 255125
| Pattern B complete | 2005-04-12 | 2005-07-01 | 255125 |  | 2% | 7% | 10% | 10% | 15% | 17% | 20% | 25% | 40% | 95% | 97% | 247471.25
| Major Tool Tooling Complete | 2005-02-15 | 2005-03-14 | 555000 |  | 25% | 50% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 555000
| Materials (MetalTek) | 2005-12-31 |  | 744746 |  | 5% | 17.6% | 18% | 67% | 67% | 67% | 67% | 67% | 67% | 100% | 100% | 744746
1 | C1
| MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-18 | 140808 |  | 0 | 0 | 75% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 140808
| MTM - machining/inspection | 2005-05-15 | 2005-09-30 | 154912 |  | 0 | 0 | 0 |  | 10% | 30% | 65% | 70% | 80% | 90% | 100% | 154912
| Receive at PPPL | 2005-05-16 | 2005-10-03 | [11 empty] | 35% | 100%
2 | C2
| MTK-casting | 2005-04-20 | 2005-06-27 | 140808 |  |  |  |  | 5% | 10% | 25% | 50% | 100% | 100% | 100% | 100% | 140808
| MTM - machining/inspection | 2005-07-13 | 2005-10-31 | 154912 | [8 empty] | 5% | 30% | 70% | 75% | 116184
| Receive at PPPL | 2005-07-14 | 2005-11-02 | [11 empty] | 10% | 15%
3 | A1
| MTK-casting | 2005-05-20 | 2005-09-06 | 140808 | [6 empty] | 5% | 20% | 60% | 80% | 99% | 100% | 140808
| MTM - machining/inspection | 2005-08-12 | 2005-12-23 | 154912 | [11 empty] | 10% | 15491.2
| Receive at PPPL | 2005-08-15 | 2005-12-26
4 | C3
| MTK-casting | 2005-06-20 | 2005-09-08 | 140808 | [7 empty] | 10% | 50% | 65% | 90% | 100% | 140808
| MTM - machining/inspection | 2005-09-14 | 2005-12-22 | 154912 | [11 empty] | 5% | 7745.6
| Receive at PPPL | 2005-09-15 | 2005-12-23
5 | C4
| MTK-casting | 2006-05-16 | 2005-10-21 | 140808 | [8 empty] | 40% | 55% | 75% | 85% | 119686.8
| MTM - machining/inspection | 2006-08-14 | 2006-01-15 | 154912 | [11 empty] | 5% | 7745.6
| Receive at PPPL | 2006-08-15 | 2006-01-17
6 | C5
| MTK-casting | 2006-05-30 | 2005-10-31 | 140808 | [9 empty] | 35% | 50% | 75% | 105606
| MTM - machining/inspection | 2006-08-28 | 2006-02-05 | 154912 | [11 empty] | 2% | 3098.24
| Receive at PPPL | 2006-08-29 | 2006-02-07
7 | C6
| MTK-casting | 2006-06-16 | 2005-11-15 | 140808 | [9 empty] | 2% | 35% | 65% | 91525.2
| MTM - machining/inspection | 2006-09-14 | 2006-02-20 | 154912
| Receive at PPPL | 2006-09-15 | 2006-02-21
8 | A2
| MTK-casting | 2005-08-17 | 2005-11-30 | 140808 | [10 empty] | 2% | 50% | 70404
| MTM - machining/inspection | 2005-11-14 | 2006-01-25 | 154912
| Receive at PPPL | 2005-11-15 | 2006-01-27
9 | A3
| MTK-casting | 2005-07-21 | 2005-11-17 | 140808 | [11 empty] | 2% | 2816.16
| MTM - machining/inspection | 2005-10-13 | 2006-02-13 | 154912
| Receive at PPPL | 2005-10-14 | 2006-02-17
10 | B1
| MTK-casting | 2005-09-16 | 2005-12-09 | 140808 | [11 empty] | 5% | 7040.4
| MTM - machining/inspection | 2005-12-14 | 2006-03-09 | 154912
| Receive at PPPL | 2005-12-15 | 2006-03-13
11 | A4
| MTK-casting | 2005-10-17 | 2006-01-06 | 140808
| MTM - machining/inspection | 2006-01-13 | 2006-04-04 | 154912
| Receive at PPPL | 2006-01-16 | 2006-04-06
12 | A5
| MTK-casting | 2006-01-13 | 2006-01-20 | 140808
| MTM - machining/inspection | 2006-04-13 | 2006-04-24 | 154912
| Receive at PPPL | 2006-04-14 | 2006-04-26
13 | A6
| MTK-casting | 2005-11-16 | 2006-02-17 | 140808
| MTM - machining/inspection | 2006-02-14 | 2006-05-12 | 154912
| Receive at PPPL | 2006-02-15 | 2006-05-15
14 | B2
| MTK-casting | 2005-12-14 | 2006-03-07 | 140808
| MTM - machining/inspection | 2006-03-14 | 2006-06-05 | 154912
| Receive at PPPL | 2006-03-15 | 2006-06-07
15 | B3
| MTK-casting | 2006-02-13 | 2006-03-30 | 140808
| MTM - machining/inspection | 2006-05-12 | 2006-06-30 | 154912
| Receive at PPPL | 2006-05-15 | 2006-07-05
16 | B4
| MTK-casting | 2006-03-16 | 2006-04-20 | 140808
| MTM - machining/inspection | 2006-06-14 | 2006-07-18 | 154912
| Receive at PPPL | 2006-06-15 | 2006-07-20
17 | B5
| MTK-casting | 2006-03-28 | 2006-05-12 | 140808
| MTM - machining/inspection | 2006-06-26 | 2006-08-11 | 154912
| Receive at PPPL | 2006-06-27 | 2006-08-15
18 | B6
| MTK-casting | 2006-04-14 | 2006-06-01 | 140808
| MTM - machining/inspection | 2006-07-13 | 2006-08-31 | 154912
| Receive at PPPL | 2006-07-14 | 2006-09-05
| EIO Project Mgt. 24 mos. |  |  | 908828 | 8.333% | 12.5% | 16.6% | 21% | 25% | 29% | 33.3% | 37.5% | 42% | 45% | 50% | 54% | 490767.12
TOTAL | [16 empty] | 3558596.57
Note on E3: Nancy Horton: For this spreadsheet, "Task Values" were based on rounded calculations which when totaled, result in a deviation from the bottom line negotiated price. Billings will reflect the agreed upon prices in EIO contract.
Note on D11: Nancy Horton: Reference: C-1 was poured on 12/20/04. C-1 casting shipped on 3/31/05 and was placed in the fixture at MTM on 4/1/05.
Note on D15: Nancy Horton: Ref: C-2 was poured on 4/15/05. 6/27/05 reflects the actual date C-2 casting was shipped from MTK. This was 5 days ahead of previously projected schedule of 7/1/05.
Note on A3: Nancy Horton: Ref: PPPL has granted the EIO team flexibility in establishing the most advantageous casting sequence, considering criteria such as learning and production efficiency. Nonetheless, the team will endeavor to deliver one of each type casting to PPPL as soon as practical, all things considered. The schedule reflected in the spreadsheet reflects the most likely sequencing option at this time.
Note on D24: Nancy Horton: Note 9 from e-mail: 12/22 reflects the latest delivery projection based on a 12 week machining schedule commencing on 10/04.
Note on D20: Nancy Horton: Note 6 from e-mail: Actual projected date is TBD after analysis and assessment of learning . Also, revised delivery date will reflect resequencing of castings at MTM to enable continued learning on the C's before moving on to the A-1.
Note on D27: Nancy Horton: Ref: C-4 was poured on 7/12/05. Revised projection based on remaining processing steps
Note on D31: Nancy Horton: Ref: C-5 was poured on 8/8/05
Note on D35: Nancy Horton: Ref: C-6 was poured on 8/31/05.
Note on D3: Nancy Horton: Note 1 from e-mail: Projections for the C type castings (Identified in sequence as # 1, 2, 4, 5, 6, & 7) are based on the most current information and plans to date. Projections for Machining and receipt at PPPL for A and B type castings (#3 & #'s 8 - 18) are not based on current casting delivery projections and are currently under analysis for the most effective production sequence and delivery based on current and anticipated learning. Therefore, the dates shown will be updated in the future based on our experience in the upcoming month.
Note on D23: Nancy Horton: Ref: C-3 was poured on 6/10/05 and was delivered to MTM on 9/21/05
Note on D19: Nancy Horton: Ref: A-1 was poured on 5/24/05
Note on Q16: Nancy Horton: note 4 from e-mail: C-2 has completed machining on 3 axis and commenced machining on the 5 axis on 10/1/05
Note on Q17: Nancy Horton: note 5 from e-mail: Draft C-2 doc package has been posted to EIO ftp for advance review. Shipping crate for C-1 will be returned to support shipment of C-2.
Note on Q20: Nancy Horton: note 7 from e-mail: While programming for A is nearly complete, the casting will be machined after C-3 and possibly even after all of the C's have commenced machining
Note on Q23: Nancy Horton: note 8 from e-mail: C-3 was completed on 9/20 and delivered to MTM on 9/21/05
Note on Q24: Nancy Horton: note 10 from e-mail: Machining of C-3 was rescheduled to commence on the 3 axis machine on 10/4/05, in order to conduct preventive maintenance on the 3axis machine prior to work.
Note on Q27: Nancy Horton: note 11 from e-mail: C-4 has been undergoing weld repair and should be sent out for X-ray around 10/5/05
Note on Q28: Nancy Horton: note 13 from e-mail: 5% reflects applicable learning from C-1 and preparation for receipt of C-4
Note on Q31: Nancy Horton: note 14 frm e-mail: C-5 is undergoing weld upgrade
Note on Q32: Nancy Horton: note 16 from e-mail: 2% reflects applicable learning from C-1 and preparation for receipt of C-5
Note on Q35: Nancy Horton: note 17 from e-mail: C-6 is scheduled for first X-ray commencing wk of 10/10/05
Note on Q39: Nancy Horton: note 19 from e-mail: A-2 was poured on 9/27/05. It has been broken out of the mold and clean-up is underway
Note on D39: Nancy Horton: A-2 was poured on 9/27/05)
Note on D28: Nancy Horton: note 12 from e-mail: Revised projection based on a 12 week machining schedule after receipt of casting
Note on D32: Nancy Horton: note 15 from e-mail: Revised projection based on 12 week machining schedule and 3 week interval between casting set-ups at MTM, for machining start date of 11/10/05
Note on D36: Nancy Horton: note 18 from e-mail: Revised projection assumes a 12 week machining schedule and a 3 week interval between machining start-ups. In this projection, machining will commence around 11/30/05
Note on Q13: Nancy Horton: note 3 from e-mail: C-1 was delivered to PPPL on 10/3/05
Note on Q7: Nancy Horton: note 2 from e-mail: B pattern is 100% complete; however, Cost of the pattern includes first article scan at Metal Tek, so this figure will remain open until after B-1 is poured and scanned.
Note on Q43: Nancy Horton: ref: Reflects Production planning
Note on Q47: Nancy Horton: ref: Reflects Production planning

## EIO Monthly Report 9-2-05
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: September 2, 2005
Casting Delivery Sequence |  | Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05 | % compl. 2/05 | % compl. 3/05 | % Complete 4/05 | % Complete 5/05 | % Complete 6/05 | % Complete 7/05 | % Complete 8/05 | % Complete 9/05 | Cost Accrual Through August
Patterns
| Pattern A complete | 2005-02-10 | 2005-04-01 | 255125 |  | 10% | 18% | 25% | 40% | 98% | 100% | 100% | 100% | 100% | 100% | 255125
| Pattern B complete | 2005-04-12 | 2005-07-01 | 255125 |  | 2% | 7% | 10% | 10% | 15% | 17% | 20% | 25% | 40% | 95% | 242368.75
| Major Tool Tooling Complete | 2005-02-15 | 2005-03-14 | 555000 |  | 25% | 50% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 555000
| Materials (MetalTek) | 2005-12-31 |  | 744746 |  | 5% | 17.6% | 18% | 67% | 67% | 67% | 67% | 67% | 67% | 100% | 744746
1 | C1
| MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-18 | 140808 |  | 0 | 0 | 75% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 140808
| MTM - machining/inspection | 2005-05-15 | 2005-09-19 | 154912 |  | 0 | 0 | 0 |  | 10% | 30% | 65% | 70% | 80% | 90% | 139420.8
| Receive at PPPL | 2005-05-16 | 2005-09-21 | [11 empty] | 35% | 0
2 | C2
| MTK-casting | 2005-04-20 | 2005-06-27 | 140808 |  |  |  |  | 5% | 10% | 25% | 50% | 100% | 100% | 100% | 140808
| MTM - machining/inspection | 2005-07-13 | 2005-09-27 | 154912 | [8 empty] | 5% | 30% | 70% | 108438.4
| Receive at PPPL | 2005-07-14 | 2005-09-29 | [11 empty] | 10%
3 | A1
| MTK-casting | 2005-05-20 | 2005-09-06 | 140808 | [6 empty] | 5% | 20% | 60% | 80% | 99% | 139399.92
| MTM - machining/inspection | 2005-08-12 | 2005-12-23 | 154912 | [11 empty] | 0
| Receive at PPPL | 2005-08-15 | 2005-12-26
4 | C3
| MTK-casting | 2005-06-20 | 2005-09-08 | 140808 | [7 empty] | 10% | 50% | 65% | 90% | 126727.2
| MTM - machining/inspection | 2005-09-14 | 2005-12-05 | 154912 | [11 empty] | 0
| Receive at PPPL | 2005-09-15 | 2005-12-07
5 | C4
| MTK-casting | 2006-05-16 | 2005-09-19 | 140808 | [8 empty] | 40% | 55% | 75% | 105606
| MTM - machining/inspection | 2006-08-14 | 2005-11-20 | 154912 | [11 empty] | 0
| Receive at PPPL | 2006-08-15 | 2005-11-23
6 | C5
| MTK-casting | 2006-05-30 | 2005-10-03 | 140808 | [9 empty] | 35% | 50% | 70404
| MTM - machining/inspection | 2006-08-28 | 2005-12-13 | 154912 | [11 empty] | 0
| Receive at PPPL | 2006-08-29 | 2005-12-15
7 | C6
| MTK-casting | 2006-06-16 | 2005-11-01 | 140808 | [9 empty] | 2% | 35% | 49282.8
| MTM - machining/inspection | 2006-09-14 | 2006-01-06 | 154912
| Receive at PPPL | 2006-09-15 | 2006-01-09
8 | A2
| MTK-casting | 2005-08-17 | 2005-11-30 | 140808 | [10 empty] | 2% | 2816.16
| MTM - machining/inspection | 2005-11-14 | 2006-01-25 | 154912
| Receive at PPPL | 2005-11-15 | 2006-01-27
9 | A3
| MTK-casting | 2005-07-21 | 2005-11-17 | 140808 | [11 empty] | 0
| MTM - machining/inspection | 2005-10-13 | 2006-02-13 | 154912
| Receive at PPPL | 2005-10-14 | 2006-02-17
10 | B1
| MTK-casting | 2005-09-16 | 2005-12-09 | 140808 | [11 empty] | 0
| MTM - machining/inspection | 2005-12-14 | 2006-03-09 | 154912
| Receive at PPPL | 2005-12-15 | 2006-03-13
11 | A4
| MTK-casting | 2005-10-17 | 2006-01-06 | 140808
| MTM - machining/inspection | 2006-01-13 | 2006-04-04 | 154912
| Receive at PPPL | 2006-01-16 | 2006-04-06
12 | A5
| MTK-casting | 2006-01-13 | 2006-01-20 | 140808
| MTM - machining/inspection | 2006-04-13 | 2006-04-24 | 154912
| Receive at PPPL | 2006-04-14 | 2006-04-26
13 | A6
| MTK-casting | 2005-11-16 | 2006-02-17 | 140808
| MTM - machining/inspection | 2006-02-14 | 2006-05-12 | 154912
| Receive at PPPL | 2006-02-15 | 2006-05-15
14 | B2
| MTK-casting | 2005-12-14 | 2006-03-07 | 140808
| MTM - machining/inspection | 2006-03-14 | 2006-06-05 | 154912
| Receive at PPPL | 2006-03-15 | 2006-06-07
15 | B3
| MTK-casting | 2006-02-13 | 2006-03-30 | 140808
| MTM - machining/inspection | 2006-05-12 | 2006-06-30 | 154912
| Receive at PPPL | 2006-05-15 | 2006-07-05
16 | B4
| MTK-casting | 2006-03-16 | 2006-04-20 | 140808
| MTM - machining/inspection | 2006-06-14 | 2006-07-18 | 154912
| Receive at PPPL | 2006-06-15 | 2006-07-20
17 | B5
| MTK-casting | 2006-03-28 | 2006-05-12 | 140808
| MTM - machining/inspection | 2006-06-26 | 2006-08-11 | 154912
| Receive at PPPL | 2006-06-27 | 2006-08-15
18 | B6
| MTK-casting | 2006-04-14 | 2006-06-01 | 140808
| MTM - machining/inspection | 2006-07-13 | 2006-08-31 | 154912
| Receive at PPPL | 2006-07-14 | 2006-09-05
| EIO Project Mgt. 24 mos. |  |  | 908828 | 8.333% | 12.5% | 16.6% | 21% | 25% | 29% | 33.3% | 37.5% | 42% | 45% | 50% | 454414
TOTAL | [15 empty] | 3275365.03
Note on D13: Nancy Horton: Note 6 in e-mail: Current projection for delivery to PPPL as of 9/2/05
Note on E3: Nancy Horton: For this spreadsheet, "Task Values" were based on rounded calculations which when totaled, result in a deviation from the bottom line negotiated price. Billings will reflect the agreed upon prices in EIO contract.
Note on D11: Nancy Horton: Reference: C-1 was poured on 12/20/04. C-1 casting shipped on 3/31/05 and was placed in the fixture at MTM on 4/1/05.
Note on D15: Nancy Horton: Ref: C-2 was poured on 4/15/05. 6/27/05 reflects the actual date C-2 casting was shipped from MTK. This was 5 days ahead of previously projected schedule of 7/1/05.
Note on D12: Nancy Horton: Note 4 in e-mail: A revised projected delivery schedule was presented during a meeting at MTM on August 9, to reflect on-going machining challenges and was further updated on 9/2 as C-1 came off the 5 axis machine and remaining hand work was assessed. New projection is 9/19/05.
Note on A3: Nancy Horton: Ref: PPPL has granted the EIO team flexibility in establishing the most advantageous casting sequence, considering criteria such as learning and production efficiency. Nonetheless, the team will endeavor to deliver one of each type casting to PPPL as soon as practical, all things considered. The schedule reflected in the spreadsheet reflects the most likely sequencing option at this time.
Note on D24: Nancy Horton: Note 13 from e-mail: 12/5 reflects the latest delivery projection based on a 12 week machining schedule and receipt of casting at MTM by 9/12.
Note on P9: Nancy Horton: Note 3 from e-mail: Metals purchase is now 100% complete.On 8/17 Metal Tek notified EIO that remaining metal purchases would be completed in August and invoiced at the end of the month.
Note on P7: Nancy Horton: Note 2 from e-mail: Pattern is estimated as 95% complete. Scanning of the pattern will commence on 9/5 with projected delivery to Metal Tek on 9/12.
Note on P12: Nancy Horton: Note 5 from e-mail: C-1has entered the last stage of machining prior to commencement of inspection and tests, which are schedule to begin in 9/8.
Note on P16: Nancy Horton: Note 8 from e-mail: 3-axis machining of C-2 should be complete by 9/9 at which time the coil will move onto the U-5 center. According to MTM’s time studies from C-1 machining, C-2 should complete machining on 9/27.
Note on P13: Nancy Horton: Note 7 from e-mail: The 35% complete for delivery to PPPL has been included to reflect the significant effort that has been invested by EIO team members & PPPL to assemble, review and approve the associated documentation required to accompany the casting. Key personnel are planning to participate in final tests at MTM in order to facilitate review and acceptance of C-1 prior to shipment. Additionally, MTM has closely coordinated the design and build of the shipping container with PPPL to ensure that the coil can be removed and set-up when it is received at Princeton.
Note on P17: Nancy Horton: Note 9 from e-mail: C-2 doc package review is underway. Lessons learned from C-1 shipment will be applied to C-2 to expedite delivery.
Note on P19: Nancy Horton: Note 10 from e-mail: A-1 was completed in August; however, release for shipment was held pending resolution of open item in the documentation package.
Note on P23: Nancy Horton: Note 12 from e-mail: C-3 is the final stages of processing prior to shipment and is expected to be completed and released for shipment on or about 9/8
Note on D20: Nancy Horton: Note 11 from e-mail: Revised delivery date will reflect resequencing of castings at MTM to enable continued learning on the C's before moving on to the A-1. This will also allow MTM more time for set-up on A prior to commencement of machining
Note on P39: Nancy Horton: Note 17 from e-mail: Documentation & Scheduling for processing of A-2 has commenced with expected pour around week of 9/26.
Note on D27: Nancy Horton: Ref: C-4 was poured on 7/12/05
Note on D31: Nancy Horton: Ref: C-5 was poured on 8/8/05
Note on D35: Nancy Horton: Ref: C-6 was poured on 8/31/05.
Note on P35: Nancy Horton: Note 16 from e-mail: C-6 was poured on 8/31 and will be removed from the mold over the Labor Day weekend.
Note on D3: Nancy Horton: Note 1 from e-mail: Projections for castings # 1-4 are based on the most current information and plans to date. Projections for Machining and receipt at PPPL for castings # 5 - 18 are not based on current casting delivery projections and are currently under analysis for the most effective production sequence and delivery based on current and anticipated learning. Therefore, the dates shown will be updated in the future based on our experience in the next two months.
Note on P27: Nancy Horton: Note 14 from e-mail: C-4 is scheduled for weld upgrade.
Note on P31: Nancy Horton: Note 15 from e-mail: X-ray on C-5 is complete and the part will return to Metal Tek for weld upgrade.
Note on D23: Nancy Horton: Ref: C-3 was poured on 6/10/05
Note on D19: Nancy Horton: Ref: A-1 was poured on 5/24/05

## EIO Monthly Report 8-2-05
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: August 2, 2005
Casting Delivery Sequence |  | Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05 | % compl. 2/05 | % compl. 3/05 | % Complete 4/05 | % Complete 5/05 | % Complete 6/05 | % Complete 7/05 | % Complete 8/05
Patterns
| Pattern A complete | 2005-02-10 | 2005-04-01 | 255125 |  | 10% | 18% | 25% | 40% | 98% | 100% | 100% | 100% | 100%
| Pattern B complete | 2005-04-12 | 2005-07-01 | 255125 |  | 2% | 7% | 10% | 10% | 15% | 17% | 20% | 25% | 40%
| Major Tool Tooling Complete | 2005-02-15 | 2005-03-14 | 555000 |  | 25% | 50% | 60% | 100% | 100% | 100% | 100% | 100% | 100%
| Materials (MetalTek) | 2005-12-31 |  | 744746 |  | 5% | 17.6% | 18% | 67% | 67% | 67% | 67% | 67% | 67%
1 | C1
| MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-18 | 140808 |  | 0 | 0 | 75% | 90% | 100% | 100% | 100% | 100% | 100%
| MTM - machining/inspection | 2005-05-15 | 2005-08-22 | 154912 |  | 0 | 0 | 0 |  | 10% | 30% | 65% | 70% | 80%
| Receive at PPPL | 2005-05-16 | 2005-08-23
2 | C2
| MTK-casting | 2005-04-20 | 2005-06-27 | 140808 |  |  |  |  | 5% | 10% | 25% | 50% | 100% | 100%
| MTM - machining/inspection | 2005-07-13 | 2005-09-27 | 154912 | [8 empty] | 5% | 30%
| Receive at PPPL | 2005-07-14 | 2005-09-29
3 | A1
| MTK-casting | 2005-05-20 | 2005-08-19 | 140808 | [6 empty] | 5% | 20% | 60% | 80%
| MTM - machining/inspection | 2005-08-12 | 2005-11-30 | 154912
| Receive at PPPL | 2005-08-15 | 2005-12-02
4 | C3
| MTK-casting | 2005-06-20 | 2005-08-05 | 140808 | [7 empty] | 10% | 50% | 65%
| MTM - machining/inspection | 2005-09-14 | 2005-10-31 | 154912
| Receive at PPPL | 2005-09-15 | 2005-11-02
5 | C4
| MTK-casting | 2006-05-16 | 2005-08-25 | 140808 | [8 empty] | 40% | 55%
| MTM - machining/inspection | 2006-08-14 | 2005-11-20 | 154912
| Receive at PPPL | 2006-08-15 | 2005-11-23
6 | C5
| MTK-casting | 2006-05-30 | 2005-09-15 | 140808 | [9 empty] | 35%
| MTM - machining/inspection | 2006-08-28 | 2005-12-13 | 154912
| Receive at PPPL | 2006-08-29 | 2005-12-15
7 | C6
| MTK-casting | 2006-06-16 | 2005-10-07 | 140808 | [9 empty] | 2%
| MTM - machining/inspection | 2006-09-14 | 2006-01-06 | 154912
| Receive at PPPL | 2006-09-15 | 2006-01-09
8 | A2
| MTK-casting | 2005-08-17 | 2005-10-28 | 140808
| MTM - machining/inspection | 2005-11-14 | 2006-01-25 | 154912
| Receive at PPPL | 2005-11-15 | 2006-01-27
9 | A3
| MTK-casting | 2005-07-21 | 2005-11-17 | 140808
| MTM - machining/inspection | 2005-10-13 | 2006-02-13 | 154912
| Receive at PPPL | 2005-10-14 | 2006-02-17
10 | B1
| MTK-casting | 2005-09-16 | 2005-12-09 | 140808
| MTM - machining/inspection | 2005-12-14 | 2006-03-09 | 154912
| Receive at PPPL | 2005-12-15 | 2006-03-13
11 | A4
| MTK-casting | 2005-10-17 | 2006-01-06 | 140808
| MTM - machining/inspection | 2006-01-13 | 2006-04-04 | 154912
| Receive at PPPL | 2006-01-16 | 2006-04-06
12 | A5
| MTK-casting | 2006-01-13 | 2006-01-20 | 140808
| MTM - machining/inspection | 2006-04-13 | 2006-04-24 | 154912
| Receive at PPPL | 2006-04-14 | 2006-04-26
13 | A6
| MTK-casting | 2005-11-16 | 2006-02-17 | 140808
| MTM - machining/inspection | 2006-02-14 | 2006-05-12 | 154912
| Receive at PPPL | 2006-02-15 | 2006-05-15
14 | B2
| MTK-casting | 2005-12-14 | 2006-03-07 | 140808
| MTM - machining/inspection | 2006-03-14 | 2006-06-05 | 154912
| Receive at PPPL | 2006-03-15 | 2006-06-07
15 | B3
| MTK-casting | 2006-02-13 | 2006-03-30 | 140808
| MTM - machining/inspection | 2006-05-12 | 2006-06-30 | 154912
| Receive at PPPL | 2006-05-15 | 2006-07-05
16 | B4
| MTK-casting | 2006-03-16 | 2006-04-20 | 140808
| MTM - machining/inspection | 2006-06-14 | 2006-07-18 | 154912
| Receive at PPPL | 2006-06-15 | 2006-07-20
17 | B5
| MTK-casting | 2006-03-28 | 2006-05-12 | 140808
| MTM - machining/inspection | 2006-06-26 | 2006-08-11 | 154912
| Receive at PPPL | 2006-06-27 | 2006-08-15
18 | B6
| MTK-casting | 2006-04-14 | 2006-06-01 | 140808
| MTM - machining/inspection | 2006-07-13 | 2006-08-31 | 154912
| Receive at PPPL | 2006-07-14 | 2006-09-05
| EIO Project Mgt. 24 mos. |  |  | 908828 | 8.333% | 12.5% | 16.6% | 21% | 25% | 29% | 33.3% | 37.5% | 42% | 45%
Note on D13: Nancy Horton: Note 6 in e-mail: Delivery to PPPL is currently projected around for the end of the month.
Note on E3: Nancy Horton: For this spreadsheet, "Task Values" were based on rounded calculations which when totaled, result in a deviation from the bottom line negotiated price. Billings will reflect the agreed upon prices in EIO contract.
Note on D11: Nancy Horton: Reference: C-1 casting shipped on 3/31/05 and was placed in the fixture at MTM on 4/1/05.
Note on D19: Nancy Horton: Note 8 from e-mail: Corrective Action on A-1 in review and production of the part is in progress.
Note on D15: Nancy Horton: Ref: 6/27/05 reflects the actual date C-2 casting was shipped from MTK. This was 5 days ahead of previously projected schedule of 7/1/05.
Note on D12: Nancy Horton: Note 4 in e-mail: Projected schedule was revised on 7/21 due to continued challenges in machining and is currently running 3 - 4 days behind the projection for machining on the 5 axis.
Note on D23: Nancy Horton: Note 10 from e-mail: Processing of C-3 was delayed at the end of July. Revised delivery date is still TBD
Note on A3: Nancy Horton: Note 1 from e-mail: PPPL has granted the EIO team flexibility in establishing the most advantageous casting sequence, considering criteria such as learning and production efficiency. Nonetheless, the team will endeavor to deliver one of each type casting to PPPL as soon as practical, all things considered. The schedule reflected in the spreadsheet reflects the most likely sequencing option at this time.
Note on N23: Nancy Horton: Ref: C-3 was poured on 6/10/05
Note on O23: Nancy Horton: Note 11 from e-mail: C-3 returned from X-Ray and is currently being welded
Note on O19: Nancy Horton: Note 9 from e-mail: Weld Upgrade of A-1 is nearly complete.
Note on O27: Nancy Horton: Note 13 from e-mail: MTK is currently grinding C-4 in preparation for shipment to X-Ray
Note on O31: Nancy Horton: Note 14 from e-mail: Pattern set-up & Molding in process for pour in early August
Note on O35: Nancy Horton: Note 15 from e-mail: Documentation & Scheduling for processing of C-6 has commenced with expected pour around the end of August
Note on O12: Nancy Horton: Note 5 from e-mail: C-1 is on the first set-up of the 5 axis machine, and there is still significant learning during this phase. Machining on the 5 axis machine is currently running several days behind the schedule submiitted to PPPL on 7/21/05. MTM has completed 40% of the groove cut and finished 40% of the T, including picking out radius to 1/8th inch. MTM is currently using a 1/4 inch ball nose on the T area and over 28 drill tap holes have been machined.
Note on O16: Nancy Horton: Note 7 from e-mail: MTM is currently roughing the second side of C-2. So far, the part is well on schedule and as predicted, is benefiting from learning on C-1. In the first 4 weeks of machining, MTM has accomplished on C-2 what it took 9 weeks to accomplish on C-1.
Note on D24: Nancy Horton: Note 12 from e-mail: Revised delivery date may impact projected completion for machining. New forecast TBD
Note on O7: Nancy Horton: Note 2 in e-mail: Lawton projects that they are 35 - 40% complete with pattern B. Figure for % complete also includes roughly 5% for Solidification modeling.
Note on O9: Nancy Horton: Note 3 in e-mail: MTK has advised that they are currently investigating market opportunities for the remainder of the materials and project completion of the task as early as 9/30/05 or sooner.

## EIO Monthly Report 7-7-05
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: July 7, 2005
Casting Delivery Sequence |  | Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05 | % compl. 2/05 | % compl. 3/05 | % Complete 4/05 | % Complete 5/05 | % Complete 6/05 | % Complete 7/05
Patterns
| Pattern A complete | 2005-02-10 | 2005-04-01 | 255125 |  | 10% | 18% | 25% | 40% | 98% | 100% | 100% | 100%
| Pattern B complete | 2005-04-12 | 2005-07-01 | 255125 |  | 2% | 7% | 10% | 10% | 15% | 17% | 20% | 25%
| Major Tool Tooling Complete | 2005-02-15 | 2005-03-14 | 555000 |  | 25% | 50% | 60% | 100% | 100% | 100% | 100% | 100%
| Materials (MetalTek) | 2005-12-31 |  | 744746 |  | 5% | 17.6% | 18% | 67% | 67% | 67% | 67% | 67%
1 | C1
| MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-18 | 140808 |  | 0 | 0 | 75% | 90% | 100% | 100% | 100% | 100%
| MTM - machining/inspection | 2005-05-15 | 2005-07-30 | 154912 |  | 0 | 0 | 0 |  | 10% | 30% | 65% | 70%
| Receive at PPPL | 2005-05-16 | 2005-08-01
2 | C2
| MTK-casting | 2005-04-20 | 2005-06-27 | 140808 |  |  |  |  | 5% | 10% | 25% | 50% | 100%
| MTM - machining/inspection | 2005-07-13 | 2005-09-27 | 154912 | [8 empty] | 5%
| Receive at PPPL | 2005-07-14 | 2005-09-29
3 | A1
| MTK-casting | 2005-05-20 | 2005-07-15 | 140808 | [6 empty] | 5% | 20% | 60%
| MTM - machining/inspection | 2005-08-12 | 2005-10-10 | 154912
| Receive at PPPL | 2005-08-15 | 2005-10-13
4 | C3
| MTK-casting | 2005-06-20 | 2005-08-05 | 140808 | [7 empty] | 10% | 50%
| MTM - machining/inspection | 2005-09-14 | 2005-10-31 | 154912
| Receive at PPPL | 2005-09-15 | 2005-11-02
8 | B1
| MTK-casting | 2005-07-21 | 2005-10-28 | 140808
| MTM - machining/inspection | 2005-10-13 | 2006-01-25 | 154912
| Receive at PPPL | 2005-10-14 | 2006-01-27
6 | A2
| MTK-casting | 2005-08-17 | 2005-09-20 | 140808
| MTM - machining/inspection | 2005-11-14 | 2005-12-13 | 154912
| Receive at PPPL | 2005-11-15 | 2005-12-15
11 | A3
| MTK-casting | 2005-09-16 | 2006-01-06 | 140808
| MTM - machining/inspection | 2005-12-14 | 2006-04-04 | 154912
| Receive at PPPL | 2005-12-15 | 2006-04-06
12 | A4
| MTK-casting | 2005-10-17 | 2006-01-20 | 140808
| MTM - machining/inspection | 2006-01-13 | 2006-04-24 | 154912
| Receive at PPPL | 2006-01-16 | 2006-04-26
13 | A5
| MTK-casting | 2005-11-16 | 2006-02-17 | 140808
| MTM - machining/inspection | 2006-02-14 | 2006-05-12 | 154912
| Receive at PPPL | 2006-02-15 | 2006-05-15
14 | A6
| MTK-casting | 2005-12-14 | 2006-03-07 | 140808
| MTM - machining/inspection | 2006-03-14 | 2006-06-05 | 154912
| Receive at PPPL | 2006-03-15 | 2006-06-07
10 | B2
| MTK-casting | 2006-01-13 | 2005-12-09 | 140808
| MTM - machining/inspection | 2006-04-13 | 2006-03-09 | 154912
| Receive at PPPL | 2006-04-14 | 2006-03-13
15 | B3
| MTK-casting | 2006-02-13 | 2006-03-30 | 140808
| MTM - machining/inspection | 2006-05-12 | 2006-06-30 | 154912
| Receive at PPPL | 2006-05-15 | 2006-07-05
16 | B4
| MTK-casting | 2006-03-16 | 2006-04-20 | 140808
| MTM - machining/inspection | 2006-06-14 | 2006-07-18 | 154912
| Receive at PPPL | 2006-06-15 | 2006-07-20
17 | B5
| MTK-casting | 2006-03-28 | 2006-05-12 | 140808
| MTM - machining/inspection | 2006-06-26 | 2006-08-11 | 154912
| Receive at PPPL | 2006-06-27 | 2006-08-15
18 | B6
| MTK-casting | 2006-04-14 | 2006-06-01 | 140808
| MTM - machining/inspection | 2006-07-13 | 2006-08-31 | 154912
| Receive at PPPL | 2006-07-14 | 2006-09-05
5 | C4
| MTK-casting | 2006-05-16 | 2005-08-25 | 140808 | [8 empty] | 40%
| MTM - machining/inspection | 2006-08-14 | 2005-11-20 | 154912
| Receive at PPPL | 2006-08-15 | 2005-11-23
7 | C5
| MTK-casting | 2006-05-30 | 2005-10-07 | 140808
| MTM - machining/inspection | 2006-08-28 | 2006-01-06 | 154912
| Receive at PPPL | 2006-08-29 | 2006-01-09
9 | C6
| MTK-casting | 2006-06-16 | 2005-11-17 | 140808
| MTM - machining/inspection | 2006-09-14 | 2006-02-13 | 154912
| Receive at PPPL | 2006-09-15 | 2016-02-17
| EIO Project Mgt. 24 mos. |  |  | 908828 | 8.333% | 12.5% | 16.6% | 21% | 25% | 29% | 33.3% | 37.5% | 42%
Note on D13: Nancy Horton: Note 5 in e-mail: Projected delivery to PPPL is considered best case. Machining is running behind the milestone schedule presented to PPPL 6/17/05. Per input on 7/7/05, MTM is conducting an internal audit to assess progress and update estimates to complete.
Note on E3: Nancy Horton: For this spreadsheet, "Task Values" were based on rounded calculations which when totaled, result in a deviation from the bottom line negotiated price. Billings will reflect the agreed upon prices in EIO contract.
Note on D11: Nancy Horton: Reference: C-1 casting shipped on 3/31/05 and was placed in the fixture at MTM on 4/1/05.
Note on D19: Nancy Horton: Note 8 from e-mail: First A casting poured on 5/24/05. Anomalies in 3D ScanCo data are currently under review. Impact to casting schedule is as yet unknown; however, C-3 is being expedited by MTK to minimize any potential delay to A-1.
Note on D15: Nancy Horton: Note 6 from e-mail: 6/27/05 reflects the actual date C-2 casting was shipped from MTK. This was 5 days ahead of previously projected schedule of 7/1/05.
Note on D12: Nancy Horton: Note 3 in e-mail: Projected schedule was revised on 6/17 due to complications in machining. Despite the extended leadtime, MTM predicts that learning on C-1 should permit machining of future castings within the 12 week schedule allotment.
Note on D23: Nancy Horton: Note 10 from e-mail: C-3 is currently ahead of projected schedule. MTK has committed to endeavor toward early delivery if possible.
Note on B70: Nancy Horton: Reference: MTK plans to pour C-4 in sequence directly after C-3, making it the 5th casting to be poured.
Note on A3: Nancy Horton: Reference: This column has been added to reflect the sequencing of castings currently projected in this spreadsheet. The sequencing of the first 5 castings is well-established. From the 6th casting forward, there are alternative sequences under consideration.
Note on D73: Nancy Horton: Reference Projected Schedule dates for casting, machining and delivery to PPPL have been updated to reflect revised pouring sequence for C-4
Note on N7: Nancy Horton: Note 1 in e-mail: Lawton estimates that they are 18% complete with pattern build.The 25% complete is calculated to include required effort for solidification modeling, which is peformed by MTK and ESI.
Note on N19: Nancy Horton: Note 9 in e-mail: A-1 is through X-ray and is in preparation for upgrade
Note on N23: Nancy Horton: Note 11 in e-mail: C-3 was poured on 6/10/05 and is currently in X-ray
Note on N71: Nancy Horton: Note 12 in e-mail: Figure of 40% represents % complete after casting is poured. C-4 is scheduled to pour 7/8/05. Set-up for pour is complete.
Note on N12: Nancy Horton: Note 4 in e-mail: The leadtime for semi-finish machining was significantly longer than inititial predictions. As of 7/7, the first side flange face and part periphery were finished (including holes) and the "T" section was semi-finished machined to .030" envelope. The part has now been flipped in the 3-axis machine and machining of the second side is underway.
Note on N9: Nancy Horton: Note 2 in e-mail: MTK has advised that they are currently investigating market opportunities for the remainder of the materials and project completion of the task as early as 9/30/05 or sooner.
Note on N16: Nancy Horton: Note 7 from e-mail: C-2 was received at MTM on 6/28 and set-up in the fixture was completed on 7/1. Machining of the part has commenced.

## EIO Monthly Report 6-2-05
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: June 2, 2005
Casting Delivery Sequence |  | Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05 | % compl. 2/05 | % compl. 3/05 | % Complete 4/05 | % Complete 5/05 | % Complete 6/05
Patterns
| Pattern A complete | 2005-02-10 | 2005-04-01 | 255125 |  | 10% | 18% | 25% | 40% | 98% | 100% | 100%
| Pattern B complete | 2005-04-12 | 2005-07-01 | 255125 |  | 2% | 7% | 10% | 10% | 15% | 17% | 20%
| Major Tool Tooling Complete | 2005-02-15 | 2005-03-14 | 555000 |  | 25% | 50% | 60% | 100% | 100% | 100% | 100%
| Materials (MetalTek) | 2005-12-31 |  | 744746 |  | 5% | 17.6% | 18% | 67% | 67% | 67% | 67%
1 | C1
| MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-18 | 140808 |  | 0 | 0 | 75% | 90% | 100% | 100% | 100%
| MTM - machining/inspection | 2005-05-15 | 2005-07-06 | 154912 |  | 0 | 0 | 0 |  | 10% | 30% | 65%
| Receive at PPPL | 2005-05-16 | 2005-07-07
2 | C2
| MTK-casting | 2005-04-20 | 2005-07-01 | 140808 |  |  |  |  | 5% | 10% | 25% | 50%
| MTM - machining/inspection | 2005-07-13 | 2005-09-27 | 154912
| Receive at PPPL | 2005-07-14 | 2005-09-29
3 | A1
| MTK-casting | 2005-05-20 | 2005-07-15 | 140808 | [6 empty] | 5% | 20%
| MTM - machining/inspection | 2005-08-12 | 2005-10-10 | 154912
| Receive at PPPL | 2005-08-15 | 2005-10-13
4 | C3
| MTK-casting | 2005-06-20 | 2005-08-05 | 140808 | [7 empty] | 10%
| MTM - machining/inspection | 2005-09-14 | 2005-10-31 | 154912
| Receive at PPPL | 2005-09-15 | 2005-11-02
8 | B1
| MTK-casting | 2005-07-21 | 2005-10-28 | 140808
| MTM - machining/inspection | 2005-10-13 | 2006-01-25 | 154912
| Receive at PPPL | 2005-10-14 | 2006-01-27
6 | A2
| MTK-casting | 2005-08-17 | 2005-09-20 | 140808
| MTM - machining/inspection | 2005-11-14 | 2005-12-13 | 154912
| Receive at PPPL | 2005-11-15 | 2005-12-15
11 | A3
| MTK-casting | 2005-09-16 | 2006-01-06 | 140808
| MTM - machining/inspection | 2005-12-14 | 2006-04-04 | 154912
| Receive at PPPL | 2005-12-15 | 2006-04-06
12 | A4
| MTK-casting | 2005-10-17 | 2006-01-20 | 140808
| MTM - machining/inspection | 2006-01-13 | 2006-04-24 | 154912
| Receive at PPPL | 2006-01-16 | 2006-04-26
13 | A5
| MTK-casting | 2005-11-16 | 2006-02-17 | 140808
| MTM - machining/inspection | 2006-02-14 | 2006-05-12 | 154912
| Receive at PPPL | 2006-02-15 | 2006-05-15
14 | A6
| MTK-casting | 2005-12-14 | 2006-03-07 | 140808
| MTM - machining/inspection | 2006-03-14 | 2006-06-05 | 154912
| Receive at PPPL | 2006-03-15 | 2006-06-07
10 | B2
| MTK-casting | 2006-01-13 | 2005-12-09 | 140808
| MTM - machining/inspection | 2006-04-13 | 2006-03-09 | 154912
| Receive at PPPL | 2006-04-14 | 2006-03-13
15 | B3
| MTK-casting | 2006-02-13 | 2006-03-30 | 140808
| MTM - machining/inspection | 2006-05-12 | 2006-06-30 | 154912
| Receive at PPPL | 2006-05-15 | 2006-07-05
16 | B4
| MTK-casting | 2006-03-16 | 2006-04-20 | 140808
| MTM - machining/inspection | 2006-06-14 | 2006-07-18 | 154912
| Receive at PPPL | 2006-06-15 | 2006-07-20
17 | B5
| MTK-casting | 2006-03-28 | 2006-05-12 | 140808
| MTM - machining/inspection | 2006-06-26 | 2006-08-11 | 154912
| Receive at PPPL | 2006-06-27 | 2006-08-15
18 | B6
| MTK-casting | 2006-04-14 | 2006-06-01 | 140808
| MTM - machining/inspection | 2006-07-13 | 2006-08-31 | 154912
| Receive at PPPL | 2006-07-14 | 2006-09-05
5 | C4
| MTK-casting | 2006-05-16 | 2005-08-25 | 140808
| MTM - machining/inspection | 2006-08-14 | 2005-11-20 | 154912
| Receive at PPPL | 2006-08-15 | 2005-11-23
7 | C5
| MTK-casting | 2006-05-30 | 2005-10-07 | 140808
| MTM - machining/inspection | 2006-08-28 | 2006-01-06 | 154912
| Receive at PPPL | 2006-08-29 | 2006-01-09
9 | C6
| MTK-casting | 2006-06-16 | 2005-11-17 | 140808
| MTM - machining/inspection | 2006-09-14 | 2006-02-13 | 154912
| Receive at PPPL | 2006-09-15 | 2016-02-17
| EIO Project Mgt. 24 mos. |  |  | 908828 | 8.333% | 12.5% | 16.6% | 21% | 25% | 29% | 33.3% | 37.5%
Note on D13: Nancy Horton: Note 5 in e-mail: Projected delivery to PPPL is currently 7/7/05.
Note on E3: Nancy Horton: For this spreadsheet, "Task Values" were based on rounded calculations which when totaled, result in a deviation from the bottom line negotiated price. Billings will reflect the agreed upon prices in EIO contract.
Note on D11: Nancy Horton: Reference: C-1 casting shipped on 3/31/05 and was placed in the fixture at MTM on 4/1/05.
Note on D19: Nancy Horton: Note 7 from e-mail: First A casting poured on 5/24/05 and looks great! Metal Tek is still planning for the 7/15 delivery date to MTM
Note on D15: Nancy Horton: Note 6 from e-mail: C-2 casting is currently on schedule for delivery to MTM as projected
Note on M7: Nancy Horton: Note 2 in e-mail: Solidification Modeling of B was completed on 5-27-05 and Lawton has initiated full production of B pattern
Note on M12: Nancy Horton: Note 4 from e-mail: Semi Finish machining is expected to be complete by June 6. Major Tool is currently projecting 14.5 weeks for machining which will change casting delivery to 7/7/05.
Note on D12: Nancy Horton: Note 3 in e-mail: Projected schedule has been revised due to complications in machining. Learning on C-1 should permit machining of future castings within the 12 week schedule allotment.
Note on M23: Nancy Horton: Note 9 from e-mail: Pattern set-up is complete for pouring C-3 on 6-7-05
Note on D23: Nancy Horton: Note 8 from e-mail: According to MTK, C-3 is still on schedule for projected delivery to MTM
Note on B70: Nancy Horton: Note 10 from e-mail: MTK now plans to pour C-4 in sequence directly after C-3, making it the 5th casting to be poured.
Note on A3: Nancy Horton: Note 1 in e-mail: This column has been added to reflect the sequencing of castings currently projected in this spreadsheet. The sequencing of the first 5 castings is well-established. From the 6th casting forward, there are alternative sequenes under consideration.
Note on D73: Nancy Horton: Note 11 from e-mail: Projected Schedule dates for casting, machining and delivery to PPPL have been updated to reflect revised pouring sequence for C-4

## EIO Monthly Report 5-6-05
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: May 6, 2005
| Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05 | % compl. 2/05 | % compl. 3/05 | % Complete 4/05 | % Complete 5/05
Patterns
Pattern A complete | 2005-02-10 | 2005-04-01 | 255125 |  | 10% | 18% | 25% | 40% | 98% | 100%
Pattern B complete | 2005-04-12 | 2005-07-01 | 255125 |  | 2% | 7% | 10% | 10% | 15% | 17%
Major Tool Tooling Complete | 2005-02-15 | 2005-03-14 | 555000 |  | 25% | 50% | 60% | 100% | 100% | 100%
Materials (MetalTek) | 2005-12-31 |  | 744746 |  | 5% | 17.6% | 18% | 67% | 67% | 67%
C1
MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-18 | 140808 |  | 0 | 0 | 75% | 90% | 100% | 100%
MTM - machining/inspection | 2005-05-15 | 2005-06-22 | 154912 |  | 0 | 0 | 0 |  | 10% | 30%
Receive at PPPL | 2005-05-16 | 2005-06-24
C2
MTK-casting | 2005-04-20 | 2005-07-01 | 140808 |  |  |  |  | 5% | 10% | 25%
MTM - machining/inspection | 2005-07-13 | 2005-09-27 | 154912
Receive at PPPL | 2005-07-14 | 2005-09-29
A1
MTK-casting | 2005-05-20 | 2005-07-15 | 140808 | [6 empty] | 5%
MTM - machining/inspection | 2005-08-12 | 2005-10-10 | 154912
Receive at PPPL | 2005-08-15 | 2005-10-13
C3
MTK-casting | 2005-06-20 | 2005-08-05 | 140808
MTM - machining/inspection | 2005-09-14 | 2005-10-31 | 154912
Receive at PPPL | 2005-09-15 | 2005-11-02
B1
MTK-casting | 2005-07-21 | 2005-10-28 | 140808
MTM - machining/inspection | 2005-10-13 | 2006-01-06 | 154912
Receive at PPPL | 2005-10-14 | 2006-01-09
A2
MTK-casting | 2005-08-17 | 2005-08-25 | 140808
MTM - machining/inspection | 2005-11-14 | 2005-11-20 | 154912
Receive at PPPL | 2005-11-15 | 2005-11-23
A3
MTK-casting | 2005-09-16 | 2006-01-06 | 140808
MTM - machining/inspection | 2005-12-14 | 2006-04-04 | 154912
Receive at PPPL | 2005-12-15 | 2006-04-06
A4
MTK-casting | 2005-10-17 | 2006-01-20 | 140808
MTM - machining/inspection | 2006-01-13 | 2006-04-24 | 154912
Receive at PPPL | 2006-01-16 | 2006-04-26
A5
MTK-casting | 2005-11-16 | 2006-02-17 | 140808
MTM - machining/inspection | 2006-02-14 | 2006-05-12 | 154912
Receive at PPPL | 2006-02-15 | 2006-05-15
A6
MTK-casting | 2005-12-14 | 2006-03-07 | 140808
MTM - machining/inspection | 2006-03-14 | 2006-06-05 | 154912
Receive at PPPL | 2006-03-15 | 2006-06-07
B2
MTK-casting | 2006-01-13 | 2005-12-09 | 140808
MTM - machining/inspection | 2006-04-13 | 2006-03-09 | 154912
Receive at PPPL | 2006-04-14 | 2006-03-13
B3
MTK-casting | 2006-02-13 | 2006-03-30 | 140808
MTM - machining/inspection | 2006-05-12 | 2006-06-30 | 154912
Receive at PPPL | 2006-05-15 | 2006-07-05
B4
MTK-casting | 2006-03-16 | 2006-04-20 | 140808
MTM - machining/inspection | 2006-06-14 | 2006-07-18 | 154912
Receive at PPPL | 2006-06-15 | 2006-07-20
B5
MTK-casting | 2006-03-28 | 2006-05-12 | 140808
MTM - machining/inspection | 2006-06-26 | 2006-08-11 | 154912
Receive at PPPL | 2006-06-27 | 2006-08-15
B6
MTK-casting | 2006-04-14 | 2006-06-01 | 140808
MTM - machining/inspection | 2006-07-13 | 2006-08-31 | 154912
Receive at PPPL | 2006-07-14 | 2006-09-05
C4
MTK-casting | 2006-05-16 | 2005-09-15 | 140808
MTM - machining/inspection | 2006-08-14 | 2005-12-13 | 154912
Receive at PPPL | 2006-08-15 | 2005-12-15
C5
MTK-casting | 2006-05-30 | 2005-10-07 | 140808
MTM - machining/inspection | 2006-08-28 | 2006-01-06 | 154912
Receive at PPPL | 2006-08-29 | 2006-01-09
C6
MTK-casting | 2006-06-16 | 2005-11-17 | 140808
MTM - machining/inspection | 2006-09-14 | 2006-02-13 | 154912
Receive at PPPL | 2006-09-15 | 2016-02-17
EIO Project Mgt. 24 mos. |  |  | 908828 | 8.333% | 12.5% | 16.6% | 21% | 25% | 29% | 33.3%
Note on C13: Nancy Horton: Note 2 in e-mail: At this time, 6/24/05 is still the projected delivery date to PPPL.
Note on D3: Nancy Horton: For this spreadsheet, "Task Values" were based on rounded calculations which when totaled, result in a deviation from the bottom line negotiated price. Billings will reflect the agreed upon prices in EIO contract.
Note on C11: Nancy Horton: Reference: C-1 casting shipped on 3/31/05 and was placed in the fixture at MTM on 4/1/05.
Note on C19: Nancy Horton: Note 4 from e-mail: Set-up of A Pattern is in progress and A-1 is rescheduled to pour on 5/10/05; however Metal Tek anticipates holding the 7/15 delivery date to MTM
Note on K7: Nancy Horton: Note 1 from e-mail: Solidification Modeling of B Pattern is underway and completion is currently projected for 6/1/05. Some modeling of the pattern has also been accomplished.
Note on A26: Nancy Horton: Note 5 from e-mail: Projected pour date for B-1 has been pushed out by one month to accommodate complexities in Solidification Modeling. An alternative casting (C-5 in this schedule's scenario) will be poured in its place that month.
Note on A74: Nancy Horton: Note 6 from e-mail: Production Schedule for C-5 Casting has been moved up by one month to accommodate change in B Pattern development leadtime (ensuring continuous pouring every 3 weeks)
Note on C15: Nancy Horton: Note 3 from e-mail: C-2 casting is currently on or ahead of projected delivery schedule to MTM.

## EIO Monthly Report 4-4-05
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: April 4, 2005
| Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05 | % compl. 2/05 | % compl. 3/05 | % Complete 4/05
Patterns
Pattern A complete | 2005-02-10 | 2005-04-01 | 255125 |  | 10% | 18% | 25% | 40% | 98%
Pattern B complete | 2005-04-12 | 2005-07-01 | 255125 |  | 2% | 7% | 10% | 10% | 15%
Major Tool Tooling Complete | 2005-02-15 | 2005-03-14 | 555000 |  | 25% | 50% | 60% | 100% | 100%
Materials (MetalTek) | 2005-12-31 |  | 744746 |  | 5% | 17.6% | 18% | 67% | 67%
C1
MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-18 | 140808 |  | 0 | 0 | 75% | 90% | 100%
MTM - machining/inspection | 2005-05-15 | 2005-06-22 | 154912 |  | 0 | 0 | 0 |  | 10%
Receive at PPPL | 2005-05-16 | 2005-06-24
C2
MTK-casting | 2005-04-20 | 2005-07-01 | 140808 |  |  |  |  | 5% | 10%
MTM - machining/inspection | 2005-07-13 | 2005-09-27 | 154912
Receive at PPPL | 2005-07-14 | 2005-09-29
A1
MTK-casting | 2005-05-20 | 2005-07-15 | 140808
MTM - machining/inspection | 2005-08-12 | 2005-10-10 | 154912
Receive at PPPL | 2005-08-15 | 2005-10-13
C3
MTK-casting | 2005-06-20 | 2005-08-05 | 140808
MTM - machining/inspection | 2005-09-14 | 2005-10-31 | 154912
Receive at PPPL | 2005-09-15 | 2005-11-02
B1
MTK-casting | 2005-07-21 | 2005-10-07 | 140808
MTM - machining/inspection | 2005-10-13 | 2006-01-06 | 154912
Receive at PPPL | 2005-10-14 | 2006-01-09
A2
MTK-casting | 2005-08-17 | 2005-08-25 | 140808
MTM - machining/inspection | 2005-11-14 | 2005-11-20 | 154912
Receive at PPPL | 2005-11-15 | 2005-11-23
A3
MTK-casting | 2005-09-16 | 2006-01-06 | 140808
MTM - machining/inspection | 2005-12-14 | 2006-04-04 | 154912
Receive at PPPL | 2005-12-15 | 2006-04-06
A4
MTK-casting | 2005-10-17 | 2006-01-20 | 140808
MTM - machining/inspection | 2006-01-13 | 2006-04-24 | 154912
Receive at PPPL | 2006-01-16 | 2006-04-26
A5
MTK-casting | 2005-11-16 | 2006-02-17 | 140808
MTM - machining/inspection | 2006-02-14 | 2006-05-12 | 154912
Receive at PPPL | 2006-02-15 | 2006-05-15
A6
MTK-casting | 2005-12-14 | 2006-03-07 | 140808
MTM - machining/inspection | 2006-03-14 | 2006-06-05 | 154912
Receive at PPPL | 2006-03-15 | 2006-06-07
B2
MTK-casting | 2006-01-13 | 2005-12-09 | 140808
MTM - machining/inspection | 2006-04-13 | 2006-03-09 | 154912
Receive at PPPL | 2006-04-14 | 2006-03-13
B3
MTK-casting | 2006-02-13 | 2006-03-30 | 140808
MTM - machining/inspection | 2006-05-12 | 2006-06-30 | 154912
Receive at PPPL | 2006-05-15 | 2006-07-05
B4
MTK-casting | 2006-03-16 | 2006-04-20 | 140808
MTM - machining/inspection | 2006-06-14 | 2006-07-18 | 154912
Receive at PPPL | 2006-06-15 | 2006-07-20
B5
MTK-casting | 2006-03-28 | 2006-05-12 | 140808
MTM - machining/inspection | 2006-06-26 | 2006-08-11 | 154912
Receive at PPPL | 2006-06-27 | 2006-08-15
B6
MTK-casting | 2006-04-14 | 2006-06-01 | 140808
MTM - machining/inspection | 2006-07-13 | 2006-08-31
Receive at PPPL | 2006-07-14 | 2006-09-05 | 154912
C4
MTK-casting | 2006-05-16 | 2005-09-15 | 140808
MTM - machining/inspection | 2006-08-14 | 2005-12-13 | 154912
Receive at PPPL | 2006-08-15 | 2005-12-15
C5
MTK-casting | 2006-05-30 | 2005-10-28 | 140808
MTM - machining/inspection | 2006-08-28 | 2006-01-25 | 154912
Receive at PPPL | 2006-08-29 | 2006-01-27
C6
MTK-casting | 2006-06-16 | 2005-11-17 | 140808
MTM - machining/inspection | 2006-09-14 | 2006-02-13 | 154912
Receive at PPPL | 2006-09-15 | 2016-02-17
EIO Project Mgt. 24 mos. |  |  | 908828 | 8.333% | 12.5% | 16.6% | 21% | 25% | 29%
Note on C13: Nancy Horton: Note 6 in e-mail: At this time, 6/24/05 is the projected delivery date to PPPL.
Note on D3: Nancy Horton: For this spreadsheet, "Task Values" were based on rounded calculations which when totaled, result in a deviation from the bottom line negotiated price. Billings will reflect the agreed upon prices in EIO contract.
Note on C11: Nancy Horton: Note 4 from e-mail: C-1 casting shipped on 3/31/05 and was placed in the fixture at MTM on 4/1/05. C-1 casting upgrade is now 100% complete.
Note on C12: Nancy Horton: Note 5 from e-mail: Projected schedule based on a 12 week leadtime. MTM is committed to seeking efficiencies and schedule gain where possible. Reassessment of leadtime planned for 4/29/05. Any changes will be noted in next month's report.
Note on J15: Nancy Horton: Note 8 from e-mail: Estimate of 10% reflects continued progress on upgraded C pattern. Reiteration of Solidification Modeling of C is complete and Pattern upgrade is nearly complete. One week slip in pour date is due to making chill patterns at local shop (chills are being produced the week of 4/4/05). Chills are used as heat-sinks to intensify the directional solidification. C-2 casting is scheduled to be poured on 4/15/05.
Note on J9: Nancy Horton: Note 3 from e-mail: Purchase of the 316 metal is complete. Purchase of remaining precious metals (includes trim elements) is under review for favorable market conditions.
Note on J6: Nancy Horton: Note 1 from e-mail: Fabrication of Pattern A is complete and the part has been scanned by 3D ScanCo. Review process is underway for anticipated shipment to Metal Tek.
Note on J7: Nancy Horton: Note 2 from e-mail: Solidification Modeling of B Pattern is ready to commence. Some modeling of the pattern has also been accomplished.
Note on C15: Nancy Horton: Note 7 from e-mail: New projected schedule date of 7/1/05 is based on 12 week casting lead-time commencing 4/15/05 (revised planned pour date for C-2).
Note on C19: Nancy Horton: Note 9 from e-mail: A-1 is still scheduled to pour on 4/22/05

## EIO Monthly Report 3-4-05
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: March 4, 2005
| Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05 | % compl. 2/05 | % compl. 3/05
Patterns
Pattern A complete | 2005-02-10 | 2005-04-01 | 255125 |  | 10% | 18% | 25% | 40%
Pattern B complete | 2005-04-12 | 2005-07-01 | 255125 |  | 2% | 7% | 10% | 10%
Major Tool Tooling Complete | 2005-02-15 | 2005-03-14 | 555000 |  | 25% | 50% | 60% | 100%
Materials (MetalTek) | 2005-12-31 |  | 744746 |  | 5% | 17.6% | 18% | 67%
C1
MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-18 | 140808 |  | 0 | 0 | 75% | 90%
MTM - machining/inspection | 2005-05-15 | 2005-06-12 | 154912 |  | 0 | 0 | 0
Receive at PPPL | 2005-05-16 | 2005-06-15
C2
MTK-casting | 2005-04-20 | 2005-06-23 | 140808 |  |  |  |  | 5%
MTM - machining/inspection | 2005-07-13 | 2005-09-19 | 154912
Receive at PPPL | 2005-07-14 | 2005-09-22
A1
MTK-casting | 2005-05-20 | 2005-07-15 | 140808
MTM - machining/inspection | 2005-08-12 | 2005-10-10 | 154912
Receive at PPPL | 2005-08-15 | 2005-10-13
C3
MTK-casting | 2005-06-20 | 2005-08-05 | 140808
MTM - machining/inspection | 2005-09-14 | 2005-10-31 | 154912
Receive at PPPL | 2005-09-15 | 2005-11-02
B1
MTK-casting | 2005-07-21 | 2005-10-07 | 140808
MTM - machining/inspection | 2005-10-13 | 2006-01-06 | 154912
Receive at PPPL | 2005-10-14 | 2006-01-09
A2
MTK-casting | 2005-08-17 | 2005-08-25 | 140808
MTM - machining/inspection | 2005-11-14 | 2005-11-20 | 154912
Receive at PPPL | 2005-11-15 | 2005-11-23
A3
MTK-casting | 2005-09-16 | 2006-01-06 | 140808
MTM - machining/inspection | 2005-12-14 | 2006-04-04 | 154912
Receive at PPPL | 2005-12-15 | 2006-04-06
A4
MTK-casting | 2005-10-17 | 2006-01-20 | 140808
MTM - machining/inspection | 2006-01-13 | 2006-04-24 | 154912
Receive at PPPL | 2006-01-16 | 2006-04-26
A5
MTK-casting | 2005-11-16 | 2006-02-17 | 140808
MTM - machining/inspection | 2006-02-14 | 2006-05-12 | 154912
Receive at PPPL | 2006-02-15 | 2006-05-15
A6
MTK-casting | 2005-12-14 | 2006-03-07 | 140808
MTM - machining/inspection | 2006-03-14 | 2006-06-05 | 154912
Receive at PPPL | 2006-03-15 | 2006-06-07
B2
MTK-casting | 2006-01-13 | 2005-12-09 | 140808
MTM - machining/inspection | 2006-04-13 | 2006-03-09 | 154912
Receive at PPPL | 2006-04-14 | 2006-03-13
B3
MTK-casting | 2006-02-13 | 2006-03-30 | 140808
MTM - machining/inspection | 2006-05-12 | 2006-06-30 | 154912
Receive at PPPL | 2006-05-15 | 2006-07-05
B4
MTK-casting | 2006-03-16 | 2006-04-20 | 140808
MTM - machining/inspection | 2006-06-14 | 2006-07-18 | 154912
Receive at PPPL | 2006-06-15 | 2006-07-20
B5
MTK-casting | 2006-03-28 | 2006-05-12 | 140808
MTM - machining/inspection | 2006-06-26 | 2006-08-11 | 154912
Receive at PPPL | 2006-06-27 | 2006-08-15
B6
MTK-casting | 2006-04-14 | 2006-06-01 | 140808
MTM - machining/inspection | 2006-07-13 | 2006-08-31
Receive at PPPL | 2006-07-14 | 2006-09-05 | 154912
C4
MTK-casting | 2006-05-16 | 2005-09-15 | 140808
MTM - machining/inspection | 2006-08-14 | 2005-12-13 | 154912
Receive at PPPL | 2006-08-15 | 2005-12-15
C5
MTK-casting | 2006-05-30 | 2005-10-28 | 140808
MTM - machining/inspection | 2006-08-28 | 2006-01-25 | 154912
Receive at PPPL | 2006-08-29 | 2006-01-27
C6
MTK-casting | 2006-06-16 | 2005-11-17 | 140808
MTM - machining/inspection | 2006-09-14 | 2006-02-13 | 154912
Receive at PPPL | 2006-09-15 | 2016-02-17
EIO Project Mgt. 24 mos. |  |  | 908828 | 8.333% | 12.5% | 16.6% | 21% | 25%
Note on A5: Nancy Horton: Note 1 from e-mail: Several items are included under the heading of Patterns. Patterns A, B & C: Lessons learned from the pouring of the first Coil C-1 are being evaluated for improvements to the patterns for all three coil types. Several iterations of the solidification models have been pursued. --Upon satisfactory completion of solidification modeling, Rework of Coil C pattern will be required. Completion is anticipated on or around March 25, 2005. -- A Pattern production is proceeding with a scheduled completion date of 4/1/05 -- B Pattern is currently on hold pending outcome of solidification model reiterations. Major Tool Tooling: Fixtures/Tooling complete except for set-up procedures which will be conducted upon receipt of the castings. Materials: Metal Tek secured a contract for all of the 316 metal required under the contract. Purchase of remaining precious metals still under close analysis.
Note on C13: Nancy Horton: Note 10 in e-mail: New projected delivery schedule of C-1 casting to PPPL is mid June.
Note on D3: Nancy Horton: For this spreadsheet, "Task Values" were based on rounded calculations which when totaled, result in a deviation from the bottom line negotiated price. Billings will reflect the agreed upon prices in EIO contract.
Note on C6: Nancy Horton: Note 2 from e-mail: During a team telecon on March 1, 2005, Lawton advised that they are working diligently toward meeting this date.
Note on C11: Nancy Horton: Note 7 from e-mail: Due to the significant weld repair required on C-1, the projected delivery schedule to Major Tool was updated to March 18, 2005. This translates to a casting lead-time of 13 weeks, which is only one week off proposed projections for casting schedule. Considering the challenges encountered, this is quite an accomplishment by the foundry and lends credibility to the remaining leadtime projections.
Note on C12: Nancy Horton: Note 9 from e-mail: The machining leadtime is 12 weeks from date of delivery of the casting. Major Tool has endeavored to capitalize on learning from the prototype and is optimistic that this schedule is attainable.
Note on C7: Nancy Horton: Note 3 from e-mail: Lawton has projected that they will deliver the Coil B Pattern around July 1, 2005. Per telecon 3-1-05, this projection is still accurate.
Note on A18: Nancy Horton: Note 13 from e-mail: If A Pattern is complete by April 1, 2005, then Metal Tek will pour the first A casting in mid April. If the A Pattern is not complete, the foundry will continue to pour C castings in order to maintain schedule.
Note on A14: Nancy Horton: Note 11 from e-mail: The EIO team members have assessed the most practical and efficient sequence for pouring and machining castings. This schedule is in part dictated by the availability of the patterns. Metal Tek plans to pour C-2 after insight gained on C-1 has been incorporated into the process. The dates reflected for the remainder of the castings reflect the most likely scenario in the event that the A Pattern is complete by 4/1 and the B Pattern by 7/1.
Note on I8: Nancy Horton: note #6 from e-mail: Kevin Blowing of Major Tool reports: "We are complete with the programming and machining of the fixtures. The only remaining work to the fixtures will be for optimization of setup. We are performing some experimental machining that may yield the need for making some changes to the fixtures, but for work scope purposes I call it complete."
Note on I11: Nancy Horton: Note #8 from e-mail: Joe Edwards of Metal Tek reports that weld repair on C-1 is nearly complete at which time the part will be sent for final radiography and inspection. As a result, part is estimated at 90% complete.
Note on I15: Nancy Horton: Note # 12 from e-mail: The figure of 5% is used to minimally reflect the significant effort being expended to run new iterations of the solidification model and subsequently rework the pattern to ensure an enhanced pour of C-2.
Note on I7: Nancy Horton: Note #5 from e-mail: No progress toward completion is being reported, although the significant activity in the rework of the solidification models for A and C will no doubt contribute to accelerated progress on B.
Note on I6: Nancy Horton: Note #4 from e-mail: Lawton is working overtime to complete the pattern by April 1, 2005. Thus far, they estimate that they are 40% complete. Time Wenninger reports that they intend to hold an internal meeting on 3/14/05 to assess progress and will report any changes in projected delivery date at that time.

## EIO Monthly Report 2-3-05
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: February 3, 2005
| Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05 | % compl. 2/05
Patterns
Pattern A complete | 2005-02-10 | 2005-04-01 | 255125 |  | 10% | 18% | 25%
Pattern B complete | 2005-04-12 | 2005-07-01 | 255125 |  | 2% | 7% | 10%
Major Tool Tooling Complete | 2005-02-15 |  | 555000 |  | 25% | 50% | 60%
Materials (MetalTek) | 2005-12-31 |  | 744746 |  | 5% | 17.6% | 18%
C1
MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-02-21 | 140808 |  | 0 | 0 | 75%
MTM - machining/inspection | 2005-05-15 | 2005-05-15 | 154912 |  | 0 | 0 | 0
Receive at PPPL | 2005-05-16 | 2005-05-27
C2
MTK-casting | 2005-04-20 | 2005-05-23 | 140808
MTM - machining/inspection | 2005-07-13 | 2005-08-15 | 154912
Receive at PPPL | 2005-07-14 | 2005-08-17
A1
MTK-casting | 2005-05-20 | 2005-06-25 | 140808
MTM - machining/inspection | 2005-08-12 | 2005-09-16 | 154912
Receive at PPPL | 2005-08-15 | 2005-09-20
C3
MTK-casting | 2005-06-20 |  | 140808
MTM - machining/inspection | 2005-09-14 |  | 154912
Receive at PPPL | 2005-09-15
B1
MTK-casting | 2005-07-21 |  | 140808
MTM - machining/inspection | 2005-10-13 |  | 154912
Receive at PPPL | 2005-10-14
A2
MTK-casting | 2005-08-17 |  | 140808
MTM - machining/inspection | 2005-11-14 |  | 154912
Receive at PPPL | 2005-11-15
A3
MTK-casting | 2005-09-16 | 2005-09-15 | 140808
MTM - machining/inspection | 2005-12-14 |  | 154912
Receive at PPPL | 2005-12-15
A4
MTK-casting | 2005-10-17 | 2005-10-05 | 140808
MTM - machining/inspection | 2006-01-13 |  | 154912
Receive at PPPL | 2006-01-16
A5
MTK-casting | 2005-11-16 | 2005-10-26 | 140808
MTM - machining/inspection | 2006-02-14 |  | 154912
Receive at PPPL | 2006-02-15
A6
MTK-casting | 2005-12-14 | 2005-11-15 | 140808
MTM - machining/inspection | 2006-03-14 |  | 154912
Receive at PPPL | 2006-03-15
B2
MTK-casting | 2006-01-13 | 2005-12-08 | 140808
MTM - machining/inspection | 2006-04-13 |  | 154912
Receive at PPPL | 2006-04-14
B3
MTK-casting | 2006-02-13 | 2006-01-05 | 140808
MTM - machining/inspection | 2006-05-12 |  | 154912
Receive at PPPL | 2006-05-15
B4
MTK-casting | 2006-03-16 | 2006-01-25 | 140808
MTM - machining/inspection | 2006-06-14 |  | 154912
Receive at PPPL | 2006-06-15
B5
MTK-casting | 2006-03-28 | 2006-02-15 | 140808
MTM - machining/inspection | 2006-06-26 |  | 154912
Receive at PPPL | 2006-06-27
B6
MTK-casting | 2006-04-14 | 2006-03-08 | 140808
MTM - machining/inspection | 2006-07-13
Receive at PPPL | 2006-07-14 |  | 154912
C4
MTK-casting | 2006-05-16 | 2006-03-31 | 140808
MTM - machining/inspection | 2006-08-14 |  | 154912
Receive at PPPL | 2006-08-15
C5
MTK-casting | 2006-05-30 | 2006-04-24 | 140808
MTM - machining/inspection | 2006-08-28 |  | 154912
Receive at PPPL | 2006-08-29
C6
MTK-casting | 2006-06-16 | 2006-05-14 | 140808
MTM - machining/inspection | 2006-09-14 |  | 154912
Receive at PPPL | 2006-09-15
EIO Project Mgt. 24 mos. |  |  | 908828 | 8.333% | 12.5% | 16.6% | 21%
Note on A5: Nancy Horton: Note 1 from e-mail: Several items are included under the heading of Patterns. Patterns A, B & C: Lessons learned from the pouring of the first Coil C-1 are being evaluated for improvements to the patterns for all three coil types. Additional solidification modeling has been conducted and enhancements to benefit the foundry are being reviewed. Major Tool Tooling: More than 85% of the programming for machining of Coil C and more than 50% of the programming for Coils A & B have been completed Materials: Presumably as a result of continued high prices in the metals market, no material purchases were reported this month by Metal Tek
Note on C13: Nancy Horton: Note 10 in e-mail: As previously reported, the first hardware deliverable under this contract will be the NCSX Winding Form referred to as C-1. Early effort toward the production of C-1 was performed under concurrent EIO contract S-04341-F, Change Order 5. Success during the fabrication of the Coil C-1 has enabled us to regain schedule advantage. Currently Metal Tek projects delivery of C-1 to Major Tool on or about 2/21/05 which could potentially put the team fully on schedule to deliver to PPPL by 5/16/05.
Note on D3: Nancy Horton: For this spreadsheet, "Task Values" were based on rounded calculations which when totaled, result in a deviation from the bottom line negotiated price. Billings will reflect the agreed upon prices in EIO contract.
Note on C6: Nancy Horton: Note 2 from e-mail: During the team meeting on January 18, 2005, Lawton reported that this was the new estimated completion date for the A pattern. Since then and as a result of solidification modeling, the schedule for completion of the Coil A Pattern will potentially slip beyond this date. This issue is currently under evaluation between Lawton and Metal Tek and no new completion date has been established.
Note on H6: Nancy Horton: Note 4 from e-mail: While progress has been made on the A Pattern, recent results from Solidification Modeling indicate that some changes in pattern design could provide new opportunities to capitalize on learning from C-1. These matters are currently under review at Metal Tek and Lawton and the full impact is not known.
Note on H7: Nancy Horton: Note 5 from e-mail: To date, Solidification Modeling for Coil B has gone through 2 iterations and is currently on hold pending resolution of modeling issues on A and C.
Note on H8: Nancy Horton: Note 6 from e-mail: Programming for the Coil C machine fixture is nearly complete and will be ready in time for delivery of C-1 to Major Tool. Programming has also commenced for the A and B Coils.
Note on C11: Nancy Horton: Note 7 from e-mail: As a result of Metal Tek's success in pouring the C-1 casting, upgrade is progressing well, allowing Metal Tek to improve upon earlier schedule projections and enabling delivery to Major Tool within the baseline schedule.
Note on C12: Nancy Horton: Note 9 from e-mail: Delivery of the Casting to Major Tool within the baseline schedule should enable Major Tool to complete the machining within the baseline schedule.
Note on C19: Nancy Horton: Note 13 from e-mail: Revised schedule for pattern delivery will impact the projected schedule date for casting A-1
Note on C7: Nancy Horton: Note 3 from e-mail: Lawton has projected that they will deliver the Coil B Pattern around July 1, 2005. Challenges resulting from solidification modeling could further impact this projection.
Note on A18: Nancy Horton: Note 12 from e-mail: PPPL has requested that EIO endeavor to deliver 8 castings by January 2006, with at least one each of type A, B and C. The opportunities and practicalities to meet this request are currently under evaluation by the EIO team members.
Note on A14: Nancy Horton: Note 11 from e-mail: The EIO team members are currently assessing the most practical and efficient sequence for pouring and machining castings. This schedule is in part dictated by the availability of the patterns. Metal Tek plans to pour C-2 after insight gained on C-1 has been incorporated into the process.
Note on H11: Nancy Horton: Note 8 from e-mail: The 75% completion figure underrepresents the level of accomplishment achieved as a result of Casting C-1. This first casting is providing key insight (learning) to facilitate the production of the remaining 17 castings. Consequently, additional foundry activities, including new iterations of solidification modeling, are being conducted prior to shipping this casting to Major Tool and Machine.

## EIO Monthly Report 1-3-05
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: January 3, 2005
| Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05
Patterns
Pattern A complete | 2005-02-10 | 2005-02-25 | 255125 |  | 10% | 18%
Pattern B complete | 2005-04-12 |  | 255125 |  | 2% | 7%
Major Tool Tooling Complete | 2005-02-15 |  | 555000 |  | 25% | 50%
Materials (MetalTek) | 2005-12-31 |  | 744746 |  | 5% | 17.6%
C1
MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-10 | 140808 |  | 0
MTM - machining/inspection | 2005-05-15 | 2005-05-26 | 154912
Receive at PPPL | 2005-05-16 | 2005-05-27
C2
MTK-casting | 2005-04-20 |  | 140808
MTM - machining/inspection | 2005-07-13 |  | 154912
Receive at PPPL | 2005-07-14
A1
MTK-casting | 2005-05-20 | 2005-06-08 | 140808
MTM - machining/inspection | 2005-08-12 | 2005-08-31 | 154912
Receive at PPPL | 2005-08-15 | 2005-09-02
C3
MTK-casting | 2005-06-20 |  | 140808
MTM - machining/inspection | 2005-09-14 |  | 154912
Receive at PPPL | 2005-09-15
B1
MTK-casting | 2005-07-21 |  | 140808
MTM - machining/inspection | 2005-10-13 |  | 154912
Receive at PPPL | 2005-10-14
A2
MTK-casting | 2005-08-17 |  | 140808
MTM - machining/inspection | 2005-11-14 |  | 154912
Receive at PPPL | 2005-11-15
A3
MTK-casting | 2005-09-16 | 2005-09-15 | 140808
MTM - machining/inspection | 2005-12-14 |  | 154912
Receive at PPPL | 2005-12-15
A4
MTK-casting | 2005-10-17 | 2005-10-05 | 140808
MTM - machining/inspection | 2006-01-13 |  | 154912
Receive at PPPL | 2006-01-16
A5
MTK-casting | 2005-11-16 | 2005-10-26 | 140808
MTM - machining/inspection | 2006-02-14 |  | 154912
Receive at PPPL | 2006-02-15
A6
MTK-casting | 2005-12-14 | 2005-11-15 | 140808
MTM - machining/inspection | 2006-03-14 |  | 154912
Receive at PPPL | 2006-03-15
B2
MTK-casting | 2006-01-13 | 2005-12-08 | 140808
MTM - machining/inspection | 2006-04-13 |  | 154912
Receive at PPPL | 2006-04-14
B3
MTK-casting | 2006-02-13 | 2006-01-05 | 140808
MTM - machining/inspection | 2006-05-12 |  | 154912
Receive at PPPL | 2006-05-15
B4
MTK-casting | 2006-03-16 | 2006-01-25 | 140808
MTM - machining/inspection | 2006-06-14 |  | 154912
Receive at PPPL | 2006-06-15
B5
MTK-casting | 2006-03-28 | 2006-02-15 | 140808
MTM - machining/inspection | 2006-06-26 |  | 154912
Receive at PPPL | 2006-06-27
B6
MTK-casting | 2006-04-14 | 2006-03-08 | 140808
MTM - machining/inspection | 2006-07-13
Receive at PPPL | 2006-07-14 |  | 154912
C4
MTK-casting | 2006-05-16 | 2006-03-31 | 140808
MTM - machining/inspection | 2006-08-14 |  | 154912
Receive at PPPL | 2006-08-15
C5
MTK-casting | 2006-05-30 | 2006-04-24 | 140808
MTM - machining/inspection | 2006-08-28 |  | 154912
Receive at PPPL | 2006-08-29
C6
MTK-casting | 2006-06-16 | 2006-05-14 | 140808
MTM - machining/inspection | 2006-09-14 |  | 154912
Receive at PPPL | 2006-09-15
EIO Project Mgt. 24 mos. |  |  | 908828 | 8.333% | 12.5% | 16.6%
Note on A5: Nancy Horton: Note 2) in e-mail: Several upfront milestones under the heading of "Patterns" have been initiated and some progress toward delivery has been accomplished as follows: Pattern A: Solidification modeling, modeling of the top half of the drag core box, as well as some gluing of the pattern. Pattern B: Stock Model complete and Solidification Modeling underway. Major Tool Tooling: Programming and internal drawings for fixtures A, B and C are complete. Fabrication of the C fixture is more than 10% complete. Materials: Metal Tek reports that they will procure metal in 17 lots. To date, they have procured 3 of the 17 lots.
Note on C13: Nancy Horton: Note 7 in e-mail: The first hardware deliverable under this contract will be the NCSX Winding Form referred to as C-1. Early effort toward the production of C-1 was performed under concurrent EIO contract S-04341-F, Change Order 5. The two key milestones under that change order were accomplished during December: Delivery of the completed pattern to Metal Tek and casting Coil C-1 through shakeout. With the initial success of the C-1 casting, we are still working toward the extremely ambitious 25 week schedule which was used for the projected schedule delivery date for C-1. As noted last month, this is a target which depends on many favorable advantages occurring during the course of production. In fact, our team's proposed baseline schedule for producing a winding form is 27 weeks: 15 weeks for casting the part, followed by 12 weeks for machining.
Note on C79: Nancy Horton: Note 9 in e-mail: The projected dates for completion of castings at Metal Tek were based on the assumption that once full-scale production of the 18 castings commences, Metal Tek projects that they will be able to produce and deliver one casting every three weeks. Therefore, if delays are experienced in the early stages of production, there is ample opportunity for recovery and acceleration over the remainder of the production period. The projected schedule change in completion of the A Pattern will have a corresponding impact on these dates. As noted, these dates will be reevaluated after the meeting on 1/18/05.
Note on G8: Nancy Horton: Note 5 from e-mail: At 50% complete, Major Tool is entitled to bill $350,000 for upfront costs.
Note on G9: Nancy Horton: Note 6 from e-mail: Metal Tek is entitled to bill for metal as they buy it. At this point, they will have spent and will bill for approximately $130,000 out of the total.
Note on D3: Nancy Horton: Note 1 from e-mail: For this spreadsheet, "Task Values" were based on rounded calculations which when totaled, result in a deviation from the bottom line negotiated price. Billings will reflect the agreed upon prices in EIO contract.
Note on G7: Nancy Horton: Note 4 from e-mail: The estimate of %Complete includes schedule and effort related to solidification modeling which is performed under Metal Tek's contract (not part of the $255,125). Lawton reports that they are about 1-2% started on fabrication of B pattern.
Note on G6: Nancy Horton: Nancy Horton: Note 3b from e-mail: The estimate of %Complete includes schedule and effort related to solidification modeling which is performed under Metal Tek's contract (not part of the $255,125). Lawton reports that they are about 8-10% complete with the A pattern.
Note on C6: Nancy Horton: Note 3a from e-mail: Due to complexities encountered during Solidification modeling, and Lawton's experience building the C Pattern, the completion date for A pattern is projected out to the end of February. Lawton has given their commitment to make every effort to improve upon this schedule if possible. This impacts the projected delivery schedule of A-1 casting to PPPL.
Note on C21: Nancy Horton: Note 8 from e-mail: The required leadtime for Pattern A will not only impact the schedule delivery date of A-1; it may also impact the delivery dates for the remaining coils, as Metal Tek projections have previously been based on a 3 week minimum leadtime between castings. Therefore, the topic of delivery order will be included on the Agenda for the meeting in St. Louis on 1/18/05, to address each company's concerns and considerations, as well as to ensure that this is still PPPL's preferred delivery sequence. Baseline and/or projected delivery schedules will be modified in next month's report, based on agreements reached at the meeting.

## EIO Monthly Report 12-3-04
Energy Industries of Ohio - NCSX Team Projected Delivery Schedule
Monthly Report dated: December 3, 2004
| Baseline Schedule date | Projected Schedule Date | Task Value | % compl. 11/04 | % compl. 12/04 | % compl. 1/05
Patterns
Pattern A complete | 2005-02-10 |  |  |  | 10%
Pattern B complete | 2005-04-12 |  |  |  | 2%
Major Tool Tooling Complete | 2005-02-15 |  |  |  | 25%
Materials (MetalTek) |  |  |  |  | 5%
C1
MTK-casting upgrade (casting covered by CO5) | 2005-02-22 | 2005-03-10 |  |  | 0
MTM - machining/inspection | 2005-05-15 | 2005-05-26
Receive at PPPL | 2005-05-16 | 2005-05-27
C2
MTK-casting | 2005-04-20
MTM - machining/inspection | 2005-07-13
Receive at PPPL | 2005-07-14
A1
MTK-casting | 2005-05-20
MTM - machining/inspection | 2005-08-12
Receive at PPPL | 2005-08-15
C3
MTK-casting | 2005-06-20
MTM - machining/inspection | 2005-09-14
Receive at PPPL | 2005-09-15
B1
MTK-casting | 2005-07-21
MTM - machining/inspection | 2005-10-13
Receive at PPPL | 2005-10-14
A2
MTK-casting | 2005-08-17
MTM - machining/inspection | 2005-11-14
Receive at PPPL | 2005-11-15
A3
MTK-casting | 2005-09-16 | 2005-09-15
MTM - machining/inspection | 2005-12-14
Receive at PPPL | 2005-12-15
A4
MTK-casting | 2005-10-17 | 2005-10-05
MTM - machining/inspection | 2006-01-13
Receive at PPPL | 2006-01-16
A5
MTK-casting | 2005-11-16 | 2005-10-26
MTM - machining/inspection | 2006-02-14
Receive at PPPL | 2006-02-15
A6
MTK-casting | 2005-12-14 | 2005-11-15
MTM - machining/inspection | 2006-03-14
Receive at PPPL | 2006-03-15
B2
MTK-casting | 2006-01-13 | 2005-12-08
MTM - machining/inspection | 2006-04-13
Receive at PPPL | 2006-04-14
B3
MTK-casting | 2006-02-13 | 2006-01-05
MTM - machining/inspection | 2006-05-12
Receive at PPPL | 2006-05-15
B4
MTK-casting | 2006-03-16 | 2006-01-25
MTM - machining/inspection | 2006-06-14
Receive at PPPL | 2006-06-15
B5
MTK-casting | 2006-03-28 | 2006-02-15
MTM - machining/inspection | 2006-06-26
Receive at PPPL | 2006-06-27
B6
MTK-casting | 2006-04-14 | 2006-03-08
MTM - machining/inspection | 2006-07-13
Receive at PPPL | 2006-07-14
C4
MTK-casting | 2006-05-16 | 2006-03-31
MTM - machining/inspection | 2006-08-14
Receive at PPPL | 2006-08-15
C5
MTK-casting | 2006-05-30 | 2006-04-24
MTM - machining/inspection | 2006-08-28
Receive at PPPL | 2006-08-29
C6
MTK-casting | 2006-06-16 | 2006-05-14
MTM - machining/inspection | 2006-09-14
Receive at PPPL | 2006-09-15
EIO Project Mgt. 24 mos. |  |  |  | 8.333% | 12.5%
Note on A5: Nancy Horton: Note 1) in e-mail: Several upfront milestones, under the heading of Patterns, have been initiated and some progress toward delivery has been accomplished. These include solidification modeling for Pattern A, along with some purchase of wood and other materials for the fabrication of both A and B patterns, preparation of the machining fixtures for winding form C, and purchase of the required materials to cast the parts, including metal. Significant progress toward completion of these tasks is expected in the upcoming months of December and January.
Note on C13: Nancy Horton: Note 2) in e-mail: The first hardware deliverable under this contract will be the NCSX Winding Form referred to as C-1. Early effort toward the production of C-1 is primarily being accomplished under concurrent EIO contract S-04341-F, Change Order 5. A key milestone toward production of C-1, fabrication of the hard tool pattern, was completed last week and final inspection and shipment to Metal Tek is anticipated on December 6, 2004. A second major accomplishment toward the development of C-1, set-up and pouring of the casting, is anticipated to commence in the upcoming week with scheduled completion on or before December 24, 2004. An extremely ambitious 25 week schedule has been used for the projected schedule delivery date for C-1. This is a target which depends on many favorable advantages occurring during the course of production. In fact, our team's proposed baseline schedule for producing a winding form is 27 weeks: 15 weeks for casting the part, followed by 12 weeks for machining. As production gets underway, we will have better knowledge of the opportunities and challenges which will impact delivery.
Note on C79: Nancy Horton: Note 3) in e-mail: Once full-scale production of the 18 castings commences, Metal Tek has projected that they will be able to produce and deliver one casting every three weeks. Therefore, if delays are experienced in the early stages of production, there is ample opportunity for recovery and acceleration over the remainder of the production period.