November 15, 2004

Contract S005242-F for Production of Modular Coil Winding Forms

Submitted by:  Energy Industries of Ohio

Introduction:

This is the second monthly report under Contract S005242-F and covers the period of October 16, 2004 to November 15, 2004.   Implementation of Grand View software for tracking and sharing data is underway by EIO.   In the future, weekly and monthly reports will be available in this system.

Actual Milestones and Administrative Accomplishments for 2004:

Previously Reported

July 2                     --RFP issued

August 3              --Proposal Submitted

August 6              --Final SOW approved by PPPL

August 18            --Negotiations Commenced

August 25            --Price and Schedule Negotiations Concluded and MOU executed

September 23      --Final NCSX-CSPEC-141-04-05 approved by PPPL

--Contract submitted to EIO for signature

--EIO Team technical meeting in Indianapolis to discuss CO5

September 27      --EIO distributed lower tier subcontracts for signature

October 1            --Final contract negotiations concluded

--Lower tier subcontracts signed

--EIO signed contract with PPPL

October 6            --PPPL signed contract with EIO effective this date

October 8            --EIO signs Lower Tier subcontracts with

Lawton, Metal Tek and Major Tool

--EIO submits Weekly Report #1 - contract deliverable SOW 5.2

October 11          --EIO Team Kick-Off meeting in Wisconsin

--First Contract Action Items Assigned

October 15          --EIO submits Weekly Report #2 - contract deliverable SOW 5.2

--EIO submission of Monthly Report #1 - contract deliverable SOW 5.3

Current Reporting Period (10/16 - 11/15)

Planned:		Milestone					                         Actual

October 22        • Subtier contractor detailed project task lists & milestone schedules due to EIO

- Lawton (C1 only)…………………………………………..  11/4/04

- Metal Tek (C1 only) ……...……………………………….. 11/10/04

- Major Tool …….…………………………………………….10/29/04

√ Weekly Report #3 due at PPPL by noon

- contract deliverable SOW 5.2……………………………10/22/04

√Prototype ships from Magna Machine to Major Tool (CO5)……….…...10/22/04

October 29        √MIT/QA Plans for all EIO team members due to PPPL…………………10/29/04

- Comments Received from PPPL………………………….11/3/04

- Comments Addressed/Plans resubmitted……………….11/15/04

• Milestone Data entered into Grand View (Process Initiated)…….…10/29/04

√ Weekly Report #4 due at PPPL by noon -

- contract deliverable ……………………………………10/29/04

November 5       √ Weekly Report #5 due at PPPL by noon

- contract deliverable ……………………………………..11/5/04

√ Stocked Model For Coil A Complete (Lawton)………………...….11/8/04

November 12      √ Weekly Report #6 due at PPPL by noon

- contract deliverable…………………………………..…11/12/04

November 15      √ EIO submission of Monthly Report #2

- contract deliverable……………………………………..11/15/04

Planned Administrative Milestones for remainder of 2004

Original Plan    Milestone						Current Forecast

November 19     --Weekly Report #7 due at PPPL by noon -

- contract deliverable………………………………….…...11/19/04

--Pattern for Coil C ships from Lawton to Metal Tek (CO 5)…..…………12/8/04

November 26     --Team Members training of Grand View complete………………………12/3/04

--Weekly Report #8 due at PPPL by noon

- contract deliverable…………………….…………………11/26/04

December 3        --Weekly Report #9 due at PPPL by noon

- contract deliverable………………………….……………12/3/04

December 10      --Weekly Report #10 due at PPPL by noon

- contract deliverable………………………………………12/10/04

December 15      --EIO submission of Monthly Report #3

- contract deliverable………………………………………12/15/04

December 17      --Weekly Report #11 due at PPPL by noon

- contract deliverable………………………………………12/17/04

December 20      --C-1 Cast (Metal Tek CO5 projected)……………………………………12/21/04

December 24      --Weekly Report #12 due at PPPL by noon

- contract deliverable………………………………………12/24/04

December 31      --Grand View fully up and operational by all team members………….12/31/04

--Weekly Report #13 due at PPPL by noon

- contract deliverable………………………………………12/31/04

Upcoming Technical Milestones for Modular Coil Winding Form C1

| Plan | Milestone | Forecast/Actual |
| --- | --- | --- |
| 11/10/04 | Design Machining Fixture for Coil C (MajorTool) | 11/10/04 |
| 11/18/04 | Coil C Pattern Received at Metal Tek (Lawton) | 12/8/04 |
| 12/8/04 | Pattern Rigging (Metal Tek) | 12/16/04 |
| 12/16/04 | Fabricate Machining Fixture for Coil C (Major Tool) | 12/16/04 |
| 12/21/04 | Melt & Pour (Metal Tek) | 12/21/04 |
| 1/7/05 | Heat Treat (Metal Tek) | 1/7/05 |
| 1/14/05 | Machine Fixture for Coil C (Major Tool) | 1/4/05 |

The following timeframes provide an approximate schedule for each type of Coil, from start to finish (including Pattern Build):

Pattern Design & Build

4 Weeks  - Solidification Modeling

8 Weeks - Pattern Build

Casting

3 Weeks - Casting Set-up

2 Weeks - Break Out

10 - 13 Weeks - Post Casting Shakeout & Cleaning

Machining

2 Weeks - Rough Machining

6 Weeks - Finished Machining

4 Weeks - Test, Assemble & Inspect

Questions about this report can be directed to the undersigned at 216-496-2314.

Nancy Horton

EIO NCSX Program Manager