October 4, 2005, Monthly Report

Contract S005242-F for Production of Modular Coil Winding Forms

Submitted by:  Energy Industries of Ohio

This is the thirteenth monthly report under Contract S005242-F.   Highlights of accomplishments/milestones to date include:  all 3 patterns (A, B, C) are complete,  8 total castings have been poured including the last of the C coil castings, 4 castings have been completed at the foundry and our first casting C-1 has been fully machined and delivered to PPPL. The learning curve at the foundry is beginning to reveal itself as castings are being poured at about 3 week intervals.  It is expected that a similar leadtime improvement will take place at the machine shop as the next few castings are completed.  Therefore, the EIO team has requested that revised forecasting be suspended for the upcoming month to allow time for analysis of the learning at the machine shop.  This situation is reflected in the attached report.  Projections for all of the C castings have been updated based on the most current information; however, all other projections are outdated and will be reassessed and updated ASAP.

The attached excel spreadsheet includes the current month, as well as previous months.  To see this month's report, click on the tab at the bottom of the spreadsheet entitled EIO Monthly Report 10-1-05.  Columns for percent complete are shown for the current month and previous two months.  For ease of printing, earlier months are "hidden" and may be accessed by highlighting columns E and N, clicking on "Tools," clicking on "columns," then clicking on "unhide."

To assist in PPPL/DOE end of the fiscal year accrual activities, a column has been added to the spreadsheet reflecting the "earned value" of the production activities to date.

The following additional points and explanations are provided to support new and revised data contained in this month's spreadsheet (Column Letter - Row Number included in parentheses).  These notes are also viewable within the spreadsheet by moving the cursor over cells with red highlights.  Unnumbered notes in the spreadsheet are carryovers from previous months which still offer assistance in interpreting the spreadsheet.

1) Projected Schedule Date (Column D, Row 3)  Projections for the C type castings (Identified in sequence as # 1, 2, 4, 5, 6, & 7) are based on the most current information and plans to date.  Projections for Machining and receipt at PPPL for A and B type castings (#3 & #'s 8 - 18) are not based on current casting delivery projections and are currently under analysis for the most effective production sequence and delivery based on current and anticipated learning.  Therefore, the dates shown will be updated in the future based on our experience in the upcoming month.

2) "% Complete" Pattern B (Column Q, Row 7)   B pattern is 100% complete; however, Cost of the pattern includes first article scan at Metal Tek, so this figure will remain open (at 97% complete) until after B-1 is poured and scanned.

3) "% Complete" C-1 Machining as of 10/05 (Column Q, Row 12)  C-1 was delivered to PPPL on 10/3/05

4) "% Complete" C-2 Machining as of 10/05 (Column Q, Row 16) C-2 has completed machining on 3 axis and commenced machining on the 5 axis on 10/1/05

5)  "% Complete" for Receiving C-2 @ PPPL as of 9/05 (Column Q - Row 17) Draft C-2 doc package has been posted to EIO ftp for advance review.  Shipping crate for C-1 will be returned to support shipment of C-2.

6) "Projected Schedule Date" for MTM Machining of A-1" (Column D - Row 20): Actual projected date is TBD after analysis and assessment of learning.  Also, revised delivery date will reflect resequencing of castings at MTM to enable continued learning on the C's before moving on to the A-1.

7) "% Complete" A-1 for Machining as of 10/05 (Column Q, Row 20)  While programming for A is nearly complete, the casting will be machined after C-3 and possibly even after all of the C's have commenced machining

8) "% Complete" C-3 for MTK Casting as of 10/05 (Column Q, Row 23):  C-3 was completed on 9/20 and delivered to MTM on 9/21/05

9) "Projected Schedule Date" for Completion of MTM Machining of C-3 (Column D - Row 24)  2/22 reflects the latest delivery projection based on a 12 week machining schedule commencing on 10/04.

10) "% Complete" C-3 for Machining as of 10/05 (Column Q, Row 24) Machining of C-3 was rescheduled to commence on the 3 axis machine on 10/4/05, in order to conduct preventive maintenance on the 3 axis machine prior to work.

11) "% Complete" C-4 for MTK Casting as of 9/05 (Column Q, Row 27) C-4 has been undergoing weld repair and should be sent out for X-ray around 10/5/05

12) "Projected Schedule Date" for Completion of MTM Machining of C-4 (Column D - Row 28) Revised projection based on a 12 week machining schedule after receipt of casting

13)   "% Complete" C-4 for Machining as of 10/05 (Column Q, Row 28) 5% reflects applicable learning from C-1 and preparation for receipt of C-4

14) "% Complete" C-5 for MTK Casting as of 9/05 (Column Q, Row 31) C-5 is undergoing weld upgrade

15)  "Projected Schedule Date" for Completion of MTM Machining of C-5 (Column D - Row 32) Revised projection based on 12 week machining schedule and 3 week interval between casting set-ups at MTM, for machining start date of  11/10/05

16) "% Complete" C-5 for Machining as of 10/05 (Column Q, Row 32)  2% reflects applicable learning from C-1 and preparation for receipt of C-5

17) "% Complete" C-6 for MTK Casting as of 10/05 (Column Q, Row 35)  C-6 is scheduled for first X-ray commencing wk of 10/10/05

18) "Projected Schedule Date" for Completion of MTM Machining of C-6 (Column D - Row 36) Revised projection assumes a 12 week machining schedule and a 3 week interval between machining start-ups.  In this projection, machining will commence around 11/30/05

19) "% Complete" A-2 for MTK Casting as of 10/05 (Column Q, Row 39) A-2 was poured on 9/27/05. It has been broken out of the mold and clean-up is underway

Small figures have been inserted in % complete for MTK Casting (columnQ) for A-3 and B-1 to reflect production planning which is already underway.

As previously mentioned, the next month is expected to yield significant insight about schedule realities and opportunities as we enter full contract production (multiple castings in process at both the foundry and machine shop and at least one of each coil type in production).  Consequently, delivery projections for the A and B castings are not current and need to be revised.  As discussed with PPPL, EIO team members will continue to assess our learning curve in order to more accurately predict winding coil deliveries.  If you would like to discuss any aspect of this report in greater detail, I can be reached at 216-496-2314.

Nancy Horton

EIO Program Manager for NCSX