## Energy Industries of Ohio (EIO) Team Weekly Status Report

Report covers the NCSX Modular Coil Winding Form Activities Under Production Contract S005242-F

Week ending June 16, 2006

# Administrative Highlights

# Above, is another great action shot from Mike Griffith of the A-2 as the final cuts are being taken! As reported below, A-2 is expected to finish machining Friday (6/16) and move into final processing over the weekend. A-2 can be seen as a testament to both resource leveling and the learning curve. 5-axis final machining for this coil form took less than 2 weeks!

# During the QA meeting this week, a tentative date of 6/21 was set for Metal Tek’s next trip out to MTM to check permeability on A-2 & B-1 (QA action item 2.2). On Thursday evening however, Mike Griffith reported to EIO that A-2 would probably be ready for inspection prior to the 21st as the machining was progressing ahead of schedule. Several calls followed later that evening to try to nail down a time when both MTK was available and A-2 was accessible.

# Although MTK has 6 Sigma certification training scheduled for next week, Barry Craig made special arrangements to send Inspection Supervisor, Bob Carlton to MTM to inspect and remediate any magnetic permeability on A-2 and B-1 (note: the accessibility of B-1 is presently in question pending completion of machining on the 40T Lucas as discussed in tech highlights below). Bob will be calling Kevin Bowling of MTM early Monday a.m. to see if A-1 is ready for inspection.   If so, he will head to Indianapolis immediately.

# FTP Postings this week

(found at:  ftp.atc-inc.org:/PPPL/shared_info)

| Location | File Name | Date |
| --- | --- | --- |
| \Quality_Review | RTResponce.doc | 6/12/06 |
| \SOW_Spec_Drawings | Readme.doc | 6/12/06 |
| \SOW_Spec_Drawings | type_a_insp_points_r2.zip | 6/12/06 |
| \Quality_Review\C4_Doc | C-4_Doc_Pack-Major_Tool_6-12-06.pdf | 6/12/06 |
| \Quality_Review\Closed_NCR-CA-RFD\NC | Signed_off_CA1671A-6tensiletest.pdf | 6/12/06 |
| \Quality_Review\Closed_NCR-CA-RFD\NC | Signed_off_NC19607_C5RT.pdf | 6/12/06 |
| \Quality_Review\Closed_NCR-CA-RFD\NC | Updated_signedNC19710afterdispositioned.pdf | 6/12/06 |
| \Quality_Review\Closed_NCR-CA-RFD\NC | SignedoffNC19713_C5IDC_TGrind.pdf | 6/12/06 |
| \Quality_Review\C5_Doc | MTM_C5datapackage_6-13-06.pdf | 6/13/06 |
| \SOW_Spec_Drawings\B-changes | S5242l6-16-06_b-style-holes.pdf | 6/16/06 |
| \Quality_Review\Closed_NCR-CA-RFD\NC | NC19710dispositioned.pdf | 6/16/06 |
| \Quality-Meeting_notes | PPPLQualityNotes6-12-06_plus.doc | 6/16/06 |

**note – file names may be changed from the original for clarity

# Administrative Action Items

# (PPPL) Pattern Storage after six castings have been delivered to MTM.

# Status: (Open - No update) Resequencing of machining the C coils means that the C pattern will need to be stored for an extended period and outdoor storage is not an option.   A & B patterns are also ready for storage. We were informed this week that with rising oil prices, PPPL is concerned about the high cost for shipment of the patterns.  Phil Heitzenroeder has asked EIO/MTK to investigate the cost for securing local storage in the St. Louis area to see if this might be a more economical option for housing the patterns until the program is complete.  EIO addressed this question with Barry Craig on 6/9. He will check on prices for pattern storage with an outside service he has used previously for this purpose.

# Technical Highlights

A-2

MTM is quickly moving thru the final machining operations on A-2.  Mike Griffith projected that the part would finish machining late and come off the U-5 late Friday. The part will then move into deburring over the weekend. Plans are presently in-place for PPPL and EIO to travel to MTM on 6/26 and 27 during the final inspection processes with the goal of releasing the part for shipment by the end of the month.

A-2 in final op

A-3

MTM reports that A3 is also making good progress.  The 1st operation on the 40’ Mitsu is well underway, with expectations to start running the 2nd operation (of 2) by mid next week.  MTM plans to complete all A3 operations on the 40’ Mitsu before the Holiday break. A-3 would then be moved to the U-5 for final machining around July 5.

A-3 on Mitsu

B-1 & B2

B-1 on the Lucas

Late Thursday afternoon, Mike Griffith informed the team that the 40T Lucas was down, noting that a repair team was immediately assigned to the center.  As of Friday afternoon, the status of the machine was still uncertain; however a crew was on standby for weekend machining should repairs be completed.

B1 is currently on operation 2 of 2 on the 40T Lucas. MTM changed the scope of work on the 40T for the B castings.  What was to be the 3rd operation (poloidal break operation) will now be run on the 30’ Mitsu (this will be called 30’ op 1 of 1).  This helps to lighten the load on the 40T and allows the shop to do both the poloidal break and the additional operation that is required on the narrow end of the B casting, all performed in one setup on the 30’ rotary table. As an interesting twist to this week’s highlights, the new operation (poloidal break portion) is being proved out on the C-6 casting (see below).

C-6

MTM has put C6 back into the machining rotation on the 30’ Mitsu for the poloidal break operation.  They have taken advantage of an opening on this machine to test run the poloidal break setup that will be used on the B castings.  Moving the poloidal break setup to this machine (for B MCWF) will further help MTM to level the cut times on each center.

C-6 – Back in play!

B-5

B-5 passed final RT at MQS in record time! The casting was turned around in a single day after receipt. Barry Craig has scheduled B-5 to go through stress relief on Monday night. After that the final processing will commence. To consolidate freight, MTK plans on shipping B-5 with B-6, at the end of the month.

B-6

B-6 is currently in welding. Barry plans on finishing the upgrading by 6/20. The casting will then be shipped back up to MQS for final RT verification. MTM will be expediting the final x-ray to try to get B-6 back by the end of the week. MTM is still on track to ship B-6 (along with B-5) by the end of the month.

# Technical Action Items

- (Major Tool) Machining C-6

Status: (Open) Cutting poloidal break

- (Major Tool) Machining  A-2
Status: (Open) Final ops on U-5

- (Major Tool) Machining A-3
Status: (Open) On 40’ Mitsu

- (Major Tool) Machining B-1
Status: (Open) On 2nd op on Lucas

- (Major Tool) Machining A-4
Status: (Open) Staged for 40’ Mitsubishi

- (Major Tool) Processing A-5
Status: (Open) on hold

- (Major Tool) Machining A-6
Status: (Open) on hold

- (Major Tool) Processing B-2
Status: (Open) Completed1st op on Lucas

- (Major Tool) Machining B-3
Status: (Open) on hold

- (Major Tool) Machining B-4
Status: (Open) on hold

- (Metal Tek) Processing B-5
Status: (Open) going into stress relief

- (Metal Tek) Processing B-6
Status: (Open) In welding

Quality Highlights

In general, this was a good week for QA, with the team managing to close some long standing items. Both the C-4 & C-5 doc packages were submitted to PPPL for review. A date has been set for Metal Tek’s permeability check and for Steve Raftopolis’s source inspection of A-2. These and other items are all detailed below.

Upcoming QA Activities

- Permeability check of A-2 & B-1 at MTM (by MTK)

- Final inspection on B-5 at MTK

- Scan of B-5 at MTK

QA Action Items

- Closed Items: (EIO recommended)

  - 19710 (2.4)  for weld repairs on C-5

  - MTM added the Torque Check to their IDC (2.6)

- Pending from EIO:

  - (EIO) Provide final documentation packages for completed MCWF’s.

    - C-4
Status: (Open) –Preliminary copy sent to PPPL 6/12. Waiting for PPPL review prior to combining MTK & MTM submissions

    - C-5
Status: (Open) – Preliminary copy sent to PPPL 6/13. Waiting for PPPL review prior to combining MTK & MTM submissions

    - A-1
Status: (Open) – In-progress at MTM

  - (EIO) Investigate and take steps to mitigate source of ferromagnetic contamination seen on C-4, B-1 and subsequent castings. Report back with update to CA 1695 so that PPPL can disposition NCR 3633.
Status: (In-Progress) –MTK will clean-up B-1 & A-2, inaccessible at the previous visit, when they are accessible.  Aiming for 12/19 or 12/20 – Inspection to be done by Bob Carlton of MTK

  - (EIO, MTM) Document Corrective Action to close NC 19783 (A-1Tee hole counter-bore depths).
Status: (Open - No update)  MTM is waiting for PPPL input (3.2) regarding their investigation into mag perm of hardware before manufacturing the required bushings.

  - (EIO, MTM) Document Corrective Action to close NC19710 (C-5 weld repairs w/o RT)
Status: (Closed)  Update sent 6/12 and dispositioned copy with attachments sent back by Frank Malinowski on 6/14

  - (EIO, MTM) Provide Stellalloy bearing plates and replacement fasteners for MCWF’s C-1 through C-5. (Needed to close NCR’s 3618 & 3651.)
Status: (Open) MTM has not yet received all fasteners & bearing plates for the C style castings are not yet machined.  MTM will determine a ship date. In progress, but no ship date yet – possibly with A-2

  - (EIO, MTM) MTM will add an IDC torque check of poloidal break hardware.
Status: (Closed) Mike Griffith confirmed that the Torque check is now added to the IDC.  The update will appear on A-2 documentation.

  - (EIO, MTK) Clarify MCWF Type A RT Technique Sheet so that locations can be matched to films.
Status: (New) EIO sent casting model photos that should help on 6/10.  These didn’t arrive, so were re-sent to PPPL Tuesday.  MTK added photos, using the model, to identify locations on the casting. Additional photos were sent on 6/14. The team is missing documentation for R-1 shots. Chuck Ruud has gone back to get this info from MQS.

- Pending from PPPL

  - Provide updated requirements documents incorporating the following changes:

    - CSPEC update addressing revised poloidal break inspection/tolerances. Poloidal break flange fit-up, 0.005” through and 0.015” at edges – edge defined as no more that 1/8” penetration. 
Status: (Open- No Update) Rapid response guidance sent 3/16.  Wording for next CSPEC revision is in process.

    - PPPL to incorporate guidance on Type A MCWF thermocouple hole placement provided 3/20 into requirements documents. 
Status: (Open- No Update) – EIO has delivered marked up drawings with proposed locations.   ECN-5218R2 implements this change, which is described by RFD-14-017.  Change will appear in drawing SE141-114, Rev-7, which should be issued, along with SE141-115, Rev.8, before 6/16.

    - PPPL to correct drawing SE-141-114, Rev. 6 - the dimensions shown in Sect. Q-Q are the correct ones, and the remnant incorrect dimensions will be deleted.
Status: (New) –An ECN is required.  ECN-5218R2 also covers this change

    - ECN needed to capture changes discussed on 6/9 regarding Type B thermocouple hole, VI bleeder hole, thru/tapped holes, & port cut-out. 
Status: (New) –ECN-5218R2 in progress. PPPL advised EIO on 6/16 that they had accepted the 6/12 proposed approach to convert (17) clearance holes on the Type B mcwf, datum E flange, to 1.375-6 UNC x 1.5” min. thread depth holes.  EIO has requested that associated drawing revision be provided by 6/19 in order to avoid programming delays.  We were advised that the drawings would be forthcoming in that time period.

    - ECN needed to address hole added to poloidal break. 
Status: (New) –   ECN-5218R2 covers this also.  Drawing SE141-058 was at Rev-2, with ECN-5112(RFD-14-019), "add lifting holes", pending.  We will make this change and the new hole and issue it as Rev-3 by 6/16.

  - PPPL will check and advise MTM on Bushings with acceptable magnetic permeability.
Status: (Open - No update) PPPL may run magnetization curves in hope of raising the permeability limits. We briefly discussed using the rejected Stellalloy bearing plates.  Phil & Mike will see if that is worth pursuing.

  - Review C-2 & C-3 documentation packages posted 5/31
Status: (Open).6/16

  - Disposition (mark) rejected SS316 bearing plate material and then close EIO’s NC 19233 & 19234.
Status: (Open).  PPPL to verify that all plates are marked with their permeability.

  - Review updated CA 1671 (for A6 test results below spec for elongation) with inspection and analysis results.  
Status (Open - No update) – in progress – Phil has been discussing with Brad, but no signed disposition yet.

- Discussion Topics for Teleconference:

  - New Specification & Drawing Changes

    - According to PPPL, issuance of ECN 5218R2 is imminent.  If received by Tuesday, add to agenda for QA telecon.

    - Peter Djordjevich (EIO) and Steve Raftopolous (PPPL) currently plan to be at MTM for A-2 inspection on 6/26.

# Nancy Horton

# EIO Program Manager for NCSX

216-496-2314