## Sheet1
NCSX Contract Plan and Reporting
Contract: Subcontract S-04344-F
Date: May 31, 2003
Schedule
A | B |  | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W
|  |  |  | Baseline |  | Forecast or Actual |  | Total | % | BCWP | Monthly Cost Baseline Plan (loaded $k) | [11 empty] | Estimate at
| Description |  | Prerequisites (list task numbers) | Start | Finish | Start | Finish | Budget | Complete | (budget x %) | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Completion
Task 1 | VVSA Manufacturing Methods. Plus related technical reports. | 64880 Lot 1 - Task 2,3, 4,8&9 | SOW 3.1 | April 10 '03 | May 23 '03 | April 10 '03 | June 20 '03 | 14222 | 10% | 1422.2 | Monthly Cost Baseline Plan (loaded $k) Apr: 4.2; Monthly Cost Baseline Plan (loaded $k) May: 10
Task 2 | MIT and Quality Plans for the PVVS | 64880 Lot 1 - Task 1,3, 4,8&9 | SOW 3.2.1 | April 10 '03 | May 23 '03 | April 10 '03 | June 20 '03 | 8321 | 80% | 6656.8 | Monthly Cost Baseline Plan (loaded $k) Apr: 2.3; Monthly Cost Baseline Plan (loaded $k) May: 6
Task 3 | Procure PVVS Materials | 64880 Lot 1 - Task 1,2,4,8&9 | SOW 3.2.2 | May 30 '03 | July 7 '03 | June 30 '03 | Aug 11 '03 | 51600 | 0% | 0 | Monthly Cost Baseline Plan (loaded $k) Jun: 25; Monthly Cost Baseline Plan (loaded $k) Jul: 26.6
Task 4 | Manufacture the PVVS | 64880 Lot 1 - Task 1,2,3,8&9 | SOW 3.2.2 | July 31 '03 | Nov 15 '03 | July 31 '03 | Nov 15 '03 | 79775 | 0% | 0 | Monthly Cost Baseline Plan (loaded $k) Jul: 10.2; Monthly Cost Baseline Plan (loaded $k) Aug: 14.5; Monthly Cost Baseline Plan (loaded $k) Sep: 20; Monthly Cost Baseline Plan (loaded $k) Oct: 20; Monthly Cost Baseline Plan (loaded $k) Nov: 15
Task 5 | Manufacture the Fixtures | 64880 Lot 3 | SOW 3.2.2 | May 30 '03 | Aug 8 '03 | June 20 '03 | Aug 18 '03 | 48237 | 0% | 0 | Monthly Cost Baseline Plan (loaded $k) May: 5; Monthly Cost Baseline Plan (loaded $k) Jun: 20; Monthly Cost Baseline Plan (loaded $k) Jul: 20; Monthly Cost Baseline Plan (loaded $k) Aug: 3.2
Task 6 | Procure Material Dies | 64880 Lot 2 - less labor | SOW 3.2.2 | May 23 '03 | June 27 '03 | June 16 '03 | July 31 '03 | 103943 | 0% | 0 | Monthly Cost Baseline Plan (loaded $k) May: 50; Monthly Cost Baseline Plan (loaded $k) Jun: 53.9
Task 7 | Manufacture Dies | 64880 Lot 2 - less Mat'l | SOW 3.2.2 | June 6 '03 | Sept 12 '03 | July 7 '03 | Sept 15 '03 | 85731 | 0% | 0 | Monthly Cost Baseline Plan (loaded $k) Jun: 10.7; Monthly Cost Baseline Plan (loaded $k) Jul: 25; Monthly Cost Baseline Plan (loaded $k) Aug: 25; Monthly Cost Baseline Plan (loaded $k) Sep: 25
Task 8 | Final MIT and QA Plans for the VVSA/Firm Fixed Cost Proposal | 64880 Lot 1 - Task 1,2,3, 4,&9 | SOW 3.3.1 &.2 | Oct 13 '03 | Nov 15 '03 | Oct 13 '03 | Nov 15 '03 | 3870 | 0% | 0 | Monthly Cost Baseline Plan (loaded $k) Oct: 1.8; Monthly Cost Baseline Plan (loaded $k) Nov: 2
Task 9 | Engineering & Project Management | 64880 Lot 1 - Task 1,2,3, 4,&8 | SOW 5.0 | April 10 '03 | Nov 15 '03 | April 10 '03 | Nov 15 '03 | 4644 | 15% | 696.6 | Monthly Cost Baseline Plan (loaded $k) May: 1; Monthly Cost Baseline Plan (loaded $k) Jun: 0.5; Monthly Cost Baseline Plan (loaded $k) Jul: 0.5; Monthly Cost Baseline Plan (loaded $k) Aug: 0.5; Monthly Cost Baseline Plan (loaded $k) Sep: 0.5; Monthly Cost Baseline Plan (loaded $k) Oct: 0.6; Monthly Cost Baseline Plan (loaded $k) Nov: 1
[8 empty] | 400343 |  | 8775.6 | 0 | 6.5 | 72 | 110.1 | 82.3 | 43.2 | 45.5 | 22.4 | 18 | 0 | 0 | 0 | 0
Task 3, 4, 5, 6 & 7 dates are pending final geometry data from PPPL