## Invoice Report
NCSX Contract Plan and Reporting (Invoicing)
Contract: Subcontract S-04344-F
Date: December 15, 2003
A | B |  | C | D | E | F | G | H | W | W |  |  |  | I | J
|  |  |  | Baseline |  | Forecast or Actual |  | Total | Total | Total |  |  |  | % | BCWP
| Description |  | Prerequisites (list task numbers) | Start | Finish | Start | Finish | Orig Budget | Budget on 11/03 Ref Q03-00639 | Q03-00639 Adjusted 1/5/04 | This Month's Invoice 12/23/2003 | Est to complete | Estimated at Completion | Completed Effort | (budget x %)
Task 1 | VVSA Manufacturing Methods. Plus related technical reports. | 64880 Lot 1 - Task 2,3, 4,8&9 | SOW 3.1 | April 10 '03 | May 23 '03 | April 10 '03 | June 20 '03 | 14222 | 15708 | 35150 | 38980.6562 | 351.5 | 39332.1562 | 99% | 34798.5
Task 2 | MIT and Quality Plans for the PVVS | 64880 Lot 1 - Task 1,3, 4,8&9 | SOW 3.2.1 | April 10 '03 | May 23 '03 | April 10 '03 | Nov 25 '03 | 8321 | 19448 | 17415 | 9460 | 8707.5 | 18167.5 | 50% | 8707.5
Task 3 | Procure PVVS Materials | 64880 Lot 1 - Task 1,2,4,8&9 | SOW 3.2.2 | May 30 '03 | July 7 '03 | June 30 '03 | Dec 22 '03 | 51600 | 17200 | 21150 | 23189.0867 | 423 | 23612.0867 | 98% | 20727
Task 4 | Manufacture the PVVS | 64880 Lot 1 - Task 1,2,3,8&9 | SOW 3.2.2 | July 31 '03 | Nov 15 '03 | July 31 '03 | Feb 19 ' 04 | 79775 | 87601 | 40022 | 29069.1503 | 25213.86 | 54283.0103 | 37% | 14808.14
Task 5 | Manufacture the Fixtures | 64880 Lot 3 | SOW 3.2.2 | May 30 '03 | Aug 8 '03 | June 20 '03 | Dec 08 '03 | 48237 | 61431 | 30500 | 33616.1594 | 610 | 34226.1594 | 98% | 29890
Task 6 | Procure Material Dies | 64880 Lot 2 - less labor | SOW 3.2.2 | May 23 '03 | June 27 '03 | June 16 '03 | Sept 18 '03 | 103943 | 130000 | 166300 | 176022.3977 | 1663 | 177685.3977 | 99% | 164637
Task 7 | Manufacture Dies | 64880 Lot 2 - less Mat'l | SOW 3.2.2 | June 6 '03 | Sept 12 '03 | July 7 '03 | Nov 21 '03 | 85731 | 129396 | 148893 | 173472.303 | 1488.93 | 174961.233 | 99% | 147404.07
Task 8 | Final MIT and QA Plans for the VVSA/Firm Fixed Cost Proposal | 64880 Lot 1 - Task 1,2,3, 4,&9 | SOW 3.3.1 &.2 | Oct 13 '03 | Nov 15 '03 | Oct 13 '03 | Feb 26' 04 | 3870 | 7480 | 8270 | 0 | 8270 | 8270 | 0% | 0
Task 9 | Engineering & Project Management | 64880 Lot 1 - Task 1,2,3, 4,&8 | SOW 5.0 | April 10 '03 | Nov 15 '03 | April 10 '03 | Feb 26' 04 | 4644 | 5236 | 5800 | 4300 | 1450 | 5750 | 75% | 4350
|  |  | H: 400343; W: 473500; W: 473500 | 488109.7533 | 48177.79 | 536287.5433 |  | 425322.21
|  |  | W: 90 % --------> | 425000
62787.5433
Adjusted to match our actual processed that relates directly to our MIT as processed 12/15/03
Increases; Task 4 - following process to greater detail Task 5 - more time inspecting than planned Task 6 - quote was estimated based on ratio actual was higher Task 7 - took longer to machine than planned

## Invoice Report History
NCSX Contract Plan and Reporting (Invoicing)
Contract: Subcontract S-04344-F
Date: December 15, 2003
A | B |  | C | D | E | F | G | H | W | W |  |  |  | I | J | Values | Values | Formula | Values | Formula | Formula | Pasted | Formula | Formula | Pasted | Pasted | Formula | Pasted
|  |  |  | Baseline |  | Forecast or Actual |  | Total | Total | Total |  |  |  | % | BCWP | 4 INVOICING | 4 INVOICING | 4 INVOICING | [8 empty] | update each inv
| Description |  | Prerequisites (list task numbers) | Start | Finish | Start | Finish | Orig Budget | Budget on 11/03 Ref Q03-00639 | Q03-00639 Adjusted 1/5/04 | This Month's Invoice 12/23/2003 | Est to complete | Estimated at Completion | Completed Effort | (budget x %) | Q639 Budget Eng Hours | Actual Eng Hrs to Date | Eng to date with FEE | From Work Summary NO FEE | From Work Summary Plus 7.5% | COST TO DATE 12/12/2003 | Cost to Date Before Adjustment | Over Budget Less all Fees | Cost to Date Total | Invoice NONE | Invoice Total 12/23/2003 | Difference From Previous Invoices | $ to Date This Month's Invoice 12/23/2003
Task 1 | VVSA Manufacturing Methods. Plus related technical reports. | 64880 Lot 1 - Task 2,3, 4,8&9 | SOW 3.1 | April 10 '03 | May 23 '03 | April 10 '03 | June 20 '03 | 14222 | 15708 | 35150 | 38980.6562 | 351.5 | 39332.1562 | 99% | 34798.5 | 327 | 365.5 | 39291.25 |  |  | 39291.25 | 39291.25 | 3830.6562 | 38980.6562 | 0 | 38980.6562 | 38980.6562 | 38980.6562
Task 2 | MIT and Quality Plans for the PVVS | 64880 Lot 1 - Task 1,3, 4,8&9 | SOW 3.2.1 | April 10 '03 | May 23 '03 | April 10 '03 | Nov 25 '03 | 8321 | 19448 | 17415 | 9460 | 8707.5 | 18167.5 | 50% | 8707.5 | 162 | 88 | 9460 |  |  | 9460 | 9460 | -7358.375 | 9460 | 0 | 9460 | 9460 | 9460
Task 3 | Procure PVVS Materials | 64880 Lot 1 - Task 1,2,4,8&9 | SOW 3.2.2 | May 30 '03 | July 7 '03 | June 30 '03 | Dec 22 '03 | 51600 | 17200 | 21150 | 23189.0867 | 423 | 23612.0867 | 98% | 20727 |  |  | 0 | 21725.04 | 23354.418 | 23354.418 | 23354.418 | 2039.0867 | 23189.0867 | 0 | 23189.0867 | 23189.0867 | 23189.0867
Task 4 | Manufacture the PVVS | 64880 Lot 1 - Task 1,2,3,8&9 | SOW 3.2.2 | July 31 '03 | Nov 15 '03 | July 31 '03 | Feb 19 ' 04 | 79775 | 87601 | 40022 | 29069.1503 | 25213.86 | 54283.0103 | 37% | 14808.14 | 120 |  | 0 | 76391.07 | 82120.4003 | 29069.1503 | 29069.1503 | -10131.386 | 29069.1503 | 0 | 29069.1503 | 29069.1503 | 29069.1503
Task 5 | Manufacture the Fixtures | 64880 Lot 3 | SOW 3.2.2 | May 30 '03 | Aug 8 '03 | June 20 '03 | Dec 08 '03 | 48237 | 61431 | 30500 | 33616.1594 | 610 | 34226.1594 | 98% | 29890 |  |  | 0 | 31505.88 | 33868.821 | 33868.821 | 33868.821 | 3116.1594 | 33616.1594 | 0 | 33616.1594 | 33616.1594 | 33616.1594
Task 6 | Procure Material Dies | 64880 Lot 2 - less labor | SOW 3.2.2 | May 23 '03 | June 27 '03 | June 16 '03 | Sept 18 '03 | 103943 | 130000 | 166300 | 176022.3977 | 1663 | 177685.3977 | 99% | 164637 |  |  | 0 | 164475.07 | 176810.7002 | 176810.7002 | 176810.7002 | 9722.3977 | 176022.3977 | 0 | 176022.3977 | 176022.3977 | 176022.3977
Task 7 | Manufacture Dies | 64880 Lot 2 - less Mat'l | SOW 3.2.2 | June 6 '03 | Sept 12 '03 | July 7 '03 | Nov 21 '03 | 85731 | 129396 | 148893 | 173472.303 | 1488.93 | 174961.233 | 99% | 147404.07 | 255 | 316 | 33970 | 163223.46 | 175465.2195 | 175465.2195 | 175465.2195 | 24579.303 | 173472.303 | 0 | 173472.303 | 173472.303 | 173472.303
Task 8 | Final MIT and QA Plans for the VVSA/Firm Fixed Cost Proposal | 64880 Lot 1 - Task 1,2,3, 4,&9 | SOW 3.3.1 &.2 | Oct 13 '03 | Nov 15 '03 | Oct 13 '03 | Feb 26' 04 | 3870 | 7480 | 8270 | 0 | 8270 | 8270 | 0% | 0 | 77 | 0 | 0 |  |  | 0 | 0 | -7649.75 | 0 | 0 | 0 | 0 | 0
Task 9 | Engineering & Project Management | 64880 Lot 1 - Task 1,2,3, 4,&8 | SOW 5.0 | April 10 '03 | Nov 15 '03 | April 10 '03 | Feb 26' 04 | 4644 | 5236 | 5800 | 4300 | 1450 | 5750 | 75% | 4350 | 54 | 40 | 4300 |  |  | 4300 | 4300 | -1387.5 | 4300 | 0 | 4300 | 4300 | 4300
[8 empty] | 400343 | 473500 | 473500 | 488109.7533 | 48177.79 | 536287.5433 |  | 425322.21 | 995 | 809.5 | 87021.25 | 457320.52 | 491619.559 | 491619.559 | 491619.559 | 16760.5921 | 488109.7533 | 0 | 488109.7533 | 488109.7533 | 488109.7533
[10 empty] | 90 % --------> | 425000 | [13 empty] | Invoice 90 % of Budgeted--------> | 425000 | 425000 | 425000
Note on R10: Mike Manuel: Lot 1 SubID 0 Seq 10
Note on R11: Mike Manuel: Lot 1 SubID 0 Seq 11
Note on R17: Mike Manuel: Lot 1 SubID 0 Seq 12
Note on R18: Mike Manuel: Lot 1 SubID 0 Seq 13
Note on R16: Mike Manuel: Lot 2 SubID 0 Seq 10 & 15
Note on R13: Mike Manuel: Lot 1 SubID 0 Seq 14
Note on AB7: Mike Manuel: Formula subtract all past invoices from Invoice Total
Note on AA7: Mike Manuel:

## Data Map
MTM Quote Submitted as pdf Source: Visual Manufacturing
MIT Submitted as pdf Source: Visual Manufacturing
Cost and Price Detail Submitted as pdf Source: Excel file with data imported from VM
Labor Input Source: Terminals and Scanners
Cost Summary Source: VM Report
Work Order Status Source: VM Report
Invoice Report Submitted as pdf Source: Excel file with data imported from VM