| DATE | ACTION |  | TIME USED | COMMENT |
| --- | --- | --- | --- | --- |
|  |  |  | SPEB |  |
| 15 Aug 2002 | SPEB Appointment Approved |  | 91 days from SPEB appointment until “Package” ready for Procurement. Primarily due to 77 day period between SPEB appointment and its first meeting. |  |
| 31 Oct 2002 | 1st meeting of SPEB |  |  |  |
|  | Eval Criteria developed |  |  |  |
| 14 Nov 2002 | SOW / Specification issued |  |  |  |
|  |  |  | Procurement |  |
| 15 Nov 2002 | FBO Notice posted (Friday) |  | 4 days |  |
| 18 Nov 2002 | RFP 03-008F issued (Monday) |  |  |  |
|  |  |  | Preparation of Proposals by Offerors |  |
| 18 Nov 2002 | RFP 03-008 issued |  | 61 days for Offerors to prepare Proposals –Two “Proposal due date” extensions granted at the request of Offerors, following PPPL announced tolerance clarifications | Normal response time ≈ 4 weeks |
| 28 Nov 2002 | Drawings/Model posted |  |  |  |
| 3 Jan 2003 | Initial Proposal Due Date |  |  |  |
| 22 Jan 2003 | Revised Proposal Date |  |  |  |
|  |  |  | SPEB Proposal Evaluation / SPEB Report Preparation / Approval |  |
| 22 Jan 2003 | 7 Proposals received |  | 75 days |  |
| 16 Mar 2003 | Initial Briefing of SSO |  |  |  |
| 25 Mar 2003 | SOW revised |  |  |  |
| 7 Apr 2003 | SSO Approved SPEB Report |  |  |  |
|  |  |  | Procurement – Subcontract Award |  |
| 14 Apr 2003 | Major Tool Subcontract signed |  | Major Tool Subcontract signed 7 days after SPEB Report approved, Rohwedder signed 11 days after approval of the Report | Subcontractors advised that revised Specification would be issued about 15 April |
| 18 Apr 2003 | Rohwedder Subcontract signed |  |  |  |
| 246 days between date of SPEB appointment approval by SSO until two Subcontracts awarded - 168 days between date of 1st SPEB meeting and two Subcontracts awarded |