## Sheet1
Task Name | Contract Start | Contract Finish | Plan start | Plan Finish | was start Feb 1 | was finish feb 1 | was start dec 14 | was finish dec 14 | Actual Start | Actual Finish | % complete | Milestone payment | prorated amount
0
Submit Proposal | 2004-07-22 08:00 | 2004-07-22 08:00 | NA | NA | NA | NA | NA | NA | NA | NA | 100 |  | 0
Teleconference to discuss Proposal | 2004-07-26 08:00 | 2004-07-30 17:00 | NA | NA | NA | NA | NA | NA | 2004-07-26 08:00 | 2004-07-30 17:00 | 100 |  | 0
Receive Order | 2004-09-24 17:00 | 2004-09-24 17:00 | NA | NA | NA | NA | NA | NA | 2004-08-13 08:00 | 2004-09-24 17:00 | 100 |  | 0
WO# 65678 PPPL VVSA Lot # 14 | 1999-01-01 08:00 | 2006-01-26 17:00 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | 0
Start Up/Engineering QLI#1 | 2004-09-24 08:00 | 2005-11-04 17:00 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | 0
Process Order | 2004-09-24 08:00 | 2005-05-20 17:00 | 2004-09-24 08:00 | 2005-07-30 | NA | NA | NA | NA | 2004-09-24 08:00 | 2005-07-30 | 100 |  | 0
Sect 5.1 Segmentation Scheme | 2004-11-04 08:00 | 2004-11-19 17:00 | NA | NA | NA | NA | NA | NA | 2004-11-04 08:00 | 2004-11-20 | 100 | 75000 | 75000
Sect 5.1.2 Fiducials | 2005-11-04 08:00 | 2005-11-04 17:00 | 2006-02-23 17:00 | 2006-02-24 17:00 | NA | NA | NA | NA | NA | NA | 98 |  | 0
Sect 5.1.3 Proc Outline & Asc Proc. | 2004-09-24 08:00 | 2005-04-29 17:00 | 2004-09-24 08:00 | 2005-05-31 17:00 | NA | NA | NA | NA | 2004-09-24 08:00 | 2005-05-31 17:00 | 100 | 95000 | 95000
Special Tooling QLI# 2 | 2004-09-20 08:00 | 2005-07-22 17:00 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | 0
Dies & Gages Lot # 10 | 2004-09-20 08:00 | 2005-05-12 17:00 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | 0
Engineering | 2004-09-20 08:00 | 2005-01-28 17:00 | NA | NA | NA | NA | NA | NA | 2004-09-20 08:00 | 2005-01-29 | 100 |  | 0
Procure Materials | 2004-11-15 08:00 | 2005-03-11 17:00 | NA | NA | NA | NA | NA | NA | 2004-11-15 08:00 | 2005-03-11 17:00 | 100 | 315000 | 315000
Machine Complete | 2005-02-21 08:00 | 2005-04-07 17:00 | NA | NA | NA | NA | NA | NA | 2005-02-21 08:00 | 2005-04-07 17:00 | 100 |  | 0
Deburr | 2005-02-28 08:00 | 2005-04-08 17:00 | NA | NA | NA | NA | NA | NA | 2005-02-28 08:00 | 2005-04-08 17:00 | 100 |  | 0
Inspection | 2005-03-01 08:00 | 2005-04-11 17:00 | NA | NA | NA | NA | NA | NA | 2005-03-01 08:00 | 2005-04-11 17:00 | 100 | 340644 | 340644
Development Panels | 2005-03-31 08:00 | 2005-05-12 17:00 | 2005-04-08 08:00 | 2005-06-10 17:00 | NA | NA | NA | NA | 2005-03-31 08:00 | 2005-06-10 17:00 | 100 |  | 0
Fixtures (2) 60 degree Lot # 11 | 2004-10-25 08:00 | 2005-05-13 17:00 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | 0
Engineering | 2004-10-25 08:00 | 2005-03-04 17:00 | NA | NA | NA | NA | NA | NA | 2004-10-25 08:00 | 2005-03-04 17:00 | 100 |  | 0
Procure Materials | 2005-03-06 08:00 | 2005-03-30 17:00 | NA | NA | NA | NA | NA | NA | 2005-03-06 08:00 | 2005-03-30 17:00 | 100 |  | 0
Fab & Machine Complete | 2005-03-13 08:00 | 2005-04-15 17:00 | 2005-04-15 17:00 | 2005-06-10 17:00 | NA | NA | NA | NA | 2005-03-13 08:00 | 2005-06-10 17:00 | 100 |  | 0
Assemble | 2005-03-28 08:00 | 2005-04-29 17:00 | 2005-04-29 17:00 | 2005-06-17 17:00 | NA | NA | NA | NA | 2005-03-28 08:00 | 2005-06-17 17:00 | 100 |  | 0
Deburr | 2005-04-12 08:00 | 2005-05-06 17:00 | 2005-05-06 17:00 | 2005-06-20 17:00 | NA | NA | NA | NA | 2005-04-12 08:00 | 2005-06-20 17:00 | 100 |  | 0
Inspection | 2005-04-22 08:00 | 2005-05-13 17:00 | 2005-05-13 17:00 | 2005-06-23 17:00 | NA | NA | NA | NA | 2005-04-22 08:00 | 2005-06-23 17:00 | 100 |  | 0
Fixture (3) 120 degree Lot # 12 | 2005-01-31 08:00 | 2005-07-22 17:00 | NA | NA | NA | NA | NA | NA | NA | NA |  |  | 0
Engineering | 2005-01-31 08:00 | 2005-05-06 17:00 | 2005-04-15 08:00 | 2005-06-08 17:00 | NA | NA | NA | NA | 2005-01-30 08:00 | 2005-06-08 17:00 | 100 |  | 0
Procure Materials | 2005-04-29 08:00 | 2005-05-13 17:00 | 2005-06-08 17:00 | 2005-06-13 17:00 | NA | NA | NA | NA | 2005-06-08 17:00 | 2005-06-13 17:00 | 100 | 220000 | 220000
Fab & Machine Complete | 2005-05-13 08:00 | 2005-06-23 17:00 | 2005-06-13 17:00 | 2005-07-29 17:00 | NA | NA | NA | NA | 2005-06-13 17:00 | 2005-07-29 17:00 | 100 |  | 0
Assemble | 2005-05-20 08:00 | 2005-07-22 17:00 | 2005-06-22 08:00 | 2005-07-29 17:00 | NA | NA | NA | NA | 2005-07-01 08:00 | 2005-07-29 17:00 | 100 |  | 0
Deburr | 2005-07-04 08:00 | 2005-07-14 17:00 | 2005-07-04 08:00 | 2005-07-29 17:00 | NA | NA | NA | NA | 2005-07-04 08:00 | 2005-07-29 17:00 | 100 |  | 0
Inspection | 2005-07-04 08:00 | 2005-07-14 17:00 | 2005-09-04 08:00 | 2005-07-29 17:00 | NA | NA | NA | NA | 2005-07-07 08:00 | 2005-07-15 17:00 | 100 |  | 0
Procure Vessel Material | 2004-10-29 08:00 | 2005-04-22 17:00 | 2004-10-29 08:00 | 2005-05-31 17:00 | NA | NA | NA | NA | 2004-10-29 08:00 | 2005-05-31 17:00 | 100 | 390000 | 390000
Production Panels Period #1 Lot # 4 | 2005-04-22 08:00 | 2005-05-23 17:00 | 2005-06-10 08:00 | 2005-08-12 17:00 | NA | NA | NA | NA | 2005-06-10 08:00 | 2005-08-12 17:00 | 100 | 260000 | 260000
Production Panels Period #2 Lot # 5 | 2005-05-24 08:00 | 2005-06-24 17:00 | 2005-06-24 17:00 | 2005-09-12 17:00 | NA | NA | NA | NA | 2005-06-24 17:00 | 2005-09-12 17:00 | 100 | 240000 | 240000
Production Panels Period #3 Lot # 6 | 2005-05-30 08:00 | 2005-07-05 17:00 | 2005-06-28 17:00 | 2005-09-16 17:00 | NA | NA | NA | NA | 2005-06-30 08:00 | 2005-09-16 17:00 | 100 | 240000 | 240000
Port Ext,Misc Hardware Period #1 Lot # 7 | 2005-03-23 08:00 | 2005-07-12 17:00 | 2005-04-04 08:00 | 2005-12-09 17:00 | NA | NA | NA | NA | 2005-03-23 08:00 | 2005-12-09 17:00 | 100 |  | 0
Port Ext,Misc Hardware Period # 2 Lot # 8 | 2005-03-23 08:00 | 2005-08-16 17:00 | 2005-04-04 08:00 | 2005-12-12 17:00 | NA | NA | NA | NA | 2005-03-23 08:00 | 2005-12-12 17:00 | 100 |  | 0
Port Ext,Misc Hardware Period # 3 Lot # 9 | 2005-03-23 08:00 | 2005-09-13 17:00 | 2005-04-04 08:00 | 2006-01-23 17:00 | NA | NA | NA | NA | 2005-04-04 08:00 | 2006-01-23 17:00 | 100 |  | 0
(1) Spacer (3) Port Ext. Fixtures Lot # 13 | 2005-06-06 08:00 | 2005-09-16 17:00 | 2005-09-16 17:00 | 2006-01-28 17:00 | NA | NA | NA | NA | 2005-09-16 17:00 | 2006-01-28 17:00 | 100 |  | 0
First 120 deg seg QLI #3 Lot # 1 | 1999-01-01 08:00 | NA | 2005-06-10 08:00 | 2005-09-23 17:00 | NA | NA | NA | NA | NA | NA |  |  | 0
1st 60 deg segment | 2005-05-02 08:00 | 2005-06-13 17:00 | 2005-06-10 08:00 | 2005-08-12 17:00 | NA | NA | NA | NA | 2005-06-17 08:00 | 2005-08-12 17:00 | 100 |  | 0
2nd 60 deg segment | 2005-05-23 08:00 | 2005-07-08 17:00 | 2005-06-23 08:00 | 2005-08-15 17:00 | NA | NA | NA | NA | 2005-07-07 08:00 | 2005-08-15 17:00 | 100 |  | 0
Join two pieces | 2005-07-10 08:00 | 2005-08-02 17:00 | 2005-08-12 08:00 | 2005-09-08 17:00 | NA | NA | NA | NA | 2005-08-12 08:00 | 2005-09-12 17:00 | 100 | 400000 | 400000
Machine for Ports | 2005-08-03 08:00 | 2005-08-18 17:00 | 2005-09-08 08:00 | 2005-09-23 17:00 | NA | NA | NA | NA | 2005-09-12 08:00 | 2005-10-01 17:00 | 100 |  | 0
Weld Ports | 1999-01-01 08:00 | 2005-09-16 17:00 | 2005-10-05 08:00 | 2006-01-17 17:00 | NA | NA | NA | NA | 2005-10-05 08:00 | 2005-12-01 17:00 |  |  | 0
Round Ports (less dome ports) | 1999-01-01 08:00 | NA | 2005-10-05 08:00 | 2005-12-09 17:00 | NA | NA | NA | NA | 2005-10-05 08:00 | 2005-12-07 17:00 | 100 |  | 0
Dome Ports 17 & 18 | 1999-01-01 17:00 | NA | 2005-12-09 17:00 | 2005-12-16 17:00 | NA | NA | NA | NA | 2005-12-07 17:00 | 2005-12-12 17:00 | 100 |  | 0
(8) Bosses | 1999-01-01 17:00 | NA | 2005-12-16 08:00 | 2005-12-20 17:00 | NA | NA | NA | NA | 2005-12-12 17:00 | 2005-12-20 17:00 | 100 |  | 0
100% Laser Scan Layout and Weld Flanges | 1999-01-01 17:00 | NA | 2005-12-20 08:00 | 2006-01-09 17:00 | NA | NA | NA | NA | 2005-12-20 08:00 | 2006-01-09 17:00 | 100 |  | 0
Polish and Rough Clean Interior | 1999-01-01 17:00 | NA | 2006-01-09 08:00 | 2006-01-16 17:00 | NA | NA | NA | NA | 2006-01-09 08:00 | 2006-01-16 17:00 | 100 |  | 0
Weld on Spacer and Covers | 1999-01-01 17:00 | NA | 2006-01-16 08:00 | 2006-01-17 17:00 | NA | NA | NA | NA | 2006-01-16 08:00 | 2006-01-17 17:00 | 100 |  | 0
Vacuum Test | 1999-01-01 08:00 | 2005-10-21 17:00 | 2006-01-17 08:00 | 2006-02-17 17:00 | NA | NA | NA | NA | NA | NA |  |  | 0
First Vacuum Test | 1999-01-01 08:00 | NA | 2006-01-17 08:00 | 2006-01-24 17:00 | NA | NA | NA | NA | 2006-01-17 08:00 | 2006-01-24 17:00 | 100 |  | 0
Heat Blankets | 1999-01-01 08:00 | NA | 2006-01-24 17:00 | 2006-01-30 17:00 | NA | NA | NA | NA | 2006-01-24 17:00 | 2006-01-30 17:00 | 100 |  | 0
Thermal Cycle | 1999-01-01 08:00 | NA | 2006-01-30 17:00 | 2006-02-08 17:00 | NA | NA | NA | NA | 2006-01-30 17:00 | 2006-02-08 17:00 | 100 |  | 0
Final Vacuum Test | 1999-01-01 08:00 | NA | 2006-02-08 17:00 | 2006-02-15 17:00 | NA | NA | NA | NA | 2006-02-08 17:00 | 2006-02-15 17:00 | 100 |  | 0
Laser check after Vacuum Test | 1999-01-01 08:00 | NA | 2006-02-15 17:00 | 2006-02-17 17:00 | NA | NA | NA | NA | 2006-02-15 17:00 | 2006-02-17 17:00 | 100 |  | 0
Cut Off Ports | 2005-10-24 08:00 | 2005-11-04 17:00 | 2006-02-17 17:00 | 2006-03-06 17:00 | NA | NA | NA | NA | 2006-02-17 17:00 | 2006-03-06 17:00 | 100 |  | 0
Final Machine | 2005-09-19 08:00 | 2005-10-07 17:00 | 2006-03-06 17:00 | 2006-03-15 17:00 | 2006-03-06 17:00 | 2006-03-13 17:00 | NA | NA | NA | NA |  |  | 0
Tack on Ports, weld on tube and block (NEW) | 1999-01-01 08:00 | NA | 2006-03-15 17:00 | 2006-03-24 17:00 | NA | NA | NA | NA | NA | NA |  |  | 0
Final Inspection | 1999-01-01 08:00 | 1999-01-01 17:00 | 2006-03-27 08:00 | 2006-03-31 17:00 | 2006-03-13 17:00 | 2006-03-20 17:00 | NA | NA | NA | NA |  |  | 0
Pack for Shipping #1 | 2005-11-07 08:00 | 2005-11-11 17:00 | 2006-04-03 08:00 | 2006-04-07 17:00 | 2006-03-20 17:00 | 2006-03-24 17:00 | NA | NA | NA | NA |  |  | 0
Receive at PPPL | 2005-11-14 08:00 | 2005-11-15 17:00 | 2006-04-10 08:00 | 2006-04-12 17:00 | 2006-03-24 17:00 | 2006-03-27 17:00 | NA | NA | NA | NA |  | 375560 | 0
Second 120 deg seg QLI# 3 Lot # 2 | 1999-01-01 08:00 | NA | 2005-08-12 08:00 | 2005-12-30 17:00 | NA | NA | NA | NA | NA | NA |  |  | 0
60 deg segment | 2005-06-24 08:00 | 2005-07-22 17:00 | 2005-08-12 08:00 | 2005-09-09 17:00 | NA | NA | NA | NA | 2005-08-12 08:00 | 2005-09-09 17:00 | 100 |  | 0
60 deg segment | 2005-07-25 08:00 | 2005-08-19 17:00 | 2005-08-26 08:00 | 2005-10-07 17:00 | NA | NA | NA | NA | 2005-08-26 08:00 | 2005-10-07 17:00 | 100 |  | 0
Join two pieces | 2005-08-22 08:00 | 2005-09-05 17:00 | 2005-10-07 17:00 | 2005-11-16 08:00 | NA | NA | NA | NA | 2005-10-07 17:00 | 2005-11-16 08:00 | 100 | 405000 | 405000
Machine for Ports | 2005-09-05 08:00 | 2005-09-23 17:00 | 2006-01-04 08:00 | 2006-01-19 17:00 | NA | NA | NA | NA | 2005-12-27 08:00 | 2006-01-19 17:00 | 100 |  | 0
Weld Ports | 1999-01-01 08:00 | 2005-10-21 17:00 | 2006-01-20 08:00 | 2006-03-03 17:00 | NA | NA | NA | NA | NA | NA |  |  | 0
NB Port | 1999-01-01 08:00 | NA | 2006-01-20 08:00 | 2006-01-25 17:00 | NA | NA | NA | NA | 2006-01-20 08:00 | 2006-01-25 17:00 | 100 |  | 0
Port 4 | 1999-01-01 08:00 | NA | 2006-01-25 17:00 | 2006-01-31 17:00 | NA | NA | NA | NA | 2006-01-25 17:00 | 2006-01-31 17:00 | 100 |  | 0
Port 12 | 1999-01-01 08:00 | NA | 2006-01-31 17:00 | 2006-02-06 17:00 | NA | NA | NA | NA | 2006-01-31 17:00 | 2006-02-06 17:00 | 100 |  | 0
Domes | 1999-01-01 08:00 | NA | 2006-02-06 17:00 | 2006-02-09 17:00 | NA | NA | NA | NA | 2006-02-06 17:00 | 2006-02-09 17:00 | 100 |  | 0
Round Ports (less dome ports) | 1999-01-01 08:00 | NA | 2006-02-09 17:00 | 2006-02-15 17:00 | NA | NA | NA | NA | 2006-02-09 17:00 | 2006-02-15 17:00 | 100 |  | 0
Dome Ports 17 & 18 | 1999-01-01 17:00 | NA | 2006-02-15 17:00 | 2006-02-20 17:00 | NA | NA | NA | NA | 2006-02-15 17:00 | 2006-02-20 17:00 | 100 |  | 0
(8) Bosses | 1999-01-01 17:00 | NA | 2006-02-20 17:00 | 2006-03-03 17:00 | 2006-02-20 17:00 | 2006-02-23 17:00 | NA | NA | 2006-02-20 17:00 | 2006-02-23 17:00 | 10 |  | 0
100% Laser Scan Layout and Weld Flanges | 1999-01-01 17:00 | NA | 2006-03-06 08:00 | 2006-03-10 17:00 | 2006-02-23 17:00 | 2006-03-06 17:00 | NA | NA | NA | NA |  |  | 0
Polish and Rough Clean Interior | 1999-01-01 17:00 | NA | 2006-03-13 08:00 | 2006-03-15 17:00 | 2006-03-06 17:00 | 2006-03-09 08:00 | NA | NA | NA | NA |  |  | 0
Weld on Spacer and Covers | 1999-01-01 17:00 | NA | 2006-03-16 08:00 | 2006-03-17 17:00 | 2006-03-09 08:00 | 2006-03-13 17:00 | NA | NA | NA | NA |  |  | 0
Vacuum Test | 1999-01-01 08:00 | 2005-11-25 17:00 | 2006-03-20 08:00 | 2006-03-31 17:00 | 2006-03-14 08:00 | 2006-04-12 17:00 | NA | NA | NA | NA |  |  | 0
First Vacuum Test | 1999-01-01 08:00 | NA | 2006-03-20 08:00 | 2006-03-24 17:00 | 2006-03-14 08:00 | 2006-03-21 08:00 | NA | NA | NA | NA |  |  | 0
Heat Blankets (deleted) | 1999-01-01 08:00 | NA | NA | NA | 2006-03-21 08:00 | 2006-03-24 08:00 | NA | NA | NA | NA |  |  | 0
Thermal Cycle (deleted) | 1999-01-01 08:00 | NA | NA | NA | 2006-03-24 08:00 | 2006-03-30 08:00 | NA | NA | NA | NA |  |  | 0
Final Vacuum Test | 1999-01-01 08:00 | NA | 2006-03-27 08:00 | 2006-03-28 17:00 | 2006-03-30 08:00 | 2006-04-10 08:00 | NA | NA | NA | NA |  |  | 0
Laser check after Vacuum Test | 1999-01-01 08:00 | NA | 2006-03-29 08:00 | 2006-03-31 17:00 | 2006-04-10 08:00 | 2006-04-12 17:00 | NA | NA | NA | NA |  |  | 0
Cut Off Ports | 2005-11-28 08:00 | 2005-12-09 17:00 | 2006-04-03 08:00 | 2006-04-11 17:00 | 2006-04-12 17:00 | 2006-04-26 17:00 | NA | NA | NA | NA |  |  | 0
Final Machine | 2005-10-24 08:00 | 2005-11-11 17:00 | 2006-04-12 08:00 | 2006-04-21 17:00 | 2006-04-26 17:00 | 2006-05-03 17:00 | NA | NA | NA | NA |  |  | 0
Tack on Ports, weld on tube and block (NEW) | 1999-01-01 08:00 | NA | 2006-04-24 08:00 | 2006-05-02 17:00 | NA | NA | NA | NA | NA | NA |  |  | 0
Final Inspection | 1999-01-01 08:00 | NA | 2006-05-03 17:00 | 2006-05-09 17:00 | NA | NA | NA | NA | NA | NA |  |  | 0
Pack for Shipping #2 | 2005-12-12 08:00 | 2005-12-16 17:00 | 2006-05-09 17:00 | 2006-05-12 17:00 | NA | NA | NA | NA | NA | NA |  |  | 0
Receive at PPPL | 2005-12-19 08:00 | 2005-12-22 17:00 | 2006-05-12 17:00 | 2006-05-15 17:00 | NA | NA | NA | NA | NA | NA |  | 375000 | 0
Third 120 deg seg QLI# 3 Lot # 3 | 1999-01-01 08:00 | NA | 2005-09-30 08:00 | 2006-05-12 17:00 | NA | NA | NA | NA | NA | NA |  |  | 0
60 deg segment | 2005-08-01 08:00 | 2005-08-26 17:00 | 2005-09-30 08:00 | 2006-01-23 08:00 | NA | NA | NA | 2006-01-06 17:00 | 2005-09-30 08:00 | 2006-01-23 08:00 | 100 |  | 0
60 deg segment | 2005-09-04 08:00 | 2005-09-30 17:00 | 2005-12-01 08:00 | 2006-01-31 17:00 | NA | NA | NA | 2006-01-06 17:00 | 2005-12-01 08:00 | 2006-01-31 17:00 | 100 |  | 0
Join two pieces | 2005-10-03 08:00 | 2005-10-17 17:00 | 2006-01-23 08:00 | 2006-02-10 17:00 | NA | NA | 2006-01-09 08:00 | 2006-01-19 17:00 | 2006-01-23 08:00 | 2006-02-10 17:00 | 100 | 375000 | 375000
Machine for Ports | 2005-10-17 08:00 | 2005-10-28 17:00 | 2006-03-16 08:00 | 2006-04-21 17:00 | 2006-02-02 17:00 | 2006-02-16 17:00 | 2006-01-19 17:00 | 2006-02-02 17:00 | NA | NA |  |  | 0
Weld Ports | 1999-01-01 08:00 | 2005-11-18 17:00 | 2006-03-13 08:00 | 2006-04-06 17:00 | 2006-02-16 17:00 | 2006-03-30 17:00 | 2006-02-06 08:00 | 2006-03-30 17:00 | NA | NA |  |  | 0
NB | 1999-01-01 08:00 | NA | 2006-03-13 08:00 | 2006-03-17 08:00 | 2006-02-16 17:00 | 2006-02-22 17:00 | 2006-02-06 08:00 | 2006-02-10 08:00 | NA | NA |  |  | 0
Port 4 | 1999-01-01 08:00 | NA | 2006-03-17 08:00 | 2006-03-22 08:00 | 2006-02-22 17:00 | 2006-02-28 17:00 | 2006-02-10 08:00 | 2006-02-17 08:00 | NA | NA |  |  | 0
Port 12 | 1999-01-01 08:00 | NA | 2006-03-22 08:00 | 2006-03-27 08:00 | 2006-03-01 17:00 | 2006-03-07 17:00 | 2006-02-17 08:00 | 2006-02-24 08:00 | NA | NA |  |  | 0
Domes | 1999-01-01 08:00 | NA | 2006-03-27 08:00 | 2006-03-29 08:00 | 2006-03-08 08:00 | 2006-03-15 17:00 | 2006-02-24 08:00 | 2006-03-01 08:00 | NA | NA |  |  | 0
Round Ports (less dome ports) | 1999-01-01 08:00 | NA | 2006-03-29 08:00 | 2006-04-03 17:00 | 2006-03-16 08:00 | 2006-03-23 17:00 | 2006-03-01 08:00 | 2006-03-09 08:00 | NA | NA |  |  | 0
Dome Ports 17 & 18 | 1999-01-01 17:00 | NA | 2006-04-03 08:00 | 2006-04-06 17:00 | 2006-03-24 08:00 | 2006-03-29 17:00 | 2006-03-09 08:00 | 2006-03-15 08:00 | NA | NA |  |  | 0
(8) Bosses | 1999-01-01 17:00 | NA | 2006-04-07 08:00 | 2006-04-14 17:00 | 2006-03-30 08:00 | 2006-04-04 17:00 | 2006-03-15 08:00 | 2006-03-21 08:00 | NA | NA |  |  | 0
100% Laser Scan Layout and Weld Flanges | 1999-01-01 17:00 | NA | 2006-04-17 08:00 | 2006-04-20 17:00 | 2006-04-05 08:00 | 2006-04-12 17:00 | 2006-03-21 08:00 | 2006-03-20 17:00 | NA | NA |  |  | 0
Polish and Rough Clean Interior | 1999-01-01 17:00 | NA | 2006-04-21 08:00 | 2006-04-26 08:00 | 2006-04-13 08:00 | 2006-04-17 17:00 | 2006-03-21 08:00 | 2006-03-24 17:00 | NA | NA |  |  | 0
Weld on Spacer and Covers | 1999-01-01 17:00 | NA | 2006-04-26 08:00 | 2006-04-28 17:00 | 2006-04-17 08:00 | 2006-04-21 17:00 | 2006-03-27 08:00 | 2006-03-30 17:00 | NA | NA |  |  | 0
Vacuum Test | 1999-01-01 08:00 | 2005-12-17 17:00 | 2006-05-01 08:00 | 2006-05-12 17:00 | 2006-04-24 08:00 | 2006-05-09 17:00 | 2006-03-31 08:00 | 2006-05-09 17:00 | NA | NA |  |  | 0
First Vacuum Test | 1999-01-01 08:00 | NA | 2006-05-01 08:00 | 2006-05-08 17:00 | 2006-04-24 08:00 | 2006-05-01 17:00 | 2006-03-31 08:00 | 2006-04-07 17:00 | NA | NA |  |  | 0
Heat Blankets (deleted) | 1999-01-01 08:00 | NA | NA | NA | NA | NA | 2006-04-10 08:00 | 2006-04-12 17:00 | NA | NA |  |  | 0
Thermal Cycle (deleted) | 1999-01-01 08:00 | NA | NA | NA | NA | NA | 2006-04-13 08:00 | 2006-04-19 17:00 | NA | NA |  |  | 0
Final Vacuum Test | 1999-01-01 08:00 | NA | 2006-05-09 08:00 | 2006-05-10 17:00 | 2006-05-05 17:00 | 2006-05-12 17:00 | 2006-04-20 08:00 | 2006-05-04 17:00 | NA | NA |  |  | 0
Laser check after Vacuum Test | 1999-01-01 08:00 | NA | 2006-05-11 08:00 | 2006-05-12 17:00 | 2006-05-15 08:00 | 2006-05-19 17:00 | 2006-05-05 08:00 | 2006-05-09 17:00 | NA | NA |  |  | 0
Cut Off Ports | 2006-01-05 08:00 | 2006-01-17 17:00 | 2006-05-15 08:00 | 2006-05-19 17:00 | 2006-05-22 08:00 | 2006-05-29 17:00 | 2006-05-10 08:00 | 2006-05-24 17:00 | NA | NA |  |  | 0
Final Machine | 2005-11-21 08:00 | 2005-12-02 17:00 | 2006-05-22 08:00 | 2006-05-26 17:00 | 2006-05-29 08:00 | 2006-06-05 17:00 | 2006-05-25 08:00 | 2006-06-01 17:00 | NA | NA |  |  | 0
Tack on Ports, weld on tube and block (NEW) | 1999-01-01 08:00 | NA | 2006-05-29 08:00 | 2006-06-05 17:00 | NA | NA | NA | NA | NA | NA |  |  | 0
Final Inspection | 1999-01-01 08:00 | NA | 2006-06-06 08:00 | 2006-06-09 17:00 | NA | NA | 2006-06-02 08:00 | 2006-06-08 17:00 | NA | NA |  |  | 0
Pack for Shipping #3 | 2006-01-17 08:00 | 2006-01-20 17:00 | 2006-06-09 08:00 | 2006-06-12 17:00 | NA | NA | 2006-06-09 08:00 | NA | NA | NA |  |  | 0
Receive at PPPL | 2006-01-23 08:00 | 2006-01-26 17:00 | 2006-06-13 08:00 | 2006-06-16 17:00 | NA | NA | NA | NA | NA | NA |  | 375000 | 0
Tooling Deliveries | 2006-01-23 08:00 | 2006-02-01 17:00 | 2006-06-13 08:00 | 2006-06-23 17:00 | NA | NA | NA | NA | NA | NA |  |  | 0
Pack for PPPL - Tooling | 2006-01-23 08:00 | 2006-01-27 17:00 | 2006-06-13 08:00 | 2006-06-19 17:00 | NA | NA | NA | NA | NA | NA |  |  | 0
Receive at PPPL - Tooling | 2006-01-30 08:00 | 2006-02-01 17:00 | 2006-06-20 08:00 | 2006-06-23 17:00 | NA | NA | NA | NA | NA | NA |  | 486000 | 0
Total value of work performed | [12 empty] | 3355644