Record of Revisions

| Revision | Date | Description of Changes |
| --- | --- | --- |
| 0 | 1/13/2005 | Initial Issue |
| 1 | 1/19/2005 | Changed to a flow chart process and revised process. |

Applicability

This procedure covers the process for preparing and processing Requests for Deviation (RFDs) on the NCSX Project.

Introduction

Prior to performing a specified step in a manufacturing or fabrication process, either the Project or a supplier may identify  an alternative design/method/material to the requirements that could result in technical, cost, or schedule savings.  The documentation to formally define this proposed departure from the established performance or design requirements is called a Request for Deviation (RFD).  The RFD is a specific written request to depart from a particular requirement(s) of the item’s current approved technical documentation.  A RFD shall be processed and adjudicated under the Engineering Change Process (ECP) process defined in the NCSX Configuration Management Plan (NCSX-PLAN-CMP) and the accompanying NCSX Configuration Control Procedure (NCSX-PROC-002).  Until the ECP associated with the RFD is approved, the item or process may not deviate from the technical requirements. The RFD may be either a letter or tabular format and shall contain the specific required information as defined in this procedure.

A deviation is distinguished from non-conformance reports (NCRs) in that NCRs address the departure after the manufacturing step that incorporates the requirement (design/method/material) has begun.  The processing of NCRs is addressed in PPPL Quality Assurance Procedure QA-005, “Control of Nonconformances.”

Referenced Documents

| NCSX-PLAN-CMP | NCSX Configuration Management Plan |
| --- | --- |
| NCSX-PROC-002 | NCSX Configuration Control |
| QA-005 | Control of Non-conformances |

Attachment:

1 – Necessary Information Needed on a RFD

ATTACHMENT 1

The RFD may be provided in any format (i.e., letter, tabular, or supplier format), but must contain at a minimum the following information in sufficient detail to permit NCSX Project assessment of the RFD:

- Initiator Name and Organization

- Date RFD was initiated

- RFD Title – short description of the deviation requested

- List of impacted documents (e.g., specification and sections, each model and drawing, SOW sections – if the SOW has been used to convey technical information).  Be as specific as possible.

- Impact on cost, schedule, and interfaces with other items – if none so state.  If there are impacts be as specific as possible.

- Full description of the deviation requested, including specific item/part impacted by this RFD and the rationale on why this deviation is needed. Include amplifying information that may assist in the NCSX Project’s assessment of this RFD.

- Attachments – to include e-mail or letter requests or sketches

- Signature of the initiator (actual or electronic or e-mail approval are all satisfactory).

The following sections of the RFD shall be completed by the Systems Engineering Manager:

- RFD number (using format of NCSX-RFD-XX-###-RRR) where:

  - XX is the two digit WBS element identifier;

  - ### is a sequential number; and

  - RRR is the revision number of the RFD.

- Project Disposition – provide contract addendum (if supplier initiated) and the ECP that approved the RFD.

Sample RFD Form

| NCSX RFD | Number: | RFD Description: |
| --- | --- | --- |
| Initiator: | Organization: |
| List of Impacted Documents: |
| Cost Impact: (If none, so state) |
| Schedule Impact: (If none, so state) |
| Impact on Interfaces with Other WBS Elements/Items: (If none, so state) |
| Full Description of the Deviation Requested: (Use continuation pages, e-mails, letter, sketches, etc. as needed and include amplifying information as appropriate) |
| Attachments: |
| Initiator Signature: Date: |
| Project Disposition (Include ECP Number): |

# Text boxes

Yes

Systems Engineering Support Manager and Design Integration Manager process changes to technical documentation, obtain approvals, and then post on the appropriate NCSX Engineering or Pro/INTRALink database.

No

RLM Recommends Approval?

END

No

PTR (if procurement) or Job Manager coordinates refinement and recommended disposition of RFD with Supplier (if procurement), WBS Manager, RLM, and Systems Engineering Support Manager.

END

- PPPL Procurement Representative  notifies Supplier that the RFD has been rejected; or

- Systems Engineering Support Manager  notifies Job Manager that the RFD has been rejected.

PPPL Procurement Representative (if existing contract) notifies Supplier via contract addendum:

- That RFD has been approved;

- Of the forthcoming changes in contract documents that will be made; and

- That the Supplier is authorized to proceed.

DI posts updated contract information on FTP server per PROC-006.

Impacts Existing Contract?

Job Manager and WBS Manager coordinates implementation of approved changes to contract documents (specifications, models, drawings, etc.) per NCSX and PPPL procedures.

PPPL Procurement Representative notifies the supplier that they are NOT authorized to proceed with the proposed departure until such time that the RFD is approved.

Yes

Supplier RFD?

No

Initiator (Anyone on the Project or a Supplier) proposes an alternative design, approach, material, etc. than currently specified.

Systems Engineering Support Manager notifies Project personnel that the ECP has been approved.

END

PPPL Procurement Representative notifies supplier that revised contract documents have been posted.

Yes

1

Supplier (if existing contract) or Job Manager prepares and submits RFD:

- To the PPPL Procurement Technical Representative (PTR) and PPPL Procurement Representative if Supplier RFD.  PTR then  provides copy to the Systems Engineering Support Manager; or

- To the Systems Engineering Support Manager if Project RFD.

Systems Engineering Support Manager processes ECP per PROC-002.

ECP Approved?

No

Yes

1