# PMW Budget - Rohwedder/Princeton PVVS project – April 21/04

|  | Original quote | Actual costs to March 23/04 | ACTUAL COSTS TO (Apr. 8/04) | ESTIMATED COST OF COMPLETION (based on revised completion date May 14/04) | Detailed description |
| --- | --- | --- | --- | --- | --- |
| 1. Non-recurring Expenses | 320 @ $42 13,440.00 | 1,116 @ $42 46,872.00 |  |  | Additional direct labour: engineering and project management expenses incurred while attempting to work out issues with measurement and bringing segments into tolerance. Additional indirect labour: QA |
| 2. Direct Labour | 560 @ $42 23,520.00 | 850 @ $42 35,700.00 sub contract mach. 5,000.00 40,700.00 | 568 @ $42 23,856.00 | 530 @ 42 22,260.00 |  |
| 3. Indirect Labour | 120 @ $42 5,040.00 | 490 @ $42 20,580.00 | 500 @ $42 21,000.00 | 300 @ 42 12,600.00 |  |
| 4. Direct Material | 31,500.00 + Pro E 14,000.00 45,500.00 | 74,585.00 + Pro E 11,809.00 86,394.00 | 2,000.00 |  |  |
| 5. Indirect Material | 2,500.00 | 4,200.00 | 2,000.00 |  |  |
| 6. Sub-contractor Dies & pressing Stress relief Rolling Welding | 65,200.00 | 8,250.00 135.00 1,200.00 2,900.00 700.00 13,185.00 | 3,300.00 | 19,000.00 | Cost over-run from sub-contractor |
| 7. Shipping | 1,800.00 | 900 | 2,100.00 |  |  |
| Sub-total | $157,000.00 | 212,831.00 Faro ($3000 US/mo @ 4 mox1.32 Cdn) 15,840.00 weld equipment ($600/mo @ 2mo.) 1,200. $229,871.00 | 54,256.00 | 10,000.00 | Estimated costs of additional Faro support necessary to complete project. |
| Markup | (2%) 3,140.00 | (0%) | (0%) | (0%) |  |
| Total | Cdn. $160,140.00 | Cdn. $229,871.00 | Cdn. $54,256.00 | Cdn. $63,860.00 |  |
| Exchange | 0.78 | 0.78 | 0.78 | 0.78 |  |
|  | US 125,000.00 Plus Faro 10,100.00 $135,100.00 | US $179,299.00 | US $42,320.00 | US $49,811.00 | Cost difference: $49,811.00 |