|  | SC Project Review of NCSX, April 8-10, 2008 |  |
| --- | --- | --- |

NCSX Fueling and Vacuum

Pumping Systems

W. Blanchard

WBS 21 and 22 Manager

- Differentially pumped RGA

Design Features

- Two legacy 1500 l/s TMPs

- System monitored, controlled

and interlocked using a PLC

Requirements

- Minimum effective pumping

speed of 1300 l/s

Interfaces

- Design consists of one

pumping duct off of one NB

transition piece and a vertical

24” duct

VACUUM PUMPING SYSTEM

SC Project Review of NCSX, April 8-10, 2008

W. Blanchard - page 2

|  |  | $ |  |  |  |  |  |  | Hours |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task ID |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Title I and II Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Preliminary Design / Management / Admin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Engr Work Planning & Design |  | 180 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Design Hardware |  |  |  |  | 80 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Design PLC Controls |  |  |  |  |  |  |  |  |  |  | 336 |  |  |  |  |  |  |
|  | Testing Equipment |  |  |  |  | 88 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Drafting Support (Electrical) |  |  |  |  |  |  | 160 |  |  |  |  |  |  |  |  |  |  |
|  | Drafting Support (Mechanical) |  |  |  |  |  |  | 20 |  |  |  |  |  |  |  |  |  |  |
| Final Design / Management / Admin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Engr Work Planning & Design |  | 220 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Mechanical Design |  |  |  |  | 88 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Design PLC Controls |  |  |  |  |  |  |  |  |  |  | 336 |  |  |  |  |  |  |
|  | Electrical Design |  |  |  |  |  |  |  |  |  |  | 64 |  |  |  |  |  |  |
|  | Electrical Design/Drafting |  |  |  |  |  |  |  |  | 272 |  |  |  |  |  |  |  |  |
|  | Drafting Support (Mechanical) |  |  |  |  |  |  |  |  | 60 |  |  |  |  |  |  |  |  |
| Subtotal Title I & II Design |  |  | 400 | 0 |  | 256 | 0 | 180 |  | 332 |  | 736 | 0 |  | 0 |  | 0 |  |
| Title III |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Engr Work Planning & Design |  | 120 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Maint/Repair Mech Pumps |  |  |  |  | 80 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Repair/Cal. Instrumentation |  |  |  |  | 80 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Electrical Installation |  |  |  |  |  | 668 |  |  |  |  |  |  |  |  |  |  |  |
|  | Fabricate/Install Hardware |  |  |  |  | 120 | 520 |  |  |  |  |  |  |  |  |  |  |  |
|  | Fabricate/Install PLC Controls |  |  |  |  |  |  |  |  |  |  | 352 |  |  |  |  |  |  |
|  | Integrated System Testing |  | 40 |  |  |  |  |  |  |  |  | 80 |  |  |  |  |  |  |
|  | Materials and Supplies | $ 118,000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Subtotal Title III |  | $ 118,000 | 160 |  | 0 | 280 | 1188 |  | 0 |  | 0 | 432 |  | 0 |  | 0 |  | 0 |

|  | SC Project Review of NCSX, April 8-10, 2008 W. Blanchard - page 3 |  |
| --- | --- | --- |

Cost Estimate

* Based on NSTX costs for system which is similar to the proposed NCSX design * Input from engineers and personnel familiar with various parts of the project

|  | SC Project Review of NCSX, April 8-10, 2008 W. Blanchard - page 4 |  |
| --- | --- | --- |

Project Schedule

'Design in FY09, procurements in FY10 and fabrication/installation in FY11

| Uncertainty of the Estimate |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | High | Medium | Low | Uncertainty | Comments/Other Considerations |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Range (%) |  |  |  |  |  |  |  |  |
|  | Design Maturity |  |  |  | X |  | There have been no design reviews therefore the design is not fixed. |  |  |  |  |  |  |  |
|  |  |  |  |  |  | -1 5%/+25% |  |  |  |  |  |  |  |  |
|  | Design Complexity |  |  |  | X |  | Anticipated to only require standard components |  |  |  |  |  |  |  |
|  | Other Comments: |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | SC Project Review of NCSX, April 8-10, 2008 W. Blanchard - page 5 |  |
| --- | --- | --- |

Risk Assessment: Low

Risk:

* Equipment or component failure

Mitigation:

* All components outside of coils and cryostat and easily accessible * Standard equipment and hardware

* Replacement parts for major components in-house

- Pulse valve controlled from central computing

- System monitored, controlled and interlocked using a PLC

Interfaces

- Injectors located at the three upper P12 port covers

Design Features

- Includes gas delivery manifold, pumpout system and gauging

Requirements

- Three gas injection systems with each injector having a maximum flow rate >50 T-l/s

FUELING SYSTEM

SC Project Review of NCSX, April 8-10, 2008

W. Blanchard - page 6

$

Task ID

Hours

Cost Estimate

* Based on NSTX costs for system which is similar to the proposed NCSX design * Input from engineers and personnel familiar with various parts of the project

80	0	120 528	0	272	0	0

40	80

192

288

120 240

40

136	0	144	0	236 560	0	0

68

144

Materials and Supplies	$	38,000

Subtotal Title III	$	38,000

Integrated System Testing

Install PLC Controls

Fabricate & Install Hardware (Electrical)

Fabricate & Install Hardware

Engr Work Planning & Design

Title III

Subtotal Title I & II Design

Drafting Support (Mechanical)

Drafting Support (Electrical)

Design PLC Controls

Design Gas handling Hardware

Final Design / Management / Admin Engr Work Planning & Design

Drafting Support

Design PLC Controls

Design Gas handling Hardware

Title I and II Design

Preliminary Design / Management / Admin

Engr Work Planning & Design

FUELING SYSTEM

SC Project Review of NCSX, April 8-10, 2008

W. Blanchard - page 7

48

88

24

96

48

448

112

|  | SC Project Review of NCSX, April 8-10, 2008 W. Blanchard - page 8 |  |
| --- | --- | --- |

Project Schedule

Design in FY09, procurements in FY10 and fabrication/installation in FY11

| Uncertainty of the Estimate |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | High | Medium | Low | Uncertainty | Comments/Other Considerations |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Range (%) |  |  |  |  |  |  |  |  |
|  | Design Maturity |  |  |  | X |  | There have been no design reviews therefore the design is not fixed. |  |  |  |  |  |  |  |
|  |  |  |  |  |  | -1 5%/+25% |  |  |  |  |  |  |  |  |
|  | Design Complexity |  |  |  | X |  | Anticipated to only require standard components |  |  |  |  |  |  |  |
|  | Other Comments: |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | SC Project Review of NCSX, April 8-10, 2008 W. Blanchard - page 9 |  |
| --- | --- | --- |

Risk Assessment: Low

Risk:

* Equipment or component failure

Mitigation:

* All components outside of coils and cryostat and easily replaceable * Standard equipment and hardware