FIELD PERIOD ASSEMBLY

SEP 15, 2003

Mike Cole, Art Brooks, Tom Brown, Jim Chrzanowski, Dave Conner,  Paul Goranson, Tom Meighan, Brad Nelson,. Bob Parsells, Erick Perry, Steve Raftopoulos, Mike Viola, Al Williams, Dave Williamson

FIELD PERIOD ASSEMBLY

The TFTR Test Cell, Figure 1.0 ,facility has been identified as the area to be used for the assembly of the Field Period Assembly.

The Field Period Assembly area will be shared with the modular coil assembly which will also be located in the this area. The TFTR test cell is approximately 121ft wide by 154 ft. long. The modular coil area will occupy the west side  of the building. The Field Period Assembly will be located in the East side of the building. Princeton will coordinate the cleanup and installation of fixtures that will be used for Field Period Assembly. Utilities such as instrument air, power and data ports will be installed based on the needs of each fixture. At the present time current utility sizing is adequate for Field Period Assembly. Data ports will be installed as needed for the metrology data that will be used during the assembly process.

The building crane will be shared with the modular coil assy. The crane capabilities are shown in Figure 2.0 and Table 1.0.

Table 1.0

| Description | Capacity |
| --- | --- |
| Crane Capacity | 110 Ton Big Hook 25 Ton Small Hook (micro control) |
| Hook Height | 42’ main hook motorized rotation small hook freely rotates height 42 ft plus |

The  Field Period Assembly area will make use of the crane primarily for picking up major components such as the Vacuum Vessel, Modular Coil, TF Coil and the Field Period Assembly. When components arrive from the vendor they will be inspected for damage and lifted off the truck and placed in an area designated for receiving inspection. All necessary documentation will be reviewed and any additional testing will be performed. When the component has passed the receiving inspection test it will be lifted to the appropriate fixture in the assembly area.

When a Field Period Assembly is completed it will be lifted from the fixture in the assembly area and set on a truck for shipment as shown in Figure 3.0. The Field Period Assembly will be driven a short distance on site to the NCSX test cell. .(Could use a picture of the Princeton site to show distance and any restrictions)

The crane is not expected to be used for day to day assembly. Local fixtures will be used for assembly. Typical lifts and the weights are shown in Table 2.0 . More details including the CG, Height and Width are shown in Appendix A.

Table 2.0

| Description | Weight |
| --- | --- |
| Vacuum Vessel | 6, 400 lbs |
| M1 Coil | 6,700 lbs |
| M2 Coil | 6,300 lbs |
| M3 Coil | 6,800 lbs |
| Half period Modular Coil | 19,800 lbs |
| Half period TF Coil | 13,400 lbs |
| Field Period Assembly | 81,000 lbs |

After a lift has been performed the crane will be released for other operations needed in the TFTR Test Cell.

# Vacuum Vessel Assembly

The Field Period Assembly will begin with the assembly of the vacuum vessel. The vacuum vessel will be assembled to the vacuum vessel support fixture see Figure 4.0 bolting the lower vertical port flange to the mating flange on the vacuum vessel support fixture. A column located in the center of the vessel will supply stability during the assembly.

The following components will be assembled to the outside of the vessel.

Saddle coils

The Field Period Assembly plan is to install 130 saddle coils on the first period. If the magnetic analysis indicates the need for more coils these coils will be added to the second and third period assembly. The plan today is to install saddle coils on the first period and add additional coils if needed.

The technique for installing the coils is to place the coil on the vessel and stud weld fasteners at the corners of the coils. The coils will be attached to these studs with clamps as shown in Figure 5.0.

Measurements of the coils will be made using a Farewell arm or laser tracker and recorded for future information which will be needed during operation. The measurement tolerance for locating these coils is +- .030.

Cooling/heating coils will be added to each period as shown in Figure 6.0.

These cooling/heating tubes will be attached to the vessel by stud welding fasteners to the vessel. “J” clamps will be used to fasten the tubes to the vessel. A 1/16 inch gap is designed between the vessel and the cooling tubes. This gap is to allow the saddle coils installation.

Stycast, a thermal conducting epoxy, will be placed between the vessel and tubes. A total of 32 tubes will be attached to the outside surface. The location of the tubes is not as critical as previous components. The cooling tubes are 0.375 od x .035 wall thickness and made of Inconel 600 and will be preformed before assembly.

Microtherm and solimide polymide foam, one half inch thick each, will be added to the outside of the vacuum vessel surface see Figure 7.0.

The insulation will be cut from sheets and wrapped around the  outside vessel surface. The insulation will be held in place with …(Glued to surface, plastic netting, pushed over studs and held in place with plastic push on retainers?)

The vacuum vessel support hardware which supports the vessel from the modular coil shell can not be installed because the clevis which attaches to the vessel shell is to large for the mod coils to slip over. The installation of the vacuum vessel support hardware will be discussed after the installation of the shell.

Assembly of the Modular Coils

The assembly of the modular coils will begin by reviewing the dimensional inspection information generated during the assembly of each half period segment sub assembly.

The assembly of the modular coils will consist of 3 steps. Step 1 is to assemble coil segments M1, M2 and M3 together to form the half period coil sub assembly. Step 2 is to dimensionally inspect the coils. The purpose of this inspection is to verify the assembly of the half period coil sub assembly has been successful and to compare this information with a second half period assembly to size the shim needed at the Field Period Assembly. Step 3 is to assemble the left and right half period sub assemblies over the vacuum vessel.

The modular coils will first be assembled into segments consisting of the three coils using the fixture shown in Figure 8.0.

This procedure will start with M1. The M1 coil segment will be placed in the fixture and measured to verify location. A shim which has been sized based on dimensional data taken during the fabrication of the M1 coil and the next coil segment, M2, will be placed on the flange. The M2 segment will be lowered into place and insulated bolts/nuts will be inserted into the flange holes. The bolt and nut assembly will be torqued to specification. Dimensional inspection data will be taken to verify the location of the coil. The M3 coil will be assembled next using the same procedure as done for the M2. coil. After the three shell segments have been assembled cryolite batt insulation will be placed between the windings. The cryolite batt insulation will be held in place with (glued to the surface of the winding form, plastic netting stretched between winding forms, other).  After the Half Period Modular Coil sub assembly has been completed it will be installed on the fixture shown in Figure 9.0 to assembly into the  Field Period assembly.

The half period modular coil sub assembly and fixture will be placed next to the vacuum vessel and fixture shown in Figure 9.

The half period modular coil sub assembly and fixture will be guided by tracks that have been positioned on the floor. As the fixture and sub assembly follows the tracks the fixture will change the location of the coils by moving up and down, pivoting on the horizontal axis, and rotating the table about a vertical axis.  By slowly advancing the fixture and adjusting the location of the coils the half period segment will fit over the vessel until the coils have been positioned correctly. Measurements of the coil location will be made during the assembly to verify the location of the coils during all moves. When the half period sub assembly is correctly positioned the load will be temporally transferred from the fixture to supports as shown in Figure 10.0.

After the fixture is removed the half period sub assembly will be supported from the floor as shown in Figure 11.

A shim that fits between the two half periods will be placed on the installed half period sub assembly. The second half period sub assembly will be installed in a similar manner as the first. When the second half period subassembly has been installed insulated bolts/nuts will be matched reamed with the first half period sub assembly and torqued to the required specification.

The modular coils will be inspected to verify the final location of the coils.

Vacuum Vessel Support Hardware

The vacuum vessel support hardware can now be installed between the vacuum vessel and the shell. A clevis sub assembly will be fitted thru access ports in the shell and screwed into bosses that are in the vessel see Figure 12.0. Threaded rod can be inserted into the clevis from the outside of the shell. Belleville washers and a nut will be attached to the threaded rod and tightened against the shell until the vacuum vessel is snug. The vessel will not be fully support until the ports have been installed and welded to the vessel.

Assembly of the TF Coils

The half period TF coil sub assembly is shown in Figure 13.0. The sub assembly consist of 3 TF coils with a cast top and bottom support structure. The assembly of the TF Coil sub assembly is shown in Figures 14.0 thru 17.0. This sub assembly will be assembled

prior to assembling the TF coils into the Field Period Assembly.  This sub assembly will be assembled in a similar manner as the modular coils. Several fixtures are added for assembling the Half period TF Coils over the shell

The assembly of the TF Coil half period sub assembly is much simpler than the module coil assembly. The TF Coil half period sub assembly can be rotated over the module coils from a single pivot point. Fixtures for the assembly are shown in Figure 18.

One end of the modular coils is supported from the ground. This allows the opposite half shell sub assembly to be cantilevered from the fixed half shell sub assembly. With no supports preventing the installation of the TF Coil half period the coils are simply rotated into position and bolted to the modular coil half period sub assembly. Supports are then placed under the TF Coil support and the procedure is repeated for the opposite side.

Assembly of External Trim Coils

After the assembly of the TF coils the External Trim Coils will be attached to the Field Period Assembly. The External Trim Coils are shown in Figure 19.

The external trim coils consist of 3 upper and  3 lower coils and one outer coil. The upper and lower coils are attached to the frame of the TF coil support structure. The outer trim coil is mounted on the outside of the TF coil see Figure 20.0. At the machine assembly level an additional outer trim coil will be added between each Field Period Assembly. The assembly of all the external trim coils is shown in Figure 21.0

Assembly of the Ports

The vacuum vessel ports are the last major items to be assembled to the Field Period Assembly. Before installing the ports the Field Period Assembly will have the components assembled as shown in Figure 20.0. A typical port configuration is shown in Figure 21.0. A backing ring is shown welded to the port. The backing ring will help position the port over the stub in the vacuum vessel see  Figure 22.0. An assembly fixture shown in Figure 23.0 will be used to maintain alignment of the ports. All of the ports will be positioned on the vessel and aligned using the alignment fixture. As each port is positioned a tack weld will hold the port stable. After all ports have been assembled the tack weld will be replaced with a full penetration weld. Blank off flanges will be installed on the ports and on the open ends of the vacuum vessel. A vacuum leak test will be performed to verify all the welds are leak tight. In addition to the vacuum leak test a dimension verification of the port locations will be performed. All fixtures shall be removed and the inspection shall be made with the ports in a “free condition”.

Vacuum Vessel Final Support Adjustment.

Before completing the Field Period Assembly the vacuum vessel has to be supported from the shell. The support hardware that was installed after the modular coils is now tightened until the vessel is barely lifted off the fixture. The vessel is now free and can move inside the shell assembly. Temporary blocking will be installed between the shell and the vessel during transport from the assembly area to the NCSX test cell. The completed port assembly is shown in  Figure 24.0

Field Period Assembly Transport.

The Field Period Assembly is lifted from the support fixture and carried to the truck for loading. The assembly will be placed  on the truck and carefully secured for delivery to the NCSX test cell.

# Text boxes

Figure 7.0

Vacuum Vessel Insulation

Figure 6.0

## Cooling and Heating Tubes

TBD

## Figure 5.0

Saddle Coil Attachment

Figure 4

Vacuum Vessel Support

## Figure 2.0

TFTR Crane

Figure 1.0

TFTR Test Cell

## Figure 3.0

## TFTR Loading Station

Figure 8.0

Modular Coil Half Period Sub Assembly

Figure 9.0

Modular Coil Half Period Sub Assembly Assembly Fixture

Figure 10.0

Load Transfer Fixture

Figure 11.

Modular Coil Half Period Support

Figure 12.0

Vacuum Vessel Support Hardware

Figure 13.0

TF Coil Assembly

Figure 14

TF Coil Half Period Assembly

Figure 15

TF Coil Half Period Assembly

Figure 16

## TF Coil Half Period Assembly

Figure 17

TF Coil Half Period Assembly

Figure 18.0

TF Coil Fixture for Assembly

Figure 19.0

One Period of the External Trim Coils

Figure 20.0

Installation of External Trim Coils

Figure 21.0

External Trim Coils Full Assembly

Figure 21.0

## Typical Port Assembly

Figure 22.0

Typical Port Attachment Configuration

TBD

Figure 23.0

Port Attachment Fixture

Figure 24.0

Vacuum Vessel Port Assembly