## Sheet1
Project Engineering Jobs | [6 empty] | Personnel | [5 empty] | Rates
[7 empty] | Name | Brooks | Brown | Morris | Reiersen | Simmons | Demographic | Rate
[7 empty] | Demographic | EA//EM | EA//EM | EA//DM | EA//EM | FC//EM | EA//DM | 97.73
[7 empty] | Loaded Rate | 149.23 | 149.23 | 97.73 | 149.23 | 157.0104 | EA//EM | 149.23
[7 empty] | Hours | 590 | 875 | 350 | 1320 | 860 | FC//EM | 157.0104
|  |  |  | 532.6095 |  |  | FTE | 34.18% | 50.7% | 20.28% | 76.48% | 49.83%
Job Title | Engineering Management and Systems Engineering Support
Job Manager | Reiersen
Job Number | 9450-82**-1M01
| Tasks | Start | Finish | Cost (k$) | Deliverables | Remarks
| General Engineering Mgmt and SE Support | 2002-10-01 | 2003-09-30 | 236.7528 | None | LOE (50% LOE for WTR, 40% LOE for RTS) |  |  |  |  | 850 | 700
| Complete development of project plans | 2002-10-01 | 2002-11-30 | 18.53 | CMP, ICMP, DMP, DOC (RTS); SEMP, RAM (WTR) | [5 empty] | 40 | 80
|  | 2002-12-01 | 2003-01-31 | 11.9384 | TEP (WTR) | [5 empty] | 80
| Complete development of implementing procedures | 2002-10-01 | 2003-01-31 | 24.4992 | (1) List of implementing procedures required up front (2) Completed procedures | [5 empty] | 80 | 80
291.7204
Job Title | Design Integration
Job Manager | Brown
Job Number | 9450-82**-2M01
| Tasks | Start | Finish | Cost (k$) | Deliverables | Remarks
| General Design Integration | 2002-10-01 | 2003-09-30 | 44.769 | None | LOE (40% LOE for TGB). Includes implementation and maintenance of Intralink, development of implementing procedures for drawign control, electronic drawing sign-off and design integration |  |  | 300
| Develop general core design integration design concepts | 2002-10-01 | 2003-09-30 | 29.846 | Report on design concepts specified for development |  |  |  | 200
| Support early auxiliary system ProE development for those major systems interfacing with WBS 1 | 2003-01-01 | 2003-09-30 | 29.846 | ProE models with approved WBS 1 interface definition. Models will be passed over to responsible WBS group. |  |  |  | 200
| Develop and maintain Pro/E model of NCSX facility | 2002-10-01 | 2003-09-30 | 60.3207 | Updates of facility models should be disseminated quarterly for project review | LOE (10% LOE for TGB, 20% for LM) |  |  | 175 | 350
164.7817
Job Title | Systems Analysis
Job Manager | Brooks
Job Number | 9450-82**-3M01
| Tasks | Start | Finish | Cost (k$) | Deliverables | Remarks
| Develop technical data | 2002-10-01 | 2003-11-30 | 17.9076 | New current waveforms, power supply requirementss, etc. provided for new coil design | [5 empty] | 120
|  | 2003-11-30 | 2003-09-30 | 22.3845 | Update technical data consistent with evolving design changes | 10% LOE |  |  |  |  | 150
| Assess potential sources of field errors in NCSX Test Cell | 2002-10-01 | 2003-01-31 | 35.8152 | Report which includes recommended height off floor for stellarator core |  |  | 240
| General systems analysis support | 2002-10-01 | 2003-09-30 | 52.2305 |  | 20% LOE for AB. Includes general EM analysis and maintenance of technical data on FTP server. Does not include work performed directly in support of WBS 1. |  | 350
76.1073
Formulas:
Start = [Finish, row above]