## Summary
NCSX CAD DESIGN REQUIREMENTS - SUMMARY SHEET
| JAN FY05 | FEB FY05 | MAR FY05 | APR FY05 | MAY FY05 | JUN FY05 | JUL FY05 | AUG FY05 | SEP FY05 | OCT FY06 | NOV FY06 | DEC FY06
ELECT DESIG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361 | 389 | 298
JONES | 42 | 42 | 48 | 44 | 36 | 38 | 34 | 39 | 5 | 0 | 0 | 0
NELSON | 40 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VANKIRK | 97 | 97 | 127 | 85 | 127 | 129 | 110 | 81 | 5 | 123 | 116 | 100
Sum Electrical | 179 | 155 | 175 | 129 | 163 | 167 | 144 | 120 | 10 | 484 | 505 | 398
Available for non-NCSX work | 301 | 325 | 305 | 351 | 317 | 313 | 336 | 360 | 470 | -4 | -25 | 82
MECH DESIGN | 0 | 0 | 0 | 8 | 170 | 179 | 162 | 41 | 0 | 71 | 68 | 85
MESSINEO | 81 | 113 | 199 | 182 | 150 | 89 | 81 | 93 | 89 | 0 | 0 | 0
MORRIS | 198 | 28 | 23 | 21 | 21 | 22 | 25 | 30 | 28 | 174 | 166 | 174
PAUL | 34 | 449 | 336 | 118 | 17 | 18 | 16 | 43 | 82 | 64 | 61 | 51
RUSHINSKI | 209 | 41 | 114 | 104 | 104 | 209 | 155 | 121 | 96 | 128 | 121 | 87
Sum Mechanical | 522 | 631 | 672 | 433 | 462 | 517 | 439 | 328 | 295 | 437 | 416 | 397
Available for non-NCSX work | 118 | 9 | -32 | 207 | 178 | 123 | 201 | 312 | 345 | 203 | 224 | 243

## Sort by Designer
NCSX CAD DESIGN REQUIREMENTS - SORTED BY DESIGNERS
[5 empty] | HOURS - 2005 | [7 empty] | 2006
ACC | JOB | ACT ID | DESC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
ELECT DESIG | Job: 4401 - Control & Protection-RAMAKRISHNAN | 445-2-135 | DESC: Overload Protect-Documentation; 2006 OCT: 1; 2006 NOV: 18; 2006 DEC: 15
ELECT DESIG | Job: 4401 - Control & Protection-RAMAKRISHNAN | 444-2-2 | DESC: DC Potential Transducers (DCPTs)-Dsn; 2006 OCT: 11; 2006 NOV: 13; 2006 DEC: 11
ELECT DESIG | Job: 4401 - Control & Protection-RAMAKRISHNAN | 445-2-110 | DESC: Overload Protect-Design; 2006 OCT: 1; 2006 NOV: 20; 2006 DEC: 17
ELECT DESIG | Job: 4401 - Control & Protection-RAMAKRISHNAN | 444-4-2 | DESC: Signal Conditioning & Cabling-Dsn; 2006 OCT: 17; 2006 NOV: 16; 2006 DEC: 14
ELECT DESIG | Job: 4401 - Control & Protection-RAMAKRISHNAN | 442-1-2 | DESC: Kirk Keys-Dsn; 2006 OCT: 41; 2006 NOV: 39
ELECT DESIG | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 453-1-2 | DESC: New Procedures; 2006 OCT: 48; 2006 NOV: 53; 2006 DEC: 45
ELECT DESIG | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 452-2-2 | DESC: Diagnostics sensor cabling-Dsn; 2006 OCT: 55; 2006 NOV: 52; 2006 DEC: 45
ELECT DESIG | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 452-1-2 | DESC: Diagnostics AC Power Distr-Dsn; 2006 OCT: 187; 2006 NOV: 178; 2006 DEC: 151
JONES | Job: 4301 - DC Systems-RAMAKRISHNAN | 431-250 | DESC: c-site dc sys DGS dsn documentation; JAN: 8; HOURS - 2005 FEB: 8; HOURS - 2005 MAR: 9; HOURS - 2005 APR: 8
JONES | Job: 4301 - DC Systems-RAMAKRISHNAN | 431-260 | Power loop design | 34 | 34 | 39 | 36 | 36 | 38 | 34 | 39 | 5
MECH DESIGN | Job:1550 - Structures Procurement -KALISH | 162-031 | DESC: Title III engr WBS 151; 2006 DEC: 14
MECH DESIGN | Job: 3101 Magnetic Diagnostics | 310-020 | DESC: Design other ex-vessel sensors; HOURS - 2005 APR: 8; HOURS - 2005 MAY: 170; HOURS - 2005 JUN: 179; HOURS - 2005 JUL: 162; HOURS - 2005 AUG: 41
MECH DESIGN | Job: 8203 - Design Integration-BROWN | 8203FY06 | DESC: Design Integration FY06; 2006 OCT: 71; 2006 NOV: 68; 2006 DEC: 71
MESSINEO | Job: 7301 - Platform Design & Fab-PERRY | 712.01 | DESC: Final Design; HOURS - 2005 FEB: 32; HOURS - 2005 MAR: 106; HOURS - 2005 APR: 97; HOURS - 2005 MAY: 65
MESSINEO | Job: 8203 - Design Integration-BROWN | 8203FY05 | Design Integration FY05 LOE | 81 | 81 | 93 | 85 | 85 | 89 | 81 | 93 | 89
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-3.09 | DESC: Design check and sign-off; HOURS - 2005 FEB: 8
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-3.04 | DESC: VV support stand - model design and drawing deta; JAN: 18
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-3.13 | DESC: Fabrication - follow-up activities; HOURS - 2005 JUL: 5; HOURS - 2005 AUG: 7; HOURS - 2005 SEP: 6; 2006 OCT: 6; 2006 NOV: 6; 2006 DEC: 6
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-4.06 | DESC: Metrology - sightline layout design details metr; 2006 DEC: 38
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-4.01 | DESC: Concept definition and requirements; 2006 OCT: 40
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-4.05 | DESC: VV Port Alignment/Weldment Fixture - design and; 2006 DEC: 58
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-3.05 | DESC: Platform - design and drawing; JAN: 80
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-3.06 | DESC: Metrology - sightline layout design details metr; JAN: 80
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-4.02 | DESC: MC Support Stand - model design and drawing deta; 2006 OCT: 120
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-4.03 | DESC: TF HP support turning fixture - model design d; 2006 OCT: 8; 2006 NOV: 112
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-4.04 | DESC: FP Assembly platform - model design drawing det; 2006 NOV: 48; 2006 DEC: 72
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-7.01 | Meetings Prep and Reporting | 20 | 20 | 23 | 21 | 21 | 22 | 20 | 23 | 22
NELSON | Job: 4301 - DC Systems-RAMAKRISHNAN | 431-210 | DESC: Organize & verify documentation; JAN: 40; HOURS - 2005 FEB: 16
PAUL | Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 161-001 | DESC: Title I design WBS 172 base support struct; JAN: 9
PAUL | Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 151-011 | DESC: Final Design Cryostat WBS 171; HOURS - 2005 AUG: 24; HOURS - 2005 SEP: 64; 2006 OCT: 64; 2006 NOV: 61; 2006 DEC: 51
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-1.07 | DESC: Design check and sign-off; HOURS - 2005 APR: 8
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-2.07 | DESC: Design check and sign-off; HOURS - 2005 APR: 8
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-5.01 | DESC: Finalize TFTR test cell FPA assembly layout draw; JAN: 3; HOURS - 2005 FEB: 21
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-1.10 | DESC: Fab / Design Review - follow-up activities; HOURS - 2005 APR: 40
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-2.10 | DESC: Fab / Design Review - follow-up activities; HOURS - 2005 APR: 40
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-1.01 | DESC: Concept definition and requirements; JAN: 6; HOURS - 2005 FEB: 54
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-2.01 | DESC: Concept definition and requirements; HOURS - 2005 FEB: 60
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-2.02 | DESC: MC Holding Fixture 1 - model design and drawing; HOURS - 2005 FEB: 30; HOURS - 2005 MAR: 30
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-2.04 | DESC: Metrology - sightline layout design details metr; HOURS - 2005 MAR: 75; HOURS - 2005 APR: 5
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-1.02 | DESC: VV Support Fixture - model design& drawing detai; HOURS - 2005 FEB: 88; HOURS - 2005 MAR: 32
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-1.04 | DESC: Metrology -sightline layout; HOURS - 2005 MAR: 120
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-2.03 | DESC: MC Assembly Fixture 2- design; HOURS - 2005 FEB: 60; HOURS - 2005 MAR: 60
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-5.03 | DESC: Develop test components as needed to qualify ass; HOURS - 2005 FEB: 120
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-7.01 | Meetings Prep and Reporting | 16 | 16 | 19 | 17 | 17 | 18 | 16 | 19 | 18
RUSHINSKI | Job: 1301 - TF Design-KALISH | 1301R-36 | DESC: Final Design Leads; JAN: 80
RUSHINSKI | Job: 1301 - TF Design-KALISH | 1301R-34 | DESC: Final Design Coil Windings; JAN: 101; HOURS - 2005 FEB: 19
RUSHINSKI | Job: 1302 - PF and CS Design -KALISH | 1302-PF | PF Design | [5 empty] | 36 | 33 | 38 | 35 | 35 | 33 | 22
RUSHINSKI | Job: 1302 - PF and CS Design -KALISH | 1302-CSS | Center Stack Support Design | [5 empty] | 58 | 53 | 60 | 55 | 55 | 53 | 34
RUSHINSKI | Job: 1303 - Trim coil Design-KALISH | 1303-TRIM | DESC: Trim Coil Design; 2006 OCT: 32; 2006 NOV: 30; 2006 DEC: 26
RUSHINSKI | Job: 1351 - TF Coil Procurement-KALISH | 131-031 | Title III engr | [5 empty] | 6 | 5 | 6 | 6 | 6 | 5 | 5
RUSHINSKI | Job: 1501 - Structures Design- Kalish | 1501-FY05 | DESC: Prelim & Final Design Structures; HOURS - 2005 MAR: 88; HOURS - 2005 APR: 81; HOURS - 2005 MAY: 81; HOURS - 2005 JUN: 84; HOURS - 2005 JUL: 42
RUSHINSKI | Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 151-001 | DESC: Title I design WBS 171 cryostat shell & struct; JAN: 17
RUSHINSKI | Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 161-011 | Final Design Base Support Structure WBS 172 | 11 | 22 | 26 | 23 | 23 | 25 | 22 | 17
VANKIRK | Job: 4101 - AC Power-RAMAKRISHNAN | 411-1-100 | DESC: Ex-Test cell AC pwr-Reactivate& new instl; 2006 OCT: 2; 2006 NOV: 2; 2006 DEC: 2
VANKIRK | Job: 4101 - AC Power-RAMAKRISHNAN | 411-3-2 | DESC: Test Cell AC Power Distr-Dsn; 2006 OCT: 2; 2006 NOV: 2; 2006 DEC: 2
VANKIRK | Job: 4101 - AC Power-RAMAKRISHNAN | 412-1-2 | DESC: D-site Pulsed AC Power Distr-Dsn; 2006 OCT: 7; 2006 NOV: 6; 2006 DEC: 5
VANKIRK | Job: 4101 - AC Power-RAMAKRISHNAN | 411-2-2 | DESC: Grounding-Dsn; 2006 OCT: 39; 2006 NOV: 37; 2006 DEC: 32
VANKIRK | Job: 4301 - DC Systems-RAMAKRISHNAN | 431-260 | Power loop design | 34 | 34 | 39 | 36 | 36 | 38 | 34 | 39 | 5
VANKIRK | Job: 4401 - Control & Protection-RAMAKRISHNAN | 444-3-2 | DESC: DC Shunts-Dsn; 2006 OCT: 14; 2006 NOV: 13; 2006 DEC: 11
VANKIRK | Job: 4401 - Control & Protection-RAMAKRISHNAN | 441-095 | DESC: Design Interlock sys; 2006 OCT: 28; 2006 NOV: 27; 2006 DEC: 23
VANKIRK | Job: 4401 - Control & Protection-RAMAKRISHNAN | 445-1-2 | DESC: Ground Fault Protection-Dsn; 2006 OCT: 31; 2006 NOV: 29; 2006 DEC: 25
VANKIRK | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451-2-2.1 | DESC: FDR C-Site; HOURS - 2005 MAY: 21; HOURS - 2005 JUN: 41; HOURS - 2005 JUL: 38; HOURS - 2005 AUG: 21
VANKIRK | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451-6-2 | DESC: FDR C-Site -Cabling; HOURS - 2005 MAY: 21; HOURS - 2005 JUN: 41; HOURS - 2005 JUL: 38; HOURS - 2005 AUG: 21
VANKIRK | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451-2-2 | DESC: PDR Power system -Dsn; HOURS - 2005 MAR: 53; HOURS - 2005 APR: 49; HOURS - 2005 MAY: 49; HOURS - 2005 JUN: 9
VANKIRK | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451-2-1 | DESC: CDR Power system -Dsn; JAN: 63; HOURS - 2005 FEB: 63; HOURS - 2005 MAR: 35
|  |  |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
|  |  | ELECT DESIG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361 | 389 | 298
|  |  | JONES | 42 | 42 | 48 | 44 | 36 | 38 | 34 | 39 | 5 | 0 | 0 | 0
|  |  | MECH DESIGN | 0 | 0 | 0 | 8 | 170 | 179 | 162 | 41 | 0 | 71 | 68 | 85
|  |  | MESSINEO | 81 | 113 | 199 | 182 | 150 | 89 | 81 | 93 | 89 | 0 | 0 | 0
|  |  | MORRIS | 198 | 28 | 23 | 21 | 21 | 22 | 25 | 30 | 28 | 174 | 166 | 174
|  |  | NELSON | 40 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PAUL | 34 | 449 | 336 | 118 | 17 | 18 | 16 | 43 | 82 | 64 | 61 | 51
|  |  | RUSHINSKI | 209 | 41 | 114 | 104 | 104 | 209 | 155 | 121 | 96 | 128 | 121 | 87
|  |  | VANKIRK | 97 | 97 | 127 | 85 | 127 | 129 | 110 | 81 | 5 | 123 | 116 | 100

## Sort by ACT ID
NCSX CAD DESIGN REQUIREMENTS - SORTED BY TASK LIST
[5 empty] | HOURS - 2005 | [7 empty] | HRS - 2006 |  |  | Due | Prioity |  | Normal
ACC | JOB | ACT ID | DESC | J | F | M | A | M | J | J | A | S | O | N | D | Date | Order |  | Order | Re-Order
MESSINEO | Job: 7301 - Platform Design & Fab-PERRY | 712.01 | Final Design | HOURS - 2005 F: 32; HOURS - 2005 M: 106; HOURS - 2005 A: 97; HOURS - 2005 M: 65 | 2007-03-02 | 10 | 2005-03-02 | 1 | 4
RUSHINSKI | Job: 1301 - TF Design-KALISH | 1301R-34 | Final Design Coil Windings | J: 101; HOURS - 2005 F: 19 |  |  | 2005-11-03 | 2 | 1
RUSHINSKI | Job: 1301 - TF Design-KALISH | 1301R-36 | Final Design Leads | J: 80 | 2005-11-03 | 1 | 2005-12-08 | 3 | 3
RUSHINSKI | Job: 1302 - PF and CS Design -KALISH | 1302-CSS | Center Stack Support Design | HOURS - 2005 J: 58; HOURS - 2005 J: 53; HOURS - 2005 A: 60; HOURS - 2005 S: 55; HRS - 2006 O: 55; HRS - 2006 N: 53; HRS - 2006 D: 34 | 2007-08-08 | 11 | 2006-04-10 | 4 | 5
RUSHINSKI | Job: 1302 - PF and CS Design -KALISH | 1302-PF | PF Design | HOURS - 2005 J: 36; HOURS - 2005 J: 33; HOURS - 2005 A: 38; HOURS - 2005 S: 35; HRS - 2006 O: 35; HRS - 2006 N: 33; HRS - 2006 D: 22 | 2007-08-27 | 13 | 2006-05-13 | 5 | 6
RUSHINSKI | Job: 1303 - Trim coil Design-KALISH | 1303-TRIM | Trim Coil Design | HRS - 2006 O: 32; HRS - 2006 N: 30; HRS - 2006 D: 26 | 2007-01-19 | 9 | 2006-05-19 | 6 | 2
RUSHINSKI | Job: 1351 - TF Coil Procurement-KALISH | 131-031 | Title III engr | HOURS - 2005 J: 6; HOURS - 2005 J: 5; HOURS - 2005 A: 6; HOURS - 2005 S: 6; HRS - 2006 O: 6; HRS - 2006 N: 5; HRS - 2006 D: 5 |  |  | 2006-06-13 | 7 | 7
RUSHINSKI | Job: 1501 - Structures Design- Kalish | 1501-FY05 | Prelim & Final Design Structures | HOURS - 2005 M: 88; HOURS - 2005 A: 81; HOURS - 2005 M: 81; HOURS - 2005 J: 84; HOURS - 2005 J: 42 | 2006-06-13 | 7 | 2006-10-23 | 8 | 8
RUSHINSKI | Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 151-001 | Title I design WBS 171 cryostat shell & struct | J: 17 |  |  | 2007-01-19 | 9 | 9
PAUL | Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 151-011 | Final Design Cryostat WBS 171 | HOURS - 2005 A: 24; HOURS - 2005 S: 64; HRS - 2006 O: 64; HRS - 2006 N: 61; HRS - 2006 D: 51 | 2007-08-25 | 12 | 2007-03-02 | 10 | 10
PAUL | Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 161-001 | Title I design WBS 172 base support struct | J: 9 |  |  | 2007-08-08 | 11 | 11
RUSHINSKI | Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 161-011 | Final Design Base Support Structure WBS 172 | 11 | 22 | 26 | 23 | 23 | 25 | 22 | 17 |  |  |  |  | 2006-10-23 | 8 | 2007-08-25 | 12 | 12
MECH DESIGN | Job:1550 - Structures Procurement -KALISH | 162-031 | Title III engr WBS 151 | HRS - 2006 D: 14 |  |  | 2007-08-27 | 13 | 13
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-1.01 | Concept definition and requirements | J: 6; HOURS - 2005 F: 54
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-1.02 | VV Support Fixture - model design& drawing detai | HOURS - 2005 F: 88; HOURS - 2005 M: 32
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-1.04 | Metrology -sightline layout | HOURS - 2005 M: 120
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-1.07 | Design check and sign-off | HOURS - 2005 A: 8
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-1.10 | Fab / Design Review - follow-up activities | HOURS - 2005 A: 40 | 2005-12-08 | 3
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-2.01 | Concept definition and requirements | HOURS - 2005 F: 60
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-2.02 | MC Holding Fixture 1 - model design and drawing | HOURS - 2005 F: 30; HOURS - 2005 M: 30
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-2.03 | MC Assembly Fixture 2- design | HOURS - 2005 F: 60; HOURS - 2005 M: 60
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-2.04 | Metrology - sightline layout design details metr | HOURS - 2005 M: 75; HOURS - 2005 A: 5
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-2.07 | Design check and sign-off | HOURS - 2005 A: 8
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-2.10 | Fab / Design Review - follow-up activities | HOURS - 2005 A: 40 | 2006-04-10 | 5
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-3.04 | VV support stand - model design and drawing deta | J: 18
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-3.05 | Platform - design and drawing | J: 80
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-3.06 | Metrology - sightline layout design details metr | J: 80
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-3.09 | Design check and sign-off | HOURS - 2005 F: 8
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-3.13 | Fabrication - follow-up activities | HOURS - 2005 J: 5; HOURS - 2005 A: 7; HOURS - 2005 S: 6; HRS - 2006 O: 6; HRS - 2006 N: 6; HRS - 2006 D: 6 | 2006-05-19 | 2 (1)
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-4.01 | Concept definition and requirements | HRS - 2006 O: 40
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-4.02 | MC Support Stand - model design and drawing deta | HRS - 2006 O: 120
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-4.03 | TF HP support turning fixture - model design d | HRS - 2006 O: 8; HRS - 2006 N: 112
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-4.04 | FP Assembly platform - model design drawing det | HRS - 2006 N: 48; HRS - 2006 D: 72
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-4.05 | VV Port Alignment/Weldment Fixture - design and | HRS - 2006 D: 58
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-4.06 | Metrology - sightline layout design details metr | HRS - 2006 D: 38 | 2006-05-13 | 6
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-5.01 | Finalize TFTR test cell FPA assembly layout draw | J: 3; HOURS - 2005 F: 21
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-5.03 | Develop test components as needed to qualify ass | HOURS - 2005 F: 120 | 2005-03-02 | 4
MORRIS | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-7.01 | Meetings Prep and Reporting | 20 | 20 | 23 | 21 | 21 | 22 | 20 | 23 | 22
PAUL | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803-7.01 | Meetings Prep and Reporting | 16 | 16 | 19 | 17 | 17 | 18 | 16 | 19 | 18
MECH DESIGN | Job: 3101 Magnetic Diagnostics | 310-020 | Design other ex-vessel sensors | HOURS - 2005 A: 8; HOURS - 2005 M: 170; HOURS - 2005 J: 179; HOURS - 2005 J: 162; HOURS - 2005 A: 41
VANKIRK | Job: 4101 - AC Power-RAMAKRISHNAN | 411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | HRS - 2006 O: 2; HRS - 2006 N: 2; HRS - 2006 D: 2
VANKIRK | Job: 4101 - AC Power-RAMAKRISHNAN | 411-2-2 | Grounding-Dsn | HRS - 2006 O: 39; HRS - 2006 N: 37; HRS - 2006 D: 32
VANKIRK | Job: 4101 - AC Power-RAMAKRISHNAN | 411-3-2 | Test Cell AC Power Distr-Dsn | HRS - 2006 O: 2; HRS - 2006 N: 2; HRS - 2006 D: 2
VANKIRK | Job: 4101 - AC Power-RAMAKRISHNAN | 412-1-2 | D-site Pulsed AC Power Distr-Dsn | HRS - 2006 O: 7; HRS - 2006 N: 6; HRS - 2006 D: 5
NELSON | Job: 4301 - DC Systems-RAMAKRISHNAN | 431-210 | Organize & verify documentation | J: 40; HOURS - 2005 F: 16
JONES | Job: 4301 - DC Systems-RAMAKRISHNAN | 431-250 | c-site dc sys DGS dsn documentation | J: 8; HOURS - 2005 F: 8; HOURS - 2005 M: 9; HOURS - 2005 A: 8
JONES | Job: 4301 - DC Systems-RAMAKRISHNAN | 431-260 | Power loop design | 34 | 34 | 39 | 36 | 36 | 38 | 34 | 39 | 5
VANKIRK | Job: 4301 - DC Systems-RAMAKRISHNAN | 431-260 | Power loop design | 34 | 34 | 39 | 36 | 36 | 38 | 34 | 39 | 5
VANKIRK | Job: 4401 - Control & Protection-RAMAKRISHNAN | 441-095 | Design Interlock sys | HRS - 2006 O: 28; HRS - 2006 N: 27; HRS - 2006 D: 23
ELECT DESIG | Job: 4401 - Control & Protection-RAMAKRISHNAN | 442-1-2 | Kirk Keys-Dsn | HRS - 2006 O: 41; HRS - 2006 N: 39
ELECT DESIG | Job: 4401 - Control & Protection-RAMAKRISHNAN | 444-2-2 | DC Potential Transducers (DCPTs)-Dsn | HRS - 2006 O: 11; HRS - 2006 N: 13; HRS - 2006 D: 11
VANKIRK | Job: 4401 - Control & Protection-RAMAKRISHNAN | 444-3-2 | DC Shunts-Dsn | HRS - 2006 O: 14; HRS - 2006 N: 13; HRS - 2006 D: 11
ELECT DESIG | Job: 4401 - Control & Protection-RAMAKRISHNAN | 444-4-2 | Signal Conditioning & Cabling-Dsn | HRS - 2006 O: 17; HRS - 2006 N: 16; HRS - 2006 D: 14
VANKIRK | Job: 4401 - Control & Protection-RAMAKRISHNAN | 445-1-2 | Ground Fault Protection-Dsn | HRS - 2006 O: 31; HRS - 2006 N: 29; HRS - 2006 D: 25
ELECT DESIG | Job: 4401 - Control & Protection-RAMAKRISHNAN | 445-2-110 | Overload Protect-Design | HRS - 2006 O: 1; HRS - 2006 N: 20; HRS - 2006 D: 17
ELECT DESIG | Job: 4401 - Control & Protection-RAMAKRISHNAN | 445-2-135 | Overload Protect-Documentation | HRS - 2006 O: 1; HRS - 2006 N: 18; HRS - 2006 D: 15
VANKIRK | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451-2-1 | CDR Power system -Dsn | J: 63; HOURS - 2005 F: 63; HOURS - 2005 M: 35
VANKIRK | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451-2-2 | PDR Power system -Dsn | HOURS - 2005 M: 53; HOURS - 2005 A: 49; HOURS - 2005 M: 49; HOURS - 2005 J: 9
VANKIRK | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451-2-2.1 | FDR C-Site | HOURS - 2005 M: 21; HOURS - 2005 J: 41; HOURS - 2005 J: 38; HOURS - 2005 A: 21
VANKIRK | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451-6-2 | FDR C-Site -Cabling | HOURS - 2005 M: 21; HOURS - 2005 J: 41; HOURS - 2005 J: 38; HOURS - 2005 A: 21
ELECT DESIG | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 452-1-2 | Diagnostics AC Power Distr-Dsn | HRS - 2006 O: 187; HRS - 2006 N: 178; HRS - 2006 D: 151
ELECT DESIG | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 452-2-2 | Diagnostics sensor cabling-Dsn | HRS - 2006 O: 55; HRS - 2006 N: 52; HRS - 2006 D: 45
ELECT DESIG | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 453-1-2 | New Procedures | HRS - 2006 O: 48; HRS - 2006 N: 53; HRS - 2006 D: 45
MESSINEO | Job: 8203 - Design Integration-BROWN | 8203FY05 | Design Integration FY05 LOE | 81 | 81 | 93 | 85 | 85 | 89 | 81 | 93 | 89
MECH DESIGN | Job: 8203 - Design Integration-BROWN | 8203FY06 | Design Integration FY06 | HRS - 2006 O: 71; HRS - 2006 N: 68; HRS - 2006 D: 71