## Schedule
[11 empty] | FY 2005 | [28 empty] | FY 2006 | [11 empty] | FY 2007 | [8 empty] | FY 2008 | [11 empty] | FY 2009
|  |  | FEB |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUG |  |  |  | SEPT |  |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
ITEM | TASK | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
VV period Arrival dates
|  | 23: C1 MC set Arrives | [10 empty] | Last MC set (C6) Arrives | [11 empty] | B3
[37 empty] | Complete MC test C1 |  | C2 |  | A1 | C3 |  | A2 | C4 |  | B1 | C5 |  | C6 | B2 |  | A3 | A4 |  | A5 | A6 |  | B4 |  | B5 | B6 Complete
| TF INFORMATION HAS NOT BEEN UPDATED | 30: Award TF Contract; 26: 1st TF arrives |  |  |  | TF wedge added | [12 empty] | All TF Coils Delivered
Target - Finish Last Field Period Assembly
Scheduled start of VV Pumpdown
1 | VV PREP STATION (Build to Print) | 7: BP; 16: PDR; 20: FDR
1.01 | Concept definition and requirements
1.02 | VV Support Fixture plus dwgs
1.03 | Metrology layout / support stand dwgs
1.04 | Structural Analysis check
1.05 | Fab Activities -
- VV alignment system
| - VV supports | [39 empty] | 1st VV |  |  |  |  | 2nd | [6 empty] | 3rd
1.08 | VV Assembly Operations (1 station)
2 | HALF PERIOD ASSEMBLY (Build to Print) | 7: LM; 16: PDR; 20: FDR
2.01 | Concept definition and requirements
2.02 | MC Holding Fixture
2.03 | Metrology layout / support stand dwgs
2.04 | Structural Analysis check
2.05 | Procurement (build to print) | [46 empty] | C4 / C5 |  |  |  |  | A3 / A4 |  |  | A5 / A6
2.06 | Fab Activities - Support fixture (2 ?)
| - Spherical seats (56) | [44 empty] | A1 / B1 / C1
2.07 | HP Assembly Operations (2 Stations) | [50 empty] | A2 / B2 / C2 | [10 empty] | A5 / B5 / C5
[57 empty] | A3 / B3 / C3 | [5 empty] | A6 / B6 / C6
[41 empty] | C2 / C3 |  |  |  | A1 / A2
A4 / B4 / C4
3 | MC INSTALLATION (Outside design & Fab) | 7: TB, LM | [15 empty] | A1 / B1 / C1 / C6
3.01 | Concept definition and requirements | 7: Done
3.02 | MC Turning Fixture and base | 28: Resized for seismic loading and Left side movement
3.03 | MC Gantry Crane | 7: 90% done
3.04 | VV support stand and Misc crane fixtures
3.05 | Platform design | 4: LM; 9: Assumes platforms ore part of contract.
3.06 | Metrology layout / support stand dwgs | bar: 25
3.07 | Structural / Seismic Analysis check
3.08 | Procurement activities
| - MCAF procurement | 18: Issue RFP 4 April; 30: Proposal Due; 4: Award 30 June; 26: FDR |  | Start Fab | [6 empty] | Deliver MCAF
3.09 | Fab Activities
- MCAF components
- Platforms (part of contract?)
3.1 | Assembly Activities
- Trial Runs - no VV
- Trial Runs - bare VVP plus MCHP
- MC Installation (1 Station)
PDR
4 | FINAL FP ASSEMBLY (Build to Print) | [39 empty] | FDR
4.01 | Concept definition and requirements | bar: 20
4.02 | MC Support Stand
4.03 | TF HP support and turning fixture
4.04 | FP Assembly platform
4.05 | VV Port Alignment/Weldment Fixture | [66 empty] | FPA-1 starts XXXXX, test cell delivery XXXXXX
4.06 | Metrology layout / support stand dwgs | [66 empty] | FPA-2 starts XXXXX, test cell delivery XXXXX | bar: 4
4.07 | Structural / Seismic Analysis check | [66 empty] | FPA-3 starts 1 Feb 08, test cell delivery 21 May 08
4.08 | Procurement
4.09 | Fabrication - follow-up activities | [55 empty] | FPA-1 | [7 empty] | FPA-3
- TF HP support
- FP Assembly platform & port fixtures
| (2 stations required) | [61 empty] | FPA-2
5 | INTERFACE / TEST ACTIVITIES
5.01 | TFTR test cell FPA arngmt dwg | bar: 27
5.02 | Design MC assembly test components | bar: 13
5.03 | Fab Activities - Test Articles
5.04 | Run test / metrology measurements
5.05 | Metrology Validation (Raftopoulos Activity)
OPEN ISSUE: TF ASSEMBLY COMPONENTS NEEDED TO ASSEMBLE A TF HP NEEDS TO BE INCLUDED IN THE SCHEDULE.
NEED TWO STAGE 2 FIXTURES BECAUSE OF OVERLAP
NEED TWO STAGE 3 FIXTURES BECAUSE OF OVERLAP
Models
All Dwgs
Models / Dwgs
Models / Dwgs
Models
Dwgs
Run A1/A2/A3 over 3rd VVHP