## Procmt Schedule
MCAF PROCUREMENT SCHEDULE timeline estimate (DRAFT A)
[11 empty] | FY2005 | [14 empty] | FY2006 | [6 empty] | FY2007
|  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUG |  |  |  | SEPT |  |  | O | N | D | J | F | M | A | S | O | N | D
ITEM | TASK | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
Define contract structure
Complete Specification Document
Complete SOW
Spec & SOW Review
Develop evaluation plan & selection criteria
Contract Plan Review
Issue RFP
Proposals Due
Award contract
MCAF Design Phase
Ref Design / Alternate concept review period
Define changes to Ref Design or propose Alt
MCAF design selection review
Rework Ref Design or develop alternate
PDR
Finish fabrication drawings
Informal interim reviews
FDR
Approve design for final costing
Submit fixed price proposal
Award fixed price contract
MCAF Fabrication Phase
Procure materials
Fab & machine parts
Assemble Turning Fixture
Assemble Gantry Crane
Assembly VV base support
Develop operations program
Operations Test
Inspection
Ship
June 15
13 MWK effort