## Manpower
[7 empty] | Personnel | [5 empty] | Rates
[7 empty] | Name | Brown | Cole | Analyst | Morris | Paul | Demographic | Rate
[7 empty] | Demographic | EA//EM | EA//EM | EA//EM | EA//DM | EA//DM | EA//DM | 97.73
[7 empty] | Loaded Rate | 149.23 | 149.23 | 149.23 | 97.73 | 97.73 | EA//EM | 149.23
|  |  | TOTAL MANPOWER COST - includes contingency and travel ($k) = | 609.4157 | TOTAL HOURS = | 4314 | Hours | 1470 | 160 | 560 | 1240 | 884 | FC//EM | 157.0104
[7 empty] | FTE | 85.17% | 9.27% | 32.44% | 71.84% | 51.22%
Job Title | Machine Assembly
Job Manager | Tom Brown
Job Number
| Tasks | Start | Finish | Cost (k$) | Deliverables | Remarks
1 | VV PREP STATION |  |  | 81.1667 |  |  |  | 236 |  | 80 | 0 | 348
1.01 | Concept definition and requirements | 2005-01-26 |  | 14.8176 |  |  |  | 60 |  |  |  | 60
1.02 | VV Support Fixture - model design and drawing details | 2005-02-14 |  | 12.9214 |  |  |  | 8 |  |  |  | 120
1.03 | Metrology - develop sightline layout and design/drawing details of unique metrology support stands | 2005-03-07 |  | 23.666 |  |  |  | 80 |  |  |  | 120
1.04 | Structural Analysis check | 2005-03-21 |  | 11.9384 | [5 empty] | 80
1.05 | Design review |  |  | 3.5815 |  |  |  | 24
1.06 | Design check and sign-off | 2005-04-11 |  | 3.1695 |  |  |  | 16 |  |  |  | 8
1.07 | Procurement |  |  | 2.3877 |  | Build to Print Procurement |  | 16
1.08 | Safety Review documentation / presentation |  |  | 2.3877 |  |  |  | 16
1.09 | Fab / Design Review - follow-up activities | 2005-07-11 | 2005-09-02 | 6.2969 |  |  |  | 16 |  |  |  | 40
2 | HALF PERIOD ASSEMBLY |  |  | 81.9275 |  |  |  | 228 |  | 80 | 0 | 368
2.01 | Concept definition and requirements | 2005-02-09 |  | 14.8176 |  |  |  | 60 |  |  |  | 60
2.02 | MC Holding Fixture - model design and drawing details | 2005-02-21 |  | 20.576 |  |  |  | 20 |  |  |  | 180
2.03 | Metrology - develop sightline layout and design/drawing details of unique metrology support stands | 2005-03-14 |  | 16.7722 |  |  |  | 60 |  |  |  | 80
2.04 | Structural / Seismic Analysis check | 2005-03-21 |  | 11.9384 | [5 empty] | 80
2.05 | Design review |  |  | 3.5815 |  |  |  | 24
2.06 | Design check and sign-off |  |  | 3.1695 |  |  |  | 16 |  |  |  | 8
2.07 | Procurement |  |  | 2.3877 |  | Build to Print Procurement |  | 16
2.08 | Safety Review documentation / presentation |  |  | 2.3877 |  |  |  | 16
2.09 | Fab / Design Review - follow-up activities | 2005-07-11 | 2005-10-30 | 6.2969 |  |  |  | 16 |  |  |  | 40
3 | MC INSTALLATION |  |  | 151.3163 |  |  |  | 482 |  | 160 | 568 | 0
3.01 | Concept definition and requirements | 2004-10-25 |  | 9.8784 |  |  |  | 40 |  |  | 40
3.02 | MC Turning Fixture and base - model design and drawing details | 2004-11-15 |  | 13.5184 |  | Vendor purchase item. Vendor generates detail dwgs |  | 12 |  |  | 120
3.03 | MC Gantry Crane - model design and drawing details | 2004-11-29 |  | 13.5184 |  | Vendor purchase item. Vendor generates detail dwgs |  | 12 |  |  | 120
3.04 | VV support stand and Misc crane fixtures | 2005-01-03 |  | 8.4153 |  | Build to Print |  | 4 |  |  | 80
3.05 | Platform - design and drawing details | 2005-01-24 |  | 8.7138 |  | Build to Print |  | 6 |  |  | 80
3.06 | Metrology - develop sightline layout and design/drawing details of unique metrology support stands | 2005-01-03 |  | 13.7876 |  |  |  | 40 |  |  | 80
3.07 | Structural / Seismic Analysis check | 2005-01-06 |  | 23.8768 | [5 empty] | 160
3.08 | Design review |  |  | 3.5815 |  |  |  | 24
3.09 | Design check and sign-off | 2005-01-24 |  | 3.1695 |  |  |  | 16 |  |  | 8
3.1 | Procurement activities |  |  | 17.9076 |  | Includes developing SOW for vendor purchased item |  | 120
3.11 | Procurement Technical Rep |  |  | 22.683 |  | Based on 8 mo Fab of complete system |  | 152
3.12 | Safety Review documentation / presentation |  |  | 2.3877 |  |  |  | 16
3.13 | Fabrication - follow-up activities | 2005-04-13 | 2005-12-02 | 9.8784 |  |  |  | 40 |  |  | 40
4 | FINAL FP ASSEMBLY |  |  | 89.2074 |  |  |  | 184 |  | 80 | 648 | 0
4.01 | Concept definition and requirements | 2005-05-02 |  | 9.8784 |  |  |  | 40 |  |  | 40
4.02 | MC Support Stand - model design and drawing details | 2005-05-09 |  | 13.5184 |  |  |  | 12 |  |  | 120
4.03 | TF HP support and turning fixture - model design and drawing details | 2005-05-30 |  | 13.5184 |  |  |  | 12 |  |  | 120
4.04 | FP Assembly platform - model design and drawing details | 2005-06-20 | [5 empty] | 12 |  |  | 120
4.05 | VV Port Alignment/Weldment Fixture - design and drawing details | 2005-07-11 |  | 13.5184 |  | Using a MC port opening fixture may simplify effort |  | 12 |  |  | 120
4.06 | Metrology - develop sightline layout and design/drawing details of unique metrology support stands | 2005-07-11 |  | 9.0122 |  |  |  | 8 |  |  | 80
4.07 | Structural / Seismic Analysis check | 2005-06-20 |  | 11.9384 | [5 empty] | 80
4.08 | Design review |  |  | 2.3877 |  |  |  | 16
4.09 | Design check and sign-off |  |  | 3.1695 |  |  |  | 16 |  |  | 8
4.1 | Procurement |  |  | 3.5815 |  | Build to Print Procurement |  | 24
4.11 | Safety Review documentation / presentation |  |  | 2.3877 |  |  |  | 16
4.12 | Fabrication - follow-up activities | 2005-12-01 | 2006-03-31 | 6.2969 |  |  |  | 16 |  |  | 40
5 | INTERFACE / TEST ACTIVITIES |  |  | 43.9191 |  |  |  | 120 |  | 80 | 0 | 144
5.01 | Finalize TFTR test cell FPA assembly layout drawings |  |  | 8.3147 |  |  |  | 40 |  |  |  | 24
5.02 | Establish an assembly interface requirements document |  |  | 5.9692 |  |  |  | 40
5.03 | Develop test components as needed to qualify assembly methods | 2005-01-24 |  | 29.6352 |  |  |  | 40 |  | 80 |  | 120
6 | FY06 / FY07 ASSEMBLY COVERAGE |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
7 | ADMINISTRATIVE ACTIVITIES |  |  | 73.3368 |  |  |  | 220 | 160 | 80 | 24 | 24
7.01 | Meetings Prep and Reporting |  |  | 28.5678 |  |  |  | 80 |  | 80 | 24 | 24
7.02 | Develop and maintain concept definition document |  |  | 8.9538 |  | Early document for circulation to FPA group for review and concept concurrence. |  | 60
7.03 | Develop and maintain assembly plan document |  |  | 11.9384 |  |  |  | 80
7.04 | Mike Cole's FY05 on-site involvement in assembly activities & reviews |  |  | 23.8768 |  |  |  |  | 160
| CONTINGENCY |  |  | 76.5418 |  | Assumes 15% level |  | 220 |  | 84 | 186 | 133
| TRAVEL EXPENSES FY05 |  |  | 12
| - WBS manager trips |  |  | 3 |  | Assumes 2 trips @ $1500
| - Turning Fixture Technical Rep |  |  | 4.5 |  | Assumes 3 trips @ $1500
| - Mike Cole |  |  | 4.5 |  | Assumes 3 trips @ $1500
As of May 9 - Used 1006 design hrs for Lew and Bruce
| Expected support activities from Steve Raftopoulos for FY05 |  |  |  |  | Assume 6 wks

## Assembly Steps
| Field Period Assembly Steps | Expected Days | nb men | man hrs | 1 FTE Crane | Measurement | Contingency | Comments
Stage 1 (VV Prep) - for one FPA that includes diagnostic sensors |  | 79.5 |  | 2356
1 | Receive VV and inspect | 4 | 3 | 96 | X | 2 |  | see note 2
2 | Mount VV on VV Prep fixture (top side up) | 0.5 | 3 | 12 | X
3 | Establish metrology setting and monuments with respect to assembly; align VV base to reference coordinate system | 3 | 3 | 72 | X | 2
4 | Install local platforms | 0 |  |  | X |  |  | These are local "steps" used as needed to reach top areas
5 | Mark surface for stud placement | 0 | [5 empty] | This effort will be done by Major Tool
6 | Attach studs (hardware) on top side for mounting diagnostics, coolant lines and insulation. [1200 studs / 25 studs per hr / 6 hrs per day] See note 1. | 8 | 3 | 192 | X |  |  | Install 50 diagnostic coils (x 4 studs) first period + 350 tube studs + 6" grid of studs (650) for insulation. 1200 total studs on top.
7 | Wind magnetic diagnostic sensors to top surface and take metrology measurements [50 diagnostic loops / 1 per hr / 6 hrs per day] | 8 | 3 | 192 | X | 2
8 | Install cooling/heating lines to vacuum vessel top surface | 8 | 4 | 256 |  |  |  | 32 tube preformed on top
9 | Install insulation to vacuum vessel to top surface | 10 | 5 | 400
10 | Flip VV to expose lower surface | 1 | 3 | 24 | X
11 | Mark surface for stud placement | 0 | [5 empty] | This effort will be done by Major Tool
12 | Attach studs (hardware) on top side for mounting diagnostics, coolant lines and insulation | 8 | 3 | 192 | X |  |  | Install 50 diagnostic coils (x 4 studs) first period + 350 tube studs + 6" grid of studs (650) for insulation. 1200 total studs on bottom.
13 | Wind magnetic diagnostic sensors to top surface and take metrology measurements [50 diagnostic loops / 1 per hr / 6 hrs per day = 8.3 days] | 8 | 3 | 192 | X | 2
14 | Install cooling/heating lines to vacuum vessel bottom surface | 8 | 4 | 256
15 | Install insulation to vacuum vessel to bottom surface | 10 | 5 | 400
16 | Prepare and transfer completed VV to holding area | 3 | 3 | 72 | X
Stage 1 (VV Prep) - for FPA that has no diagnostic sensors |  | 61.5 |  | 1796
1 | Receive VV inspect | 4 | 3 | 96 | X | 2
2 | Mount VV on VV Prep fixture (top side up) | 0.5 | 3 | 12 | X
3 | Establish metrology setting and monuments with respect to assembly; align VV base to reference coordinate system | 3 | 3 | 72 | X | 2
4 | Install local platforms | 0 |  |  | X |  |  | These are local "steps" used as needed to reach top areas
5 | Mark surface for stud placement | 0 | [5 empty] | This effort will be done by Major Tool
6 | Attach studs (hardware) on top side for coolant lines and insulation. [1000 studs / 25 studs per hr / 6 hrs per day = 6.7days] See note 1. | 7 | 3 | 168 | X |  |  | 350 tube studs + 6" grid of studs (650) for insulation. 1000 total studs on top.
7 | Install cooling/heating lines to vacuum vessel top surface | 8 | 3 | 192
8 | Install insulation to vacuum vessel to top surface | 10 | 5 | 400
9 | Flip VV to expose lower surface | 1 | 3 | 24 | X
10 | Mark surface for stud placement | 0 | [5 empty] | This effort will be done by Major Tool
11 | Attach studs (hardware) on top side for coolant lines and insulation. [1000 studs / 25 studs per hr / 6 hrs per day = 6.7days] See note 1. | 7 | 3 | 168 | X |  |  | 350 tube studs + 6" grid of studs (650) for insulation. 1000 total studs on bottom.
12 | Install cooling/heating lines to vacuum vessel bottom surface | 8 | 3 | 192
13 | Install insulation to vacuum vessel to bottom surface | 10 | 5 | 400
14 | Prepare and transfer completed VV to holding area | 3 | 3 | 72 | X
Stage 2 (MC Half Period Assembly) - two operations required |  | 27 |  | 808 |  |  |  | Requires two operations for a complete Field Period
1 | Mount Type A in fixture and set spherical seats | 2 | 3 | 48 | X | 2
2 | Mount the Type B in fixture, locating it on the Type A spherical seats; check A-to-B alignment. | 2 | 3 | 48 | X | 2
3 | Add shims between A and B and ream 24 holes | 5 | 5 | 200 | X
4 | Bolt together Type A and B; check alignment | 2 | 3 | 48 |  | 2
4 | Set Type B spherical seats; adjust fixture to accept Type C | 2 | 3 | 48 | X | 2
5 | Mount the Type C in fixture, locating it on the Type B spherical seats; check alignment. | 2 | 3 | 48 | X | 2
6 | Add shims between B and C and ream 24 holes | 5 | 5 | 200 | X
7 | Bolt together Type B and C; check alignment | 2 | 3 | 48 | X | 2
8 | Set Type C spherical seats; make final alignment check | 2 | 3 | 48 | X | 2
9 | Mount all turning fixture interfacing hardware | 2 | 3 | 48 | X
10 | Prepare and transfer completed MC half period assembly to holding area | 1 | 3 | 24 | X
Stage 3 (MC installation) |  | 30 |  | 816
1 | Mount VV to MC turning fixture base and gantry frame; perform metrology check | 2 | 3 | 48 | X | 2 | 2 | Extra days needed if VV needs adjusting
2 | Mount MC on turning fixture; set orientation and perform metrology checks | 2 | 3 | 48 | X | 2 | 3 | Extra days needed the first time through
3 | Rotate right MC to stand-off position and check position | 3 | 3 | 72 | X | 2
4 | Transfer load to gantry crane and recheck position | 2 | 3 | 48 | X | 2
5 | Move MC turning fixture to left side and mount MC on turning fixture; set orientation and perform metrology checks | 2 | 3 | 48 | X | 2
6 | Rotate left MC to stand-off position and check position | 3 | 3 | 72 | X | 2
7 | Move left and right MC to final position and take gap measurements to validate shim dimensions | 2 | 3 | 48 | X | 2
8 | Install shims (back off left and right MC’s as reqd); ream 24 holes | 7 | 5 | 280 | X
9 | Bolt together at flange interface. | 2 | 3 | 48
10 | Perform final metrology position check of completed full period assembly as well as check spherical seat position of the Type-C MC that interfaces with the next FP Assembly. | 2 | 2 | 32 | X | 2
11 | Attach VV to MC using final hardware links; secure VV at each end to MC's using temporary supports. | 2 | 3 | 48 | X
12 | Prepare and transfer completed assembly to Stage 4 area | 1 | 3 | 24 | X
Stage 4 (Final FP Assembly) |  | 70 |  | 2968
1 | Mount MC/VV assembly to support frame at final assembly station; perform metrology checks | 2 | 3 | 48 | X | 2
2 | Position and weld all ports to VV except for the two large horizontal diagnostic ports | 20 | 6 | 960 | X | 2 |  | 22 ports at this time. Need an alignment method to support two teams
3 | Inspect Welds | 5 | 2 | 80
4 | Assemble left TF Coil Assembly and check position | 3 | 4 | 96 | X | 2
5 | Change platforms | 2 | 3 | 48 | X
6 | Assemble right TF Coil Assembly (requires support readjustment) and perform measurement checks | 3 | 4 | 96 | X | 2 |  | Currently assumes readjustment of stage 4 supports to accommodate rotating right side TF
7 | Attach TF coils to MC's | 3 | 3 | 72 | X
8 | Change platforms | 2 | 4 | 64 | X
9 | Position and weld two large horizontal diagnostic ports to VV | 8 | 3 | 192 | X | 2
10 | Inspect Welds | 1 | 2 | 16
12 | Assemble external trim coils, I&C, leads and coolant lines | 10 | 6 | 480 | X | 2 |  | It is assumed that this effort is carried out during steps 7 thru 10, a parallel effort. The 10 days is not counted in the total elapsed time. Note: number men increased over Rev 5 (was 3).
11 | Close up VV (added blank-off flanges and weld on end plates), bakeout VV to 350 deg C and leak check | 20 | 4 | 640 |  |  |  | It is assumed that this occurs continuously (for a 7 day work week). This saves 5 days in the schedule.
13 | Using metrology measurements adjust final support base interfaces | 2 | 3 | 48 | X | 2
14 | Prepare Field Period for shipment | 2 | 3 | 48 | X
15 | Transfer completed assembly to C-site test cell | 2 | 5 | 80 | X
| Total VV Prep assembly days | 220.5 | [5 empty] | Assumes 2 diagnostic periods and 1 non-diagnostic period.
| Total MC Half Period assembly days | 162
| Total MC installation days | 90
| Total Final FP Assembly days | 210
Notes:
1 | Background data used for estimating.
If you have the stud locations identified in advance, they are in close proximity, and you are shooting the same studs, you can shoot 30-40 studs an hour.
If you are changing sizes or have to change locations, then 20-30 an hour is reasonable. (Steve Kemp input)
2 | The measurement manpower estimate implies that this activity is accomplished by an engineer and technician working together (both metrology trained).

## Schedule
| Updated 8/22/05 | [9 empty] | FY 2005 | [28 empty] | FY 2006 | [11 empty] | FY 2007 | [8 empty] | FY 2008 | [11 empty] | FY 2009
|  |  | FEB |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUG |  |  |  | SEPT |  |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
ITEM | TASK | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
Target - Finish Last Field Period Assembly
Scheduled start of VV Pumpdown
1 | VV PREP STATION (Build to Print) | BP | [13 empty] | PDR |  |  |  |  | FDR | [14 empty] | O: VV period Arrival dates
1.01 | Concept definition and requirements
1.02 | VV Support Fixture plus dwgs
1.03 | Metrology layout / support stand dwgs
1.04 | Structural Analysis
1.05 | Fab Activities -
- VV alignment system
| - VV supports | [34 empty] | FY 2006 M: 1st VV; FY 2006 A: 2nd; FY 2007 M: 3rd
2.06 | VV Assembly Operations (1 station)
[17 empty] | C1 MC set Arrives | [18 empty] | FY 2006 A: Last MC set (C6) Arrives
[41 empty] | Complete MC test C1 | C2 |  |  |  | A1,C3 |  | A2,C4 |  | B1,C5, C6 |  |  | B2 | A3 | A4,5,6 |  |  | B3,B4 |  |  | B5 |  | B6 Complete
2 | HALF PERIOD ASSEMBLY (Build to Print) | LM | [13 empty] | PDR |  |  |  |  | FDR
2.01 | Concept definition and requirements
2.02 | MC Holding Fixture
2.03 | Metrology layout / support stand dwgs
2.04 | Structural Analysis
2.05 | Procurement (build to print) | [34 empty] | FY 2006 O: C4 / C5; FY 2007 M: A3 / A4; FY 2007 J: A5 / A6
2.06 | Fab Activities - Support fixture (2 ?)
| - Spherical seats (56) | [34 empty] | FY 2006 A: A1 / B1 / C1
2.07 | HP Assembly Operations (2 Stations) | [34 empty] | FY 2006 J: A2 / B2 / C2; FY 2008 J: A5 / B5 / C5
[56 empty] | A3 / B3 / C3 | [6 empty] | A6 / B6 / C6
[41 empty] | C2 / C3 |  |  |  | A1 / A2 | [12 empty] | A4 / B4 / C4
3 | MC INSTALLATION (Outside design & Fab) | TB, LM | [33 empty] | FY 2006 N: A1 / B1 / C1 / C6
3.01 | Concept definition and requirements | Done
3.02 | MC Turning Fixture and base | [7 empty] | Resized for seismic loading and Left side movement
3.03 | MC Gantry Crane | 90% done
3.04 | VV support stand and Misc crane fixtures | [11 empty] | TB
3.05 | Platform design | [8 empty] | LM |  |  |  |  | Assumes platforms are part of contract.
3.06 | Metrology layout / support stand dwgs | [11 empty] | LM
3.07 | Structural Analysis
3.08 | Procurement activities
| - MCAF procurement | [17 empty] | Issue RFP 4 April | [9 empty] | Award 30 June | [6 empty] | N: FDR; FY 2006 F: Start Fab; FY 2006 J: Deliver MCAF
3.09 | Fab Activities | [23 empty] | Proposal Due
- MCAF components
- Platforms (part of contract?)
3.1 | Assembly Activities
- Trial Runs - no VV
- Trial Runs - bare VVP plus MCHP
- MC Installation (1 Station)
4 | FINAL FP ASSEMBLY (Build to Print) | Morris / Paul | [32 empty] | PDR | D: FDR
4.01 | Concept definition and requirements | [19 empty] | BP
4.02 | MC Support Stand
4.03 | TF HP support and turning fixture
4.04 | FP Assembly platform
4.05 | VV Port Alignment/Weldment Fixture | [25 empty] | LM | [8 empty] | FY 2008 J: FPA-1 starts XXXXX, test cell delivery XXXXXX
4.06 | Metrology layout / support stand dwgs | [21 empty] | LM | [12 empty] | FY 2008 J: FPA-2 starts XXXXX, test cell delivery XXXXX
4.07 | Structural Analysis | [34 empty] | FY 2008 J: FPA-3 starts 1 Feb 08, test cell delivery 21 May 08
4.08 | Procurement (May not be needed)
4.09 | Fabrication - follow-up activities | [34 empty] | FY 2007 J: FPA-1; FY 2008 A: FPA-3
- TF HP support
- FP Assembly platform & port fixtures
| (2 stations required) | [34 empty] | FY 2008 J: FPA-2
5 | TF HP ASSEMBLY (Build to Print) | GS | [28 empty] | PDR |  |  |  |  | O: FDR
5.01 | Concept definition and requirements
5.02 | TF Rotation Fixture plus dwgs
5.03 | Metrology layout / support stand dwgs
5.04 | Structural Analysis
5.05 | Fab Activities -
5.06 | TF HP Assembly Operations (1 station)
6 | INTERFACE / TEST ACTIVITIES
6.01 | TFTR test cell FPA arngmt dwg | [23 empty] | LM
6.02 | Design MC assembly test components | [18 empty] | BP
6.03 | Fab Activities - Test Articles
6.04 | Run test / metrology measurements
6.05 | Metrology Validation (Raftopoulos Activity)
NEED TWO STAGE 2 FIXTURES BECAUSE OF OVERLAP
Models
All Dwgs
Models / Dwgs
Models / Dwgs
Models
Dwgs
Run A1/B1/C1 over 3rd VVP
Models
Dwgs
GS scheculed to continue work on TF winding fixture

## Schedule time line
ITEM | TASK | START | END | COMMENTS
1 | VV PREP STATION (Build to Print)
1.01 | Concept definition and requirements | 2005-03-09 | 2005-03-18
1.02 | VV Support Fixture plus dwgs | 2005-03-21 | 2005-04-12
1.03 | Metrology layout / support stand dwgs | 2005-04-13 | 2005-05-06
1.04 | Structural Analysis | 2005-03-16 | 2005-04-01
| PDR / FDR | 2005-05-10 | 2005-06-14
1.05 | Fab Activities -
| - VV alignment system | 2005-06-20 |  | Fab activities need to be coordinated with Larry Dudek
| - VV supports | 2005-08-01
2.06 | VV Assembly Operations (1 station) |  |  | Ron's call
2 | HALF PERIOD ASSEMBLY (Build to Print)
2.01 | Concept definition and requirements | - | 2005-03-25 | Concept complet, reqmts write-up done by 3/25
2.02 | MC Holding Fixture | - | 2005-05-20 | Model complete; dwgs done by 5/20
2.03 | Metrology layout / support stand dwgs | 2005-04-18 | 2005-04-29
2.04 | Structural Analysis | 2005-04-04 | 2005-04-15
| PDR / FDR | 2005-05-31 | 2005-06-29
2.05 | Procurement (build to print) |  |  | In-house vs outside fab is TBD
2.06 | Fab Activities - Support fixture (2 ?)
2.07 | HP Assembly Operations (2 Stations) |  |  | Ron's call
3 | MC INSTALLATION (Outside design & Fab)
3.01 | Concept definition and requirements | - | 2005-04-08 | Concept complet, reqmts write-up done by 4/8
3.02 | MC Turning Fixture and base | 2005-03-07 | 2005-03-18
3.03 | MC Gantry Crane | 2005-03-21 | 2005-03-25
3.04 | VV support stand and Misc crane fixtures | 2005-04-01 | 2005-04-20
3.05 | Platform design | 2005-03-14 | 2005-03-25
3.06 | Metrology layout / support stand dwgs | 2005-03-28 | 2005-04-15
3.07 | Structural Analysis | 2005-08-22 | 2005-09-02
3.08 | Procurement activities |  |  | See schedule
- MCAF procurement
3.09 | Fab Activities |  |  | See schedule
- MCAF components
- Platforms (part of contract?)
3.1 | Assembly Activities |  |  | Ron's call
- Trial Runs - no VV
- Trial Runs - bare VVP plus MCHP
- MC Installation (1 Station)
4 | FINAL FP ASSEMBLY (Build to Print)
4.01 | Concept definition and requirements | 2005-07-04 | 2005-07-15
4.02 | MC Support Stand | 2005-07-18 | 2005-08-05
4.03 | TF HP support and turning fixture | 2005-08-08 | 2005-08-26
4.04 | FP Assembly platform | 2005-08-29 | 2005-09-23
4.05 | VV Port Alignment/Weldment Fixture | 2005-08-08 | 2005-08-26
4.06 | Metrology layout / support stand dwgs | 2005-07-13 | 2005-08-03
4.07 | Structural Analysis | 2005-08-22 | 2005-09-02
| PDR / FDR | 2005-10-20 | 2005-11-29
4.08 | Procurement (May not be needed) |  |  | Fab activities need to be coordinated with Larry Dudek
4.09 | Fabrication - follow-up activities |  |  | Ron's call
- TF HP support
- FP Assembly platform & port fixtures
(2 stations required)
5 | TF HP ASSEMBLY (Build to Print)
5.01 | Concept definition and requirements | 2005-05-02 | 2005-05-13
5.02 | TF Rotation Fixture plus dwgs | 2005-05-16 | 2005-08-19
5.03 | Metrology layout / support stand dwgs | 2005-07-18 | 2005-07-29
5.04 | Structural Analysis | 2005-07-11 | 2005-07-29
| PDR / FDR | 2005-08-30 | 2005-09-27
5.05 | Fab Activities - |  |  | Fab activities need to be coordinated with Larry Dudek
5.06 | TF HP Assembly Operations (1 station) |  |  | Ron's call
6 | INTERFACE / TEST ACTIVITIES
6.01 | TFTR test cell FPA arngmt dwg | 2005-06-13 | 2005-07-13
6.02 | Design MC assembly test components | 2005-05-09 | 2005-06-10
6.03 | Fab Activities - Test Articles | 2005-06-13 | 2005-07-29
6.04 | Run test / metrology measurements | 2005-08-01 | 2005-09-02
6.05 | Metrology Validation (Raftopoulos Activity) | 2005-08-01 | 2005-09-02

## Procmt Schedule
[11 empty] | FY2005 | [14 empty] | FY2006 | [6 empty] | FY2007
|  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUG |  |  |  | SEPT |  |  | O | N | D | J | F | M | A | S | O | N | D | J
ITEM | TASK | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
Define contract structure
Complete Specification Document
Complete SOW
Spec & SOW Review
Develop evaluation plan & selection criteria
Contract Plan Review
Issue RFP
Proposals Due
Award contract
MCAF Design Phase
Ref Design / Alternate concept review period
Define changes to Ref Design or propose Alt
MCAFdesign selection review
Rework Ref Design or develop alternate
PDR
Finish fabrication drawings
Informal interim reviews
FDR
Approve design for final costing
Submit fixed price proposal
Award fixed price contract
MCAF Fabrication Phase
Procure materials
Fab & machine parts
Assemble Turning Fixture
Assemble Gantry Crane
Assembly VV base support
Develop operations program
Operations Test
Inspection
Ship
June 15
13 MWK effort

## PPPL Designers
NCSX MECHANICAL CAD DESIGN MANPOWER - 3/14/05
WBS | Lead Engr | Designer | Task | March | April | May | June | July | Aug | Sept
18 | T. Brown | B. Paul | VV prep station (Station 1)
18 | T. Brown | L. Morris | HP assembly (Station 2)
18 | T. Brown | L. Morris | MC installation (Station 3)
18 | D. Loesser | Morris / Paul | Final FP Assembly (Station 4)
18 | T. Brown | B. Paul | Installation test activities
18 | T. Brown | L. Morris | Test cell asmbly instl / services dwgs
18 | T. Brown | G. Steill | TF HP Assembly
13 | M. Kalish | J. Rushinski | TF winding
13 | M. Kalish | J. Rushinski | PF windings
13 | M. Kalish | J. Rushinski | Trim coils
15 | B. Parsells | J. Rushinski | Machine structure
16 | G. Gettelfinger | J. Rushinski | Conv. magnet system lead routings
13 | M. Kalish | G. Steill | TF winding fixtures
7 | E. Perry | M. Messineo | Test cell platforms
62 | G. Gettelfinger | M. Messineo | Cryostat shell
62 | G. Gettelfinger | M. Messineo | Cryostat port boots
62 | G. Gettelfinger | M. Messineo | Machine support / installation
62 | G. Gettelfinger | M. Messineo | VV spacer installation
| G. Gettelfinger | G. Steill | Core coolant routing
| T. Brown | G. Steill | Lead routing outside of core
Originally a LM / BP effort
1.5 mo follow-up
Task available if needed to fill up slack time

## HW Cost
|  | Cost Estimate | Nb | Total Cost
| Hardware Items | ($K) | Stations | ($K)
1 | VV PREP STATION | 40 | 1 | 40
1.02 | VV Support Fixture | 20
1.03 | VV Prep Station Platform | 10
1.04 | VV Prep Station Metrology support stands | 10
2 | HALF PERIOD ASSEMBLY | 30 | 2 | 60
2.01 | MC HP Assembly fixture | 20
2.02 | HP Assembly Metrology support stands | 10
3 | MC INSTALLATION | 335 | 1 | 335
3.02 | MC Turning Fixture and base | 250
3.03 | MC Gantry Crane | 25
3.04 | VV support stand and Misc crane fixtures | 30
3.05 | Platform | 20
3.06 | MC Installation Metrology support stands | 10
4 | FINAL FP ASSEMBLY | 95 | 2 | 190
4.02 | MC Support Stand | 20
4.03 | TF HP support and turning fixture | 15
4.04 | MC Tempory End Support | 10
4.05 | FP Assembly platform | 30
4.06 | VV Port Alignment/Weldment Fixture | 10
4.07 | Final FP Assembly Metrology support stands | 10
5 | INTERFACE / TEST ACTIVITIES | 15 | 1 | 15
5.03 | Matrology test component | 15
| Total Hardware Cost Estimate ($K) | 515 |  | 640
Note: This is a VERY preliminary cost estimate