## Manpower
[7 empty] | Personnel | [5 empty] | Rates
[7 empty] | Name | Brown | Cole | Analyst | Morris | Paul | Demographic | Rate
[7 empty] | Demographic | EA//EM | EA//EM | EA//EM | EA//DM | EA//DM | EA//DM | 97.73
[7 empty] | Loaded Rate | 149.23 | 149.23 | 149.23 | 97.73 | 97.73 | EA//EM | 149.23
|  |  | TOTAL MANPOWER COST - includes contingency and travel ($k) = | 609.4157 | TOTAL HOURS = | 4314 | Hours | 1470 | 160 | 560 | 1240 | 884 | FC//EM | 157.0104
[7 empty] | FTE | 85.17% | 9.27% | 32.44% | 71.84% | 51.22%
Job Title | Machine Assembly
Job Manager | Tom Brown
Job Number
| Tasks | Start | Finish | Cost (k$) | Deliverables | Remarks
1 | VV PREP STATION |  |  | 81.1667 |  |  |  | 236 |  | 80 | 0 | 348
1.01 | Concept definition and requirements | 2005-01-26 |  | 14.8176 |  |  |  | 60 |  |  |  | 60
1.02 | VV Support Fixture - model design and drawing details | 2005-02-14 |  | 12.9214 |  |  |  | 8 |  |  |  | 120
1.03 | Metrology - develop sightline layout and design/drawing details of unique metrology support stands | 2005-03-07 |  | 23.666 |  |  |  | 80 |  |  |  | 120
1.04 | Structural Analysis check | 2005-03-21 |  | 11.9384 | [5 empty] | 80
1.05 | Design review |  |  | 3.5815 |  |  |  | 24
1.06 | Design check and sign-off | 2005-04-11 |  | 3.1695 |  |  |  | 16 |  |  |  | 8
1.07 | Procurement |  |  | 2.3877 |  | Build to Print Procurement |  | 16
1.08 | Safety Review documentation / presentation |  |  | 2.3877 |  |  |  | 16
1.09 | Fab / Design Review - follow-up activities | 2005-07-11 | 2005-09-02 | 6.2969 |  |  |  | 16 |  |  |  | 40
2 | HALF PERIOD ASSEMBLY |  |  | 81.9275 |  |  |  | 228 |  | 80 | 0 | 368
2.01 | Concept definition and requirements | 2005-02-09 |  | 14.8176 |  |  |  | 60 |  |  |  | 60
2.02 | MC Holding Fixture - model design and drawing details | 2005-02-21 |  | 20.576 |  |  |  | 20 |  |  |  | 180
2.03 | Metrology - develop sightline layout and design/drawing details of unique metrology support stands | 2005-03-14 |  | 16.7722 |  |  |  | 60 |  |  |  | 80
2.04 | Structural / Seismic Analysis check | 2005-03-21 |  | 11.9384 | [5 empty] | 80
2.05 | Design review |  |  | 3.5815 |  |  |  | 24
2.06 | Design check and sign-off |  |  | 3.1695 |  |  |  | 16 |  |  |  | 8
2.07 | Procurement |  |  | 2.3877 |  | Build to Print Procurement |  | 16
2.08 | Safety Review documentation / presentation |  |  | 2.3877 |  |  |  | 16
2.09 | Fab / Design Review - follow-up activities | 2005-07-11 | 2005-10-30 | 6.2969 |  |  |  | 16 |  |  |  | 40
3 | MC INSTALLATION |  |  | 151.3163 |  |  |  | 482 |  | 160 | 568 | 0
3.01 | Concept definition and requirements | 2004-10-25 |  | 9.8784 |  |  |  | 40 |  |  | 40
3.02 | MC Turning Fixture and base - model design and drawing details | 2004-11-15 |  | 13.5184 |  | Vendor purchase item. Vendor generates detail dwgs |  | 12 |  |  | 120
3.03 | MC Gantry Crane - model design and drawing details | 2004-11-29 |  | 13.5184 |  | Vendor purchase item. Vendor generates detail dwgs |  | 12 |  |  | 120
3.04 | VV support stand and Misc crane fixtures | 2005-01-03 |  | 8.4153 |  | Build to Print |  | 4 |  |  | 80
3.05 | Platform - design and drawing details | 2005-01-24 |  | 8.7138 |  | Build to Print |  | 6 |  |  | 80
3.06 | Metrology - develop sightline layout and design/drawing details of unique metrology support stands | 2005-01-03 |  | 13.7876 |  |  |  | 40 |  |  | 80
3.07 | Structural / Seismic Analysis check | 2005-01-06 |  | 23.8768 | [5 empty] | 160
3.08 | Design review |  |  | 3.5815 |  |  |  | 24
3.09 | Design check and sign-off | 2005-01-24 |  | 3.1695 |  |  |  | 16 |  |  | 8
3.1 | Procurement activities |  |  | 17.9076 |  | Includes developing SOW for vendor purchased item |  | 120
3.11 | Procurement Technical Rep |  |  | 22.683 |  | Based on 8 mo Fab of complete system |  | 152
3.12 | Safety Review documentation / presentation |  |  | 2.3877 |  |  |  | 16
3.13 | Fabrication - follow-up activities | 2005-04-13 | 2005-12-02 | 9.8784 |  |  |  | 40 |  |  | 40
4 | FINAL FP ASSEMBLY |  |  | 89.2074 |  |  |  | 184 |  | 80 | 648 | 0
4.01 | Concept definition and requirements | 2005-05-02 |  | 9.8784 |  |  |  | 40 |  |  | 40
4.02 | MC Support Stand - model design and drawing details | 2005-05-09 |  | 13.5184 |  |  |  | 12 |  |  | 120
4.03 | TF HP support and turning fixture - model design and drawing details | 2005-05-30 |  | 13.5184 |  |  |  | 12 |  |  | 120
4.04 | FP Assembly platform - model design and drawing details | 2005-06-20 | [5 empty] | 12 |  |  | 120
4.05 | VV Port Alignment/Weldment Fixture - design and drawing details | 2005-07-11 |  | 13.5184 |  | Using a MC port opening fixture may simplify effort |  | 12 |  |  | 120
4.06 | Metrology - develop sightline layout and design/drawing details of unique metrology support stands | 2005-07-11 |  | 9.0122 |  |  |  | 8 |  |  | 80
4.07 | Structural / Seismic Analysis check | 2005-06-20 |  | 11.9384 | [5 empty] | 80
4.08 | Design review |  |  | 2.3877 |  |  |  | 16
4.09 | Design check and sign-off |  |  | 3.1695 |  |  |  | 16 |  |  | 8
4.1 | Procurement |  |  | 3.5815 |  | Build to Print Procurement |  | 24
4.11 | Safety Review documentation / presentation |  |  | 2.3877 |  |  |  | 16
4.12 | Fabrication - follow-up activities | 2005-12-01 | 2006-03-31 | 6.2969 |  |  |  | 16 |  |  | 40
5 | INTERFACE / TEST ACTIVITIES |  |  | 43.9191 |  |  |  | 120 |  | 80 | 0 | 144
5.01 | Finalize TFTR test cell FPA assembly layout drawings |  |  | 8.3147 |  |  |  | 40 |  |  |  | 24
5.02 | Establish an assembly interface requirements document |  |  | 5.9692 |  |  |  | 40
5.03 | Develop test components as needed to qualify assembly methods | 2005-01-24 |  | 29.6352 |  |  |  | 40 |  | 80 |  | 120
6 | FY06 / FY07 ASSEMBLY COVERAGE |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
7 | ADMINISTRATIVE ACTIVITIES |  |  | 73.3368 |  |  |  | 220 | 160 | 80 | 24 | 24
7.01 | Meetings Prep and Reporting |  |  | 28.5678 |  |  |  | 80 |  | 80 | 24 | 24
7.02 | Develop and maintain concept definition document |  |  | 8.9538 |  | Early document for circulation to FPA group for review and concept concurrence. |  | 60
7.03 | Develop and maintain assembly plan document |  |  | 11.9384 |  |  |  | 80
7.04 | Mike Cole's FY05 on-site involvement in assembly activities & reviews |  |  | 23.8768 |  |  |  |  | 160
| CONTINGENCY |  |  | 76.5418 |  | Assumes 15% level |  | 220 |  | 84 | 186 | 133
| TRAVEL EXPENSES FY05 |  |  | 12
| - WBS manager trips |  |  | 3 |  | Assumes 2 trips @ $1500
| - Turning Fixture Technical Rep |  |  | 4.5 |  | Assumes 3 trips @ $1500
| - Mike Cole |  |  | 4.5 |  | Assumes 3 trips @ $1500
| Expected support activities from Steve Raftopoulos for FY05 |  |  |  |  | Assume 6 wks

## Assembly Steps
| Field Period Assembly Steps | Expected Days | nb men | man hrs | 1 FTE Crane | Measurement | Contingency | Comments
Stage 1 (VV Prep) - for one FPA that includes diagnostic sensors |  | 79.5 |  | 2356
1 | Receive VV and inspect | 4 | 3 | 96 | X | 2 |  | see note 2
2 | Mount VV on VV Prep fixture (top side up) | 0.5 | 3 | 12 | X
3 | Establish metrology setting and monuments with respect to assembly; align VV base to reference coordinate system | 3 | 3 | 72 | X | 2
4 | Install local platforms | 0 |  |  | X |  |  | These are local "steps" used as needed to reach top areas
5 | Mark surface for stud placement | 0 | [5 empty] | This effort will be done by Major Tool
6 | Attach studs (hardware) on top side for mounting diagnostics, coolant lines and insulation. [1200 studs / 25 studs per hr / 6 hrs per day] See note 1. | 8 | 3 | 192 | X |  |  | Install 50 diagnostic coils (x 4 studs) first period + 350 tube studs + 6" grid of studs (650) for insulation. 1200 total studs on top.
7 | Wind magnetic diagnostic sensors to top surface and take metrology measurements [50 diagnostic loops / 1 per hr / 6 hrs per day] | 8 | 3 | 192 | X | 2
8 | Install cooling/heating lines to vacuum vessel top surface | 8 | 4 | 256 |  |  |  | 32 tube preformed on top
9 | Install insulation to vacuum vessel to top surface | 10 | 5 | 400
10 | Flip VV to expose lower surface | 1 | 3 | 24 | X
11 | Mark surface for stud placement | 0 | [5 empty] | This effort will be done by Major Tool
12 | Attach studs (hardware) on top side for mounting diagnostics, coolant lines and insulation | 8 | 3 | 192 | X |  |  | Install 50 diagnostic coils (x 4 studs) first period + 350 tube studs + 6" grid of studs (650) for insulation. 1200 total studs on bottom.
13 | Wind magnetic diagnostic sensors to top surface and take metrology measurements [50 diagnostic loops / 1 per hr / 6 hrs per day = 8.3 days] | 8 | 3 | 192 | X | 2
14 | Install cooling/heating lines to vacuum vessel bottom surface | 8 | 4 | 256
15 | Install insulation to vacuum vessel to bottom surface | 10 | 5 | 400
16 | Prepare and transfer completed VV to holding area | 3 | 3 | 72 | X
Stage 1 (VV Prep) - for FPA that has no diagnostic sensors |  | 61.5 |  | 1796
1 | Receive VV inspect | 4 | 3 | 96 | X | 2
2 | Mount VV on VV Prep fixture (top side up) | 0.5 | 3 | 12 | X
3 | Establish metrology setting and monuments with respect to assembly; align VV base to reference coordinate system | 3 | 3 | 72 | X | 2
4 | Install local platforms | 0 |  |  | X |  |  | These are local "steps" used as needed to reach top areas
5 | Mark surface for stud placement | 0 | [5 empty] | This effort will be done by Major Tool
6 | Attach studs (hardware) on top side for coolant lines and insulation. [1000 studs / 25 studs per hr / 6 hrs per day = 6.7days] See note 1. | 7 | 3 | 168 | X |  |  | 350 tube studs + 6" grid of studs (650) for insulation. 1000 total studs on top.
7 | Install cooling/heating lines to vacuum vessel top surface | 8 | 3 | 192
8 | Install insulation to vacuum vessel to top surface | 10 | 5 | 400
9 | Flip VV to expose lower surface | 1 | 3 | 24 | X
10 | Mark surface for stud placement | 0 | [5 empty] | This effort will be done by Major Tool
11 | Attach studs (hardware) on top side for coolant lines and insulation. [1000 studs / 25 studs per hr / 6 hrs per day = 6.7days] See note 1. | 7 | 3 | 168 | X |  |  | 350 tube studs + 6" grid of studs (650) for insulation. 1000 total studs on bottom.
12 | Install cooling/heating lines to vacuum vessel bottom surface | 8 | 3 | 192
13 | Install insulation to vacuum vessel to bottom surface | 10 | 5 | 400
14 | Prepare and transfer completed VV to holding area | 3 | 3 | 72 | X
Stage 2 (MC Half Period Assembly) - two operations required |  | 27 |  | 808 |  |  |  | Requires two operations for a complete Field Period
1 | Mount Type A in fixture and set spherical seats | 2 | 3 | 48 | X | 2
2 | Mount the Type B in fixture, locating it on the Type A spherical seats; check A-to-B alignment. | 2 | 3 | 48 | X | 2
3 | Add shims between A and B and ream 24 holes | 5 | 5 | 200 | X
4 | Bolt together Type A and B; check alignment | 2 | 3 | 48 |  | 2
4 | Set Type B spherical seats; adjust fixture to accept Type C | 2 | 3 | 48 | X | 2
5 | Mount the Type C in fixture, locating it on the Type B spherical seats; check alignment. | 2 | 3 | 48 | X | 2
6 | Add shims between B and C and ream 24 holes | 5 | 5 | 200 | X
7 | Bolt together Type B and C; check alignment | 2 | 3 | 48 | X | 2
8 | Set Type C spherical seats; make final alignment check | 2 | 3 | 48 | X | 2
9 | Mount all turning fixture interfacing hardware | 2 | 3 | 48 | X
10 | Prepare and transfer completed MC half period assembly to holding area | 1 | 3 | 24 | X
Stage 3 (MC installation) |  | 30 |  | 816
1 | Mount VV to MC turning fixture base and gantry frame; perform metrology check | 2 | 3 | 48 | X | 2 | 2 | Extra days needed if VV needs adjusting
2 | Mount MC on turning fixture; set orientation and perform metrology checks | 2 | 3 | 48 | X | 2 | 3 | Extra days needed the first time through
3 | Rotate right MC to stand-off position and check position | 3 | 3 | 72 | X | 2
4 | Transfer load to gantry crane and recheck position | 2 | 3 | 48 | X | 2
5 | Move MC turning fixture to left side and mount MC on turning fixture; set orientation and perform metrology checks | 2 | 3 | 48 | X | 2
6 | Rotate left MC to stand-off position and check position | 3 | 3 | 72 | X | 2
7 | Move left and right MC to final position and take gap measurements to validate shim dimensions | 2 | 3 | 48 | X | 2
8 | Install shims (back off left and right MC’s as reqd); ream 24 holes | 7 | 5 | 280 | X
9 | Bolt together at flange interface. | 2 | 3 | 48
10 | Perform final metrology position check of completed full period assembly as well as check spherical seat position of the Type-C MC that interfaces with the next FP Assembly. | 2 | 2 | 32 | X | 2
11 | Attach VV to MC using final hardware links; secure VV at each end to MC's using temporary supports. | 2 | 3 | 48 | X
12 | Prepare and transfer completed assembly to Stage 4 area | 1 | 3 | 24 | X
Stage 4 (Final FP Assembly) |  | 70 |  | 2968
1 | Mount MC/VV assembly to support frame at final assembly station; perform metrology checks | 2 | 3 | 48 | X | 2
2 | Position and weld all ports to VV except for the two large horizontal diagnostic ports | 20 | 6 | 960 | X | 2 |  | 22 ports at this time. Need an alignment method to support two teams
3 | Inspect Welds | 5 | 2 | 80
4 | Assemble left TF Coil Assembly and check position | 3 | 4 | 96 | X | 2
5 | Change platforms | 2 | 3 | 48 | X
6 | Assemble right TF Coil Assembly (requires support readjustment) and perform measurement checks | 3 | 4 | 96 | X | 2 |  | Currently assumes readjustment of stage 4 supports to accommodate rotating right side TF
7 | Attach TF coils to MC's | 3 | 3 | 72 | X
8 | Change platforms | 2 | 4 | 64 | X
9 | Position and weld two large horizontal diagnostic ports to VV | 8 | 3 | 192 | X | 2
10 | Inspect Welds | 1 | 2 | 16
12 | Assemble external trim coils, I&C, leads and coolant lines | 10 | 6 | 480 | X | 2 |  | It is assumed that this effort is carried out during steps 7 thru 10, a parallel effort. The 10 days is not counted in the total elapsed time. Note: number men increased over Rev 5 (was 3).
11 | Close up VV (added blank-off flanges and weld on end plates), bakeout VV to 350 deg C and leak check | 20 | 4 | 640 |  |  |  | It is assumed that this occurs continuously (for a 7 day work week). This saves 5 days in the schedule.
13 | Using metrology measurements adjust final support base interfaces | 2 | 3 | 48 | X | 2
14 | Prepare Field Period for shipment | 2 | 3 | 48 | X
15 | Transfer completed assembly to C-site test cell | 2 | 5 | 80 | X
| Total VV Prep assembly days | 220.5 | [5 empty] | Assumes 2 diagnostic periods and 1 non-diagnostic period.
| Total MC Half Period assembly days | 162
| Total MC installation days | 90
| Total Final FP Assembly days | 210
Notes:
1 | Background data used for estimating.
If you have the stud locations identified in advance, they are in close proximity, and you are shooting the same studs, you can shoot 30-40 studs an hour.
If you are changing sizes or have to change locations, then 20-30 an hour is reasonable. (Steve Kemp input)
2 | The measurement manpower estimate implies that this activity is accomplished by an engineer and technician working together (both metrology trained).

## Schedule
[11 empty] | FY 2005 | [28 empty] | FY 2006 | [11 empty] | FY 2007 | [8 empty] | FY 2008 | [11 empty] | FY 2009
|  |  | FEB |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUG |  |  |  | SEPT |  |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
ITEM | TASK | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
VV period Arrival dates
[17 empty] | C1 MC set Arrives | [18 empty] | FY 2006 A: Last MC set (C6) Arrives; FY 2007 A: B3
[37 empty] | Complete MC test C1 |  | C2 |  |  | C3 |  |  | A2 |  |  | A4 |  |  | A6 |  | C4 | C5 |  | C6 | B2 |  | B4 |  | B5 | B6 Complete
| TF INFORMATION HAS NOT BEEN UPDATED | [16 empty] | Award TF Contract | [16 empty] | 1st TF arrives | J: TF wedge added; FY 2007 F: All TF Coils Delivered
Target - Finish Last Field Period Assembly
Scheduled start of VV Pumpdown
1 | VV PREP STATION (Build to Print) | BP | [13 empty] | PDR |  |  |  |  | FDR
1.01 | Concept definition and requirements
1.02 | VV Support Fixture plus dwgs
1.03 | Metrology layout / support stand dwgs
1.04 | Structural Analysis check
1.05 | Fab Activities -
- VV alignment system
| - VV supports | [34 empty] | FY 2006 M: 1st VV; FY 2006 A: 2nd; FY 2006 D: 3rd
1.08 | VV Assembly Operations (1 station)
2 | HALF PERIOD ASSEMBLY (Build to Print) | LM | [13 empty] | PDR |  |  |  |  | FDR
2.01 | Concept definition and requirements
2.02 | MC Holding Fixture
2.03 | Metrology layout / support stand dwgs
2.04 | Structural Analysis check
2.05 | Procurement (build to print) | [34 empty] | FY 2007 M: C4 / C5; FY 2007 A: A2 / B2 / C2
2.06 | Fab Activities - Support fixture (2 ?)
| - Spherical seats (56) | [34 empty] | FY 2006 A: A1 / B1 / C1; FY 2007 M: C1 / C6
2.07 | HP Assembly Operations (2 Stations) | [34 empty] | FY 2008 J: A5 / B5 / C5
[57 empty] | A3 / B3 / C3 | [5 empty] | A6 / B6 / C6
[41 empty] | C2 / C3 |  |  |  | A1 / A2 |  |  | A3 / A4 |  |  | A5 / A6
A4 / B4 / C4
3 | MC INSTALLATION (Outside design & Fab) | TB, LM
3.01 | Concept definition and requirements | Done
3.02 | MC Turning Fixture and base | [7 empty] | Resized for seismic loading and Left side movement
3.03 | MC Gantry Crane | 90% done
3.04 | VV support stand and Misc crane fixtures
3.05 | Platform design | [8 empty] | LM |  |  |  |  | Assumes platforms ore part of contract.
3.06 | Metrology layout / support stand dwgs | [11 empty] | LM
3.07 | Structural / Seismic Analysis check
3.08 | Procurement activities
| - MCAF procurement | [10 empty] | Issue RFP 4 April | [5 empty] | Proposal Due |  |  |  |  | Award 30 June | [11 empty] | FDR | N: Start Fab; FY 2006 J: Deliver MCAF
3.09 | Fab Activities
- MCAF components
- Platforms (part of contract?)
3.1 | Assembly Activities
- Trial Runs - no VV
- Trial Runs - bare VVP plus MCHP
- MC Installation (1 Station)
PDR
4 | FINAL FP ASSEMBLY (Build to Print) | [34 empty] | FY 2006 M: FDR
4.01 | Concept definition and requirements | [19 empty] | BP
4.02 | MC Support Stand
4.03 | TF HP support and turning fixture
4.04 | FP Assembly platform
4.05 | VV Port Alignment/Weldment Fixture | [34 empty] | FY 2008 J: FPA-1 starts XXXXX, test cell delivery XXXXXX
4.06 | Metrology layout / support stand dwgs | [21 empty] | LM | [12 empty] | FY 2008 J: FPA-2 starts XXXXX, test cell delivery XXXXX
4.07 | Structural / Seismic Analysis check | [34 empty] | FY 2008 J: FPA-3 starts 1 Feb 08, test cell delivery 21 May 08
4.08 | Procurement
4.09 | Fabrication - follow-up activities | [34 empty] | FY 2007 J: FPA-1; FY 2008 M: FPA-3
- TF HP support
- FP Assembly platform & port fixtures
| (2 stations required) | [34 empty] | FY 2008 J: FPA-2
5 | INTERFACE / TEST ACTIVITIES
5.01 | TFTR test cell FPA arngmt dwg | [20 empty] | LM
5.02 | Design MC assembly test components | [18 empty] | BP
5.03 | Fab Activities - Test Articles
5.04 | Run test / metrology measurements
5.05 | Metrology Validation (Raftopoulos Activity)
OPEN ISSUE: TF ASSEMBLY COMPONENTS NEEDED TO ASSEMBLE A TF HP NEEDS TO BE INCLUDED IN THE SCHEDULE.
NEED THREE STAGE 2 FIXTURES BECAUSE OF OVERLAP
NEED TWO STAGE 3 FIXTURES BECAUSE OF OVERLAP
Models
All Dwgs
Models / Dwgs
Models / Dwgs
Models
Dwgs

## HW Cost
|  | Cost Estimate | Nb | Total Cost
| Hardware Items | ($K) | Stations | ($K)
1 | VV PREP STATION | 40 | 1 | 40
1.02 | VV Support Fixture | 20
1.03 | VV Prep Station Platform | 10
1.04 | VV Prep Station Metrology support stands | 10
2 | HALF PERIOD ASSEMBLY | 30 | 2 | 60
2.01 | MC HP Assembly fixture | 20
2.02 | HP Assembly Metrology support stands | 10
3 | MC INSTALLATION | 335 | 1 | 335
3.02 | MC Turning Fixture and base | 250
3.03 | MC Gantry Crane | 25
3.04 | VV support stand and Misc crane fixtures | 30
3.05 | Platform | 20
3.06 | MC Installation Metrology support stands | 10
4 | FINAL FP ASSEMBLY | 95 | 2 | 190
4.02 | MC Support Stand | 20
4.03 | TF HP support and turning fixture | 15
4.04 | MC Tempory End Support | 10
4.05 | FP Assembly platform | 30
4.06 | VV Port Alignment/Weldment Fixture | 10
4.07 | Final FP Assembly Metrology support stands | 10
5 | INTERFACE / TEST ACTIVITIES | 15 | 1 | 15
5.03 | Matrology test component | 15
| Total Hardware Cost Estimate ($K) | 515 |  | 640
Note: This is a VERY preliminary cost estimate